## CON
|  | ROBINSON CONTRACTORS Ltd |  | INSPECTION AND TEST PLAN |  |  |  |  | Project Number -
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Date submitted:
|  |  |  | Construction Process: Concrete Works - Owhata Retaining Wall |  |  |  |  | Prepared By: Downer New Zealand
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 600 - Structural concrete |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
Setout, Materials and Preparation
.1 | Survey Set Out | GPS Setout of the Retaining wall as per the construction drawings. | W | Length of the retaining wall | Visual Inspection | N/A | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works.
.2 | Materials Approvals | Submit testing data fir the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill | H | Once for each material | Quarry Testing Data | Engineer's Acceptance | InEight Records | Contractor
Construction and Finshing
.3 | Bases, Footings and/or Toes | Subgrade Cut / Base Thickness | M | Every 5m section | Visual Inspection | As per drawing | QC Sheets | Contractor | THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
.4 |  | Subgrade Testing | H | Every 20m | Scalar Penetrometer | ≥ 3 blows per 100mm. 500mm depth. | QC Sheets | Contractor
.5 |  | Reinforcing WSP INSPECTION | M H | Every 6m panels | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer
.6 |  | Formwork | H | Every 6m | Visual Inspection | As per drawing | QC Sheets | Contractor | FORMWORK SUPPLIED BY DOKA
|  | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa at 28 days | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
.7 |  | Dowels (greased and plain ended) | H | Every 300mm centers | Visual Inspection | R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS | QC Sheets | Contractor
.9 | Walls | Reinforcing WSP INSPECTION | M H | Every 6m panels | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer
.10 |  | Formwork | H | Every 5m | Visual Inspection | As per drawing | QC Sheets | Contractor | FORMWORK SUPPLIED BY DOKA
0.11 |  | Dowels (greased & plain ended) | M | Every 300mm centers | Visual Inspection | R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 5.0m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED | QC Sheets | Contractor
.12 |  | Finish / Joints | W | All areas | Visual Inspection | Smooth, off shutter finish. Cut joints as appropriate. | QC Sheets | Contractor
.13 |  | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa, at 28 days | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
0.14 |  | Weep Holes | W | Every 2,000mm | Visual Inspection | As per drawing | QC Sheets | Contractor | 50mm Ø WEEPHOLES THROUGH WALL STEM AT 2.0m INTERVALS
.15 | Backfill | Backfill behind wall (Shared service trench) | W | Refer to Shared Service Trench ITP
.16 | Joints | Completed Joints | W | All concrete orders | Visual Inspection | Concrete strength 25MPa, at 28 days | Concrete Dockets | Contractor | SIKAFLEX SEALANT OR APPROVED EQUIVALENT
0.17 |  | Joint formwork | w | At joints between sections | Visual Inspection | Smooth, off shutter finish. Construction joints as per drawing | QC Sheets | Contractor | COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
.18 | Subsoil drainage - front of wall Subsoil drainage - back of wall | Subsoil drain - back of wall | H | Length of wall | N/A | As per drawing | QC Sheets | Contractor
|  | Installation of subsoil drain | H | Lentgh of wall | N/A | As per drawing | QC Sheets | Contractor | 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
Close Out
.20 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor
.21 | As-built drawings | Survey | H | At completion of construction | Asbuilts to besubmitted at the completion of construction, information to be captured | Asbuilts reviewed and submitted | In Eight record | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.