## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Retaining Wall |  |  |  |  | Yes | ITP - Retaining Wall
section | Setout, Materials and Preparation
checkpoint | .1 - Survey Set Out
label | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
label | W
label | Minimum Test Frequency - Length of the retaining wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - N/A
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
label | Comments - Setout location prior to commencing works.
checkpoint | .2 - Materials Approvals
label | Detail of Activity - Submit testing data fir the following materials:
label | – AP65
label | – GAP 40
label | – GAP 20
label | – Hardfill
label | H
label | Minimum Test Frequency - Once for each material
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Engineer's Acceptance
label | Record documents - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Construction and Finshing
checkpoint | .3 - Bases, Footings and/or Toes
label | Detail of Activity - Subgrade Cut / Base Thickness
label | M
label | Minimum Test Frequency - Every 5m section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
checkpoint | .4 - Bases, Footings and/or Toes
label | Detail of Activity - Subgrade Testing
label | H
label | Minimum Test Frequency - Every 20m
label | Inspection / Test method - Scalar Penetrometer
label | Acceptance Criteria - ≥ 3 blows per 100mm. 500mm depth.
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .5 - Bases, Footings and/or Toes
label | Detail of Activity - Reinforcing
label | M
label | Minimum Test Frequency - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
checkpoint | .5 - Bases, Footings and/or Toes (2)
label | Detail of Activity - WSP INSPECTION
label | H
label | Minimum Test Frequency - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .6 - Bases, Footings and/or Toes
label | Detail of Activity - Formwork
label | Minimum Test Frequency - Every 6m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - FORMWORK SUPPLIED BY DOKA
checkpoint | .6 - Bases, Footings and/or Toes (2)
label | Detail of Activity - Concrete
label | H
label | Minimum Test Frequency - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
label | • THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .7 - Bases, Footings and/or Toes
label | Detail of Activity - Dowels (greased and plain ended)
label | H
label | Minimum Test Frequency - Every 300mm centers
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .9 - Walls
label | Detail of Activity - Reinforcing
label | M
label | Minimum Test Frequency - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
checkpoint | .9 - Walls (2)
label | Detail of Activity - WSP INSPECTION
label | H
label | Minimum Test Frequency - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500 MILD STEEL.
label | • MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .10 - Walls
label | Detail of Activity - Formwork
label | H
label | Minimum Test Frequency - Every 5m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .11 - Walls
label | Detail of Activity - Dowels (greased & plain ended)
label | M
label | Minimum Test Frequency - Every 300mm centers
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 5.0m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | .12 - Walls
label | Detail of Activity - Finish / Joints
label | W
label | Minimum Test Frequency - All areas
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint | .13 - Walls
label | Detail of Activity - Concrete
label | H
label | Minimum Test Frequency - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | • ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .14 - Walls
label | Detail of Activity - Weep Holes
label | W
label | Minimum Test Frequency - Every 2,000mm
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT 2.0m INTERVALS
checkpoint | .15 - Backfill
label | Detail of Activity - Backfill behind wall (Shared service trench)
label | W
label | Minimum Test Frequency - Refer to Shared Service Trench ITP
label | Inspection / Test method - Refer to Shared Service Trench ITP
label | Acceptance Criteria - Refer to Shared Service Trench ITP
label | Record documents - Refer to Shared Service Trench ITP
label | Responsibility - Refer to Shared Service Trench ITP
label | Comments - Refer to Shared Service Trench ITP
checkpoint | .16 - Joints
label | Detail of Activity - Completed Joints
label | W
label | Minimum Test Frequency - All concrete orders
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT
checkpoint | .17 - Joints
label | Detail of Activity - Joint formwork
label | W
label | Minimum Test Frequency - At joints between sections
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
checkpoint | .18 - Subsoil drainage - front of wall
label | Detail of Activity - Subsoil drain - back of wall
label | H
label | Minimum Test Frequency - Length of wall
label | Inspection / Test method - N/A
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .18 - Subsoil drainage - back of wall
label | Detail of Activity - Installation of subsoil drain
label | H
label | Minimum Test Frequency - Length of wall
label | Inspection / Test method - N/A
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
holdpoint | AUTHORITY HOLDPOINT
section | Close Out
checkpoint | .20 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | Record documents - Review
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | .21 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured
label | Acceptance Criteria - Asbuilts reviewed and submitted
label | Record documents - In Eight record
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature