## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP001 – Demolition and Service Location | itp |  |  |  | Yes | ITP001 – Demolition and Service Location | 4126bb83-2a4c-4cdd-803a-64e600bee7ff
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - The current revision of drawings are being used including subcontractors copy.
label | e451fa2a-bf7a-5311-bae7-0b261bd9e103 |  | note | Frequency - Prior to commencing works
label | c52621fc-8a80-5d03-aadf-8140d8e698b8 |  | note | Acceptance Criteria - Current revision drawings are being used, including the subcontractors copy. Current revision to be obtained via Aconex
label | 6eef650b-6ce2-59d0-9e87-0080bd0ab51f |  | note | Reference Documents - Current Revision Drawings in Aconex
label | a56bcad9-9f6b-5681-ba9e-f09cddb2e98e |  | note | Inspection/ Test Method - Visual Inspection
label | 5a881b14-b6e5-546f-9179-d6387cdc5ec7 |  | note | Record of conformity - This ITP signed
label | ca83b3d3-a2de-5969-87e2-3f6d880fca04 |  | note | HP*
label | a944e7db-7d6a-5e41-9c12-818db97a77af |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Dilapidation Report
label | 5ce6a6f3-3a9a-5654-9e78-65439ce98201 |  | note | Frequency - Prior to commencing works
label | 963323c9-c3c3-529b-be80-bcbe4c7c598d |  | note | Acceptance Criteria - Prior to the Works, the Contractor must provide the Contract Administrator and Principal’s Design Consultant with a fully detailed dilapidation survey recording the current condition of aircraft pavements, aircraft pavement surface features, underground services, roads, drives, footpaths and adjoining premises.
label | e7c26a3c-89a4-5ea5-8e53-2972a6eeddd5 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.23.1
label | 1d92130c-9ceb-5e38-9696-692220aa23c7 |  | note | Inspection/ Test Method - Verify
label | 4913e422-961a-57d4-a0b0-87ad09e119d7 |  | note | Record of conformity - Aconex Correspondence
label | 64ee6ce5-c0c8-5541-8951-5eea4f12363b |  | note | HP
label | c53aaf24-6e9b-5941-8d00-bf5c37bc3145 |  | note | Responsibility - FH Project Engineer / Contract Administrator / Principal’s Design Consultant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Service Location and Detection Methodology
label | e90a3039-1e71-54f4-97d9-821ca3ab356f |  | note | Frequency - Prior to commencing works
label | 9af3d57e-cbd7-515c-b7ee-0118b617559a |  | note | Acceptance Criteria - The Contractor must submit a methodology of service detection to the Contract Administrator for review.
label | eb4ab646-b3f5-53ac-89b2-ae66d8ebe08a |  | note | • Within 20m of intrusive works the Contractor must locate and mark the ground position of all underground services and structures.
label | 5514b730-423d-558d-8d36-818fd8c1c85a |  | note | • Services located within the works area must be exposed using hand tools or specialist sensitive excavation techniques (NDD).
label | 499aa3fa-69b6-5d26-b153-018be7217f77 |  | note | • This methodology is contained within the work procedure for demolition.
label | dd731314-fe0f-5983-9bf1-ed21e9489d2b |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.2.1 & AECOM – MAP MP 2.0 Spec. Cl3.2.2
label | be60e866-7601-55c3-8068-978389eca1c3 |  | note | • FH-DP1PM-WP001 Section 3.2
label | 4bb4c060-5878-5250-ab3c-444e2d7d1617 |  | note | Inspection/ Test Method - Verify
label | 23a35fc7-eb6b-5697-8739-3c093c7f97b2 |  | note | Record of conformity - This ITP signed
label | fcc1c18a-eec5-5ff4-a987-21937a8c83ae |  | note | WP
label | 39b5a662-39e0-501d-8a1f-9b37e582e602 |  | note | Responsibility - FH Project Engineer Contract Administrator
checkpoint-status |  |  | checkpoint | 1.4 - Demolition Work Plan
label | 4fd5e26f-d17e-512f-a72d-4c887e6f2db3 |  | note | Frequency - Prior to commencing works
label | 6c0978f7-03c7-524c-96ac-a24df2eeed17 |  | note | Acceptance Criteria - The Contractor must prepare a Demolition Work Plan and shall submit this plan to the Contract Administrator at least ten (10) business days prior to the works commencing for approval.
label | 3ad95fbd-4265-509f-9ffe-f701602bf94c |  | note | • The Contractor must maintain pavements surrounding the demolition site in a clean condition that is free from debris and saw and core cuttings, slurry etc
label | 567494d0-deb2-5ae4-94eb-e51344c05deb |  | note | • Precautions to protect the existing remaining pavement from damage must be undertaken where tracked equipment are required to traverse or operate on existing pavement.
label | dee362ba-0ed9-5c1d-8f43-d89323b881e1 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.5 & AECOM – MAP MP 2.0 Spec. Cl4.6.3
label | 3820e23a-f39e-533a-a083-44fd7ea0421f |  | note | Inspection/ Test Method - Verify
label | b92cd670-f161-51cd-8d90-496f342093d2 |  | note | Record of conformity - This ITP signed
label | dbd2e819-061c-5536-83bf-fb9282317efa |  | note | HP
label | 8d30254a-663a-5764-89ad-78053f197b07 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Obtain approvals to start works
label | e354c684-42ab-5450-b061-334fbbabb57c |  | note | Frequency - Prior to commencing works
label | 85ce99f6-295c-5f3f-bdb1-a12636c6f41e |  | note | Acceptance Criteria - The Contractor needs to obtain all required works approval from the Principal as required. This must include excavations, hot works, electrical isolation permits and crane access. Evidence of permits being obtained by the Contractor must be submitted to the Contract Administrator prior to works commencing.
label | 466e523f-8c6c-5ce3-b36e-34558fd44f75 |  | note | • Fulton Hogan Excavation permit issued to plant operators.
label | e554df67-6da7-522e-a049-99fc26249bff |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.4
label | d56c0406-5f05-54b6-aa77-a6ea803f685e |  | note | Inspection/ Test Method - Verify
label | 7696d8e3-09a9-56b8-864b-2874d6c453d7 |  | note | Record of conformity - This ITP signed
label | d32d235f-459b-5f41-b6b4-12cffa6af0a7 |  | note | HP
label | a25071ba-1f84-5abf-a4ac-1847d9949ac1 |  | note | Responsibility - FH Project Engineer Contract Administrator
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Implementation of all measures and controls
label | 78525fc0-b343-5724-832b-ab985d5edcce |  | note | Frequency - Prior to commencing works
label | 43bf98c3-a6ad-5087-8ada-cadeba1448af |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 5a91760f-12e3-53b0-a795-ad547753ee70 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 6e892edc-ac91-54c9-832b-a744d2412a2d |  | note | Inspection/ Test Method - Visual Inspection
label | f404247d-c887-5d11-8e7b-099885f4decb |  | note | Record of conformity - This ITP signed
label | e32b9ec4-0eb1-55a8-b690-3cf4da4c4da9 |  | note | HP*
label | a2da9781-bcef-5de3-b0c6-ac827ea40447 |  | note | Responsibility - FH Project Engineer / Site Supervisor
checkpoint-group |  |  | section | 2. Demolition Works
checkpoint-status |  |  | checkpoint | 2.1 - Services Detection
label | 1b660b5e-4e36-5b70-97df-5d1e3990b79b |  | note | Frequency - Each Lot
label | 2ae8213c-d4f0-5260-b5c2-d4bb9c0b4264 |  | note | Acceptance Criteria - Confirmation that Services Detection has been Completed for the Works area(s)
label | 90737bb8-a522-5edf-8c63-a781fe9a2d92 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl3.3.1
label | 1fb3479b-0015-5794-b62f-67909d873052 |  | note | Inspection/ Test Method - Visual Inspection
label | c1da686a-90e5-5561-a911-d802b00deabd |  | note | Record of conformity - This ITP signed
label | 54287634-139b-5bfb-a94f-e736befc7095 |  | note | HP
label | 4f40739f-11ce-546f-b341-1a8142905b4d |  | note | Responsibility - FH Project Engineer / Foreman
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Discovery of Contaminated Materials
label | b275801d-e1e8-5d0b-b202-55ffa61ebd80 |  | note | Frequency - Each Lot
label | ceafb911-9098-5277-92d6-f3a343f6506f |  | note | Acceptance Criteria - If contaminated or hazardous materials are found, immediate notice is to be given to the Principal’s Representative. These include the following;
label | 62afce4a-859c-568a-b266-fdc782169eef |  | note | • Asbestos or material containing asbestos;
label | a3a7db0c-4c2a-5621-8240-245e23e24d96 |  | note | • Flammable or explosive liquids or gases;
label | 34f5220f-9e7f-560f-a047-0a8b8f800d7a |  | note | • Toxic, infective or contaminated materials;
label | 21961daa-d9b5-5358-be91-88c825caf57c |  | note | • Radiation or radioactive materials;
label | 33766565-94c0-5ce0-9225-0a3debe3514a |  | note | • Noxious or explosive chemicals; and
label | 615d5aed-9918-5754-a8fe-9d958c24f0f7 |  | note | • Tanks or other containers which have been used for storage of explosive, toxic, infective or contaminated substances.
label | 3869b836-7cd3-516f-a9e8-707536159340 |  | note | ○ A proposal for the procedure to remove contaminated or hazardous materials from the site to be agreed between FH, APAM and AECOM in accordance with all statutory and contractual requirements to approved locations.
label | 63b1c77e-4ceb-5364-9651-262595b24922 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl1.19
label | f9783270-b99a-5ce6-9a07-a076383e2a9e |  | note | • FH-DP1PM-WP001 Section 3.3.7.
label | 64d31025-da8d-537d-995e-1663bd59385c |  | note | Inspection/ Test Method - Verify
label | e6b8a0c5-9ced-5c5a-a8d5-77613e4fcd87 |  | note | Record of conformity - This ITP signed
label | 14f307bd-391f-59e3-af7e-138c7bfdf3c2 |  | note | HP*
label | 264a18d9-6447-54e7-98ea-97a188dbc396 |  | note | Responsibility - FH Project Engineer / Contract Administrator
checkpoint-status |  |  | checkpoint | 2.3 - Disposal of Demolished Materials
label | e4f64fb8-a33f-5fbb-afd3-3f3ba9d6f392 |  | note | Frequency - Each Lot
label | 63daef29-7b0e-55f1-90e0-946d0baf2b64 |  | note | Acceptance Criteria - The disposal of demolished materials is to be managed under the approved Construction Environmental Management Plan (CEMP).
label | 19d0096f-ebd2-51a0-9e23-4c2e6b401b32 |  | note | Reference Documents - AECOM – MAP MP 2.0 Spec. Cl4.6.5
label | f5052e03-03f8-518d-9561-e4747afc5922 |  | note | Inspection/ Test Method - Verify
label | fde1eaf0-4726-5622-af2a-3516769a9e10 |  | note | Record of conformity - This ITP signed
label | 7e66fe75-ff60-5ee2-bf2e-bab4304e3b17 |  | note | HP*
label | add96f63-5270-543a-bf82-38b717d8f343 |  | note | Responsibility - FH Project Engineer / Foreman
checkpoint-status |  |  | checkpoint | 2.4 - Completion
label | a8d501ff-5c3b-5239-8e70-ef7b279912e8 |  | note | Frequency - Each Lot
label | 46d81abd-0266-5a89-a775-dc7fe607a15b |  | note | Acceptance Criteria - The Contractor to make the area safe and clean post completion of works. Any temporary supports are to be removed at completion of demolition.
label | 209d3bdd-787f-5983-a9b0-169853ce0927 |  | note | Reference Documents - FH-DP1PM-WP001 Section 3.3.14
label | de87db96-f05c-568f-bd84-57adc63304ab |  | note | Inspection/ Test Method - Inspection
label | dc4f8a50-a0ae-5687-994f-a4da22b4b19f |  | note | Record of conformity - This ITP signed
label | ef0aec62-1520-54dd-a51d-3958d6f48f63 |  | note | HP*
label | c1a0ca52-3f5f-5ffe-a3b0-093bedb3ee31 |  | note | Responsibility - FH Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 88f6e925-9f70-5997-abd1-0a63557faabc |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | d29489dc-31c6-5878-a2ea-15d6c6699b00 |  | textbox | Name:
text | 05b0406e-962e-58b1-a9e4-d01002915775 |  | textbox | Position:
text | e37fe8b5-98aa-5054-8c3d-bdb014c9b9fd |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | FH-DP1-PM-ITP008 - Minor Asphalt Works |  |  |  |  | Yes | ITP008 – Subsoil Drainage | 6a3a8108-fdea-4b27-b7b6-8f56ff1e63d8
checkpoint-group |  |  | section | 1. Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 8f268b77-edc8-559c-853d-6b1fbacc8545 |  | note | Frequency - Prior to commenc ing any activity
label | 44850c9f-7f88-5222-896f-a3ac58e287ec |  | note | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex
label | fb7bd970-1d09-5c80-b080-92a06e930a8c |  | note | Reference Documents - Drawings and drawing registers on Aconex
label | 9cdf7216-b75e-5449-b282-3f37f77f5faa |  | note | Inspection/ Test Method - Visual inspection
label | 34b38ecf-7efd-53a7-8891-9dacfad9ff19 |  | note | Record of conformity - This ITP signed
label | d08e489f-6373-5fe2-8b8a-ba7cc3340a58 |  | note | HP*
label | 67038ed8-460b-5cc6-97db-d3f8976f8bae |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | add06799-dc56-58ee-92d3-898ce4b37d01 |  | note | Frequency - Prior to commenc ing any activity
label | 79b883c3-21cf-549a-ad51-604ebbc3fdc9 |  | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | 9cf10057-e1ac-523f-8d4b-f772c238f695 |  | note | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | 7523015a-29cc-541e-855e-53a7ea3922d8 |  | note | Inspection/ Test Method - Visual Inspection
label | feda99c4-8f88-5f0a-92e6-68d71ec96bd8 |  | note | Record of conformity - This ITP signed
label | 708363b5-9bd0-5a26-89f8-fb45f697b165 |  | note | HP*
label | b10ae669-02a8-51ad-871a-bfdd132d45ea |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 1.3 - Definition of the work area
label | 76fd599f-6143-58f3-b15d-077302dff450 |  | note | Frequency - Prior to commenc ing any activity
label | e9241b5a-bad1-5588-94c2-fb8b6ae96151 |  | note | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | 7a91de06-e0f3-5ee0-b19d-ef7fb93798db |  | note | Reference Documents - Drawings
label | d2b079c3-74a3-52af-b89a-fac750f92994 |  | note | Inspection/ Test Method - Visual Inspection
label | abaa4c0d-bfc1-5a5e-bd46-f3f3ff3212ad |  | note | Record of conformity - This ITP signed
label | 6e037040-19b8-5d4a-a76f-426c312fcdbd |  | note | HP*
label | 12fb8905-d8ec-59bb-9c91-7dada119ac11 |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 2. Subsoil Material
checkpoint-status |  |  | checkpoint | 2.1 - Subsurface Drainage Pipes
label | 5b1925f7-85ad-56c6-b35d-3d2c73ebe5a3 |  | note | Frequency - Prior to Start
label | 7effdd2e-fb98-5819-9cd8-f90802a82890 |  | note | Acceptance Criteria - Subsoil Pipe material to be 150mm slotted agi class 1000 SN20, or approved alternative.
label | e515e9a4-cd2a-559d-9f85-9d094d83f037 |  | note | Reference Documents - Drawings
label | 09a2fbdb-cd77-54dd-8a25-b080147ed8ee |  | note | Inspection/ Test Method - Verify
label | cfa7f4a6-7190-5860-982b-fb28a2517e97 |  | note | Record of conformity - This ITP signed
label | 7f6b8c54-112b-587d-8148-b478d5af2921 |  | note | HP*
label | dec25b73-495c-5caa-a981-640f287b550b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 2.2 - Bedding & Backfill Material
label | 62ed14ae-6013-589f-a5dc-b3e9a78cac3a |  | note | Frequency - Each Lot
label | 58b4dd78-db35-5bf6-b304-7190bdd4f441 |  | note | Acceptance Criteria - Backfill filter material - approved alternative, complying with VicRoads Section 702.
label | aa077d17-d9c5-5567-a42c-142505863e41 |  | note | Reference Documents - AECOM- MAPMP 2.0 Spec. Cl 8.4.2 Design Drawings
label | 25682e3a-a455-596d-b60b-dbf4b69f28c3 |  | note | Inspection/ Test Method - Verify
label | 7244b799-1c2e-59e6-96b5-8ee27eed68bf |  | note | Record of conformity - This ITP signed
label | 0b03a671-847d-55ad-8f00-768ef060c72e |  | note | HP*
label | c16df0f7-a77e-5bfa-a2c0-6e13618c115b |  | note | Responsibility - Project Engineer
checkpoint-group |  |  | section | 3. Excavation and Installation
checkpoint-status |  |  | checkpoint | 3.1 - Trench Excavation
label | 23194073-219c-564e-964f-6448fb697248 |  | note | Frequency - Each Lot
label | b3c07443-e9c5-501c-8031-b74ebf24a8b1 |  | note | Acceptance Criteria - Trenches excavated to dimensions and grades shown on design drawings. Excavation to allow for 100mm bedding material. The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations. Excavated material disposed per approved CEMP.
label | d1944bcf-28e3-5dfb-94f0-b5753780ff7c |  | note | HP: Base of trench inspected prior to placing bedding material
label | 59a87ee4-ef43-5f53-95a4-16c9c7562ef5 |  | note | Reference Documents - Drawings & AECOM – "MAPMP 2.0
label | 8b422297-646c-5036-ba32-d6b7e2b76b23 |  | note | Spec. Cl 8.5.3, 8.5.4, 8.5.5 & 8.5.7"
label | 9aec0526-a4fb-5872-876e-ded8cd8280af |  | note | Vic Roads 702.08
label | 12dfeb7e-fe71-5700-b880-5ee83b91eb9c |  | note | Inspection/ Test Method - Verify
label | 4338d00e-102a-568a-ad17-414863d53984 |  | note | Record of conformity - This ITP Signed
label | 6e83994b-a128-59df-a423-14efdfcc3d72 |  | note | HP
label | 6595edd1-ce7b-5dbd-8bf6-1b417e8c4a58 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Bedding, Laying Pipes & Backfill
label | d2ed11b4-d7be-58eb-b425-66cf6ff2d059 |  | note | Frequency - Each Lot
label | d9540ec8-8a4b-5c65-858c-751b44f8132c |  | note | Acceptance Criteria - In accordance to the dimensions outlined in the drawings. Tolerances: +/- 50mm from specified line +/- 25mm from specified level Minimum Grade 1 in 250, unless approved or designed otherwise. Bedding to be tamped and screeded or graded to level.
label | 1b565ae0-2542-5f73-bd78-5d470666811d |  | note | Reference Documents - Drawings & AECOM – MAPMP 2.0 Spec. Cl 8.5.4 & 8.5.5 Vic Roads 702.03, 702.09
label | 336325ab-803a-50a9-91c6-d7dbd5c5d19b |  | note | Inspection/ Test Method - Visual Inspection
label | 48ec3f4b-e2a4-5c47-99c3-a14b1c24203b |  | note | Record of conformity - This ITP Signed
label | 21b735ef-7f7d-5eee-8f78-dffa3516fdac |  | note | HP
label | 88bc3b59-c230-58f2-8714-3e0499e5da10 |  | note | Responsibility - Project Engineer / Principal’s Representative
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Laying and Jointing of Pipes
label | 6d4f86ce-de6a-5360-b858-2317f3eefa2f |  | note | Frequency - Each Lot
label | bb96d8f9-4bf8-5e84-b204-9ddb5e725324 |  | note | Acceptance Criteria - Pipes laid at the depths and lines indicated on drawings.
label | 7367ed3a-2fae-50e1-9007-627997583b55 |  | note | Reference Documents - Drawings
label | 1850a5a0-4369-5c8e-996c-0321dfefd88e |  | note | Inspection/ Test Method - Visual Inspection
label | a6b7bf54-587a-586d-9468-71847a7457af |  | note | Record of conformity - This ITP Signed
label | fb6f9ed6-62cd-5e9c-a094-81af3d87929c |  | note | HP*
label | 1e94b7c5-bfb8-52b9-9488-7c1726ed382e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.4 - Subsoil Drain Outlet
label | db97bb79-82cc-58f9-b541-43f958caa2f0 |  | note | Frequency - Each lot
label | f8c8b260-7666-50e0-9422-ee411b23ddb5 |  | note | Acceptance Criteria - Outlets from subsoil drains shall be constructed to discharge into stormwater drainage system.
label | 2a3b7cd8-896c-522d-8005-29bf0cd36bae |  | note | Reference Documents - AECOM – MAPMP 2.0 Spec. Cl 8.5.6
label | 7cda3f4f-dac1-5fe7-a6ea-772590689dd1 |  | note | Inspection/ Test Method - Verify
label | dcfa8aa1-bf50-5039-b62c-8c81b2cd43ee |  | note | Record of conformity - This ITP Signed
label | 2b0397c8-2e90-51ed-b003-276d2600e77c |  | note | HP*
label | 8531e4db-5e90-5a82-90d4-566bdcf8ce1e |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.5 - Flush out risers
label | c085b5e2-cda3-53a6-8375-13ac5d21808b |  | note | Frequency - Each Lot
label | 7e17ee1f-082f-5df2-9223-c7e0142de366 |  | note | Acceptance Criteria - To be the same diameter as the subsoil pipe and be installed in locations indicated on the drawings.
label | 71a25b99-0e42-57f2-aace-0d0303ef0396 |  | note | Reference Documents - Drawings & Vic Roads 702.10
label | 47f6d33e-bf99-5243-abee-1dc950f03749 |  | note | Inspection/ Test Method - Visual Inspection
label | a4a60bd6-1095-5f6c-9e1c-f76389380ee6 |  | note | Record of conformity - This ITP Signed
label | 2826828f-7a03-576e-9c2f-84dfa7d62647 |  | note | HP*
label | 2ede5a57-3f10-5db4-a648-3a2e925e9ad5 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 3.6 - Flushing Test
label | 86194e5d-fa26-52dd-9432-9b70ea8e25e6 |  | note | Frequency - Each Lot
label | 8d1ee07c-02ea-53c6-a536-4e105934a014 |  | note | Acceptance Criteria - A flushing test shall be carried out on each subsurface drainage line after completion of subsurface drains, flushers and outlets. The test shall be witnessed by the Principal’s representative.
label | 479a4cf2-95ac-5cec-9e28-fbe14683478d |  | note | Reference Documents - Drawings & Vic Roads 702.09
label | 5682edbb-896b-511a-b604-c8bf17ff8dd3 |  | note | Inspection/ Test Method - Visual Inspection
label | 689412b3-5d1b-5839-9101-c1e4a640d89c |  | note | Record of conformity - This ITP Signed
label | 375a87ba-fe71-529e-8bea-796531e8a69c |  | note | WP
label | b4c6cfd4-f065-5216-9a78-114d2541da1a |  | note | Responsibility - Project Engineer / Principal’s Representative
checkpoint-group |  |  | section | 4. Post Construction
checkpoint-status |  |  | checkpoint | 4.1 - Records
label | 7f46220c-2c64-558d-94a7-b03efcae8388 |  | note | Frequency - Each Lot
label | 1d97d353-2260-567d-8336-7f28071d72cd |  | note | Acceptance Criteria - Levels and alignment recorded in as built documentation and provided to superintendent.
label | 064bb156-4185-582b-8f00-e6779bceee8d |  | note | Reference Documents - Vic Roads 702.03
label | b1f8dd07-f351-55cf-97a0-718b65b4c569 |  | note | Inspection/ Test Method - Inspection
label | 32cf3a7e-c3b4-5c55-8ff8-131dac998d06 |  | note | Record of conformity - Aconex Correspond ence
label | 849d96ba-3a9a-5caf-ae07-88b456ae7b60 |  | note | SCP
label | 6fa0c136-8058-58d5-8169-77b48c050265 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | Final Inspection
label | 48abf1b3-2720-5940-a07e-c4d48607bc98 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8a527336-437b-50d4-b052-40d71833d66b |  | textbox | Name:
text | 92fad45b-70e9-5976-bb60-6274d2634f41 |  | textbox | Position:
text | 05abea65-5051-55e5-bc9a-b875c8d49e5d |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP022 – Native Grass Protection |  |  |  |  | Yes | ITP022 – Native Grass Protection | bee085c5-ea93-43a1-80dd-a3e7f7dcecc7
checkpoint-group |  |  | section | 1. Preliminary Activities
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 97a5077d-1543-5714-b6d8-fe7d285c8a47 |  | note | Frequency - Prior to site establishment
label | 07900bea-ee78-50ea-8b27-5e033d9007b2 |  | note | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
label | a83d0e72-23d5-57e1-b64b-1ef276cb719f |  | note | Reference Documents - Consultant reports
label | 2633dbae-6842-555b-b148-d5b68900c4e8 |  | note | Inspection/ Test Method - Visual inspection
label | 605a4a9b-4eae-5a3f-8f24-a9df901dcb15 |  | note | Record of conformity - This Signed ITP
label | 0cf75c13-b335-5146-bbd6-9dba0347d4b3 |  | note | HP*
label | d3376edf-d6d5-51ef-8a11-751a1841ecec |  | note | Responsibility - FH Project Engineer
label | 3ee6d271-1927-534d-bccb-515962c2b977 |  | note | Checked By
text | 104a7a08-16bb-5cc6-a6f9-ae6ffd73ff4b |  | textbox | Name
text | 292f60e4-046a-50c0-84db-04917ee3ad9d |  | textbox | Position
text | 7537d677-ddb1-5c8d-8283-00862dcee57d |  | textbox | Date
checkpoint-status |  |  | checkpoint | 1.2 - Check the Google Earth Mapping
label | 0c52afe2-1015-5eae-a74d-beb1efd09914 |  | note | Frequency - During site establishment
label | 9b2812b2-d002-5587-a28d-8247b328c9e7 |  | note | Acceptance Criteria - Review the Google Earth mapping which outlines the boundary of the native grasses at the time they were mapped.
label | 52bbb6b0-d7dc-52e9-85c5-47e684efcc15 |  | note | Reference Documents - Google Earth Mapping
label | bff35185-70ad-5d1e-813c-6c717c9e9e7a |  | note | Inspection/ Test Method - Visual inspection
label | 7c924f7a-330b-58ae-8607-5047bf331a52 |  | note | Record of conformity - This Signed ITP
label | dfbbccf8-448b-5071-9747-798658616f3c |  | note | HP*
label | 54475a94-532f-53ca-8ed7-3a4e758d1dc1 |  | note | Responsibility - FH Project Engineer
label | 73678c61-a0eb-51fe-b4b9-74de734f890b |  | note | Checked By
text | 7f2db4f6-71d3-5df8-9696-cf642447f6d1 |  | textbox | Name
text | 5870e086-ef0d-5088-b88d-4393a838866e |  | textbox | Position
text | cad23399-5222-5b97-865d-8ef8e60fed76 |  | textbox | Date
checkpoint-group |  |  | section | 3. Implementation of Controls to Protect the Native Grasses
checkpoint-status |  |  | checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
label | cad67f38-b0c5-56bd-9ca5-79539c289fad |  | note | Frequency - Prior to commencing any activity
label | 6df58813-4677-5544-a37f-426a50266bf1 |  | note | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. FH Project Engineer must verify the set out survey data file matches the ECP. Signage will be placed onto the bollards stating ‘Native Grass Boundary Area.’ NTGVVP Nationally Significant Grasses to protect within this area.
label | 2bdd86c0-705b-5967-a0a6-9feadba81641 |  | note | Reference Documents - CEMP & ECP
label | c1e2613f-408a-5bac-998a-09733ac1226e |  | note | Inspection/ Test Method - Inspect
label | 557c8d9d-cb38-5a96-a8fc-a019e71c05e3 |  | note | Record of conformity - This Signed ITP
label | 9dfd0a68-a3e0-5b7a-8cd8-e08a02ba5c62 |  | note | HP*
label | a533efbb-aaf6-5b19-9582-8196307e9fab |  | note | Responsibility - FH Project Engineer
label | 14f8c1b1-b43e-5ed2-a119-af3d073ec3e7 |  | note | Checked By
text | 2a9799f7-c5a1-5dfe-bb5f-ffa196183d7a |  | textbox | Name
text | 5e4fe02c-40d6-5a3a-a493-0db09100f466 |  | textbox | Position
text | 1fccc880-f7e5-594c-9ef3-e87f2b5021a1 |  | textbox | Date
checkpoint-status |  |  | checkpoint | 3.2 - Use temporary fencing and signage to block access to the Significant native grasses where we are working in close proximity.
label | 402a7e03-1ada-51fa-a19f-cc599cc2fc95 |  | note | Frequency - Prior to commencing any activity
label | 54f9a3cc-55d5-514e-b4be-280539a6ff37 |  | note | Acceptance Criteria - For works in close proximity to the native grasses, delineate the native grass boundary using temporary fencing or t-top bollards with signage stating, “Vegetation Protection – No Go Zone.” Where possible this fencing will be installed at a distance away from the actual native grass boundary to act as a ‘buffer zone’.
label | feb7c8a2-bb26-5788-a76f-6b58b681e8cc |  | note | Reference Documents - CEMP & ECP
label | 877326f5-590c-522e-b22e-6f4b1b86e942 |  | note | Inspection/ Test Method - Inspect
label | 77642930-b12d-5741-a462-4e2597d60101 |  | note | Record of conformity - This Signed ITP
label | bf7bc1d0-9ddd-5987-98cb-b5a77a8e17d7 |  | note | HP*
label | abbddda1-5441-5e46-8227-163635c06630 |  | note | Responsibility - FH Project Engineer
label | 12940442-87e3-5da2-821b-9977401e6a04 |  | note | Checked By
text | 47de9c16-ee36-5c1d-b78a-cbd2baeae213 |  | textbox | Name
text | c672030c-3a10-5351-b18f-a645385a7c2e |  | textbox | Position
text | fa4f8ae6-4b7d-58a7-8e5f-da098959bdd6 |  | textbox | Date
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | d8587498-b935-5adf-a4a6-052dea72e5de |  | note | Frequency - Prior to commencing any activity
label | 02a853ee-bf64-52a0-84f7-8ab88e75bb56 |  | note | Acceptance Criteria - Project Engineer and Superintendent / Foreman to confirm the ECP requirements of native grass delineation have been met; and verify the delineation has been set up correctly using a GPS Rover.
label | b58c14e2-7c11-504b-8347-bddc87bc70dd |  | note | Reference Documents - CEMP & EMP
label | ac312a57-c49c-52d2-ae6e-6c2af4b0c432 |  | note | Inspection/ Test Method - Inspect
label | d7de184b-a5e4-53b2-b7c4-52ce75de9922 |  | note | Record of conformity - This signed ITP
label | 2545beab-33e9-5b63-8154-f9115b97fe25 |  | note | HP
label | 5582e6eb-21ea-5781-a463-bf962aaa363f |  | note | Responsibility - FH Project Engineer
label | 705e8d28-701e-5481-852f-83ef000cd273 |  | note | Checked By
text | 8dc47b1c-62f7-5b5e-85fd-f4a1e3a3bad8 |  | textbox | Name
text | 4ef76219-73bd-5e92-9747-f1337acc2ae4 |  | textbox | Position
text | abee31b2-fab1-59d1-8ec7-6aed144d180e |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | e71c5b37-8d23-5843-85da-5a753a2cccd4 |  | note | Frequency - Prior to commencing any activity
label | 5e658ff3-9e5d-56d3-92ad-3bf7e9d55784 |  | note | Reference Documents - CEMP & EMP
label | 57a14d08-493a-5616-bb9c-befe5e249be7 |  | note | Inspection/ Test Method - Inspect
label | c068ce28-1000-59e8-bb5d-c10a644dc496 |  | note | Record of conformity - This signed ITP
label | 2b6b532f-77cf-5daa-aae7-701203ec2c55 |  | note | HP
label | 4940bb04-68dd-5f9e-b340-ee979eb6e38d |  | note | Responsibility - Superintendent / Foreman
label | c8c023c0-2e08-503e-8cda-d611860b02f5 |  | note | Checked By
text | 21595c30-dd2e-515f-ab6f-481f77f9c67f |  | textbox | Name
text | ae022b2c-1d92-58c8-b9a9-5b0379ba3445 |  | textbox | Position
text | f0c8cedc-4314-586e-a571-3fa3df4bd8e8 |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | 4. APAM Hold Point Release - Second Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Release of Hold Point for Native grass Protection
label | 09bf67c7-6ef4-5b24-a209-5b24bc588072 |  | note | Frequency - Prior to commencing construction
label | d033f7bb-eb5f-50ec-b879-ab8348e7d63a |  | note | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required. All parties are to sign off on this Hold Point Release document
label | 70203a1d-25d4-5b0d-bfb5-118ad7e25306 |  | note | Reference Documents - CEMP and ECP
label | 2d23acaf-5f9c-504d-9113-5cf1b3c46364 |  | note | Inspection/ Test Method - Visual
label | 4be8b80d-2d41-509e-b055-a98fc65b1618 |  | note | Record of conformity - This Signed ITP
label | 81087161-28f4-5372-9cfc-743448975d13 |  | note | HP
label | cc81507c-68a1-51d6-b176-6c13f0a35326 |  | note | Responsibility - APAM Fulton Hogan Environmental Manager or Project Manager
label | 1e9068e1-ec65-5913-b662-c8bb64daa910 |  | note | Checked By
text | baa74f55-8e61-554c-8793-0df345478405 |  | textbox | FH Name
text | d2fe5c16-666c-518b-9193-df8b847dc406 |  | textbox | Position
text | d554d2f2-33fa-50fb-8fde-84079cd6a9ef |  | textbox | Date
label | 7bce95d3-9a68-54fa-9cf6-716562e74236 |  | note | Checked By
text | cc05224d-d160-5ad7-81f0-03ddf828ee38 |  | textbox | APAM Name
text | 02831059-8bce-5bc6-b7d6-6dfd7ea70cec |  | textbox | Position
text | 856af1c4-2f3b-57c3-a3ac-c4d1616523fe |  | textbox | Date
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | b5f14223-83af-5988-bce0-d2787254b3cb |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 5667f712-4d35-5f56-91af-9cb8bd315874 |  | note | FH Environmental Team
label | cb65dbfa-783e-502d-a5cd-37d4090117d1 |  | note | Name: Tirrell Slaney
label | 06cd603c-7231-524f-8a38-6facc10e3546 |  | note | Position: Environment and Sustainability Advisor
text | 7806662f-c172-53cc-ac4c-d4c3352005b3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7a0ecfb6-d6b4-55e1-ad9b-901c3b4be952 |  | note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
label | 11c383dd-47f0-53c0-9b48-eca5100071be |  | note | FH Environmental Team
label | 35255392-be4a-5269-9652-39a895f1334d |  | note | Name: Kevin Gatt
label | cde55f7d-26bc-5612-9275-cf00f9193c77 |  | note | Position: Project Manager
text | 4b6b9a95-0e7f-5210-b797-c28f85fe6836 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP