## Master List Templates
Id | Type | Name | Values | Prompting Name
7727bf24-112f-4633-b1e5-3704fcd5a8c9 | checklist | 1. Prepour (11/16 PCOR) |  | 11/16 P/COR - Cage:
b73d1681-6a33-4614-adc3-29e7902a5c67 | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
6d87d21e-cec3-4c55-9af0-157967bba405 | checkpoint | Cage Inspection
6fd408f7-25d6-5bf4-8f9f-7c95e9648233 | note | Fittings Drawing No.: 3246
274a0cc3-e0d0-5cb6-8b98-2934bc6b1e79 | textbox | Cage Length (+/- 50mm)
ff2cdbb0-972f-40de-8fff-38700cad881c | checkpoint | Correct Type & Number of Studs
e4ab8020-1dac-48a3-9491-59e972851545 | checkpoint | Fittings Verification
4270f8e5-054f-5caf-ac85-01757eef75c2 | note | Correct amount, location, depth & orientation of fittings - tick to indicate conformance.
0c5f7aa3-6dfc-5b4c-be8a-2481861cf74e | note | Tubes & Hole Formers (+/- 3mm)
94a9de1e-5219-583f-87c9-35c20879c233 | tickbox | 6
5ff72f8a-7e4e-5ec6-ad77-7af910eb9a6c | note | Earths (+/- 10mm)
1a1d6907-3ca1-5505-a97d-f6651078b622 | tickbox | 3
f4e3e930-243d-510c-871e-a0f04af53f00 | note | Internal Butt Plates (+/- 10mm)
137ea398-fed2-54b8-bde5-75b72ecc464a | tickbox | 1
f3d207eb-d9a6-5039-97b7-c15b195f19f9 | note | Splice Wires (+/- 0mm)
e4e55f78-5d64-5c19-8f87-d21f13a66758 | tickbox | 2
a0a28aa0-6705-45af-b03f-9e5179d7d13d | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
1ea0c6ec-80c7-4d5e-afde-2d0fd8573822 | checkpoint | Primary Reinforcement Design No.
a372046c-893b-5d41-aac5-510de2374a9a | textbox | No.
e62edd93-6171-4d60-82ef-68519a0a81ab | checkpoint | Diameter Verification
15bd9a90-617c-573d-8348-56ccbc80a200 | note | Specification Reference: Diameter at each 1-metre interval must be within the specified MIN–MAX tolerance (mm), as per design.
5553ac48-6351-5b5c-9d40-fa089e709e7e | tickbox | Measured diameters are within tolerance
be83d1a1-6ee1-59d9-90d0-62f9cf65ae07 | tickbox | Visual check - no deformation or variation
c356a1c3-43d9-5b1d-af8b-6f10e2d3a384 | tickbox | Reinforcement Tag/Package reference confirmed.
d514423a-74e1-5edc-8c4f-bc42f4a79c6b | textbox | Enter measured diameter(s) only if variation is found, then raise an issue.
91401d7c-a3f2-4155-a8b2-8432478a7561 | checkpoint | Circumferential Pitch Verification
96d99db4-c4ec-53ef-8d73-97347f499650 | note | Specification Reference: Pitch must be located at the design spacing and match the correct circumferential wire size and type. Tolerance: -0mm
86170031-65a5-5cb1-a66d-91ce12745e21 | tickbox | Pitch is at correct design position and within tolerance
832c0433-7ea2-5ea8-b87d-350bdbcf4eda | tickbox | Correct wire size and type confirmed (as per reinforcement tag/drawing)
44d2d92a-26af-5a43-9f16-0474eac0e675 | textbox | Enter pitch measurement(s) only if out-of-tolerance condition is found, then raise an issue.
672a3002-f3df-4561-97e0-3833f1a0e59a | checkpoint | Longitudinal Wire Verification
4e0f1a13-4434-5a0a-926a-5ded0ec43b0a | note | Specification Reference: Longitudinal wire introduction points (spacing and alignment) must be within MIN–MAX tolerance per design.
cf431e8e-7561-500d-8c93-53b71786e738 | tickbox | Spot-check confirms introduction points fall within tolerance
2e8079a0-897d-55e0-a9a9-4427aa128317 | textbox | Enter introduction measurement(s) only if out-of-tolerance condition is found, then raise an issue.
04b1b998-d5a4-4af4-ab74-d7592eb39d4b | checkpoint | Visual Verification
2e2ba353-725b-5127-a97e-3d329d7db1e9 | tickbox | No visible deformation or excessive variation
2339fa1a-08a4-53c7-95d7-f06f95eadbe6 | tickbox | No unwelded longitudinals or circumferentials
e80e9ddb-153b-4746-bedd-19e7a38460d0 | section | Acceptance & Traceability
579ab6b2-149f-4c94-8dd2-d9a4f20760b9 | checkpoint | Accepted?
357c24ca-148e-5a24-b3ef-7fe7eaed2acd | note | Take a photo of the completed Package (Front and Back)
0a6cb126-a1a6-4e57-9d03-b548755f48e7 | signoff | Accepteance Signoff
fd927f6c-a38c-48ed-bc37-60b54723bf78 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3246 |  | 11/16 P/COR - Cage:
7a837aa2-c13c-4ddb-8dab-a824b39a7790 | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
053acf10-b4e1-4feb-af01-725d657e76b1 | checkpoint-no-value | Cage inspection details
f77ea5fe-f44b-5ac3-a3bf-16699f8bf203 | note | Fittings Drawing Number: 3246
e3a078d6-6173-5775-a959-727a13d5490e | textbox | Cage Length (+/- 50mm)
1c0cdd38-4b92-4c90-938d-2cc7d2b052b3 | checkpoint | Correct Type & Number of Studs
b0767ab1-3ed0-4df0-863b-79931f297934 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
839220b0-d1b0-5317-a014-72a5a444e9d1 | note | 6
c4079d1b-38cb-458a-884f-8ccbc47001c2 | checkpoint | - Earths (+/-10 mm)
194de852-f62c-58ee-8858-0662b7074d27 | note | 3
1d4db3ac-4b38-4f62-9d47-d0201c7e9ed4 | checkpoint | - Others (+/-10 mm)
bc1a13b3-0e25-57f6-80b2-6355ca545aa5 | note | 1
bcd23654-171e-4dfa-9481-570eb6f08879 | checkpoint | - Splice Wires (+/- 0mm)
892b48d1-6dfb-557f-9550-fd4492c75a0d | note | 2
3e45d487-78fa-49fd-89cf-ee75053f4808 | checkpoint | ANTI-ACCESS Wires
8bc67854-501e-4554-95aa-2a49f083d59f | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
4608a904-a9af-4b53-9081-75c02782b3de | checkpoint | Cage Diameter Details
f71a9c05-9493-58b8-bbd2-681a41ed8941 | note | Primary Reingocement Drawign No.: 1765
3a3bfd27-bf9e-5432-aa2d-3a7a3b35b142 | note | Longotudinal Size: 9.88
511c6212-4c68-50f5-a01b-6b880d929152 | note | Circumferential Size: 5.55
838a722f-5759-4932-ab06-cbefd8da7b9f | checkpoint-no-value | Distance from Tip (m) Min - Max
cda872cc-1518-5a57-9092-d113502d9a96 | tickbox | TIP 195 - 200
96be274a-c49f-5f3a-8d66-fd0d7ca94359 | tickbox | 1m 210 - 215
b79e0cbb-3329-542f-8177-0736eaafe36b | tickbox | 2m 225 - 230
cd335cfe-8945-5658-a4b9-37a0d12a2d11 | tickbox | 3m 240 - 245
7deed267-ffd5-5a75-a840-eb1914e2efa9 | tickbox | 4m 255 - 260
1cd75a2f-71c8-5e52-be8d-1d242b9cd028 | tickbox | 5m 270 - 275
baa63306-b74b-5ec4-bd0d-6d43ce77798b | tickbox | 6m 285 - 290
2beb4560-d988-5089-b8a6-0fbe59e9eedd | tickbox | 7m 300 - 305
37202374-74c6-5c25-8c58-140eefb6c35b | tickbox | 8m 315 - 320
7c55f8cf-d131-567f-8886-22bc8f2596ba | tickbox | 9m 330 - 335
0cdb0909-f6fa-55e3-aa71-0af74276213c | tickbox | 10m 345 - 350
dee42c0c-aeac-5c66-811c-b8dc4612cf54 | tickbox | 11m 360 - 365
53680034-e9f9-498e-a230-9bdbec24a309 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fa09eb79-10e4-42b9-b554-f991a9fb11ce | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
430a8bd6-fbb7-463c-9a30-6b7fd6625ddf | checkpoint-no-value | Longitudinals Details
0bee6f51-ebd6-5a5f-a619-ba1317a6791a | note | Number of Longitudinal
bb1329f9-27e6-5be7-87c1-878c120c6ada | note | Longitudinal introduction Min (m)
f29580c8-de76-5d0c-b2e8-49b344d8d072 | note | Longitudinal introduction Max (m)
11e9f38e-5400-4915-82da-a71ee1fde362 | checkpoint | 12 (1.4m -1.6m)
e67e494f-3591-4637-860f-1af611cafbfc | checkpoint | 16 (4.4m - 4.6m)
4fdc290b-e6f3-4ea7-80e7-6f7f27c63f86 | checkpoint | 20 (6.9m - 7.1m)
3975ae13-fc9d-4447-8226-ede21d0ec1c4 | checkpoint | 24 (9.9m - 10.1m)
03615099-d038-4f6d-8cbc-459250fcffaf | checkpoint | 28 (13.9m - 14.1m)
517361fb-7b23-42cb-b975-b6f691338a0e | checkpoint | Acceptance
4b9527a2-4748-4c73-a161-e2ec3252bd03 | section | Acceptance & Traceability
c5ac0398-a717-460c-bb40-5ac664fc8aee | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
20485187-7899-41e1-9086-82e686cd076e | signoff | Accepted? (Y/N) Initial
138297f0-5dfe-4523-9d4f-f881585602c4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3248 |  | 12.5/16 P/COR - Cage:
a088705a-9487-4e9f-9475-435e7697cc4c | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
e1a7128f-1f69-4178-846c-740bb4adf8ab | checkpoint-no-value | Cage inspection details
24e31726-fcb4-57ba-92c4-b91217809e6b | note | Fittings Drawing Number: 3248
64bf3951-4ce4-57e3-9d2e-48a3156fcf96 | textbox | Cage Length (+/- 50mm)
b86ec3e4-5366-417b-b4d6-a4adf22407ba | checkpoint | Pole Cap - M24
33502014-257a-5163-9fb2-268cf5e59c7a | button | 4No. 5fw x 35mm long | Y, N
614ad8fe-f806-5997-99b1-342fdc76b601 | button | Seated Square (+/- 2mm) | Y, N
4a47f610-1def-57ec-a09b-d0b94bb5dfab | button | Thread Tapped | Y, N
a2fd89d1-c529-4055-a7d0-6ee4dfd0af75 | checkpoint | Correct Type & Number of Studs
141c3e37-b01c-4c60-a6a9-d306f9acc1f1 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
e3ab6daf-dd41-580a-8202-eee901266c54 | note | 6
22714eaa-7082-49f6-be40-73dca55d7f6d | checkpoint | - Earths (+/-10 mm)
59b49db2-6b14-558a-a0bf-fec37382f4fe | note | 4
7ff025c8-febf-4f85-a1c1-7a5bb86a4c7a | checkpoint | - Others (+/-10 mm)
6feb116f-f872-531c-88c6-e887fc25af7a | note | 1
68b4ed1e-a61f-4b30-a00c-98dd705a9113 | checkpoint | - Splice Wires (+/- 0mm)
7372c2f5-b5b6-521b-8c9f-15908de774c8 | note | 6
4165988c-0375-48d3-8153-3eb5ba065137 | checkpoint | ANTI-ACCESS Wires
76f40190-da91-4173-9136-3ce06a6404cd | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
dee40e2f-2bf5-4edd-9498-f70fb6dffd9e | checkpoint | Cage Diameter Details
10eac8bd-9bf3-5b9e-99ef-6072f6bbf77c | note | Primary Reingocement Drawign No.: 1764
587059be-acb4-533b-9540-34622b785507 | note | Longotudinal Size: 9.88
b7f08c9a-5ef8-547c-b77c-efea5b281ee4 | note | Circumferential Size: 5.55
f2b6b6b5-6d57-472b-8fd6-2475a8dfdfd8 | checkpoint-no-value | Distance from Tip (m) Min - Max
3d5376be-62cf-5894-9cfc-451d16387cef | tickbox | TIP 195 - 200
792c62bf-42de-58f8-b8ee-e83539f9a409 | tickbox | 1m 210 - 215
cf9ffd66-6c03-5314-a7ee-8b44ffd5c994 | tickbox | 2m 225 - 230
18bae7b4-1095-51e9-aaa0-93df7db97fce | tickbox | 3m 240 - 245
58f4c681-4d17-5cd1-a313-8e2c683fa048 | tickbox | 4m 255 - 260
1c5513c1-294a-5576-bcf2-e141a464b79f | tickbox | 5m 270 - 275
1ebdbb8b-9246-5cee-a8d5-491a9ea558ac | tickbox | 6m 285 - 290
e6f0f8f7-1705-53f6-85ad-35511d59030c | tickbox | 7m 300 - 305
a033b60f-9ac4-5577-b5e9-836511ab1194 | tickbox | 8m 315 - 320
2c05e30e-4290-52c3-bcf2-8b2e73d749b5 | tickbox | 9m 330 - 335
e77910ad-9e35-59b7-9210-e01ac7a0cb5a | tickbox | 10m 345 - 350
ae538cb7-f871-5a6f-b3e7-d2fce792a788 | tickbox | 11m 360 - 365
1bfd4180-559d-5ad5-b58d-a87e8d094539 | tickbox | 12m 375 - 380
807be7ef-9698-54e8-b9f3-a7ac278161f3 | tickbox | 13m 390 - 395
1e398136-6c14-4e7f-81c5-a66a2210cf52 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
763485db-35e6-4ecb-8c75-6417e57f3e4d | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
41a6da3a-dab1-460c-b3ed-aaf2a593bd10 | checkpoint-no-value | Longitudinals Details
5e52dbc5-9fc3-56a4-83d7-18deae539f1e | note | Number of Longitudinal
3fb431c9-694c-5954-9371-c1e1b93fd3f3 | note | Longitudinal introduction Min (m)
5fd75918-263c-569d-81a2-0e13baf41176 | note | Longitudinal introduction Max (m)
7717066d-31d5-4184-a8de-1bd945dc6e23 | checkpoint | 12 (1.4m -1.6m)
726b599f-b209-43a3-871f-6c30eefd1a94 | checkpoint | 16 (4.4m - 4.6m)
389d4e9c-294e-439c-a013-13e18025a199 | checkpoint | 20 (6.9m - 7.1m)
b07f0fde-f29a-4bd3-98e9-0fd0030f8b58 | checkpoint | 24 (9.9m - 10.1m)
dd8dcfdf-3d1c-42cc-a7c9-79f342ed65d4 | checkpoint | 28 (13.9m - 14.1m)
777313bb-29f5-43ed-b22d-85a5a3379532 | checkpoint | Acceptance
d3f88fa8-7cff-43cb-bc2c-2d814d67421c | section | Acceptance & Traceability
9cae71a3-3dc2-4c82-858f-2b30c2cdc13b | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
d0c9f3da-f7a2-4246-b0b1-b14d7d5f850b | signoff | Accepted? (Y/N) Initial
d2973624-523a-4fed-8cfe-d187a49bac85 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 3249 |  | 12.5/24 P/COR - Cage:
56cd6fe7-e17b-4b2f-8f50-19108b3e9dec | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
af8e7a41-30a9-4a70-806e-38239d677707 | checkpoint-no-value | Cage inspection details
9b0fb319-d7aa-599b-b41b-e163f6e4f407 | note | Fittings Drawing Number: 3249
2837cbd5-4c17-51af-bd12-eb5e426ac114 | textbox | Cage Length (+/- 50mm)
1a331a1c-a72d-496e-9160-eecd31103c72 | checkpoint | Pole Cap - M24
af5b0609-87e9-5c07-a456-8653672e39ba | button | 4No. 5fw x 35mm long | Y, N
e2e1fca4-be35-5b55-b23f-a2ac0d248edf | button | Seated Square (+/- 2mm) | Y, N
1e8e7741-702a-5d60-89f9-7414aa3fb673 | button | Thread Tapped | Y, N
ac40409e-5703-4f84-b99b-490d8085e905 | checkpoint | Correct Type & Number of Studs
712dcc76-bb8c-46f3-8a2a-1cff7215b160 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
de7b03b6-2f33-5af8-acd5-853bc065b94c | note | 6
af57ba30-0d0a-4b49-8978-2c2949a3b2fb | checkpoint | - Earths (+/-10 mm)
6997d620-e698-53aa-8ae6-7aa547479cb5 | note | 5
86b336f4-32ee-46e7-acab-dd8dfa41dc4d | checkpoint | - Others (+/-10 mm)
437eaf52-17e4-5eee-b96f-f2de4da0d242 | note | 1
fc4c84c9-6b0e-4dbd-ab08-5497c6fc8165 | checkpoint | - Splice Wires (+/- 0mm)
9f10eaa1-ed09-53f3-80d2-282b09299a27 | note | 6
bf2c230f-cde2-4ec2-8e4e-9b5e2276d58c | checkpoint | ANTI-ACCESS Wires
754da598-b2f8-4679-82ff-3716815bc9dc | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
5c39e25c-5693-474f-869a-7b14397a4689 | checkpoint | Cage Diameter Details
e27e8997-ad02-572d-8249-08cd74aeda2e | note | Primary Reingocement Drawign No.: 1766
7a6e558e-4cc5-5fff-8126-93fdf23ac970 | note | Longotudinal Size: 9.88
a8d01f3f-0285-57ce-b348-9414e44b0d85 | note | Circumferential Size: 5.55
cc46df13-3d55-4db6-bc1e-54544d46339a | checkpoint-no-value | Distance from Tip (m) Min - Max
faacdad0-4b22-53cc-92b3-d40876949044 | tickbox | TIP 195 - 200
d727cb5c-339a-5b78-97db-581408513ef7 | tickbox | 1m 210 - 215
3afaa058-66d3-5e6a-86a7-391502cf5804 | tickbox | 2m 225 - 230
f03113be-75bb-52df-ad59-ba74d220b079 | tickbox | 3m 240 - 245
17d671f2-0309-5770-b1b0-479d36fd64f4 | tickbox | 4m 255 - 260
7d5f0825-185f-58be-9931-74e102ba35b2 | tickbox | 5m 270 - 275
417a9109-4549-55db-901d-bde109ad662a | tickbox | 6m 285 - 290
9c60a0e0-58ec-5555-9c07-1d2395dddd81 | tickbox | 7m 300 - 305
2d257d7b-a776-51c1-97ae-bd05bf127c4b | tickbox | 8m 315 - 320
cfc0bc64-cca4-5f23-a24c-23b2de4ff77c | tickbox | 9m 330 - 335
c91f8c39-f61f-5d1c-9a2d-f792e2582eed | tickbox | 10m 345 - 350
20d6efc8-4e04-559e-9208-17b2ccaa86cc | tickbox | 11m 360 - 365
6ef3ac7f-d6ef-59ad-961f-fd510faa996b | tickbox | 12m 375 - 380
389440f0-8515-5a67-8cb3-bc3dd096da49 | tickbox | 13m 390 - 395
069bc1fe-e4b5-479a-a4f8-1ccfd9890c52 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
39a54ecb-27b8-4de3-817b-8f84789e8652 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
d9847f2a-1563-4326-966b-6676545089cc | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
4c28218a-9486-4f5d-9f2c-d36b28febd47 | checkpoint-no-value | Longitudinals Details
c9d63758-4882-53d5-9496-6f77d442a0d8 | note | Number of Longitudinal
9bc1b02d-03d7-554b-aad5-f76cd25b76ac | note | Longitudinal introduction Min (m)
5a6ba63c-ac26-5c1b-8d8f-604d6c28fe70 | note | Longitudinal introduction Max (m)
1f648762-8d1b-4ce1-b570-a030450aa474 | checkpoint | 16 (1.4m - 1.6m)
86bd4edb-39e8-4a65-9e28-c440cfd96552 | checkpoint | 20 (2.4m - 2.6m)
72ac5c43-ef6d-4a3c-9d89-70fc25e675a9 | checkpoint | 24 (4.4m - 4.6m)
07e49ec5-4a67-4194-936f-a4fde0e7d212 | checkpoint | 28 (8.4m - 8.6m)
ad56e298-2cdc-4093-b928-b4278008d93a | checkpoint | Acceptance
109d52bc-e228-4113-ad24-0aa5bd4192ee | section | Acceptance & Traceability
7e1feb1c-3f96-423f-a0e5-3345fd5ea8fd | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
d41fa4f2-4633-4cfc-ac5a-18986bc1a1b5 | signoff | Accepted? (Y/N) Initial
26756598-5be8-4a0f-9038-e7e32419dcc4 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5589 |  | 11/16 SPAN - Cage:
c73bdafb-b7d4-4d09-8093-f1112a3791cd | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
e667259d-007b-4e2f-afa5-33712c87571c | checkpoint-no-value | Cage inspection details
0736ec19-ee30-536d-b6d9-d32259a99d81 | note | Fittings Drawing Number: 5589
a92bde2a-e9c1-51c5-8ccb-1b084e00731e | textbox | Cage Length (+/- 50mm)
a0adf7c0-6298-45bc-8e58-6f66a18bcdef | checkpoint | Correct Type & Number of Studs
1f1fa794-d0e2-46b5-b550-ea99275900e4 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
2705fc95-abad-5ad7-913b-9cbf55a426fb | note | 6
902e6167-42f0-41cd-8778-d71bd56bb9ab | checkpoint | - Earths (+/-10 mm)
cf8e75d4-db1a-5ae9-b646-838f82bacc6f | note | 2
7ddb9318-e6d6-4f4f-8aa0-f522e74b9f50 | checkpoint | - Splice Wires (+/- 0mm)
a9351838-f772-5389-8410-715bd7f696cb | note | 2
1ae766a8-e6ce-4050-aac8-18a2e6e2afa0 | checkpoint | ANTI-ACCESS Wires
d35c27b5-315a-41ae-9e19-c368ccf522c4 | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
4a5cd9b9-ef53-4dfa-837c-a4aacf7a61bf | checkpoint | Cage Diameter Details
add99e13-f631-55a2-8ea9-3c4cf10dd74d | note | Primary Reingocement Drawign No.: 1765
0737e1d7-e2de-5525-b0b1-5e56d1dbe5fe | note | Longotudinal Size: 9.88
a96a1e4f-837d-566b-8fa1-afdea66f2f0e | note | Circumferential Size: 5.55
574a5595-e205-4d77-9bf6-2cd671c3f960 | checkpoint-no-value | Distance from Tip (m) Min - Max
e23a42e2-82e6-5be9-9309-49a11d7ad42b | tickbox | TIP 195 - 200
98347156-321f-5391-bdb3-ab280f5f1e5f | tickbox | 1m 210 - 215
ea206c6d-ea1b-5194-affc-c33e54439a42 | tickbox | 2m 225 - 230
81ca6c86-9554-5767-ba6a-bd5814738930 | tickbox | 3m 240 - 245
99130bf9-72b9-54f9-b5ee-efeef559bbad | tickbox | 4m 255 - 260
e317324f-a784-53fd-bccb-00e2ec1cf2f5 | tickbox | 5m 270 - 275
c64bb5ee-7572-5da7-8ade-3c5c010f72dc | tickbox | 6m 285 - 290
ed8538f4-2190-511c-994c-19c63adcbba8 | tickbox | 7m 300 - 305
50805332-a2fd-53a9-a85e-bb86303411b1 | tickbox | 8m 315 - 320
208de21d-5489-5e97-8e1d-88d16179fe3b | tickbox | 9m 330 - 335
052ea74d-1b9c-5f59-9c4f-b02b59899b7d | tickbox | 10m 345 - 350
28cbde63-f4f7-514b-a75e-4114861c4bff | tickbox | 11m 360 - 365
d112fc3f-6072-4a18-9fc6-8196b250b9a0 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
c562b6cf-3532-4a14-9d88-db0ef999ae2e | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 11m (1.5m>11m)
bc0e8581-f220-495c-b876-e6511d41a161 | checkpoint-no-value | Longitudinals Details
6d332a3a-b59b-5d65-ac68-c8c4519218d4 | note | Number of Longitudinal
ab77be31-c5fb-5877-a547-4cc5410139d4 | note | Longitudinal introduction Min (m)
415c962c-5e0d-58ec-bca4-94fe387c027d | note | Longitudinal introduction Max (m)
eb3dd763-b117-49d5-b0e3-b81f887a253b | checkpoint | 12 (1.4m -1.6m)
1fe0024f-5ad8-4851-a36f-dcdd1564f4ef | checkpoint | 16 (4.4m - 4.6m)
b92925fd-090d-409e-9cdd-f6218e711429 | checkpoint | 20 (6.9m - 7.1m)
a97905f2-ed13-40fd-9dac-e18f5291c4f3 | checkpoint | 24 (9.9m - 10.1m)
5dd1cf85-a976-46db-acb9-8f33a680c3d2 | checkpoint | 28 (13.9m - 14.1m)
aa8793b9-f554-4c02-8192-834db141f1c1 | checkpoint | Acceptance
2eab78bf-5734-4672-91bf-fd3c75c51a32 | section | Acceptance & Traceability
ea352781-d993-45ee-a706-25d32a9400b2 | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
8ac793e3-bbaf-479c-96b4-295122ceee70 | signoff | Accepted? (Y/N) Initial
6fef6a68-0533-4108-999a-346725b445a8 | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5593 |  | 12.5/24 SPAN W/S - Cage:
f6e5c00e-0df8-41ae-ba2c-c4e4307b33e1 | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
473baf41-a997-495b-beb0-a3569f440bc0 | checkpoint-no-value | Cage inspection details
7e3fd408-4e86-5ac0-865a-942d43fffef6 | note | Fittings Drawing Number: 5593
64af15b4-50d5-59ab-82ba-5b89e35efabe | textbox | Cage Length (+/- 50mm)
fb91c63f-8889-4bc2-909a-5f06b01ab3aa | checkpoint | Pole Cap - M24
f8c5324d-7d58-586f-b6c0-1f02f301fcfc | button | 4No. 5fw x 35mm long | Y, N
36a1435f-1c6f-5e99-98fa-dc3d713ead03 | button | Seated Square (+/- 2mm) | Y, N
88642b89-87da-55ef-b5a2-4c34b350430e | button | Thread Tapped | Y, N
04396cf2-6475-41ae-bc50-2c23c706c252 | checkpoint | Correct Type & Number of Studs
5a15b685-79b4-493c-a2fe-d730af92baea | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
b8f7c6ff-82bb-5190-bc90-c67272eaf8dd | note | 6
ff262906-4fef-4d7f-893b-16a894346e25 | checkpoint | - Earths (+/-10 mm)
430b5dbb-9081-5956-870c-dbd6a9b1ebf0 | note | 4
188fdc77-cb73-417c-bebb-4e418f10c8b0 | checkpoint | - Steps (+/-10 mm)
11b01569-b0a8-5886-ac94-9bd0ea285b2d | note | 7
786d51ea-67bf-46f2-99c2-64009cea5451 | checkpoint | - Splice Wires (+/- 0mm)
f23877e7-8384-5f7f-92b2-23048e18295d | note | 6
51f95ff4-15fe-48cc-aa2e-fb2b6a83f6a4 | checkpoint | ANTI-ACCESS Wires
f3b71e3d-82ae-4c9e-bdf6-8e605f09925b | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
49b5d406-dd32-488e-8603-62bb0e0ecd27 | checkpoint | Cage Diameter Details
7619ffec-d23e-547d-9e95-f0b474368bc1 | note | Primary Reingocement Drawign No.: 1766
57842c89-65f9-50e1-8d48-a4ad52942cdf | note | Longotudinal Size: 9.88
386600b5-12c2-5025-a743-bc13e816fe0f | note | Circumferential Size: 5.55
16806b2b-3e43-47d0-81df-b2c4170aa9ab | checkpoint-no-value | Distance from Tip (m) Min - Max
b99148c5-d341-5353-922a-3bd0762b0811 | tickbox | TIP 195 - 200
f3276907-c684-50c6-b91a-eb2d82a93ed4 | tickbox | 1m 210 - 215
d3cb9ece-c6d1-55f2-adb2-fe2f9ed905ca | tickbox | 2m 225 - 230
e27cf682-1db8-588b-a7a1-675cc26f5dd1 | tickbox | 3m 240 - 245
5c587646-4535-545f-ae58-d4085f183cb9 | tickbox | 4m 255 - 260
a6dc6021-db74-52f1-b054-bad0362ace65 | tickbox | 5m 270 - 275
64f7fb61-2461-56c5-ae52-6e28cd43d0fe | tickbox | 6m 285 - 290
98cc8c9c-6342-5e47-bbdf-9b83e3edf606 | tickbox | 7m 300 - 305
be81092d-5e94-5b03-bae1-da6d73c911bb | tickbox | 8m 315 - 320
b6175cdc-549a-5742-8caf-cb5f1fd78ca3 | tickbox | 9m 330 - 335
b5661983-932b-57a1-ad89-22bb5f5eee7c | tickbox | 10m 345 - 350
372bcd54-5c52-5292-b78b-c73171113546 | tickbox | 11m 360 - 365
cbaf8199-ff16-5e70-918a-54fb5219e836 | tickbox | 12m 375 - 380
0d44584e-0def-5224-9b43-78e559d42d80 | tickbox | 13m 390 - 395
ec08196c-fe37-4134-b1fc-e1a5f2a82a63 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 0.5m (Tip>0.5m)
479d886c-88e2-4252-8661-2eeb2b7ca121 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 9.1m (1.5m>10.6m)
c151c6ef-211f-48e6-a77c-7227b62d1d8f | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.9m (10.6m>12.5m)
355411e9-fec6-4e59-a19b-1f915fb47944 | checkpoint-no-value | Longitudinals Details
36536db3-92d3-5d20-b913-0ca98f133704 | note | Number of Longitudinal
8d434f0d-b28e-5e1d-a305-91c54a6332ca | note | Longitudinal introduction Min (m)
a3d060bc-8e94-5e8e-81fb-269dadb7c964 | note | Longitudinal introduction Max (m)
43715909-72e6-4e4a-a8ab-cd6a276c275e | checkpoint | 16 (1.4m - 1.6m)
c31a6fc8-e106-4041-9d3b-9a9ecf513393 | checkpoint | 20 (2.4m - 2.6m)
2ad4962d-08ff-4d15-9f37-aa2938bc9faf | checkpoint | 24 (4.4m - 4.6m)
fbed1f1e-1537-49d5-8118-7833160652aa | checkpoint | 28 (8.4m - 8.6m)
ea35251d-1072-445e-a4df-ebd8a2c88020 | checkpoint | Acceptance
92607073-b0b1-44b5-85bf-6c862adf8786 | section | Acceptance & Traceability
f5f061e8-5db1-448b-a310-42dae81bf6d3 | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
2fb49253-7705-4624-bdce-5c41a1631533 | signoff | Accepted? (Y/N) Initial
3828ab13-7bfd-4733-b2e5-df918d0d74fc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5594 |  | 12.5/16 SPAN W/S - Cage:
f27c050b-d801-4714-aa38-9eb7252e707f | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
93b0b319-f988-4ae7-987f-a9a2a69b131e | checkpoint-no-value | Cage inspection details
82fe3052-cbab-573f-8902-3cf1df87385a | note | Fittings Drawing Number: 5594
de3b377a-8ef4-5326-a155-3eb2d442c07b | textbox | Cage Length (+/- 50mm)
64c0d07f-e62c-4795-8469-f394208052bd | checkpoint | Pole Cap - M24
6a4073ab-791f-5207-843e-044fe07ba069 | button | 4No. 5fw x 35mm long | Y, N
9d71c366-dc28-5ed3-8207-b3fc1b12f7bb | button | Seated Square (+/- 2mm) | Y, N
e8f6b0ce-0d48-5061-9a98-66a427fe26dc | button | Thread Tapped | Y, N
b293f3c7-3ebf-442d-8f21-ef30f82d7fe5 | checkpoint | Correct Type & Number of Studs
a7f7a90e-d2d8-46da-ac6c-831153cca327 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
f9426846-a7b1-556b-9cea-40f4b22c9173 | note | 6
93b84c79-49e7-4949-8554-1359bae45ead | checkpoint | - Earths (+/-10 mm)
f384b6c0-abaa-5ea7-a33b-bfef4c432e75 | note | 4
c6e7e469-a033-4341-99f9-e70a568f765d | checkpoint | - Steps (+/-10 mm)
2cb18d18-c74c-589e-bf8e-f0c67833cd22 | note | 7
ca05cb3c-10af-4725-8688-772cafb0e459 | checkpoint | - Splice Wires (+/- 0mm)
3423f176-3591-5354-a994-7ea372bf3bc6 | note | 6
485a3147-50e4-482d-8e18-fe95ab4e9163 | checkpoint | ANTI-ACCESS Wires
07f43247-01ee-4969-881e-8b006f82ac4d | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
ef9fd327-576a-4c15-a08d-b68367e206c0 | checkpoint | Cage Diameter Details
1f273cb3-abb1-5d2a-86bf-f6c0c39f9487 | note | Primary Reingocement Drawign No.: 1764
a6df44d1-f3ed-505c-a7fe-4ff272708895 | note | Longotudinal Size: 9.88
78595ebf-ecb9-56e2-baba-0e2e49c2eba4 | note | Circumferential Size: 5.55
a1f50101-bad8-471e-a7e1-93e3ec2430c1 | checkpoint-no-value | Distance from Tip (m) Min - Max
683918bd-c4fd-5900-8e21-fe54ababc2e2 | tickbox | TIP 195 - 200
c444b7a7-bbe4-587a-8824-9251123da8a9 | tickbox | 1m 210 - 215
4e4b9dd5-15e1-5cd2-af34-7fb268c3f91f | tickbox | 2m 225 - 230
969d8b4d-7c88-54da-a880-aca0a5afa08e | tickbox | 3m 240 - 245
8d7a53da-2a94-58fa-ac66-0859ce957b45 | tickbox | 4m 255 - 260
6736d553-9051-5889-bf16-a5f0e2cb6248 | tickbox | 5m 270 - 275
bde09ee6-5e07-59aa-ae97-1bb9fd84a7bc | tickbox | 6m 285 - 290
a098e223-8197-595c-b85f-e61901cf62f6 | tickbox | 7m 300 - 305
aedfeaaa-0e16-5340-b389-626600868d84 | tickbox | 8m 315 - 320
b161811c-c0f4-5fc1-80b0-ceabe55b3bc2 | tickbox | 9m 330 - 335
72c6f837-432a-5cd2-aa40-7913d9242a53 | tickbox | 10m 345 - 350
265ae906-bbf4-5fad-a8f4-0c090c999800 | tickbox | 11m 360 - 365
fbc272f5-a6bb-5d40-9787-4b80cfee5a01 | tickbox | 12m 375 - 380
724e74c0-b9e4-5616-92f4-34c2e665b82f | tickbox | 13m 390 - 395
a7e49f18-a1ee-4840-84d5-583ce21aa245 | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
fea45de1-aabf-4a19-af19-f2dc68fb637f | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
c6844705-1892-4494-80d2-530df6a57f8e | checkpoint-no-value | Longitudinals Details
897d632b-de8a-58f7-afeb-6cb75967e86c | note | Number of Longitudinal
93568b1e-75ae-5c33-8087-2304db809802 | note | Longitudinal introduction Min (m)
e4ab5efb-a53e-5289-bd01-bb6ec40e5730 | note | Longitudinal introduction Max (m)
b71ad0df-5ab9-42e7-8ab4-3733622496b8 | checkpoint | 12 (1.4m -1.6m)
0fa21303-81ec-4800-bf17-9006e85c98b1 | checkpoint | 16 (4.4m - 4.6m)
07d89d18-f5fb-4ed1-b7d4-39e6a0fbedf5 | checkpoint | 20 (6.9m - 7.1m)
bfa3ea27-d8e0-4b34-97b5-1f4cfd93703f | checkpoint | 24 (9.9m - 10.1m)
705b1420-66bf-4239-ad6f-d8cbaadbcf00 | checkpoint | 28 (13.9m - 14.1m)
ece5c504-995f-4392-9257-0f8a21401d75 | checkpoint | Acceptance
d2434d60-ab9f-489e-8a79-586e116789c2 | section | Acceptance & Traceability
fd9758cc-1442-4d37-9c00-a74e111bae1e | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
938f6446-d907-43b5-bc0a-38313763c541 | signoff | Accepted? (Y/N) Initial
b9751522-4e1a-4492-bcd9-a58a054eb4dc | checklist | 1. Prepour (Secondary and Primary cage inspections): Fitting Layout 5595 |  | 12.5/16 SPAN N/S - Cage:
db9cb702-e411-4189-ba04-ee6bdd5be38f | section | QA_FOR_010_Reinforcment Inspection (Secondary Welding)
2882432a-1787-43df-9949-fff00850bd50 | checkpoint-no-value | Cage inspection details
148cc336-3e14-528f-bdc8-3247d60083e0 | note | Fittings Drawing Number: 5595
63c9460c-cb46-5a5f-9671-1b39bb49724c | textbox | Cage Length (+/- 50mm)
42ef8c96-dd04-423a-9233-2351a673522e | checkpoint | Pole Cap - M24
e1dd98ae-0cff-597b-8fde-3cbf9c6b9a08 | button | 4No. Welds | Y, N
c10ae6de-af67-51b5-8678-c12b74eab35a | button | Seated Square (+/- 2mm) | Y, N
4e84611b-430b-59c6-b01c-b10197be76b4 | button | Thread Tapped | Y, N
011545f4-c4d0-4ae9-99b5-7ed1be4d2f1a | checkpoint | Correct Type & Number of Studs
c4978b4e-8c5c-4e66-961c-e714a60f7c65 | checkpoint | CORRECT NUMBER, LOCATION, DEPTH & ORIENTATION OF FITTINGS - Tubes & Hole Formers (±3 mm)
1e0c14c9-be0e-5e9d-9727-fa43eaebae64 | note | 6
e7c74590-5f01-467d-be37-ef105c830cd2 | checkpoint | - Earths (+/-10 mm)
c4754220-b7a5-501b-8240-291dd9e797af | note | 4
0329b24f-8489-4d1e-869d-fdd658b3dc20 | checkpoint | - Splice Wires (+/- 0mm)
20884513-df4e-5e0a-853e-472364ee65fa | note | 6
603a23b6-988d-4737-acef-c98d0cb8549b | checkpoint | ANTI-ACCESS Wires
b35a9d04-41a4-4efc-af30-33e5795bbf91 | section | QA_FOR_011_Reinforcment Inspection (Primary Welding)
ce0f7c09-5143-4325-b718-302807762da9 | checkpoint | Cage Diameter Details
6238ae9d-2024-5f93-824a-c31a7eeaceca | note | Primary Reingocement Drawign No.: 1764
c8e7149b-16df-5c0b-b2c3-097f59931de0 | note | Longotudinal Size: 9.88
2c77af15-819a-5dc3-b370-9ee61b6553a0 | note | Circumferential Size: 5.55
7fe2d4ba-e2df-48c0-8a54-c592ac55678b | checkpoint-no-value | Distance from Tip (m) Min - Max
d5d4f296-d494-56b6-b534-70752af7ec04 | tickbox | TIP 195 - 200
89ce744f-6c26-5188-8eee-b05f4d127639 | tickbox | 1m 210 - 215
3379899a-e358-5e39-85b9-75728d1d815d | tickbox | 2m 225 - 230
16d0d4a3-0385-57a4-b47b-a014ed484efb | tickbox | 3m 240 - 245
57fc1a3d-1fcd-5d84-867d-421abd1021bd | tickbox | 4m 255 - 260
96131855-56c2-59d8-abb8-56601fc997fa | tickbox | 5m 270 - 275
f3491eca-cd87-527e-97a5-51b0f0ebae4b | tickbox | 6m 285 - 290
d1d755b0-54ac-5a02-983a-28a722a19c61 | tickbox | 7m 300 - 305
cce3ab02-2268-503d-9e92-adaba83f2337 | tickbox | 8m 315 - 320
887aeb15-ecc3-518b-9aed-dac2920653b6 | tickbox | 9m 330 - 335
3e65f8c8-d9e5-5387-9de5-b50f91ee3eb9 | tickbox | 10m 345 - 350
cd9f06e1-cd1a-5e23-9c58-d1c44351df16 | tickbox | 11m 360 - 365
1c1a5005-92a6-5e3f-8149-b37c8a3d50dd | tickbox | 12m 375 - 380
8eca0c86-bf43-56a3-8439-04fe6e8dd03f | tickbox | 13m 390 - 395
a8827e6d-2eb0-41b0-a3f1-9d1905f810ef | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 80 pitch for 1.5m (Tip>1.5m)
0871f9b3-f385-4dd3-9dfd-0e62fb8dce6d | checkpoint | Check Pitch Finish - Distance from Tip - Circumferential Pitch - 160 pitch for 11m (1.5m>12.5m)
cd8974b2-0e0d-4a41-8507-ef701b7a49d2 | checkpoint-no-value | Longitudinals Details
331109f1-e8d3-5d09-884c-2b2a5bf057c7 | note | Number of Longitudinal
26fd10ca-e0a8-5322-a945-5433f3432062 | note | Longitudinal introduction Min (m)
efcaa250-af69-555b-8aef-4b4b5965fae5 | note | Longitudinal introduction Max (m)
c355aec6-f15b-49e1-8a3e-1ce21be9ae77 | checkpoint | 12 (1.4m -1.6m)
3258cd4a-4872-44c2-909f-afc1000a3baa | checkpoint | 16 (4.4m - 4.6m)
691fb529-0e78-4f31-a806-fe5a87d817ed | checkpoint | 20 (6.9m - 7.1m)
77bdac51-7691-47b2-b435-a4992f474c37 | checkpoint | 24 (9.9m - 10.1m)
47c9df14-425d-4c8c-a2c1-6c1542e4e3a5 | checkpoint | 28 (13.9m - 14.1m)
87a1af3a-135f-479f-a68d-3d18ee0ff339 | checkpoint | Acceptance
20006314-c9e1-4452-bbed-add50d26cd65 | section | Acceptance & Traceability
cc3d0128-a60a-48ee-8a7f-4595729b4dba | checkpoint | Take a photo of the completed Package or Production Tag (Front & Back)
f86a588f-e182-4c96-952e-760ad3c16f4c | signoff | Accepted? (Y/N) Initial
5584b714-a7d1-42b8-bbc9-cf1cb540cc1f | checklist | 2. Postpour (11/16 PCOR) |  | 11/16 PCOR - Product Number:
ef78a5d2-e36c-460d-8dbf-69a28caebe7b | section | QA_FOR_021_Finished Production Inspection
4e5c7ac0-ebd9-4008-9035-ecdaf0f0920f | checkpoint | Product Details
1b42eb4a-e241-5e63-a017-07fb640f0941 | number | Mould Number
6e47c74a-ccde-51be-87f1-dafcbb07722e | note | Fittings Drawing No.: 3246
74044f15-23e3-50c2-b005-26d4ebdde14b | note | Reinforcement Design No.: XXXX
4a5fb6a6-93e6-42c7-886c-14c1dc7b94e2 | checkpoint | Product Inspection
732f24e7-6bd5-5e53-a8f8-17a0af145e16 | textbox | Product Length (+/-50mm)
2e6f6267-68b5-5f1f-a5f8-13e44890f82e | button | Fittings Tapped & Plugged? | Y,N
7581d23a-dfda-57ca-9314-98b847e8d0ac | textbox | Wall Thickness - Tip (mm)
e3ba7b90-b3f4-5377-9279-4448ea1e672b | textbox | Wall Thickness - Butt (mm)
5a56abc4-b99c-4526-b98e-562a5c001002 | checkpoint | Fittings Verification
2b872a58-db4d-5a30-ba4e-69383c39ee31 | note | Correct amount, location, depth & orientation of fittings - tick to indicate conformance.
137eacac-1135-534d-be88-c56f84823c88 | tickbox | Hole Formers (+/- 3mm) = 6
7f5d737c-4cd5-5cbc-8d5f-8685896b4b0e | tickbox | Earths (+/- 10mm) = 3
ce58eafb-6266-55ab-9c8d-fceab66043e4 | tickbox | Internal Butt Plate(+/- 10mm) = 1
2db1ced2-df0d-4429-bd82-4c863fe5d024 | section | QA_FOR_022_Visual Quality Inspection
d02efc67-f601-456d-826d-b76d714e1771 | checkpoint | Visual Inspection
901c5e67-2db1-516a-a6d1-e45d11d1fe21 | note | Raise Issue for Each Occurance - Reference Quality Code.
49a892f8-f605-5e71-8b46-8fc89d47b005 | note | A. Exposed reinforcement
41f0d3b9-f3d2-588a-93e7-e789213c8b5c | note | B. Squareness of ends
ef4770be-1daf-5b31-9df1-8d3e26b94fbd | note | C. External finish
dda66ab9-b853-5e67-b4f4-84025cb04f76 | note | D. Exposed reinforcement
f9ca7ebf-cff6-5207-a9ca-b152da3d1a7d | note | E. Squareness of ends
8905a0fb-d4f4-5f2d-a686-1c4668bc355e | note | F. External finish
d6723bcc-db19-58a1-96c0-ac6fee1b25ad | note | G. Exposed reinforcement
5cffea96-bbdb-5947-b183-bd1b280f8c43 | note | H. Squareness of ends
30791372-1ea5-5875-91f2-509c0f7be54e | note | I. External finish
7ae71bd0-5402-5ef6-a436-9c786df01f4d | note | J. Exposed reinforcement
e452dcc1-517e-5424-9fe8-8ae14a808bad | note | K. Squareness of ends
735c6087-dbcc-580d-b953-24189352d4da | note | L. External finish
a6d5d6e5-65fc-5f97-a6ef-ffa14d7aa1e3 | note | M. Exposed reinforcement
9176d58d-ba35-56e3-9574-f2ac93c679f4 | note | N. Squareness of ends
4e4e3082-3051-533f-94ee-416dc26a3b27 | note | O. External finish
b529a6d6-8dbf-5299-a958-cc3e85df4cc5 | note | P. Exposed reinforcement
faa5df6e-8672-52f9-818c-fc7b466e8a05 | note | Q. Squareness of ends
d49890d8-002e-5e3b-a824-9eb43d140b86 | note | R. External finish
ea9f7ea0-eb06-51c4-bbe7-e52d45074ea4 | note | S. Exposed reinforcement
eae29272-1d60-5d47-8cd5-fe2b63322365 | note | T. Squareness of ends
ee27a01f-7f62-544b-a18e-a0bb3633b28f | textbox | Total Faults
daab700b-0f92-5294-81ba-5361717f89cb | textbox | Corrective action taken to rectify:
bfea48cc-1e33-472c-8778-aa4970af770b | section | Acceptance & Traceability
dade7a5e-4bc6-46a4-92cc-81071af2d81d | checkpoint | Accepted?
759b6de8-4b37-59f8-a61c-d7b96f975b8a | note | Take a photo of the completed Package (Front and Back)
c27cbd2a-d7eb-43c2-b76d-a944de109bd5 | signoff | Acceptance Signoff