## Master List Templates
Id | Type | Name | Values | Prompting Name
| checklist | 1. Prepour (11/16 P/COR) |  | 11/16 P/COR - Cage:
| section | QA_FOR_010_Reinforcement Inspection (Secondary Welding)
| checkpoint | Secondary Reinforcement Inspection
| note | Fittings Drawing No.: 3246
| textbox | Cage Length (+/- 50mm)
| checkpoint | Correct Type & Number of Studs
| checkpoint | Fittings Verification
| note | Inspect correct amount, location, depth & orientation of fittings - tick to indicate conformance P
| tickbox | Hole Formers (+/- 3mm) - Qty: 6
| tickbox | Earths (+/- 10mm) - Qty: 3
| tickbox | Internal Butt Plate (+/- 10mm) - Qty: 1
| tickbox | Splice Wires (+/- 0mm) - Qty: 2
| dropdown | Additonal Splice Wires Added | 0,1,2,3,4,5,6,7,8,9,10
| section | QA_FOR_011_Reinforcement Inspection (Primary Welding)
| checkpoint | Primary Reinforcement Inspection
| note | Primary Reinforcement Design No.: 1765
| checkpoint | Diameter Verification - tick to indicate conformance P
| note | Spec: Diameter at each 1-metre interval must be within the specified MIN–MAX tolerance (mm), as per design.
| tickbox | Measured diameters are within tolerance
| tickbox | Prodcution Tag/Package reference confirmed.
| textbox | Enter measured diameter(s) only if variation is found, then raise an issue.
| checkpoint | Circumferential Verification - tick to indicate conformance P
| note | Spec: Pitch must be located at the design spacing and match the correct circumferential wire size and type. Tolerance: -0mm
| tickbox | Pitch is at correct design position and correct spacing
| tickbox | Correct wire size and type confirmed as per design
| tickbox | Cut circumferentials replaced to a min of 2 longitundinals
| textbox | Enter measurement(s) only if out-of-tolerance condition is found, then raise an issue.
| checkpoint | Longitudinal Wire Verification - tick to indicate conformance P
| note | Spec: Longitudinal introduction points (spacing & alignment) must be within MIN–MAX tolerance, as per design.
| tickbox | Spot-check confirms introduction points fall within tolerance
| textbox | Enter introduction measurement(s) only if out-of-tolerance condition is found, then raise an issue.
| checkpoint | Visual Verification - tick to indicate conformance P
| tickbox | No visible deformation or excessive variation
| tickbox | No unwelded longitudinals or circumferentials
| section | Acceptance & Traceability
| checkpoint | Take a photo of the completed Production Tag (Front & Back)
| signoff | Accepteance Signoff