## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Mangere Bridge School - Classroom Refurbishments
Classrooms
Room 1
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 2
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 3
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 4
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 5
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 6
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 7
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 19
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 8
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 9
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Room 10
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Principal
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Interview
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Corridor
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Reception
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Office 1
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Office 2
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Tuatara Room
Office 1
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Office 2
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Office 3
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Corridor
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation
Meeting Room
|  |  | Floor Prep |  | Floor Preparation
|  |  | Moisture Fix |  | Floor Preparation - Moisture Fix
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet Tile |  | Carpet Tile Installation
|  |  | Entrance Mat |  | Entry Mat Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Floor Preparation - Moisture Fix
checkpoint | Check area clear of all other trades and their materials
checkpoint | Have moisture readings been taken or are required
checkpoint | Is the pH level acceptable? | Yes, No
checkpoint | Check the concrete substrate dryness (RH)
checkpoint | Surface is clean, dry, and free from dust, debris or contaminants
checkpoint | Grind Floor
checkpoint | Does floor have U3 finish (3mm variance over 3m) | Yes, No
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply Moisture Fix
checkpoint | Disc purged material
checkpoint | Apply Floor Levelling Compound
checkpoint | Apply feather coat, Sanded, Edges
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving location/type if required
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Tile Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
checkpoint | Measure area
section | Installation
checkpoint | Confirm carpet tile pattern direction/layout
checkpoint | Glue out floors
checkpoint | Install carpet tiles
checkpoint | Install trims as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Entry Mat Installation
section | Details
checkpoint | 1. PRE-INSTALLATION CHECKLIST
button | CLIENT Handover of Area | YES, NO, N/A
button | Confirm materials delivered | YES, NO, N/A
button | Gather Materials and Tools | YES, NO, N/A
checkpoint | 2. SURFACE PREPARATION
button | Check Area clear of all other trades and their materials | YES, NO, N/A
button | Surface is clean, dry, and free from dust and debris. | YES, NO, N/A
button | Check Recess Level meets requirements | YES, NO, N/A
button | Assess, Discuss, Price, Confirm required works | PROCEED, NOT PROCEED, N/A
signoff | Hold works to confirm preparation required
checkpoint | 3. PREPARE ENTRY MAT FOR INSTALLATION
button | Install Matwell frame | YES, NO, N/A
button | Level Floor to suit Thickness | YES, NO, N/A
button | Dimention measured on site | YES, NO, N/A
checkpoint | 4. ENTRY MAT INSTALLATION
button | Drop Entry Mat in to matwell | YES, NO, N/A
checkpoint | 5. FINAL INSPECTION
button | Confirm no visible defects or issues. | PASS, FAIL, N/A
checkpoint | 6. SUBCONTRACTOR VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Subcontractor representative (Full name)
checkpoint | 7. CLIENT VERIFICATION
textbox | Actions/Remedial Items (if any)
signoff | Verified by CLIENT representative (Full name)

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.