## Master List Templates
Warnings | Id | Type | Name | Values | Prompting Name | Resource Id
| 1160a0dd-a4be-5fa8-a1d1-ab35e05c56b0 | checklist | Add Dayworks Checklist |  | Dayworks | feb8889b-f085-4036-a74a-d10f9db6ebea
| 2d1f5d57-dc93-5aff-98dd-91532b123bc6 | checkpoint | Has an ATS / SI been received for this work
| c202477a-d92d-4389-a502-b981fa335613 | textbox | Person requesting work:
| dd7e962b-77f3-4dda-95d8-cc30ee0cf4db | textbox | Description of work
| 439b0f70-210b-4082-b5de-02ed56114b70 | textbox | Labour / operative undertaking work
| 0ac387b4-c483-4cbb-b1d7-04eff1209305 | textbox | Hours Worked:
| fa2324f1-38d1-4614-8ef1-58a1393f1df9 | textbox | Materials Used:
| f2e42fec-c4f0-5517-bba6-c7836c0af86d | checkpoint | Job Completed Satisfactorily
| 683a7547-43ae-5590-bcbc-a142953938db | checkpoint | Signed Off
|  | checklist | Add Rework Checklist |  | Rework Checklist. Date: | 07063395-ba5b-4f23-badc-ebc86a6f61d2
folder-normal is not dependant but can't have own status |  | folder-normal | Rework Details
| 1e1027e7-c911-546b-9bb7-747d41373ca5 | checklist | H&S - Daily Pre Start Checklist |  | Daily Prestart - | 91211b6f-4cd0-41fd-927a-9560e6bece46
| fa22e969-c6fe-5a7f-a111-ea7657569d39 | checkpoint | Attendees documented
| 27d4b1e1-df4c-5e55-aad6-66b983f53e99 | checkpoint-no-value | Where is each person working and what are they doing?
| 7988f19d-60e1-5237-bfff-910f001b3d6d | checkpoint-no-value | Are any permits required?
| ede2f6a9-7448-45f2-935b-a6011d280a12 | button |  | No,Yes
| cd8df684-1f17-52be-9398-d09fa9213635 | checkpoint-no-value | Are there any work Hazards?
| 97d04245-0255-48f3-a32c-9ad60461d3e9 | button |  | No,Yes
| dd58497a-84e6-5c75-94f4-42b6ea7c68fb | checkpoint | A JSEA been completed & Approved?
| a99fa536-2576-5b7f-a969-d169e5812c0a | checkpoint-no-value | Are there any concerns; Safety or Production?
| 9fd2eec5-b42e-4f13-9a31-091e1ebf3aa5 | button |  | No,Yes
| 8b8a5394-baaf-5be6-98a1-63223840f9cf | checkpoint | Everyone has got their minimum PPE for site and task related PPE
| 596162ba-5fd3-5150-9a43-509384a28d2f | checkpoint | All plant tagged and in good condition
| c51f193f-fd82-5f84-b090-7864c4fe1869 | checkpoint | All employees have attended this meeting and are aware of their roles in safety and the daily hazards
folder-normal must be display normal but was flat |  | checklist | H&S - JSEA Checklist |  | Task - | b46a5bc9-f371-4e95-a513-2945ade91b46
checklist-flat is not dependant but can't have own status |  | checklist-flat | Form complete
folder-normal is not dependant but can't have own status |  | folder-normal | Signed Off
| 5ba069a4-2ba7-5e38-8988-4e7379b66565 | checklist | H&S - Site Toolbox Checklist |  | Site Toolbox | ce73aeb1-8d8a-4f29-ad7a-b6f98d51e405
| 68684a64-89f0-5cfc-a95c-6df6db123c5c | checkpoint-no-value | Employees Attending
| 97d47134-50e2-5400-ac91-d0ef40e65f03 | checkpoint | Site Activity / Safe Work Practices / Accident-Incident Investigations Discussed
| d1b10fb4-be90-5b7b-a7f2-a9e03dedcd09 | checkpoint | Employee issue raised
| a5f2dec0-b141-5905-b63d-da61c9c217c3 | checkpoint | Safe Observations
| 497dab5a-7bce-5d22-9168-80652a56604a | checkpoint | JSEA completed
| fe6add21-2102-566b-994d-8b4beb1d1dab | checklist | H&S - Toolbox - Code of Conduct |  | Code of Safe Conduct Policy - Date: | ef9246ef-0d4d-4f1b-b22f-366b13a0f532
Signoffs not allowed on checklist-sectioned. | 02a8f91c-d951-518c-bb6f-e15d4144a9bd | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 295ee194-a3ff-5101-91c4-a1d858397415 | checkpoint | Ensure Safety
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | All Salute Construct employees are required at all times to take all practicable steps to ensure their own safety and to ensure that they do not harm any fellow workers or any other person through their actions or inactions.
| 52eebc35-1d88-597c-bbbb-d1afdc55054e | checkpoint | SITE WORKERS MUST ALWAYS:
| f705179c-fcc9-4799-98a1-bbb7a86dae95 | checkpoint | SITE WORKERS MUST ALWAYS:
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Report (immediately) to their supervisor or employer every accident (or near miss incident where someone could have been injured) that they witness.
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Maintain work areas in a clean and tidy condition.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Wear the correct protective clothing and equipment and use the correct safety device or equipment that is required for each job. Safety footwear, Hi visibility vest and hard hats must be worn at all times.
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | Operate and maintain all vehicles and machinery in a safe and correct manner.
| 33f32e3c-deba-4049-8624-43bd7b66dbf7 | note | Check for underground services(electricity,gas,sewage,telecommunications and water)and over head power lines – and not proceed until sure of their presence or absence and, if present, their location.
| 46393ea0-57e2-423b-a072-aa26c83f124c | checkpoint | SITE WORKERS MUST ALWAYS:
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Check for overhead lines (electric and telecommunications) and ensure a safe operating distance between any machine being operated and the lines.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Be aware of the movement of people and vehicles around the site when working.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Check electrical leads and equipment before use and always use a transformer or an earth leakage circuit breaker.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Keep hand tools in good clean condition and always use the right tool for the job.
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Know what action to take in an emergency situation.
| 35863eb2-7681-5de7-bc71-3d14ebf6eb52 | checkpoint | SITE WORKERS MUST NEVER:
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Use any chemical or substance unless they know what it is; what risks are associated with it; how to handle it correctly; and the first aid emergency procedures for it.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Remove or alter any protective safety device or equipment without authorisation from their employer.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Smoke while working or while in designated smoke free areas.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Work while affected by alcohol or drugs.
| ddef7dce-a546-4596-9469-9ac50762ef46 | note | Assault, abuse or harass fellow workers or members of the public.
| a0c03b53-47fa-47ba-9f7d-033a5e1567f4 | checkpoint | SITE WORKERS MUST NEVER:
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Indulge in practical jokes or horseplay that place safety at risk.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Carry out any task or use any plant or equipment or apply any chemical or substance unless trained in its safe use or unless adequately supervised by someone who has been trained.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Bring audio players of any type on site.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Bring children or animals on to the site.
| eb54f746-cdcb-5e88-a488-1f8e3987e843 | checkpoint | If uncertain about anything, don’t proceed! ask first – and act only when you understand.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| c14650a5-526b-5f1d-85a9-8334e5b4c1ec | checklist | H&S - Toolbox - Core Drilling |  | Core Drilling Policy - Date: | d6ec02d7-447e-48fe-9429-cd086c63a132
Signoffs not allowed on checklist-sectioned. | cb1ff3d7-0d3c-537f-8724-4b77f5fe5b46 | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 271ce954-e33e-500f-a03e-c05358c15d2d | checkpoint-no-value | Attendees
| d49b9e46-9f30-5f29-9b05-7b5f622c75b0 | checkpoint | Purpose and Scope
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | All holes, with no exceptions are to be piloted holed first and sighted from below where a wheelie bin (or equivalent) is to be placed to catch slurry and core holes
| bf23deef-9775-4b51-a9e0-8dd534b9ebd6 | note | Danger tape is to be used in a way to now allow any person to enter into hazard areas
| 15d796ba-d3c5-441c-8b2a-fbe824328e41 | note | Where any hole is close to the edge of a building, an aco prop with timber bolted on the end must be used to prevent core from falling. Danger tape is always required
| 06ab7ab6-3f15-5fa7-ad05-38becf36facf | checkpoint | Supervision
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | If any hole is not pilot holed and a wire marker cannot be seen on underneath of penetration no core drilling can continue
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | if any part of procedure cannot be followed, then the relevant Salute supervision must be contacted
| 558946b9-e16b-4d52-a458-cce298487d69 | note | All new drillers to any site must first be instructed by an Salute Supervisor on the jobs specific requirements and procedure
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Only an Salute Supervisor can instruct any driller, whether or not employed by Salute Construct to drill a hole for any penetration related to contract
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | No holes are to be drilled for any other trade unless instructed by an Salute Supervisor
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 460cbb0d-5f4c-57ba-9bc1-c0e658a746d8 | checklist | H&S - Toolbox - Drug and Alcohol |  | Drug and Alcohol Policy - Date: | 96d20342-e7f6-4050-8ea2-dcbd0223494b
Signoffs not allowed on checklist-sectioned. | 095e7689-7b24-5b2b-adc3-a6c20ab2e5ed | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 5627170d-a6e7-5591-a7f8-f5b1003ba86a | checkpoint | Commitment
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | We are committed to responsibly meeting our occupational health and safety obligations by providing a working environment free from the effects of drugs and alcohol.
| 0326fd77-6558-5ef0-8d60-d28d28f7e930 | checkpoint | We will:
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Work with employees, their representatives and sub-contractors to promote an environment free from the harmful effects of drug and alcohol impairment.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Raise awareness and provide training about the potentially harmful effects of drugs and alcohol in the workplace.
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Offer to help and rehabilitate employees with drug and alcohol problems.
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | Actively support the training programmes of industry bodies focused on improving safe work practices.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Treat all workers consistently across the organisation in testing, selection and application of the procedures.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Protect privacy and confidentiality in the operation of this policy.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Comply with relevant health and safety legislation, regulations, codes of practice and Salute safe operating procedures.
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Ensure the organisation complies with its legal duties by removing anyone from the worksite who is deemed ‘unfit for work’ or ‘under the influence’, or where the presence of drugs or alcohol is in excess of accepted standards.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 21f70e5f-eba9-586e-b106-abc79b263bd2 | checklist | H&S - Toolbox - Edge Protection |  | Edge Protection Policy - Date: | ec0d19d1-0446-4d3f-af3f-821ce6eae789
Signoffs not allowed on checklist-sectioned. | 69b9284f-aca9-5430-a2e4-aef8cc687e9a | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| d49b9e46-9f30-5f29-9b05-7b5f622c75b0 | checkpoint | Purpose and Scope
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | Where unable to elimiate the fall, the intent of the edge protection policy is to isolate the fall os persons, objects and materials.
| bf23deef-9775-4b51-a9e0-8dd534b9ebd6 | note | - Edge protection is planned to consider design and strength, completeion of all work within edge protection systems, inspect and record daily completeness and state of repair
| 15d796ba-d3c5-441c-8b2a-fbe824328e41 | note | As a Subcontractor - you will submit plans and supervise your work . You will inspect the completeness and state of repair (daily) and report immediately any incomplete or damaged edge protection system
| ca7a8b72-6a7a-4c76-834f-55d45cdce986 | note | As an Individual - you will not alter any edge protection system without approval. You will secure and report immediately any incomplete or damaged edge protection system
| 241d90fb-b9fb-5f60-9c7e-7e7d488d5fc8 | checkpoint | Planning
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | With edge protection, planning is essential to establish:
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | The extent and integrity of protection requires
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Who will be involved
| 558946b9-e16b-4d52-a458-cce298487d69 | note | The hazards involved in erecting and dismantling
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | How those hazards are controlled to prevent injury
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | How, why and when it will be carried out
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Qualification, training and supervision requirements
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Equipment choices, including mentods of access, and
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | PPE and Clothing
| 71752b22-7471-51c1-9e9d-709910639532 | checkpoint | Edge Protection Use
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Examples of where edge protection is applied included, but is not limited to:
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Building facades, excavation perimeters
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | No Go Zones and Restricted Areas, including isolation and warning signage
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Open perimeters of floors and roofs
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Openings in floors and walls
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Scaffolding (toe boards, screens, shrink wrap)
| 8d34fb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Sides and ends of crane load in/load out platforms
TemplateReference '22s4f409-80c1-4586-83d3-8f6332da6fae' must be a UUID | 22s4f409-80c1-4586-83d3-8f6332da6fae | note | Daily edge perimeter checks monitor the integrity of the edge protection system
| d35dff35-f9d6-5b45-bc4e-5e92d2158e2d | checkpoint | Edge Protection Methods
| 68064460-9b7f-5bb2-904b-cb8cb24e0c60 | checkpoint | Protection Against Falling Objects
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Use of short lanyards to attach hand tools to work belts or aprons
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Measures shall be taken to prevent tools. materials and other objects falling from height. Methods to achieve this result include, but are not limited to:
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Use of screens, barricades and other isolation to contain plant, materials and equipment at its source (work, storage areas)
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Use of shrink wrap, mesh and or projecting fans
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Overhead gantrys or tunnel systems to protect public
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Teathering portable tools to prevent them falling
| 57db21cd-eaff-5de7-8e32-8267d0855c96 | checkpoint | Definitions and Reference
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Edge protection mean the use of temporary or permanent protection at a place of work to prevent persons, objects and materials falling form one level to another. This can be above or below ground level.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 6812f2f1-e06e-51bb-9b63-8af48dbfd588 | checklist | H&S - Toolbox - Environmental Policy |  | Environmental Policy - Date: | c182a682-006e-4a4b-8148-af56546936a8
Signoffs not allowed on checklist-sectioned. | ebe15e5b-ea81-502f-857c-d2d97235e8a4 | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 5627170d-a6e7-5591-a7f8-f5b1003ba86a | checkpoint | Commitment
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | We are committed to working together to protect the environment by reducing the impacts associated with our manufacturing, construction and extraction operations, and the distribution and use of our building materials.
| 0326fd77-6558-5ef0-8d60-d28d28f7e930 | checkpoint | We will:
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Implement projects and programmes that improve our energy efficiency and reduce our CO2 emissions.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Reduce our waste to landfill and work with our supply chain to ensure that our operations, our product composition and design take account of the waste hierarchy.
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Improve our water efficiency and minimise the impacts from water discharged from our operations.
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | Ensure all our manufactured products use raw materials from verified sources where these are available.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Provide innovative, practical system solutions to enable buildings and infrastructure to be sustainable.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Support industry education on sustainable construction practices, design principles and measures.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| a77bb7b6-68fa-5960-8722-f40e533d85e8 | checklist | H&S - Toolbox - Floor Penetration |  | Floor Penetration Policy - Date: | daf0e880-0fe7-4064-8b9b-c9e819d58654
Signoffs not allowed on checklist-sectioned. | 57288c85-1746-52c5-bc60-287c51914846 | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| d49b9e46-9f30-5f29-9b05-7b5f622c75b0 | checkpoint | Purpose and Scope
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | It is Salute Constructs intent that no person shall be at risk from a fall through fragile floors (floors that cannot safely withstand the weight of a person) and floor openings.
| bf23deef-9775-4b51-a9e0-8dd534b9ebd6 | note | - Fragile floors and openings are protected against a fall
| 15d796ba-d3c5-441c-8b2a-fbe824328e41 | note | - All ‘No Go Zones’ are identified, physically isolated, and communicated clearly at inductions, prestart and briefings
| ca7a8b72-6a7a-4c76-834f-55d45cdce986 | note | As a sub-contractor - You will submit a plan and supervise your work to meet Fletchers Floor Penetration Protection Guidance
TemplateReference '3r6a8b72-6a7a-4c76-834f-55d45cdce986' must be a UUID | 3r6a8b72-6a7a-4c76-834f-55d45cdce986 | note | As an individual you will - Not put yourself at risk of a fall through material that cannot safely support your weight, Not put yourself at risk of a fall through a floor opening, Not interfere with any protection to a floor opening, Report immediately to Salute staff and prevent access to [any unprotected floor opening, instances where requested to work on or near an unprotected floor opening or fragile floor, and areas where material cannot safely support your weight
| 5083782d-2262-5506-a4b0-04c50b49d852 | checkpoint | Floor Openings
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Floor openings range in size from:
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | To small penetrations such as for single pipes through a floor.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Large lift shafts, stair wells, atriums
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | To medium size such as building services shafts
| dc31ccd0-9781-56d7-ba1c-301fbca78268 | checkpoint | Requirements
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Existing structures and refurbishment:
| 558946b9-e16b-4d52-a458-cce298487d69 | note | - Review client/building owner hazard registers to identify possible fragile floors and penetrations
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | - Ask the client/building owner specifically regarding fragile floors and penetrations they may know of.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | - Treat all services riser floors as fragile/penetrations and protect as detailed below until confirmation of structural integrity is obtained from a chartered engineer.
| 8d34fb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | - All floor penetration protection (guarding or covers) must be securely fixed in place to prevent displacement through disturbance and prevent premature removal. Securely fixed means bolted (preferable as it allows removal and replacement), but may include pinning or other means of secure fixing
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | All penetrations shall be assessed against the risk of persons and/or materials/plant falling and shall be suitably protected. Notwithstanding this risk assessment the minimum standards below shall be followed:
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | - All penetrations in floors or work areas greater than 150mm dia. (or sq.) shall be guarded or covered with a secured cover, built to the minimum standard of a light-duty platform or to suit any greater load that could be imposed on it.
TemplateReference '22s4f409-80c1-4586-83d3-8f6332da6fae' must be a UUID | 22s4f409-80c1-4586-83d3-8f6332da6fae | note | Note: If guardrails etc. are used they shall be solid or mesh protected (floor to topguardrail) to prevent persons, tools and materials falling onto persons below.
TemplateReference '2333309-80c1-4586-83d3-8f6332da6fae' must be a UUID | 2333309-80c1-4586-83d3-8f6332da6fae | note | All penetration protection systems must display the attached signage to warn people of floor penetrations below
| 60c0f65d-a240-5a42-889a-a3ffefd7ccd0 | checkpoint | Referencing and Statutory Compliance
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Health and Safety in Employment Act 1992, Health and Safety in Employment Regulations 1995
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Best Practice Guidelines for working at heights in New Zealand 2012
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Department of Labour presentation on penetration and openings project
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Work at Height Policy and application specific guidance
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 1ff56ac7-09a7-51f1-947c-dae63222d72a | checklist | H&S - Toolbox - Hand Held Grinders |  | Hand Held Grinders Policy - Date: | 8502d6c3-6c27-42a4-984b-e1d316f7a08a
Signoffs not allowed on checklist-sectioned. | 57ffb0f8-fe45-5eac-a687-eb69b4998f37 | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 7d1db919-7c5d-56a4-ba64-02e0dd6cddbb | checkpoint | Purpose and Scope of Policy
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | The purpose of this policy is to enable Salute Construct employees and contractors to understand the requirements of the safe use of hand held grinders.
| 60c0f65d-a240-5a42-889a-a3ffefd7ccd0 | checkpoint | Referencing and Statutory Compliance
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Reference should be made to:
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | - Health and Safety in Employment Act 1992, Health and Safety Regulations 1995
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | - Safety line Essentials – Angle Grinders, Department of Consumer and Employment Protection
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | - Salute Construct ‘Toolbox talk – Safe use of angle grinders’
| 558946b9-e16b-4d52-a458-cce298487d69 | note | - Salute Construct ‘Hot Work Policy’ HSM Document 32
| dc31ccd0-9781-56d7-ba1c-301fbca78268 | checkpoint | Requirements
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | The minimum safety requirements for hand held grinders used on a Salute Construct site shall include the following:
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Kickback Protection (if the disc jams – it stops)
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Re-start Protection (prevents the grinder from unintentionally starting if power is temporarily lost)
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Full face shield (mandatory PPE to protect the user)
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Multi-position Locking Guard (positioned to protect the user)
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Handle (to allow safe two handed use)
| 8d34fb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Note: Hand held grinders must always be used in conjunction with an industrial RCD.
TemplateReference 'f2832e3c-deba-404t-8624-43bd7b66dbf7' must be a UUID | f2832e3c-deba-404t-8624-43bd7b66dbf7 | note | Further Safety Features recommended are
TemplateReference '558946b9-e16b-4d52-a4t8-cce298487d69' must be a UUID | 558946b9-e16b-4d52-a4t8-cce298487d69 | note | Anti-Vibration Handles
TemplateReference '6d03794e-eft1-4663-94f0-81261207beb5' must be a UUID | 6d03794e-eft1-4663-94f0-81261207beb5 | note | Soft start up
TemplateReference 'ec3f7tce-a546-4596-9469-9ac50762ef46' must be a UUID | ec3f7tce-a546-4596-9469-9ac50762ef46 | note | Multi-position handles
TemplateReference '0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0 | note | Electronic overload protection
TemplateReference '8677f409-80c1-458t-83d3-8f6332da6fae' must be a UUID | 8677f409-80c1-458t-83d3-8f6332da6fae | note | Wheel Safety
TemplateReference '8d34fb8d-bd0c-4481-tc84-d7db6b49c1b0' must be a UUID | 8d34fb8d-bd0c-4481-tc84-d7db6b49c1b0 | note | Cutting wheels or discs should not be used for grinding jobs, and grinding wheels should not be used for cutting jobs
TemplateReference 'ec3f7tce-ar46-4596-9469-9ac50762ef46' must be a UUID | ec3f7tce-ar46-4596-9469-9ac50762ef46 | note | Wheels designed for a particular revolution speed should not be used on machines of different speeds
TemplateReference '0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0 | note | Wheels should be used only for the specific material and purpose for which they are designed, and according to the manufacturer's recommendations
TemplateReference '8677f409-80c1-458t-83r3-8f6332da6fae' must be a UUID | 8677f409-80c1-458t-83r3-8f6332da6fae | note | Wheels worn down through use should be discarded and NEVER used on smaller machines
TemplateReference '8d34fb8d-bd0c-4481-tc84-d7rb6b49c1b0' must be a UUID | 8d34fb8d-bd0c-4481-tc84-d7rb6b49c1b0 | note | If subjected to excess pressure wheels can shatter at high speed, exposing the users and others close by to the risk of serious injury
TemplateReference 'ec3f3tce-a546-4596-9469-9ac50762ef46' must be a UUID | ec3f3tce-a546-4596-9469-9ac50762ef46 | note | Users of Hand Held Grinders must
TemplateReference '0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0 | note | Have a correct hot work permit before starting work
TemplateReference '8677f439-80c1-458t-83d3-8f6332da6fae' must be a UUID | 8677f439-80c1-458t-83d3-8f6332da6fae | note | Be trained in their safe use
TemplateReference '8d34fb3d-bd0c-4481-tc84-d7db6b49c1b0' must be a UUID | 8d34fb3d-bd0c-4481-tc84-d7db6b49c1b0 | note | Check the disk is appropriate for the work intended and it is fitted correctly
TemplateReference 'ec3f7t3e-ar46-4596-9469-9ac50762ef46' must be a UUID | ec3f7t3e-ar46-4596-9469-9ac50762ef46 | note | Wear the appropriate PPE: safety glasses/ face shield, gloves, hearing protection, safety footwear, high visibility vest or clothes, and protective overalls
TemplateReference '0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0 | note | Check for others in the vicinity and ensure safe distances are maintained
TemplateReference '8677f409-80c1-458t-83r3-8f3332da6fae' must be a UUID | 8677f409-80c1-458t-83r3-8f3332da6fae | note | Remain on fire watch for a period of 30 minutes following conclusion of the work if there is a risk of sparks igniting material
TemplateReference '8d34fb8d-bd0c-4481-tc84-d7r36b49c1b0' must be a UUID | 8d34fb8d-bd0c-4481-tc84-d7r36b49c1b0 | note | Contractors will be expected to provide evidence that any person (whether employee, subcontract employee or self-employed) who will use a grinder in the execution of contract works is a competent operator
| bd335018-00f5-5ffe-a939-cda353e05249 | checkpoint | Standard Forms
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Task Analysis
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 01d4418b-cb00-5606-8f18-31e89883db4e | checklist | H&S - Toolbox - Minor Trench Collapse Procedure |  | Minor trench Collapse Procedure - Date: | 29de7d1e-3934-4d8f-ab26-9d17bc4ee8cc
Signoffs not allowed on checklist-sectioned. | ab094f17-5c91-53c0-a3d0-9a5d8b03afb3 | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 7284ba75-3a8c-566a-8771-5596b37623b6 | checkpoint | Scope of Policy
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | This minor Trench collapse procedure will apply when no individual has been buried and is still visible and is not in any danger or loss of life.
| f50d0b95-fbff-5f55-9719-cc6244216846 | checkpoint | Procedure
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Area is to be made safe, with all non-required employees to be removed from area. Area is to be barricaded off.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | A JSEA must be done before entering area and to be signed off by Salute Safety rep and client safety rep.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | The JSEA must make a safe way of removing the employee, no other employee can be put into a hazardous situation where his safety could be put in jeopardy. If it is not possible to achieve, emergency services are to be called.
TemplateReference '558946b9-e16b-4d52-a4t8-cce298487d69' must be a UUID | 558946b9-e16b-4d52-a4t8-cce298487d69 | note | If urgency is required to free a trapped employee and emergency services have not arrived, then Salute Construct Major trench collapse procedure is to be enforced.
| dfd23a91-b756-5165-b978-fdb00c0179a4 | checkpoint | Notes
| 558946b9-e16b-4d52-a458-cce298487d69 | note | No Staff to leave site before notified by Salute Project Manager.
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | All ground immediately surrounding collapse area is to be considered unstable. No heavy machinery to be used to remove spoil from trench in case it harms the trapped person.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Works are only to continue after direction from Salute Construct Project Manager. Area is to be barricaded off until inspection complete.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 29cd3e51-eaba-5c83-98aa-ca8a6974e09d | checklist | H&S - Toolbox - PPE |  | Personal Protective Equipment (PPE) Policy - Date: | 43d5487d-614d-4d2b-aa56-1388268fa6c6
Signoffs not allowed on checklist-sectioned. | a4502560-83b4-530d-82c6-1ef64acd5acc | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| d49b9e46-9f30-5f29-9b05-7b5f622c75b0 | checkpoint | Purpose and Scope
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | The purpose of this policy is to minimise injury to Salute Construct employees, contractors and other persons in the workplace through the use and care of personal protective equipment (PPE).
| 60c0f65d-a240-5a42-889a-a3ffefd7ccd0 | checkpoint | Referencing and Statutory Compliance
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Health and Safety in Employment Act 1992, Health and Safety in Employment Regulations 1995
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | AS/NZS 1269.3:2005 Occupational Noise Management - Hearing Protection Programme
| 44f32e3c-deba-4049-8624-43bd7b66dbf7 | note | AS/NZS 1337.6:2012 Personal eye protection – Prescription eye protectors against low and medium impact
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | AS/NZS 1270:2002 Acoustics – Hearing Protection
| 22f32e3c-deba-4049-8624-43bd7b66dbf7 | note | AS/NZS 2210.1:2010 Safety, protective and occupational footwear - Guide to selection, care and use
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | AS/NZS 1801 Occupational protective helmets
TemplateReference '333332e3c-deba-4049-824-43bd7b66dbf7' must be a UUID | 333332e3c-deba-4049-824-43bd7b66dbf7 | note | AS/NZS 4501.2:2006 Occupational protective clothing - General requirements
| 33f32e3c-deba-4049-8624-43bd7b66dbf7 | note | AS/NZS 1337.1:2010 Personal eye protection – Eye and face protectors for occupational applications
| 34432e3c-deba-4049-8624-43bd7b66dbf7 | note | AS/NZS 4602.1:2011 High Visibility Safety Garments – Garments for high risk applications
| 35532e3c-deba-4049-8624-43bd7b66dbf7 | note | Best practice guidelines for Personal Protective Equipment in New Zealand 2012
| 36632e3c-deba-4049-8624-43bd7b66dbf7 | note | MBIE: Fact Sheet-Noise Levels Created by Common Construction Tools
| 37732e3c-deba-4049-8624-43bd7b66dbf7 | note | National Institute of Occupational Safety and Health (NIOSH) – Eye safety
| 38832e3c-deba-4049-8624-43bd7b66dbf7 | note | Classified Hearing Protection Selection – MBIE March 2013
TemplateReference '399f32e3c-deba-4049-8624-43bd7b66dbf7' must be a UUID | 399f32e3c-deba-4049-8624-43bd7b66dbf7 | note | Provision for Prescription Safety Glasses Policy
| f68cb2b8-3d3e-566a-a94f-ae40e6cc2b47 | checkpoint | Employers, contractors, employees and other persons shall take steps to ensure:
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | The policy applies from the front (or any) entrance of Salute projects where construction work is carried out; or any yard or workshop. The following areas are excluded from the policy:
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Personal protective equipment and clothing on all Salute projects and customer work sites is used and worn at all times.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | The minimum PPE requirement for site entry is:
| fb2618d2-17e6-443d-9de2-75a556fe229a | note | a) Safety boots with steel toe cap or equivalent, b) Hi visibility vest or clothing (NB: Hi-vis vests and clothing shall be worn with zips/fixings closed) c) Protective helmet and d) Protective eye wear (safety glasses; visor; goggles). e) Gloves to be carried (excluding visitors) and worn if required by task. f) Hearing protection shall be carried and used if required by task/ or conditions require. g) Full face shield must be worn when using grinders.
| 33f32e3c-deba-4049-8624-43bd7b66dbf7 | note | Office/administration areas, Lunchroom, Visitor car parks, where there is a designated and clear path to the sign in office areas that does not cross operational vehicle traffic flows or does not pass through hazardous sections of the site.
| 429f7d65-621e-50c7-8738-98bf30ccaf70 | checkpoint | Personnel – Responsibilities and Duties
| fe368f48-e93d-59a1-80a6-6a9b0187e6ca | checkpoint | Guidelines for Issue and Use of PPE
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | Head Protection - Head Protective helmets shall be compliant with AS/NZS 1801. Issue dates will be recorded inside the helmet and on the PPE proforma. White protective helmets will be replaced every three years and coloured protective helmets every two years. Any damaged helmet must be replaced immediately.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | Eye Protection - Glasses are to be compliant with AS/NZS 1337 standards. Refer to HSM 41 Provision of Prescription Safety Glasses.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | Foot Protection - Every worker employed on construction sites must wear safety boots with steel toe cap or equivalent which are compliant with AS/NZS 2210.
| ec3f7dce-a546-4596-9469-9ac50762ef46 | note | Hi Vis Vest/Jacket - Hi Vis Jackets shall be compliant with AS/NZS 4602.
| ddef7dce-a546-4596-9469-9ac50762ef46 | note | Hearing Protection - Correct Class hearing protection as specified in the “Classified Hearing Protection” document – MBIE March 2013, in the form of ear muffs or plugs must be worn, if exposed to levels of noise approaching 85dB[A] or greater. Refer MBIE Fact Sheet-Noise Levels Created by Common Construction Tools for examples.
| 9999794e-ef51-4663-94f0-81261207beb5 | note | Face Protection - Face shields are to be compliant with AS/NZS 1337.
TemplateReference '23453794e-ef51-4663-94f0-81261207beb5' must be a UUID | 23453794e-ef51-4663-94f0-81261207beb5 | note | Specialist Protective Equipment - Where specialist protective equipment is required, consultation with industry experts is to be conducted to ensure the protective equipment will perform and provide the necessary protection. It is not sufficient to rely on the product salesperson to provide these assurances.
| 85424948-4cb2-5995-bcd9-50d8521fb173 | checkpoint | Cleaning & Maintenance of PPE
| f2832e3c-deba-4049-8624-43bd7b66dbf7 | note | It is the responsibility of the user to ensure that issued PPE is regularly inspected and kept in a good serviceable condition.
| 558946b9-e16b-4d52-a458-cce298487d69 | note | All issues of non-disposable PPE shall be recorded and any PPE removed from service must be disposed of immediately.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| cbb0274c-fe90-5409-adc5-848ad265f3c1 | checklist | H&S - Toolbox - Trench Rescue Operations |  | Trench Rescue Operations Policy - Date: | 9c3b2a3e-53fb-48e3-a50c-af1d7a44dec0
Signoffs not allowed on checklist-sectioned. | b267e963-6511-524c-94ad-041be65ac6fd | signoff | Signoff
| 99161e3b-7b6b-5a96-9f20-8c7f71c98fbf | section | Information
| 7284ba75-3a8c-566a-8771-5596b37623b6 | checkpoint | Scope of Policy
| c4cfd721-ca1d-51b4-92fe-b6b2284ad8f7 | checkpoint | Purpose of Policy
| aea95a16-e2b8-4351-a1ef-bd8c5363f3df | note | The purpose of this procedure is to establish guidelines for the response of Salute personnel and equipment to trench rescue incidents. Because trench rescue operations present a significant danger to Salute personnel, the safe and effective management of these operations require special considerations. It shall be the policy of Salute Construct that NO personnel shall be allowed into an unsafe trench or excavation. This procedure identifies some of the critical issues which must be included in managing these incidents.
| 77f23041-f205-5a9a-ad92-f9b3285f0576 | checkpoint | Tactical Considerations
| 558946b9-e16b-4d52-a458-cce298487d69 | note | For the purpose of emergency response, an excavation shall be defined by any depression, hole, trench, or earth wall, manmade or natural, of four feet or greater.
| dcc5ff34-ab7e-4f06-8ea2-ddc7ebdfb325 | note | Trench collapses generally occur due to unstable soil conditions combined with improper or inadequate shoring. The potential for additional collapse is considered a primary hazard to personnel. Removing soil or debris, adding weight near the edge of an open cut, vibration (such as vehicle movement), rain, or simply the passage of time, may cause additional collapse at any time during the rescue operation.
| ec9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Due to the inherent dangers associated with these operations, risk management shall be applied to all trench rescue operations and shall be continuously re-assessed throughout the incident. A phased approach to trench rescue operations which include; Arrival, Pre-entry operations, Entry operations, and Termination, can be utilized to safely and effectively mitigate these high-risk / low-frequency events.
| a49d92a5-f666-57e5-81a6-31a7705212df | checkpoint | Phase I Arrival.
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | I. ESTABLISH COMMAND
TemplateReference '0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0 | note | A. First arriving employee shall assume Command and begin an immediate size up of the situation while ensuring that apparatus remains at least 50 feet from the location of the trench failure. Command Shall contact emergency services and supervisors. When emergency services arrive hand over scene giving any information gathered. Command shall cordon off area and restrict access.
TemplateReference '0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0 | note | B. First arriving Safety Officer should be assigned Control. Control responsibilities include: • Assuming technical rescue operations control. • Identifying hazards and critical factors. • Developing a rescue plan and back-up plan. • Communicating with all employees to getting equipment ready.
TemplateReference '0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0 | note | C. Designate a Safety Officer. Considerations for Safety Officer include: • Experience • Qualifications
TemplateReference '0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0 | note | D. Following the transfer of Command to Control, a Technical Advisor should be assigned to join the Command Team at their location, to assist in managing personnel and resources engaged in the technical aspects of the incident. The Technical Advisor is responsible for ensuring that the rescue plan developed by control and communicated to Command is a sound plan in terms of the safety and welfare of both victim(s) and rescuers. Considerations for the Technical Advisor include: • Experience • Qualifications
| 558946b9-e16b-4d52-a458-cce298487d69 | note | The Technical Advisor position within the Command Team should be filled prior to the implementation of any rescue plan proposed by Control.
TemplateReference '558946b9-e16b-4d52-a4t8-cce298487d69' must be a UUID | 558946b9-e16b-4d52-a4t8-cce298487d69 | note | II. Size-Up
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | A. Secure a witness or responsible party to assist in gathering information to determine exactly what happened. If no witnesses are present, Command may have to look for clues on the scene to determine what happened.
TemplateReference '6d03794e-eft1-4663-94f0-81261207beb5' must be a UUID | 6d03794e-eft1-4663-94f0-81261207beb5 | note | B. Assess the immediate and potential hazards to the rescuers.
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | C. Isolate immediate hazard area, secure the scene, and deny entry for all non-rescue personnel.
TemplateReference '8677f409-80c1-458t-83d3-8f6332da6fae' must be a UUID | 8677f409-80c1-458t-83d3-8f6332da6fae | note | D. Assess on-scene capabilities and determine the need for additional resources.
| 3bfafcd9-53e3-5a2b-924a-cab906bcab8e | checkpoint | Phase II Pre-entry Operations
| 15cb325a-2b6e-5405-b6b3-84747d9a3973 | checkpoint | Phase III Entry Operations
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | Entry operations shall be conducted under the direction of Control and assisted by most experienced/qualified team members. Control shall be responsible for entry operations. Control shall ensure that all personnel operating in the hazard zone are accounted for and wearing appropriate PPE.
TemplateReference '0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0 | note | MAKE THE TRENCH SAFE
TemplateReference '0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0 | note | A. Place ingress and egress ladders into the trench. There should be at least 2 ladders placed into the trench no more than 50 feet apart.
TemplateReference '0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0 | note | B. Decide on the shoring system to be used (i.e. hydraulic shore, pneumatic shore, timber shore).
| 558946b9-e16b-4d52-a458-cce298487d69 | note | D. Remove dirt from the collapsed zone while remaining in the safe zone.
TemplateReference '558946b9-e16b-4d52-a4t8-cce298487d69' must be a UUID | 558946b9-e16b-4d52-a4t8-cce298487d69 | note | E. Secure all utilities, pipe, or other obstructions in the trench.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | VICTIM REMOVAL / INCIDENTS WITHOUT COLLAPSE
TemplateReference '6d03794e-eft1-4663-94f0-81261207beb5' must be a UUID | 6d03794e-eft1-4663-94f0-81261207beb5 | note | A. Create a safe zone around the victim.
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | B. Remove objects trapping the victim such as pipes, lumber, machinery, etc.
TemplateReference '8h77f409-80c1-458t-83d3-8f6332da6fae' must be a UUID | 8h77f409-80c1-458t-83d3-8f6332da6fae | note | C. Assess victim’s condition.
TemplateReference '6d765684e-eft1-4663-94f0-8126120eeeb5' must be a UUID | 6d765684e-eft1-4663-94f0-8126120eeeb5 | note | D. Properly package the patient and remove from the trench.
| 96765409-80c1-4586-83d3-8fee32da6fae | note | VICTIM REMOVAL / INCIDENTS WITH COLLAPSE
TemplateReference 'e677659-80c1-458t-83d3-8f633eea6fae' must be a UUID | e677659-80c1-458t-83d3-8f633eea6fae | note | A. Begin dirt removal while operating from a safe zone.
TemplateReference 'e67ae59-80c1-458t-83d3-8f63543a6fae' must be a UUID | e67ae59-80c1-458t-83d3-8f63543a6fae | note | B. Continue extending safe zone into collapse zone.
TemplateReference '0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r84-d7db6b49c1b0 | note | C. Create a safe zone in the non-collapsed area of the trench, from both ends if possible, by implementing an approved shoring system.
| 11165409-80c1-4586-83d3-8fee32da6fae | note | C. Create a safe zone around the victim.
TemplateReference '8767659-80c1-458t-83d3-8f633eea6fae' must be a UUID | 8767659-80c1-458t-83d3-8f633eea6fae | note | D. Uncover victim to below the diaphragm utilizing small shovels, buckets, or by hand and assess the victim’s condition.
TemplateReference '567ae59-80c1-458t-83d3-8f63543a6fae' must be a UUID | 567ae59-80c1-458t-83d3-8f63543a6fae | note | E. Completely uncover the victim, properly package the patient and remove from the trench.
TemplateReference 'ff77659-80c1-458t-83d3-8f633eea6fae' must be a UUID | ff77659-80c1-458t-83d3-8f633eea6fae | note | TREATMENT
TemplateReference 'ffffe59-80c1-458t-83d3-8f63543a6fae' must be a UUID | ffffe59-80c1-458t-83d3-8f63543a6fae | note | A. Conduct a primary survey upon reaching the victim.
| 1ffff409-80c1-4586-83d3-8fee32da6fae | note | B. Initiate C-spine precautions as soon as possible.
TemplateReference '876fff9-80c1-458t-83d3-8f633eea6fae' must be a UUID | 876fff9-80c1-458t-83d3-8f633eea6fae | note | C. Conduct a secondary survey and correct any life threatening conditions.
TemplateReference '567fe59-80c1-458t-83d3-8f63543a6fae' must be a UUID | 567fe59-80c1-458t-83d3-8f63543a6fae | note | D. Consider removing the victim from danger prior to providing definitive care
| 0c8dc872-cc64-584d-92b7-c1448199ba9d | checkpoint | Phase IV Termination
| 0c9bfb8d-bd0c-4481-8c84-d7db6b49c1b0 | note | A. Ensure personnel accountability.
TemplateReference '0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-3d0c-4481-8c84-d7db6b49c1b0 | note | B. Remove tools, equipment, and the trench shoring system (last-in / first-out) from the trench. In cases of a fatality, consider leaving everything in place until the investigative process has been completed
TemplateReference '0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8c84-d7db6b49c1b0 | note | C. Remain on site until advised by Salute Management otherwise.
TemplateReference '0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0' must be a UUID | 0c9bfbtd-bd0c-4481-8r34-d7db6b49c1b0 | note | D. Return to service after turning the scene over to the responsible party and ensuring the scene is secure.
| 4effe19a-dcb3-5010-958f-f14bd30a108c | checkpoint | ADDITIONAL CONSIDERATIONS
| 558946b9-e16b-4d52-a458-cce298487d69 | note | COMMAND STRUCTURE
TemplateReference '558946b9-e16b-4d52-a4t8-cce298487d69' must be a UUID | 558946b9-e16b-4d52-a4t8-cce298487d69 | note | A. The first arriving unit employee shall assume Command of the incident. This employee shall remain in Command until Command is transferred to improve the quality of the Command organization. A Command Team shall be assembled to include, at a minimum, a Safety Officer and First Aider.
| 6d03794e-ef51-4663-94f0-81261207beb5 | note | B. Considerations for the Technical Advisor include: • Experience • Qualifications
TemplateReference '6d03794e-eft1-4663-94f0-81261207beb5' must be a UUID | 6d03794e-eft1-4663-94f0-81261207beb5 | note | The first arriving Safety Officer shall be assigned Control. Control teams, Lobby, Ventilation, Air Monitoring, Shoring, cut teams, and any other such functional team operating in the hazard zone shall be under the direction of Control. Control will communicate directly with all employees assigned to these functions within control and shall keep Command informed during all phases of the rescue operation.
| 8677f409-80c1-4586-83d3-8f6332da6fae | note | Considerations for Safety Officer include: • Experience • Qualifications
TemplateReference '8h77f409-80c1-458t-83d3-8f6332da6fae' must be a UUID | 8h77f409-80c1-458t-83d3-8f6332da6fae | note | OTHER CONSIDERATIONS
TemplateReference '6d765684e-eft1-4663-94f0-8126120eeeb5' must be a UUID | 6d765684e-eft1-4663-94f0-8126120eeeb5 | note | A. Consider the effects of inclement weather on the hazard profile, the victim(s), and the rescuers.
| 96765409-80c1-4586-83d3-8fee32da6fae | note | B. Maintain awareness of the time of day and ensure sufficient lighting is available on the scene if operations extend into the night.
TemplateReference 'e677659-80c1-458t-83d3-8f633eea6fae' must be a UUID | e677659-80c1-458t-83d3-8f633eea6fae | note | C. Trench incidents attract the news media; Do not talk to any parties not directly involved with the incident.
TemplateReference 'e67ae59-80c1-458t-83d3-8f63543a6fae' must be a UUID | e67ae59-80c1-458t-83d3-8f63543a6fae | note | D. Request Worksafe response if there has been a serious injury or death.
| 2b861131-7b9e-51e9-95bf-a57d2d62e13a | section | Photos
| 5d508b00-c516-5b45-bba4-eba0da97809a | checkpoint | Attendee Photo attached
| f7dcc2b9-0615-5962-9fe6-5a69f9e035b7 | signoff | Signoff
| 159e52b8-bcc6-5ea4-8549-d3d3879cc58c | checklist | H&S - Weekly H&S Checklist |  | H&S Week Starting: | fe5f4384-8c6c-4a74-9342-d8f68ffc8792
| b7d0dee7-466b-5605-a546-e0bb54958c78 | checkpoint | Task Analysis/JSA
| fdc4f074-af69-5361-9371-b1d133d6aa19 | checkpoint | Toolbox Minutes
| a84f6423-0dab-5305-8174-f63df6ea1a85 | checkpoint | Hot Works Permits/Confined Spaces/Working at heights
| d0224e46-6654-59a3-bda5-21697a85d6f9 | checkpoint | Site Safety Inspection Checklists
| aea79918-4222-57c5-8e2d-57f32feffef1 | checkpoint | Hazard ID
| b28632b0-aa7a-50d0-94be-ff15d347a348 | checkpoint | Accident/Incident/Near Miss Investigation Report
| 401b396c-6b43-515c-a04f-fd4d0460c668 | checkpoint | Notice/Record of Serious Harm Accident
| 8f720956-0552-5a22-b456-040b52f8df8a | checkpoint | Additional Heath & Safety Documentation
|  | checklist | H&S - Weekly Site Inspection Checklist |  | H&S - Weekly Site Inspection Checklist | 536a2430-3f9c-4e38-9f83-98d26caf5cb2
|  | section | Weekly Site Inspection
|  | checkpoint | Weekly Site Inspection Checklist
| f68711da-05da-5f1b-a981-66e84f013a82 | textbox | Location:
| 53d8e4fe-6472-51c8-ab93-7d2eaa36aa5f | textbox | Date:
| a6f37e8f-14f3-505d-ad5c-b7c4b9a12274 | textbox | Name of Inspector:
|  | section | Site Control
|  | checkpoint | Hazard board up to date
|  | checkpoint | Toolbox talk
|  | checkpoint | Inductions up to date
|  | section | Site Facilities
|  | checkpoint | Offices Clean
|  | checkpoint | Smoko Sheds
|  | checkpoint | Fridge
|  | checkpoint | Toilets
|  | checkpoint | Containers
|  | section | General Site
|  | checkpoint | Access Ways
|  | checkpoint | Stairways Clear
|  | section | PPE
|  | checkpoint | Signage Displayed
|  | checkpoint | Hardhats
|  | checkpoint | Glasses worn
|  | checkpoint | Gloves
|  | section | First Aid
|  | checkpoint | Box Available and stocked
|  | checkpoint | Fire Extinguishers Available
|  | section | Cutting/Grinding
|  | checkpoint | Hot work permits
|  | checkpoint | Fire Extinguishers on hand
|  | checkpoint | Full Face Shield
|  | section | Electrical Equipment
|  | checkpoint | Current Tags
|  | checkpoint | Leads placed safely
|  | checkpoint | Equipment in good condition
|  | checkpoint | Adequate lighting
|  | section | Chemicals
|  | checkpoint | Correctly stored
|  | checkpoint | MSDS Available
|  | checkpoint | Operators using PPE
|  | section | PAT Tools
|  | checkpoint | PAT Tool WOF
|  | checkpoint | PAT signage
|  | checkpoint | Staff trained
|  | section | EWP
|  | checkpoint | Current WOF
|  | checkpoint | Log Books being used
|  | checkpoint | Staff Competent
|  | section | Scaffolding
|  | checkpoint | Tags
|  | checkpoint | Midrails/Handrails
|  | checkpoint | Toe Boards
|  | checkpoint | Ladders
|  | checkpoint | Platforms Clear
| ba8f4a80-eeca-5bed-a0d7-be96d2469cfd | checklist | QA - Architrave Checklist |  | Architrave Checklist | 4506e0f2-a9ea-4d0e-8923-4f4762061533
| dec8aa18-7150-55ca-a9fd-5149dfd7617b | checkpoint | Level and Flush with walls
| a280682d-b851-5417-abd4-735761d759da | checkpoint | Gaps and joints angle are acceptable
| 57da5f96-0acb-53df-bb4f-05f60bc48235 | checkpoint | Silicon and finishing nails have been used correctly
| d1ca4abd-0faf-55ad-a477-162c80275745 | checklist | QA - AXON Panel Checklist |  | AXON Panel - | 3093d545-f653-4bd3-82ba-cef3dcfe2fc3
| efbb5e5e-154f-56ea-b250-55f234522708 | checkpoint | Technical Literature followed
| f365bd84-51c6-50b5-991d-4b7d4f968ab3 | checkpoint | Panel layout followed
| 9141804b-878d-51c9-afba-833b47f0bc94 | checkpoint | Panels cut neat / sanded / primed
| 83551f39-445c-532a-a1f2-4d8074545f8c | checkpoint | All tapes / flashings installed
| 0eb4b68b-267a-5def-96ef-e8ab1a27e8a8 | checkpoint | Board nailed positively with 25 mm brads
| be9f3b1e-730f-5823-bce0-07c17c93eb81 | checkpoint | Sealants applied neatly
| e7a5ec63-a5a3-5445-b9a5-49438f890660 | checklist | QA - Cavity Installation Checklist |  | Cavity Installation | e336d883-524d-4da7-88e4-3e8cba180bff
| a9a977d8-6bc2-5973-9cb2-334efab86f9a | checkpoint | Spec followed for timber type
| 5fec4597-6b84-5607-866d-347d4ea53cd1 | checkpoint | Flashings Installed ( Tape with aluband)
| 8092df42-487a-49bf-87c2-16ed1f76219a | textbox | ( Please note flashings )
| da230167-300e-5644-83c3-8c3aa551856c | checkpoint | Ventstrip Install
| 3e1f8c50-4df3-52e6-a7da-7a5b0fc750f1 | checkpoint | Cavity batterns fixed plumb
| 88d47398-e935-5707-a2c0-71713bf4e908 | checkpoint | Cavity batterns at correct Centres
| 920a0164-e62b-59f6-aa39-a0f56f17d532 | checkpoint | Signed off ready for Board/Cladding
| 478ed2d9-d10f-5037-b4d2-b35d97198d6b | checklist | QA - Cedar Cladding Checklist |  | Cedar Cladding - | 07fc4f51-033b-43e5-92e9-0334733af759
| de8678ae-3f76-52a5-8aa8-94d0b162a497 | checkpoint | Cavity Inspected and passed
| caa0e170-9019-54a6-b172-1ce8a69a6f34 | checkpoint | Datums set correctly
| baf0f771-510f-55c1-8741-7c99a1fc3637 | checkpoint | All flashings and penetrations set and sealed
| f0466b30-36f6-54be-b714-49b60863b79d | checkpoint | Corners formed correctly
| d69c0999-246e-529b-85ad-996a4fdb8747 | checkpoint | Joints formed correctly
| e7e8c0c8-58e7-5c21-8b6d-f3f276b8b9e5 | checkpoint | Nailed in alignment
| d1ecc084-143a-5a18-a09c-20cd05ce77ec | checkpoint | Drip Edges Straight
| 7c598409-44f1-5a60-a410-e1dc0a2b72b3 | checkpoint | Painting to exposed edges
| a029f982-e33b-562e-b254-cacd5398904e | checkpoint | Cedar complete
| 81a5e0c0-35f7-585f-816a-9d780bac754f | checklist | QA - CLD Batten Checklist |  | CLD Batten - | 35c93138-aa9e-4768-b3c7-d36b39444f4f
| efbb5e5e-154f-56ea-b250-55f234522708 | checkpoint | Technical Literature followed
| 48927636-7f74-5633-9e36-414775794269 | checkpoint | Batten layout followed
| 204acca2-4dbb-581f-af6b-2989e65d2a11 | checkpoint | Head flashings installed/taped/level
| b27cb623-921f-5935-ad3e-e99bd50fac49 | checkpoint | Vermin strip installed
| 0f6c1989-e3f0-5119-b1a8-043c292d51f6 | checkpoint | Battens level and nailed at 200mm centres
| 482c3b96-9cb2-5aca-9cc7-8b6e15c8b11a | checkpoint | Area complete
| dd1a3534-36a2-5ea5-84cc-0928a4136f46 | checklist | QA - Doors Checklist |  | Doors | a5205297-cd74-4909-8a41-cffd7d8e6290
| 3f7f4451-21a6-5b02-ba01-a6064277ba28 | checkpoint | Correct door to location
| 9888df3d-ce0a-5e29-bfe2-60d0ced86459 | checkpoint | Door fixed to location with correct undercut
| dd9ea886-9e7b-5024-90e9-bdc25534db74 | checkpoint | Hinge Side Plumb and fixed at correct intervals
| 2f4632ac-02d7-5e84-bd0b-06df3a9136e9 | checkpoint | All margins neat with no Whind in door frame
| 9db3cf97-1e2e-50b7-978c-88cc2d58096d | checkpoint | Slider/Bifold/Wardrobe margins and closes correctly
| b7f48a04-51b4-58b6-b9ac-ac3311f8a56a | checkpoint | Door stop fixed correctly
| 768a516d-5424-543e-a2ac-b5a6bb9d802e | checkpoint | Door complete
| 08a9418a-3ad0-5a8d-ab64-02fd85b9270f | checklist | QA - Gutter Framing Checklist |  | Roof & Gutter Framing | bbc38115-ff0d-4e5e-baaa-8fca22274554
| 46bd5a5a-2d00-58bf-885d-91b610d9d2fb | checkpoint | Plans / Specs followed and correct type of timber used
| 157df4ea-54de-5b82-ad28-16abbc9e59c1 | checkpoint | Rafters at correct locations
| 1c93758a-48e5-5506-9d00-9449a3d99277 | checkpoint | Engineer details followed including brackets
| e158d1e9-d4d0-5ca5-9e05-4db92a3527a7 | checkpoint | Gutter Falls to correct location
| a105dda8-ee8b-5613-bf82-ec5f5691a1e3 | checkpoint | 3mm gaps in Ply
| 007f659d-2626-525f-a1cb-591f662c6137 | checkpoint | Sumps formed correctly
folder-normal must be display normal but was flat |  | checklist | QA - Insulation Install Checklist |  | Insulation Install | e3068fd7-3c11-4eab-bf1f-e782a88d212e
checklist-flat is not dependant but can't have own status |  | checklist-flat | Area tidy and accessible
checklist-flat is not dependant but can't have own status |  | checklist-flat | Plans / Specs followed
folder-normal is not dependant but can't have own status |  | folder-normal | Friction fitted
folder-normal is not dependant but can't have own status |  | folder-normal | No gaps in product
folder-normal is not dependant but can't have own status |  | folder-normal | No bulging
folder-normal is not dependant but can't have own status |  | folder-normal | No Compression
folder-normal is not dependant but can't have own status |  | folder-normal | Signed off ready for linings
folder-normal is not dependant but can't have own status |  | folder-normal | Area left tidy and accessible
| 625d0774-35c5-55f9-bb62-fd8c63d5154b | checklist | QA - Lattice Frame Checklist |  | Lattice Frame | ac2458e7-3c38-4f2a-8d8e-442b6b7ca8ad
| 7af1a7ec-2e5e-5178-83be-f3a326d4dbcf | checkpoint | Plans/Specs followed and correct type of timber used
| a12d847a-9ff3-571d-8526-a4e1ce99811f | checkpoint | Safety Mesh Installed as per manufacturers recommendations
| 02479fd6-d4b8-5f16-9d89-e5f268a93daf | checkpoint | Battens perpendicular to purlins at 600c
| 68f5ff20-0dfe-5a6f-8ce0-ad2ae4807c23 | checkpoint | Nogs Installed at 600c
| e98b73cf-1d76-56c9-af45-c10d3d66f6c8 | checkpoint | Engineered plans followed
| 377f6ca3-a0a8-5cae-9007-3082fd3a3ff0 | checkpoint | Complete ready for Ply
| 37111547-bad0-4563-b1aa-d05d0db3159a | checklist | QA - Louvre Install |  | Louvre Install | d7223255-d2aa-4467-887a-75cc004b2973
| b07be924-533b-4669-bad7-90c4d16c1deb | checkpoint | Correct Location
| b5390fb8-ab96-43a2-9ee3-afa0a64cddd3 | checkpoint | Louvre fixed level
| 2633dd96-7e5e-4d40-8139-3807302247a0 | checkpoint | Correct fixing / spacings as per manufacturer / engineer detail
| 8a7462d7-1481-47a2-8b46-7ee2cdaf4fa5 | checkpoint | Sealant applied correctly
| 10e0a468-999e-44ad-8db0-ce8a97cfae41 | checkpoint | Job complete and area left clean and tidy
folder-normal must be display normal but was flat |  | checklist | QA - Ortech Panel System Checklist |  | Ortech Panel System | d47e8877-73c1-4e87-af13-8a88ba4f0bce
checklist-flat is not dependant but can't have own status |  | checklist-flat | Area tidy and accessible
checklist-flat is not dependant but can't have own status |  | checklist-flat | Fixing of timber plate and neoprene at 600mm centres
folder-normal is not dependant but can't have own status |  | folder-normal | Ortech Shop drawings followed
folder-normal is not dependant but can't have own status |  | folder-normal | I purlins and tees fixed in location
folder-normal is not dependant but can't have own status |  | folder-normal | Insulation / Durra fixed with wedges
folder-normal is not dependant but can't have own status |  | folder-normal | Edge protection in place
folder-normal is not dependant but can't have own status |  | folder-normal | Ortech lifted and bolted into place
folder-normal is not dependant but can't have own status |  | folder-normal | Area left tidy and accessible
| 1d1276aa-339c-5f7d-8896-3e3004262ffd | checklist | QA - Plywood To Walls Checklist |  | Plywood To Walls | feedd963-0724-4056-8a6b-abfa1772d0e6
| 86e84210-bf6a-561e-b13a-94a4ab2b8fa9 | checkpoint | Plans / Specs followed and correct type of board used
| c870cb87-704f-57f3-a61f-24e328f16d13 | checkpoint | Wall signed off ready to line
| 390d0bfa-64a2-58b5-a99f-afaf77126188 | checkpoint | Plywood Fixed at Correct centres - 200 Perimeter
| 3f370f2b-c506-5303-b4eb-cb3f66382b5a | checkpoint | All screws at correct depth
| bd5b91d6-7118-5fce-94c3-1fd25c5e7629 | checkpoint | All screw imbedding substate
| a4937760-83ed-5a43-9040-404ab85bd1d8 | checklist | QA - Plywood Under Membrane |  | Plywood Under Membrane | b1e6b572-47a7-4835-8f71-8c990aad9920
| 86e84210-bf6a-561e-b13a-94a4ab2b8fa9 | checkpoint | Plans / Specs followed and correct type of board used
| b91955a7-caa2-59ac-95d2-8a4165c298af | checkpoint | Plywood Fixed at Correct centres - 150 Perimeter.
| 390d0bfa-64a2-58b5-a99f-afaf77126188 | checkpoint | Plywood Fixed at Correct centres - 200 Perimeter
| e8f595b3-5c53-50fe-8726-4afb356a951d | checkpoint | 3mm gaps between ply joints
| b71630be-0bcd-5567-8ef9-ff4e2fd7f853 | checkpoint | Brick Format
| b0529a13-294d-5e53-8247-9a4c539d535b | checkpoint | Screwed and complete for membrane
| 02088465-cc0d-5ad7-a6af-1c0c2328b4bd | checkpoint | Angle Fillets
| 49bdb9da-a65e-5e80-934e-02214b3ec019 | checklist | QA - RAB Checklist |  | RAB - | e3b6640a-e6ab-4431-884a-238f11122dd4
| 2e6ff214-96e7-5718-a09b-fcf0b38fe53b | checkpoint | Plans / specs followed
| 4f9841d1-3333-5f69-a7a1-e7c930467818 | checkpoint | Flashings in place
| 2d955f73-adc9-50b2-b27e-63ab00ef9a9c | checkpoint | Sheet neatly cut and 1-2mm gaps at join
| 55dc53b3-14f4-566a-a6bd-7baf65e311ea | checkpoint | Correct nails / nailing pattern
| b0a9d4c8-73da-5a9e-82b7-79f7059b6f86 | checkpoint | All nails flat and not puncturing board
| d101ae18-4a5d-50d9-9632-448ede1661c0 | checkpoint | Taped / Sealed
| b8c177c2-c595-5912-8ab5-a57fc689f246 | checkpoint | Area RAB complete
| edc345a4-18b4-519d-98a9-da58afd62bdf | checklist | QA - Rockwall |  | QA - Rockwall | e0e25c97-2e5a-4a81-892e-cf17530d73a1
| 676f10d4-88c8-5c20-84bb-2d093eb0994b | checkpoint | Plan identifying location of Rockwall followed
| de686d72-804c-56c5-a299-329a006da28f | checkpoint | Rockwall cut to correct size 150mm past Tall wall/Firefly each side
| 8af8aa41-c9ac-5aa0-929c-2ec376f140e0 | checkpoint | Trapezoidal Rockwall fitted correctly to underside of Traydeck
| 0c9f90aa-cbce-570b-a0ad-d3503b140170 | checkpoint | Galv support angles fitted correctly 150mm each side
| b5366393-bcb3-5c8d-af56-e6412de661fb | checkpoint | Inspection carried out ( note person / Time )
| 482c3b96-9cb2-5aca-9cc7-8b6e15c8b11a | checkpoint | Area complete
| 6b33b381-05e8-59ee-bd8a-9630eaf09545 | checkpoint | Request Sign Off
folder-normal must be display normal but was flat |  | checklist | QA - Roof Subframe Checklist |  | Roof Subframe | 43082a54-c095-4446-957a-ce9d3005b8ea
checklist-flat is not dependant but can't have own status |  | checklist-flat | Area tidy and accessible
checklist-flat is not dependant but can't have own status |  | checklist-flat | Rafters at 400c / Nogs 400c
folder-normal is not dependant but can't have own status |  | folder-normal | Hexagon Mesh fixed
folder-normal is not dependant but can't have own status |  | folder-normal | All brackets / hold downs fixed
folder-normal is not dependant but can't have own status |  | folder-normal | Insulation and friction fitted ready for ply. Photos must be taken
folder-normal is not dependant but can't have own status |  | folder-normal | Ply fixed for membrane following manufacturers recommendations
folder-normal is not dependant but can't have own status |  | folder-normal | Area complete ready for taping
folder-normal is not dependant but can't have own status |  | folder-normal | Area left tidy and accessible
| 7f3dc87b-dd7f-4b1a-9b67-c76ed1782e99 | checklist | QA - Sheet Linning Checklist |  | Sheet Linning | 5d8d2ddf-1391-4fd7-a0dd-41003448762d
| be8efb8e-cd78-4887-b95b-87c31180fc0e | checkpoint | Framing ready/signed off for linings
| 394a6eaa-9fc0-413f-9906-78a61253a092 | checkpoint | Sheet linnings as per Specs
| 49fa7937-6cc2-41fd-9f9d-33b35f2cfbf7 | checkpoint | Correct fixings and centers
| 85374c43-f071-41fb-9112-828c0e4f0163 | checkpoint | Sheet joints/expansion joints or rebates formed correctly
| 159ad904-529f-40b5-8415-d7c98339d5ea | checkpoint | Area ready for Wraps or plastering
| 23bdcfe4-ed85-4777-bde5-0e5f7d742ab0 | checkpoint | Plastering complete and ready for paint
| 63c16f40-9b08-5a84-856e-8e0145bfb01f | checklist | QA - Soffits Checklist |  | Soffits | fab14b43-b651-43b9-bbd1-c9a3d8f05379
| 2851fc22-db14-5baa-9ee0-c425ec2a041f | checkpoint | All Specs for timber followed
| 2c56ccc3-9bb4-531d-8d03-492b7a1692d9 | checkpoint | Soffits to correct RL/Fascias installed neatly and pre primed
| f1e43ad6-7588-5a6b-a99b-0e6325ee024c | checkpoint | Bulkheads at correct location
| 5f3b0efd-8718-5c18-8dba-27b748b1fef8 | checkpoint | Soffits lined with correct board
| 512227cc-31a4-51e2-b6a6-debf65a25828 | checkpoint | All plastering complete
| e924d4b7-8e29-54d7-90ee-75d6ea4a60d1 | checkpoint | Ready for paint
| c670651a-9c88-424a-9a3d-894653848ee3 | checklist | QA - Sound Down Checklist |  | Sound Down Checklist | 76a750bb-e10b-4a49-b172-d29e55435e7c
| 740f5983-d05b-42fe-9220-5148a8ddf083 | section | Section #1 Before install
| d044963f-8a01-4fab-92e0-2951e8a4bc45 | checkpoint | # 1.1 - Have all the documents and specifications been supplied to the installer.
| d6311b89-0e70-4970-91b7-fe127e9462c4 | checkpoint | # 1.2 - Confirm installer has been briefed by the site supervisors on any substrate/structure issues.
| f764e0ea-dce6-488c-b578-a81fc59e687b | checkpoint | # 1.3 - Are the supplied products as per the project specifications.
| 23bee156-787e-451d-a034-df42346e0456 | checkpoint | # 1.4 - Have the sound down products been stored in clean dry environment.
| 63a06951-61ee-4c66-be65-80e2ef329c89 | checkpoint | # 1.5 - Have the sound down products been supplied in good condition.
| 87171ecc-3209-4bd9-a763-3c72268b73f1 | checkpoint | # 1.6 - Is the installation area clean and clear of debris ,water ,dust and grease.
| e4b01709-f9f9-493f-9219-13b111182edc | checkpoint | # 1.7 - Has the floor been inspected for loose items like screws or nails that may impact the floors acoustics.
| 5e72c4a1-78db-40a4-9257-51443b98411a | checkpoint | # 1.8 - Does the CLT floor have less than 16% moisture content.
| b5237be0-5819-4a2a-acf9-4ede7f07346b | checkpoint | # 1.9 - Does the installer have sound down PAB (pre assembled batten) setout tools.
| d2255cb8-9b09-4ac4-be7b-9c0ea0a2d9ad | checkpoint | # 1.10 - Have all the wall linings been signed off before the floor install starts.
| 8665d13e-005c-428d-872b-9c6665d0e554 | section | Section #2 During the install
| b23e933b-3665-4010-a049-763af070046a | checkpoint | # 2.1 - Has the area been planned out ,wall gaps, control joints ,staggered sheets.
| f86dfe19-4a7d-4226-b985-c6e726e6f37d | checkpoint | # 2.2 - Has the layout considered penetrations.
| e1824502-a816-4779-89f6-ea9347184d31 | checkpoint | # 2.3 - Has the installer verified the correct orientation of the sound down PAB.
| 804f09d9-3a6d-4b35-88ea-398fe99aa290 | checkpoint | # 2.4 - Has the PAB been installed 30mm from walls and other battens.
| 7c8cda8f-bd63-45c5-a424-a5dfa1aebdfd | checkpoint | # 2.5 - Has the insulation filled the whole cavity without compressing or crushing.
| 0747b706-63d9-4ad0-922b-19d23c89cfa4 | checkpoint | # 2.6 - Has the Maglok/Osb flooring been fastened with the correct fixings and fixing spacings.
| fd2c47b2-5de6-46c7-a177-f33d194aa670 | checkpoint | # 2.7 - Has the Maglok/Osb flooring been filled with continuous adhesive and all excess glue removed.
| 6580597c-a043-463e-b22b-16fa87451668 | checkpoint | # 2.8 - Have control joints been placed between rooms/spaces or min. every 7.2 x 7.2m
| f65c9f66-de3a-4585-ae1b-24abf46fc91f | checkpoint | # 2.9 - Has the backing rod been installed in the wall to floor joints/control joints to allow for uniform sealant widths and depth.
| 6ca88aa2-9edd-4987-9a06-e9f31b0f71ea | checkpoint | # 2.10 - If in a wet area, have stainless steel fixings been used and fixings been covered with the correct wet area sealant.
| 54102ce7-79ba-48ab-be8c-575e5c75342e | section | Section #3 After installation
| 4ead7d01-da84-4aa3-9f7a-7c31fe4dd965 | checkpoint | # 3.1 - Is the area free from loose items /screws, nails and offcuts.
| 357c4b35-f837-4efb-8ddb-f17101eb7670 | checkpoint | # 3.2 - Is the area closed off and secure for a period of 24 hours after installation.
| b78f8990-f353-4f3c-94c5-1ebf403bf60f | checkpoint | # 3.3 - Is the area protected from wind and rain.
| 52b231fc-b127-52b4-88e5-0a8da17bedd8 | checklist | QA - Steel Stud Checklist |  | Steel Stud | 3d0ce886-5c4d-47bb-9fc2-18b0006e42cb
| 9bd7fbd4-20b6-58b5-a1dc-b6e382b8860f | checkpoint | Bottom tracks set-out to correct revision / Fixed correctly
| 407271b7-aca3-599f-924a-a51e2ed9af03 | checkpoint | Top tracks fixed correctly
| 0e0f1477-a41c-5bc4-8f75-e9eab4e91e2a | checkpoint | Studs at specified centres (fixed only at base, free at head)
| dc53e278-bc3f-5685-a8bb-fe92afe6cca1 | checkpoint | Walls plumb and true
| 30246a4b-7741-52d3-80cc-da6027fce33a | checkpoint | All nogs installed notched correctly
| 35fd355e-f890-5c47-a515-b0058a9f6efa | checkpoint | Area steel stud complete
| 66518502-6ab5-5c39-b884-684202d5d6c5 | checklist | QA - Timber Floors Checklist |  | Timber Floors - | 2b80eb35-7b60-46de-9e34-3eb8765c1979
| 8877b081-4f6e-5ac8-8496-395163263566 | checkpoint | Bearers installed
| c9e3360d-74d4-5170-a77e-6c323742762e | checkpoint | Floor Joists Installed
| 220d946b-9441-5811-ae0b-913b76df33d2 | checkpoint | Engineer Details followed
| b62da46d-261b-57fa-9004-047a0f0b0f6e | checkpoint | Flooring Installed
| 0e393fda-75de-5fd6-ac6a-4c88c014bea3 | checkpoint | Flooring Complete
| 5528d624-d02c-56bb-9fc1-bdce239ac90e | checklist | QA - Timber Framing Checklist |  | Timber Framing | 11aceebe-8e70-417f-a24d-52e487a5dcfc
| 46bd5a5a-2d00-58bf-885d-91b610d9d2fb | checkpoint | Plans / Specs followed and correct type of timber used
| 6e5ea994-16d6-50a7-ae6a-cf60218f3990 | checkpoint | Check for location
| 8be93110-bc88-55c2-a4c5-1b1d880ee0c8 | checkpoint | Bolted at correct centres (please indicate)
| 70cb533e-4071-524c-b5b6-f53c41ccbec3 | checkpoint | Studs installed (Plumb)
| 08ad4dc0-cca1-5071-865c-147f15ea456b | checkpoint | Nogs installed (Level)
| 1c3799cc-f068-5d21-af0a-6f1876c43e34 | checkpoint | Correct centres (please indicate)
| 38c6a3f8-7c38-5886-911d-b37cc7da7eb1 | checkpoint | Check for Straight
| 5b48b148-e7e0-5098-a87e-eb3f5b8e3f67 | checkpoint | Check for Level
| 6574ebe8-80a9-549c-90fa-7a76d6f70646 | checkpoint | Seismic/Engineer details apply
| 16073dd3-393d-5ac7-abe3-ac3e8b6cc449 | checklist | QA - Titan Facade on CLD |  | Titan Facade on CLD | 386f694d-775f-480b-89bd-b5ef507b8f67
| 3dfa42d3-e151-5968-9ba7-8456d69aa162 | checkpoint | Plans/Specs followed
| f242dda0-e32f-5767-a510-5f4f66d3a737 | checkpoint | Sheet layout correct
| b48a54a8-452b-5af5-a910-8d0124f8e0c7 | checkpoint | All cuts straight and primed
| a9c53399-95bf-5e4e-9e40-85f672375f8d | checkpoint | Adhesive applied to CLD batten as per spec
| 385f1391-d001-5a0a-b6f0-b8cb7fe59a2f | checkpoint | Board countersunk screwed at 200mm centres
| 3f5f302b-5729-5607-a0bd-57a54f32e371 | checkpoint | Sealants applied neatly to all joints
| 146d2c6b-16cb-5955-ab80-c1e5269d4aaf | checkpoint | Filling of screws ready for paint
| b5c33e73-2a69-52d2-bbbc-aa6c8b65fbf0 | checklist | QA - Trims Checklist |  | Trims | 78f8ab5e-1c56-4ab6-bc07-d48f1f6a406a
| c0fbfec6-6141-5032-bb11-cb310f01b5f6 | checkpoint | Correct trim used
| 2e9dce60-c949-5862-9c17-63a77ac6622d | checkpoint | All internal comers scribed
| b1188c50-7529-5ffa-9208-aeafd12e7637 | checkpoint | Adhesive applied to skirting
| fe3c7c7e-47fb-5a22-be4a-b4a86bd5ae0f | checkpoint | All external comers neat
| dc86b891-24b5-57d7-8163-91a0ec6c0dff | checkpoint | Skirting fixed correctly and all edges sanded
| d9295c06-e663-59fd-9cd3-fbadf001e9cd | checkpoint | Areas complete ready for paint
| 4a810ac8-ecb6-5317-801b-de9247d90e4c | checklist | QA - Weatherboards Checklist |  | Weatherboards | 593b5f84-238c-4e44-95e0-ab4a34b408b1
| 3dfa42d3-e151-5968-9ba7-8456d69aa162 | checkpoint | Plans/Specs followed
| a3e5331d-ae72-5759-a736-69a04f3d4e9f | checkpoint | Datums for weatherboards set correctly
| 1c63563f-6ce7-59b1-8a72-ac7d11d8a048 | checkpoint | Weatherboards cut with primed ends
| e0d53a95-6288-5052-92cd-9c104a8de8a3 | checkpoint | Installed and Nailed to every Stud location with Stainless Stud R Jolt
| 16421791-f21d-5445-8e0d-5d4ec7ca7866 | checkpoint | Scribers/soakers installed
| 2708ff9a-4b2a-5ad1-b1ab-31f262458514 | checkpoint | Sealant applied
| 482c3b96-9cb2-5aca-9cc7-8b6e15c8b11a | checkpoint | Area complete
| 6bd09b6f-e125-51fb-94e9-1c7128bbcfa3 | checklist | QA - Wraps/Tape Install Checklist |  | Wraps/Tape Install | 13a2685c-4d10-42b6-82cd-e712a0472f2f
| 64b33629-e35a-552b-ab81-3cd83ff1109c | checkpoint | Plans / Specs followed and correct type of paper/wraps used
| 3297b8f8-ee1d-5b4b-b5fe-1074b741d49e | checkpoint | Paper install level
| 407dbd1b-8d62-5e6a-8276-1f0c4c842925 | checkpoint | Packing tape applied
| 15b64986-a3d4-57a5-8011-95c976401461 | checkpoint | All Flashing Tape installed prior taped onto paper
| 9f2a77da-aec4-5c74-95b2-6402f5fec779 | checkpoint | All tapes applied around window
| 57abdda5-08b4-5a38-a514-e8c4be4ef91a | checkpoint | Signoff prior to claddings
folder-normal must be display normal but was flat |  | checklist | QA - Wrapshield Checklist |  | Wrapshield | 791b1541-3f03-4ada-8a1b-c1dbd3d53eb1
checklist-flat is not dependant but can't have own status |  | checklist-flat | Area tidy and accessible
checklist-flat is not dependant but can't have own status |  | checklist-flat | All surfaces clean of devris and dry at install
folder-normal is not dependant but can't have own status |  | folder-normal | Method of direction ok
folder-normal is not dependant but can't have own status |  | folder-normal | All laps 6 inches horizontally 3 inches vertically
folder-normal is not dependant but can't have own status |  | folder-normal | Vertical Seams Staggered
folder-normal is not dependant but can't have own status |  | folder-normal | Roller used for Adhesion at seams
folder-normal is not dependant but can't have own status |  | folder-normal | Penetrations sealed
|  | folder-normal | Handover
folder-normal is not dependant but can't have own status |  | folder-normal | Area left tidy and accessible