## Master Captain's Culvert
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1401A - Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Master ITP |  | Name / Signature | Name / Signature | Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH 05 RS220 RP 3.3
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Enviornmental Controls | W | Contractor to ensure all the enviornmental Controls are in place as per EMP | Prior to commencement | Visual inspection | EMP | Photos, Site log | Site Engineer
2 | River diversion (Temp) and Control Drop Installation | H | Engineer to accept the methodology for construction of the Control Drop point | Prior to commencement | Review | Confirmation from the Engineer | Emails and site visits | Site Engineer | CPS Engineer
3 |  | H | Location to be confirmed with the Engineer | Prior to commencement | Markout | Confirmation from the Engineer | Photos, Site log | Site Engineer | CPS Engineer
4 |  | W | Locate existing services by hand digging | Prior to commencement | Potholing | All conflicts have been located | Permit To Dig | Site Engineer
|  | H | After regrading, Engineer to determine location and number of controlled drops | During Construction | Visual inspection | Engineer acceptance | CONQA | Site Engineer | CPS Engineer
5 |  | H | The engineer shall be notified and afforded the opportunity to be onsite and to direct as necessary as the construction of the control drops | During Construction | Visual inspection | Engineer acceptance | CONQA | Site Engineer | CPS Engineer
6 | Debris Clearance | H | Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,emails | Site Engineer | CPS Engineer
7 | Stream and Bank Regrade | H | Location and extent of bund is to be confirmed on-site with the engineer. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,Photos emails | Site Engineer | CPS Engineer
8 |  | H | Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer. | After clearing debris | Visual inspection | Confirmation from the Engineer | Site visits,emails | Site Engineer | CPS Engineer
9 | Gabion basket installation |  | separate ITP provided
10 | Subsoil Drain |  | separate ITP provided
11 | Parking bay construction |  | separate ITP provided
12 | Kerb and Channel |  | separate ITP provided
13 | GuardRail |  | separate ITP provided
14 | swale | H | The Engineer needs to inspect and adjust the transition and swale if needed. | Once the swale is set out. | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer |  | to confirm test period and requirements
15 | Berm Demolising | H | Final inspection to be done before berm demolision | Before Diverting back the River | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
16 | General Planting | H | The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary. | During planting | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
17 | Site Clean Up | W | Confirm site clean up is done regularly and all rubbish and trays are taken away. | As required | Visual |  | Photos, Site log | Site Engineer
18 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Registe | Site Engineer
19 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: