## Gabion Retaining Wall
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1401A - Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Gabion basket |  | Name / Signature | Name / Signature | Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEE-SH5-HAWKESBAY/EcdE5rU8bVJIsQZl4Zp9baABfxxCQozxCgxwS3hyx4bLQw?e=daq3wt |  | Compliance with Work Instructions and Specifications
Detailed Location:SH 05 RS220 RP 3.3
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | W | Set out the base of the Gabion basket | Prior to commencement | Markout | Consistency with Construction Drawing | Photos | Site Engineer
2 | Procure Gabion Baskets Materials | W | As per Project Specification | Procurement | Document Review | Zinc aluminium, plastic coating mesh size, selvedge wire Stainless steel rings | Product spec sheet | Site Engineer
3 | Gabion Baskets | W | 2.0m x1.0m x1.0m Gabion baskets | Prior to commencement | Ensure delivery docket matches materials delivered | Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately | Delivery Dockets | Site Engineer
4 | Gabion Rock Material Diameter | H | Rock Infill shall be 100mm minimum and 250mm maximum particle size based diameter | All material used | Ensure delivery docket matches materials delivered | Compliance with requirements noted on bulk fill checksheet | Delivery Dockets | Site Engineer
5 | Excavate Base of Wall | H | Excavate footprint of the wall area to the correct line and level and ensure area safe to work in. | As required | Survey | Consistency with Construction Drawing | Survey Receipt | Site Engineer
6 |  | H | Base of excavation to be checked by Geotech engineer / CPS Engineer | After excavation | Visual inspection | Confirmation from the Engineer | Site visits,Photos emails | Site Engineer | CPS Engineer
7 |  | H | Clegg Test the base of the excavation after placing 250mm AP65. | Prior to construction of wall | Lab Testing | Confirmation from the Engineer | Lab test result | Site Engineer | CPS Engineer
8 | Subsoil Drainage | H | Subsoil drainage is required for this wall construction then follow the ITP for Subsoil Drainage | Prior to construction of wall | Document Review |  | ITP Subsoil Drainage | Site Engineer | CPS Engineer
9 | Construct Wall | W | Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level. | As required | Visual |  | Photo's | Site Engineer
10 |  | W | Tie the first layer of baskets together using Manufacturers specs for tying baskets | As required | Visual |  | Photo's | Site Engineer
11 |  | W | Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square | Every basket | Visual |  | Photo's | Site Engineer
12 |  | W | Tip Gabion material slowly into the baskets to fill the voids as much as possible | Every basket | Visual |  |  | Site Engineer
13 |  | W | Ensure line and level of front face is as per design | Each Lift | Visual |  |  | Site Engineer
14 |  | W | Tie next layers of bottom to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again | Every basket | Visual |  |  | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: