## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guardrail & Wire Rope Barriers |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH05 RS 220 RP3.3
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 |  | H | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | OFI or NTD/NTC | Site Engineer | Design Engineer
2 | Survey Setout | H | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer
3 | Material Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer | CPS
4 |  | H | All materials to be sourced from registered suppliers | Prior to commencement | Document Review | Registered suppliers | Materials register | Site Engineer | CPS
5 |  | H | Proposed galvanising repair methodology to be approved by Engineer | Prior to commencement | Document Review | Best practice | Approved / Signature | Site Engineer | CPS
6 | Guardrail Installation | H | Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers | On Procurement of installer | Written confirmation | ASHTAS operative and installer course | Attendance Certificate | Site Engineer | CPS
7 |  | W | Nu-Guard 31 shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 Guardrail Installation Checksheet | Site Engineer
8 |  | W | W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | Installation Checklist | Site Engineer
9 |  | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 |  | Site Engineer
10 | Fit for purpose Inspection | H | Barrier to undergo fit for purpose inspection by competent person | Prior to trafficking, | Visual inspection | Pass inspection | Confirmation from inspector | Site Engineer | CPS
11 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
12 | As-builts |  | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: