## Rock Armouring
[5 empty] | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
[5 empty] | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
[5 empty] | Procedure: | Rock Armouring |  | Name / Signature | Name / Signature | Site Engineer
| Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
| Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
| 1 | Survey Setout | H | Set out extents and check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing - | Survey receipt | Site Engineer
| 2 |  | H (CPS) | Engineer to confirm the extend with site conditions - Drawings C03, C04, C10 | Prior to commencement | Visual Inspection | Engineers Acceptance | Raise RFI on Procore | Site Engineer | CPS Engineer
| 3 |  | H (CPS) | Inspect fill foundation | Per area as required | Inspection by the Geotechnical Design Manager | Fill foundation must be approved, in writing, before filling commences | CS-4100 Subgrade Approval | Site Engineer | CPS Engineer
| 5 | Material Compliance Testing | H | Material to meet specifications dependant (D50 of 125mm Class 1) | Each material used | Document Review |  |  | Site Engineer
nbh | 6 |  | H | Rock Construction Material | 1 test per Lot | Lab Testing |  | Lab Test Report | Site Engineer
| 7 |  | H | Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 |  | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
| 8 | Construction of Engineered Fill Embankment | H (CPS) | Location of bank regrading to be agreed with CPS Engineer - Drawing C10 item 3.2 | Prior to commencement | Visual Inspection | Engineers Acceptance | Raise RFI on Procore | Site Engineer | CPS Engineer
|  |  | W | Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap | Prior to commencement | Visual Inspection | Intake Earthworks ITP completed |  | Site Engineer
| 9 | Geotextile Placement | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection |  | Photo's | Site Engineer
| 10 | Riprap Placement | W (CPS) | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photo's | Site Engineer | CPS Engineer
| 13 | Survey As Built | H | Ensure rock slopes comply with design prior to next process taking place | At completion of Lot | Measurement |  | Survey receipt | Site Engineer
| 14 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
| 15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
| 16 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Asbuilts, NCR's and RFI's | Site Engineer
| 18 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
| QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
| QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: