## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Environmental Controls
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Contractor to ensure all the environmental Controls are in place as per EMP
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - EMP
label | Records - Photos, Site log
checkpoint | 2 - River diversion (Temp) and Control Drop Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to accept the methodology for construction of the Control Drop point
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Emails and site visits
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location to be confirmed with the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Photos, Site log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Locate existing services by hand digging
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located
label | Records - Permit To Dig
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - After regrading, Engineer to determine location and number of controlled drops
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The engineer shall be notified and afforded the opportunity to be onsite and to direct as necessary as the construction of the control drops
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Debris Clearance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Stream and Bank Regrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,Photos emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Gabion Basket Installation
label | Detail - separate ITP provided
checkpoint | 10 - Subsoil Drain
label | Detail - separate ITP provided
checkpoint | 11 - Parking Bay Construction
label | Detail - separate ITP provided
checkpoint | 12 - Kerb and Channel
label | Detail - separate ITP provided
checkpoint | 13 - Guardrail
label | Detail - separate ITP provided
checkpoint | 14 - Swale
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | Frequency - Once the swale is set out.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Berm Demolising
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection to be done before berm demolision
label | Frequency - Before Diverting back the River
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - General Planting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | Frequency - During planting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Site Clean Up
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm site clean up is done regularly and all rubbish and trays are taken away.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photos, Site log
checkpoint | 18 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Registe
checkpoint | 19 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT