## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out the base of the Gabion basket
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Photos
checkpoint | 2 - Procure Gabion Baskets Materials
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - As per Project Specification
label | Frequency - Procurement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Zinc aluminium, plastic coating mesh size, selvedge wire Stainless steel rings
label | Records - Product spec sheet
checkpoint | 3 - Gabion Baskets
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - 2.0m x1.0m x1.0m Gabion baskets
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
label | Records - Delivery Dockets
checkpoint | 4 - Gabion Rock Material Diameter
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Infill shall be 100mm minimum and 250mm maximum particle size based diameter
label | Frequency - All material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Compliance with requirements noted on bulk fill checksheet
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | Frequency - After excavation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits, Photos emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Clegg Test the base of the excavation after placing 250mm AP65.
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Lab test result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subsoil drainage is required for this wall construction then follow the ITP for Subsoil Drainage
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - ITP Subsoil Drainage
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Construct Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tie the first layer of baskets together using Manufacturers specs for tying baskets
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure line and level of front face is as per design
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tie next layers of bottom to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT