## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All materials to be sourced from registered suppliers
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Registered suppliers
label | Records - Materials register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Best practice
label | Records - Approved / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | Frequency - On Procurement of installer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | Conformance Criteria - ASHTAS operative and installer course
label | Records - Attendance Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Nu-Guard 31 shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117 Guardrail Installation Checksheet
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
checkpoint | 10 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person
label | Frequency - Prior to trafficking,
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pass inspection
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 12 - As-builts
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing