## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out kerb line and level at 1m offset to EOS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | Frequency - 1/600m3, minimum of 1 per source (but make three cylinders)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | Conformance Criteria - 20MPa at 28 days
label | Records - Concrete Delivery Dockets and lab test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Kerb Foundation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Sub base construction is completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Stringing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check weather forecast and avoid adverse conditions
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Slip forming
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | Frequency - Prior to slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - To ensure the correct concrete mix is delivered
label | Records - Concrete Delivery Dockets and lab test results
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Expansion joints to be formed at 5m centres
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Kerbing Specification
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 13 - Tie-in with pre-cast components
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Work Instruction
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Protection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Backfilling to commence only after 72 hours
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT