## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | 4bdfc2f9-d444-4927-8bc0-f8f80ec25e59
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Environmental Controls
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Contractor to ensure all the environmental Controls are in place as per EMP
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - EMP
label | Records - Photos, Site log
checkpoint | 2 - River diversion (Temp) and Control Drop Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to accept the methodology for construction of the Control Drop point
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Emails and site visits
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location to be confirmed with the Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Photos, Site log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Locate existing services by hand digging
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located
label | Records - Permit To Dig
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - After regrading, Engineer to determine location and number of controlled drops
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The engineer shall be notified and afforded the opportunity to be onsite and to direct as necessary as the construction of the control drops
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Debris Clearance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Stream and Bank Regrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,Photos emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | Frequency - After clearing debris
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits,emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Gabion Basket Installation
label | Detail - separate ITP provided
checkpoint | 10 - Subsoil Drain
label | Detail - separate ITP provided
checkpoint | 11 - Parking Bay Construction
label | Detail - separate ITP provided
checkpoint | 12 - Kerb and Channel
label | Detail - separate ITP provided
checkpoint | 13 - Guardrail
label | Detail - separate ITP provided
checkpoint | 14 - Swale
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | Frequency - Once the swale is set out.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Berm Demolising
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection to be done before berm demolision
label | Frequency - Before Diverting back the River
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - General Planting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | Frequency - During planting
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Site Clean Up
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm site clean up is done regularly and all rubbish and trays are taken away.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photos, Site log
checkpoint | 18 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Registe
checkpoint | 19 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | 4691bc5c-891f-4887-aec2-a2dbd86e25da
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out the base of the Gabion basket
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Photos
checkpoint | 2 - Procure Gabion Baskets Materials
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - As per Project Specification
label | Frequency - Procurement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Zinc aluminium, plastic coating mesh size, selvedge wire Stainless steel rings
label | Records - Product spec sheet
checkpoint | 3 - Gabion Baskets
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - 2.0m x1.0m x1.0m Gabion baskets
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
label | Records - Delivery Dockets
checkpoint | 4 - Gabion Rock Material Diameter
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Infill shall be 100mm minimum and 250mm maximum particle size based diameter
label | Frequency - All material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Compliance with requirements noted on bulk fill checksheet
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | Frequency - After excavation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Site visits, Photos emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Clegg Test the base of the excavation after placing 250mm AP65.
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Confirmation from the Engineer
label | Records - Lab test result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subsoil drainage is required for this wall construction then follow the ITP for Subsoil Drainage
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - ITP Subsoil Drainage
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Construct Wall
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tie the first layer of baskets together using Manufacturers specs for tying baskets
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Photo's
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure line and level of front face is as per design
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Tie next layers of bottom to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
label | Frequency - Every basket
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | f2a2ecde-fa69-4c4d-ae22-46fb3e016e3f
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All materials to be sourced from registered suppliers
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Registered suppliers
label | Records - Materials register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Best practice
label | Records - Approved / Signature
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | Frequency - On Procurement of installer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | Conformance Criteria - ASHTAS operative and installer course
label | Records - Attendance Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Nu-Guard 31 shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117 Guardrail Installation Checksheet
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - Installation Checklist
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
checkpoint | 10 - Fit for purpose Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Barrier to undergo fit for purpose inspection by competent person
label | Frequency - Prior to trafficking,
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pass inspection
label | Records - Confirmation from inspector
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 12 - As-builts
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | 78d668af-78db-490b-a9f1-3bcf1df2fffb
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out kerb line and level at 1m offset to EOS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | Frequency - 1/600m3, minimum of 1 per source (but make three cylinders)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | Conformance Criteria - 20MPa at 28 days
label | Records - Concrete Delivery Dockets and lab test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Kerb Foundation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Sub base construction is completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Stringing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check weather forecast and avoid adverse conditions
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Slip forming
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | Frequency - Prior to slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - To ensure the correct concrete mix is delivered
label | Records - Concrete Delivery Dockets and lab test results
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Expansion joints to be formed at 5m centres
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Kerbing Specification
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 13 - Tie-in with pre-cast components
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Work Instruction
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Protection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Backfilling to commence only after 72 hours
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring | itp |  |  |  |  | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring | 7a9b9391-1d71-4fe3-b275-b40102e12acb
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing -
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - H (CPS)
label | Detail - Engineer to confirm the extend with site conditions - Drawings C03, C04, C10
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Raise RFI on Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H (CPS)
label | Detail - Inspect fill foundation
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant (D50 of 125mm Class 1)
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Construction Material
label | Frequency - 1 test per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Construction of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - H (CPS)
label | Detail - Location of bank regrading to be agreed with CPS Engineer - Drawing C10 item 3.2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Raise RFI on Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Intake Earthworks ITP completed
checkpoint | 9 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 10 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W (CPS)
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 13 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure rock slopes comply with design prior to next process taking place
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 18 - Completion Sign Off From Fields Below
label | Records - Signatures