## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | a74680a6-5be7-4648-b23c-174380971beb |  | checklist | 0003 Containment |  |  |  |  | Yes | 0003 Containment (V3) | 073f5a2e-f391-4158-b59d-5bd0aa4e6c5a
checkpoint-group | 71aa308b-6803-4e67-aae8-ebd58a3dfbb8 |  | section | Preliminary Inspections and Tests
checkpoint-status | ac395927-b132-4633-9c74-d968bcc17347 |  | checkpoint | RDM & Consent Approval
holdpoint | 02511aa4-3550-43ca-9be3-4ede21fd9a21 |  | signoff | Nominated Authority Sign off
checkpoint-status | 06beca58-7739-4fdb-a25b-1973f57bfb99 |  | checkpoint | Define LOT Area
checkpoint-status | ab4718d2-7a79-4a39-930f-521a4fcde983 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 7169c81f-ccf8-4287-b1c2-e97f22522fbf |  | checkpoint | Draw up proposed route of Cable Containment
checkpoint-status | 1995fc84-5def-4681-9d54-b0ad61f19258 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 3f9fcfb6-fc74-445d-b8e4-265c3a9887b4 |  | section | Containment
checkpoint-status | 0be21546-fcf0-4330-9755-3aa167b8a918 |  | checkpoint | Pre-start meeting
checkpoint-status | 8a9227a2-18cc-4500-a8c1-e3b92ce4a55d |  | checkpoint | Site Inspection and JRA.
checkpoint-status | ce13c2fe-f11f-4043-ba4b-a130d819839f |  | checkpoint | Ensure reference Drawings are listed in Reference Documentation.
checkpoint-status | c66d2076-e436-496e-9dd6-c43975c3f264 |  | checkpoint | Ensure cable ladders and trays are provided to support cable runs (where necessary).
checkpoint-status | 365c5ec5-d13c-482e-b915-76e66e8f8b13 |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity.
checkpoint-status | d89ad2e1-48eb-4622-945e-3d6ed8a681c9 |  | checkpoint | Ensure cable ladder and tray is installed as manufacturer's instructions, complete with all necessary splice plates, bends and fixings.
checkpoint-status | ff8aca96-b492-4665-92e8-e1f384a89f6e |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable.
checkpoint-status | 528d8001-eacc-4f48-b44b-36cb31adab9c |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009.
checkpoint-status | 98bc9601-3433-4a13-b284-8902ffd6a061 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 3771c947-e602-4545-a85a-397c693cdba3 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 31aea5c2-ea39-49d0-ba20-fcaea0376cba |  | section | Completion Inspections and Tests
checkpoint-status | 4dd0fe94-28a1-4569-a20d-318873249c6b |  | checkpoint | Inspection by supervisor
checkpoint-status | 3b09232e-50bd-4956-8e3e-d8f66d03e35f |  | checkpoint | Seismic Bracing
holdpoint | 487f6d53-29ee-4c22-93a5-86f40373378c |  | signoff | Nominated Authority Sign off
checkpoint-status | d76daef7-c21f-407f-ab07-9c812b901082 |  | checkpoint | Notice of Completion
holdpoint | 4f4e803f-6480-49d5-972a-7e0869e98875 |  | signoff | Nominated Authority Sign off
checklist-sectioned | d1176dc4-5a71-4164-865f-84fe9b8850e6 |  | checklist | 0011 GPO/Electrical Equipment |  |  |  |  | Yes | 0011 GPO/Electrical Equipment (V2) | 087b0bfe-cc72-4196-a127-7a996f9a2005
checkpoint-group | 35994d35-2b63-43bf-8417-181aa18e5729 |  | section | Preliminary Inspections and Tests
checkpoint-status | 1d591cab-612b-4255-b7a4-201013360ae9 |  | checkpoint | RDM & Consent Approval
holdpoint | c5709c79-01c8-4b94-bb86-29c981b1686e |  | signoff | Nominated Authority Sign off
checkpoint-status | 2a746e3d-00dc-45fc-a610-61922b10fdb4 |  | checkpoint | Define LOT Area
checkpoint-status | 4124aa62-44dc-4e37-bf03-6b06948fdc0d |  | checkpoint | Understanding of the Scope of works
checkpoint-status | c622e9d6-9e98-467b-8e90-4aca9ee769e0 |  | checkpoint | McKay SHD GPO/Electrical Equipment
checkpoint-status | 3b0ca000-0f2f-4c85-a7a0-3b51edc2a1e7 |  | checkpoint | Site inspection and SWMS
checkpoint-group | e4520479-5790-4d2d-bc54-9a70e84104c8 |  | section | GPO & Electrical Install
checkpoint-status | 4182c5f7-c311-460b-8064-816d4b5050a7 |  | checkpoint | Pre-start meeting
checkpoint-status | 2f4ef9a2-6136-4b1b-8ad5-a5f28e389c9d |  | checkpoint | Site Inspection, JRA .
checkpoint-status | c61fd4fb-5b77-4368-a532-e6b2ab3f06b2 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 961522b5-7232-49dc-b78e-e11d18ad6374 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | d3b4de06-5767-49e7-9329-6263fef4e016 |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | ec0d1a92-8f83-431c-80c9-eb25282b7300 |  | checkpoint | Electrical Equipment Check Sheet/s Completed as required.
checkpoint-status | 21e3c881-c400-4386-8532-f06168a87fbf |  | checkpoint | All test sheets completed as per AS/NZS 3000:2007 as required.
checkpoint-status | 3af512ee-afa1-4f3d-8a35-9e324b68c063 |  | checkpoint | All refuse removed from work area.
checkpoint-status | a7b83a25-3660-46ea-b48f-bfde0d692a39 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 3ad58e64-f349-4818-ba35-a63f04dccb11 |  | section | Completion Inspections and Tests
checkpoint-status | 70031877-6d55-46c9-a753-ebd5045c57e8 |  | checkpoint | Inspection by supervisor
checkpoint-status | 64c4eb17-4658-42d2-9f29-df1ff4ca588b |  | checkpoint | Notice of Completion
holdpoint | 3ed003ce-1e51-439e-8cbf-1f6d458e2c9a |  | signoff | Nominated Authority Sign off
checklist-sectioned | 8e47aaaa-e9f1-4586-bba4-ea4c97db97ac |  | checklist | 0005 Earthing/Bonding |  |  |  |  | Yes | 0005 Earthing/Bonding | 09e24762-0b89-42ee-94c9-36c8e38bc994
checkpoint-group | 833d70d3-345a-4952-bfa4-d494099823b8 |  | section | Preliminary Inspections and Tests
checkpoint-status | 325541e2-0155-4f12-a76b-8dab4192d232 |  | checkpoint | RDM & Consent Approval
holdpoint | e90f7a09-9607-4c67-806a-aa139208bc65 |  | signoff | Nominated Authority Sign off
checkpoint-status | b7a4318d-7c89-4c84-b91a-5bfc4ddf8f3f |  | checkpoint | Define LOT Area
checkpoint-status | d8e10308-ef7b-4da1-bb8b-d4415a67cafe |  | checkpoint | Understanding of the Scope of works
checkpoint-status | fc3a44c7-0d3a-41e4-a47a-e0c4c27434e9 |  | checkpoint | McKay SHD proposed Lighting Layout
checkpoint-status | 18ea42cd-669c-411a-a0eb-94105bdef783 |  | checkpoint | Site inspection and SWMS
checkpoint-status | bf32a3dd-7516-46b2-9d1a-509573051b9e |  | checkpoint | Hot works permit
checkpoint-group | 9217db2f-11c3-4df7-b374-1657bb60bc35 |  | section | Earthing & Bonding
checkpoint-status | c9416a2f-3b5a-4d7e-8848-979f8f8f36cc |  | checkpoint | Pre-start meeting
checkpoint-status | 134ea78a-1df8-4154-a0c1-8099e72bd02a |  | checkpoint | Weld 120mm2 copper wire to steel pile as specified on pile plan.
checkpoint-status | 2931c156-7d82-4a19-8f9c-94a002e4e99f |  | checkpoint | Test the resistance between earth points and end of the earth cable, record readings on McKay I&T Form 20 - Earthing Resistance Test sheet.
checkpoint-status | 0db1d29a-5753-4405-b770-43225600fcdc |  | checkpoint | Feed and cable tie copper earth wire towards exit point.
checkpoint-status | 33e4d0a8-6ae6-4e18-a5ef-dac56ee9094b |  | checkpoint | Test the resistance between the reo bar, other steel piles and end of 120mm2 earth wire, record readings on McKay I&T Form 20 - Earthing Resistance Test sheet.
checkpoint-status | 7d7161a6-2a8e-4a6c-933e-7d49f38ee7dd |  | checkpoint | All Earth, Bonding and Equipotential Bonding to AS/NZS 3000:2007
label | 46956003-e810-56ed-85dd-2da31e2194b6 |  | note | Once concrete had cured, test between earth lead with trailing lead and record reading.
checkpoint-status | 86482caa-31d5-429e-a1d0-5c6e2da8e07b |  | checkpoint | Number each test point on a plan as reference to each recorded result and take photo.
checkpoint-status | 053f14f9-2199-47f1-924c-354daf86332f |  | checkpoint | Complete McKay I&T Form 20 - Earthing Resistance Test sheet.
checkpoint-group | 23b2cd3a-c874-4dcb-84f1-9163e9ee3a74 |  | section | Completion Inspections and Tests
checkpoint-status | 9b1d4288-551c-482b-9af4-579e068c0474 |  | checkpoint | Inspection by supervisor
checkpoint-status | df0cc609-a189-4568-b0d9-8d357d3455eb |  | checkpoint | Notice of Completion
holdpoint | 35efcb87-2454-4788-be13-b64ca28a5a1d |  | signoff | Nominated Authority Sign off
checklist-sectioned | 9c329254-8e09-4793-8e4b-78c88e5b7377 |  | checklist | 0007 Switchboards |  |  |  |  | Yes | 0007 Switchboards | 19b8079a-887c-4e68-866c-f281bbe3c876
checkpoint-group | 67f160f3-5b8e-417e-b233-e4420f943b1e |  | section | Preliminary Inspections and Tests
checkpoint-status | f94bcbcb-4ef0-4d66-b6b3-d696a9cdc3ba |  | checkpoint | RDM & Consent Approval
holdpoint | 5a32b4c0-c317-49dc-b19a-47e66d12ef7e |  | signoff | Nominated Authority Sign off
checkpoint-status | 10f3a875-3d58-4e28-b4f9-083435743492 |  | checkpoint | Define LOT Area
checkpoint-status | 23661e9c-478a-4af8-a0be-261dc36c2d21 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 6585763f-44a0-4a61-a9d2-9c2571b782fe |  | checkpoint | Confirm Position
checkpoint-status | 857547a1-aaf5-4110-9e1c-cc67721b657b |  | checkpoint | Site inspection and SWMS
checkpoint-group | 38fe5e9b-f835-49af-93ee-726c4cf9eb26 |  | section | Switchboard Installation
checkpoint-status | d7105692-8d95-4f10-a4b4-6af10cd4d000 |  | checkpoint | Pre-start meeting
checkpoint-status | 13f46979-dbcc-4b48-9ba4-5d86e3e35840 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 55a07ae3-0c63-4a5d-8dec-9d9175a61c08 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | 2b714097-0c1b-459c-a397-bdae4cbd6cee |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | e394a1e8-94da-4300-9c84-e750e58310dd |  | checkpoint | CTT labelling completed.
checkpoint-status | 05560e91-f311-4c1a-acdf-ff08c1a32ecc |  | checkpoint | All Cable glands compressed.
checkpoint-status | 8defdf71-04f3-4752-ba86-059ed823ef72 |  | checkpoint | Seismic Restraints installed as required
checkpoint-status | a5cc0d86-ada9-4ac9-8bfd-005f2cd541c6 |  | checkpoint | Complete McKay Test Forms 0 & 20.
checkpoint-status | ef1c28dc-6ff0-430b-9c07-86fd9ec5a7f2 |  | checkpoint | All ASNZS 3000:2007 tests sheets completed.
checkpoint-status | 46cd0665-2399-4da6-9632-d8e2f0c15a85 |  | checkpoint | All Refuse removed from work area.
checkpoint-status | 72671e7f-eb1f-4687-ae76-ce0719f5c12b |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 4c5ba1c8-f98a-40a9-b995-01e19a214333 |  | section | Completion Inspections and Tests
checkpoint-status | c152a2f0-7f0f-4935-b192-f9d5787fa776 |  | checkpoint | Inspection by supervisor
checkpoint-status | 173513a3-1a94-4abe-8823-4455b156558a |  | checkpoint | Notice of Completion
holdpoint | 016f560e-3e97-4253-8d7a-29480cff82fc |  | signoff | Nominated Authority Sign off
checklist-sectioned | aaa4c8f3-19b6-4de2-b34e-184e4fa4e022 |  | checklist | 0003 Containment |  |  |  |  | Yes | 0003 Containment (V4.1) | 282033a8-49bd-4a7d-9d34-5aba8fe7e99c
checkpoint-group | 67aa2add-bb59-4172-97df-5c41ef935a0f |  | section | Containment
checkpoint-status | 7413b1a7-385a-4c90-91f1-1d387dd76225 |  | checkpoint | Pre-start meeting (5)
checkpoint-status | e1b93033-d0f2-4888-bde1-dd12a536a3d3 |  | checkpoint | Site Inspection and JRA. (5)
checkpoint-status | df53e2d7-473f-4972-ba7b-ea58922d1f68 |  | checkpoint | Ensure reference Drawings are listed in Reference Documentation. (4)
checkpoint-status | 1006eb25-afe3-4d91-b2cc-62c3bd21a813 |  | checkpoint | Ensure cable ladders and trays are provided to support cable runs (where necessary). (6)
checkpoint-status | 34412239-a413-41cf-994f-29e0a17665f9 |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity. (6)
checkpoint-status | 22df879d-0341-49ab-90b6-e1e40f3bf56b |  | checkpoint | Ensure cable ladder and tray is installed as manufacturer's instructions, complete with all necessary splice plates, bends and fixings. (6)
checkpoint-status | d938701c-7e43-4294-84d2-c076733b01e2 |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable. (6)
checkpoint-status | 3f88424c-c156-42df-a29f-5fc8d33447bf |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009. (7)
checkpoint-status | 11b00299-a03c-48b4-9b68-2842361e8cd7 |  | checkpoint | All refuse removed from work area. (6)
checkpoint-status | c9ac2cac-ebcb-49b2-9b32-5b77e8daad18 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA. (6)
checkpoint-group | 652b7988-ac6b-431b-a632-641b6a738b86 |  | section | Completion Inspections and Tests
checkpoint-status | 6d8edcf6-180a-4937-a696-6c614175c6a6 |  | checkpoint | Notice of Completion. (9)
holdpoint | f21055bb-587b-4275-b423-eaadc3e3ba06 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 3ca51c3b-264b-4ef4-b4be-e90173ab7762 |  | checklist | 0012 Street Pole Foundation and Erection |  |  |  |  | Yes | 0012 Street Pole Foundation and Erection (V2) | 3086f25c-de28-4030-8c1c-8840eba17993
checkpoint-group | b3b7b503-9207-4e7c-9fc8-51315fa81e11 |  | section | Preliminary Inspections and Tests
checkpoint-status | e58aa382-8819-4d03-ad95-295c9696b49d |  | checkpoint | RDM & Consent Approval
holdpoint | 5a75ad03-7131-475e-a5a9-0d0482fa8b5b |  | signoff | Nominated Authority Sign off
checkpoint-status | a87d8731-543e-4570-99fb-b494c233ab8e |  | checkpoint | Define LOT Area
checkpoint-status | cf43ca87-4983-46e8-855c-914ff83275f9 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 3e2b616d-459e-47da-b64c-346217e751d2 |  | checkpoint | Ensure materials available
checkpoint-status | f70fb217-5c4c-42bd-957f-b11a101bf6db |  | checkpoint | Site inspection and SWMS
checkpoint-group | 2090193f-4b35-4ef2-bde0-2af4816b4631 |  | section | Street Light Foundation & Erection
checkpoint-status | 6e5cf9bd-d1e3-4bca-a2dd-01c4f60081b6 |  | checkpoint | Pre-start meeting
checkpoint-status | b9b1f206-ef3b-46e3-b0e2-d6c34b633e0b |  | checkpoint | Site Inspection, JRA .
checkpoint-status | e4d3819e-ff51-4328-9550-ca3d55fe7333 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 96342f21-1373-43c8-bcb1-864ab2125ab3 |  | checkpoint | Layout and location drawing confirmed as current and accurate
checkpoint-status | 46a3afd2-76b7-4f5f-9251-1f645883c70d |  | checkpoint | Excavation completed. (Photos to be taken)
checkpoint-status | 8186337d-2696-4724-a7e9-cf4cb7b6d224 |  | checkpoint | Foundation Installed. (Photos to be taken)
checkpoint-status | f1389254-bdd0-4864-9289-fada4c51ad3d |  | checkpoint | Pole Installation and equipment (Luminaire, Fusing and Earthing) as per AS/NZS 3000:2007.
checkpoint-status | a19515b6-4364-44ad-b3d8-70d264a1aa70 |  | checkpoint | Grouting completed within 7 days of installing the pole as per Specification references 26.
checkpoint-status | a663e626-28f1-4b98-84b6-384d13b93e03 |  | checkpoint | All test sheets completed as per AS/NZS 3000:2007.
checkpoint-status | d4010c0d-5331-464b-b484-10018355e192 |  | checkpoint | All refuse removed from work area.
checkpoint-status | afcb9c04-ce62-4de6-9428-ca4b045a01b9 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | ab431783-6412-4b5b-bee1-bc8045d5ebdc |  | section | Completion Inspections and Tests
checkpoint-status | c4425dff-4ca1-433a-a979-f35376ca81a2 |  | checkpoint | Inspection by supervisor
checkpoint-status | 07fa9cf5-20e1-47ce-b90b-d50bf5df166a |  | checkpoint | Notice of Completion
holdpoint | 2ef9f62d-60c9-48e7-93ec-1607c12bd1dc |  | signoff | Nominated Authority Sign off
checklist-sectioned | 123038cc-c51a-4c7a-b834-294bb7d6b4a3 |  | checklist | 0008 Underground Submains |  |  |  |  | Yes | 0008 Underground Submains V1 | 3172f92f-0e67-43b3-95e4-f77e2992a7ad
checkpoint-group | 2d58da34-d9e5-4fc0-bfad-ae52f1196850 |  | section | Preliminary Inspections and Tests
checkpoint-status | 669b1f3a-1485-4aea-8c01-8946372f8bc0 |  | checkpoint | RDM & Consent Approval
holdpoint | 4e842c30-2e11-4024-b153-bd6107685fde |  | signoff | Nominated Authority Sign off
checkpoint-status | 76414f94-43d5-4ab1-a857-03d4f70c1b94 |  | checkpoint | Define LOT Area
checkpoint-status | f41efc7b-18d8-4f8f-bd26-d1576ecc7699 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 8948f5d5-647f-4f48-8d23-0b2d6a0691ff |  | checkpoint | Trench Inspection
checkpoint-status | 5fa2ffd8-54a7-42a7-9887-3a9e7db9f198 |  | checkpoint | Drum Delivery Test Certificate
holdpoint | 1acd38b1-1b75-4e98-a021-b8bd8ca2f922 |  | signoff | Nominated Authority Sign off
checkpoint-status | b8d8ee1d-25af-4e39-bf4f-ce96e00ed5f4 |  | checkpoint | Site inspection and SWMS
checkpoint-group | c1fb37fc-8254-495c-b04d-2fbb30940830 |  | section | Underground Submains
checkpoint-status | 94e2064d-9c62-4edb-8732-a1077e0a9ba0 |  | checkpoint | Drawings referenced in Reference Documentation
checkpoint-status | 21b8c440-19f7-4db9-adc6-226f0ab71fe2 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | f4004cd5-c1ba-4c40-a965-9f2bf7650e16 |  | checkpoint | Installed to AS/NZS 3000:2007 and AS/NZS 3008:2007.
checkpoint-status | a23ef7af-270e-4c46-ba93-043312f86982 |  | checkpoint | CCT labelling completed.
checkpoint-status | d193494b-014d-42f2-bad9-61e75ee84ca2 |  | checkpoint | McKay I&T 19 A, and 19D Inspection and Test forms completed.
checkpoint-status | 8d8df260-108a-426d-8086-034cb28cca21 |  | checkpoint | Seismic Loops installed as required.
checkpoint-status | cb0965a5-0f36-43c2-ae34-908acfdfd8f3 |  | checkpoint | All AS/NZS 3000:2007 tests sheets completed.
holdpoint | 6eb7b1dc-4ff0-4422-a5d1-677538524adf |  | signoff | Nominated Authority Sign off
checkpoint-status | 899fe638-dbeb-4d71-aadf-e71a622e0db2 |  | checkpoint | All refuse removed from work area.
checkpoint-status | d06454c0-aa8a-40d6-8505-1625e2a89697 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 09d0df61-2945-40d5-8f63-f0f9330b55e7 |  | section | Completion Inspections and Tests
checkpoint-status | 0b91c8f8-43ec-4021-82f8-f4bb5ece8a93 |  | checkpoint | Inspection by supervisor
checkpoint-status | a517f307-1d2e-4776-ac14-9af039a4a23d |  | checkpoint | Notice of Completion
holdpoint | f29292bc-a94f-4851-88b0-c1ade0357e58 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 5d10d7db-b442-401f-8766-8f096e6e9547 |  | checklist | 0008 Underground Submains |  |  |  |  | Yes | 0008 Underground Submains V2 | 31f1ab5c-327c-473e-850a-b848ea4fb120
checkpoint-group | 8a3f1f1b-840b-4142-9dca-5606f3e62668 |  | section | Preliminary Inspections and Tests
checkpoint-status | 86efd4e4-7c19-4c72-a328-2b61addbb5f4 |  | checkpoint | RDM & Consent Approval
holdpoint | d1b28eef-41c9-4df5-87e8-0e35abf34787 |  | signoff | Nominated Authority Sign off
checkpoint-status | 78a032ae-cdbd-433d-91c5-84867b918779 |  | checkpoint | Define LOT Area
checkpoint-status | 202b3cad-7f72-48da-884a-481a6b0f035e |  | checkpoint | Understanding of the Scope of works
checkpoint-status | ad37007d-2aa9-4baf-8ebd-4173343dd9f2 |  | checkpoint | Trench Inspection
checkpoint-status | 4ae4c2d8-644f-4c42-8118-f2c4f5154447 |  | checkpoint | Drum Delivery Test Certificate
holdpoint | 69e5c608-f31b-4481-84ad-f3835522e76f |  | signoff | Nominated Authority Sign off
checkpoint-status | e9ad0147-710f-4d5b-a1de-2fb4ddc0a7e0 |  | checkpoint | Site inspection and SWMS
checkpoint-group | a660efb8-bea1-4fc8-9924-f2eebb224704 |  | section | Underground Submains
checkpoint-status | b1c407b2-dda0-49f9-8381-ca81d0dbe676 |  | checkpoint | Pre-start meeting
checkpoint-status | 607d7273-454d-4efb-b255-879361695518 |  | checkpoint | Drawings referenced in Reference Documentation
checkpoint-status | 03cf7c3e-13b2-4daa-bd27-8cca74d87866 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | 680ba68a-02f6-447d-93b7-4b16514c7dad |  | checkpoint | Installed to AS/NZS 3000:2007 and AS/NZS 3008:2007.
checkpoint-status | 261eeaf3-14b6-489e-9b9e-8bcf5d52e854 |  | checkpoint | CCT labelling completed.
checkpoint-status | 7c1f4017-d52a-4041-93d4-553333680fd9 |  | checkpoint | McKay I&T 19 A, and 19D Inspection and Test forms completed.
checkpoint-status | 8e51a08b-efbe-404b-ab63-6abf6647b67b |  | checkpoint | Seismic Loops installed as required.
checkpoint-status | c33a5b2d-4a58-4aa5-b4c8-215a61bb769b |  | checkpoint | All AS/NZS 3000:2007 tests sheets completed.
holdpoint | b33821c2-0844-413f-9d57-d127e0ff2c06 |  | signoff | Nominated Authority Sign off
checkpoint-status | 59374932-7ba7-429e-b18a-4b0114a48898 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 1efcb7c9-a9a5-491f-9499-3ad75cf81bd2 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 771e356e-4364-46c9-adf1-644d155a1422 |  | section | Completion Inspections and Tests
checkpoint-status | 0374e745-e21b-4b73-9f58-6ac542b91d3f |  | checkpoint | Inspection by supervisor
checkpoint-status | 67f0300c-b336-4858-9091-17abea93af7c |  | checkpoint | Notice of Completion
holdpoint | 26f32517-2164-4760-b624-1c7ead7b2253 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 8b1ee5e7-0dc0-4049-92a6-b02bdca07d3e |  | checklist | 0011 GPO/Electrical Equipment |  |  |  |  | Yes | 0011 GPO/Electrical Equipment | 43ac1fbe-02f8-4742-a26a-3be1b73764ae
checkpoint-group | e5e4d211-690a-4946-9b4d-84d3b81fd198 |  | section | Preliminary Inspections and Tests
checkpoint-status | c2a6b007-cd26-4bbf-94f9-25970676eba7 |  | checkpoint | RDM & Consent Approval
holdpoint | 7f67f5d8-1b50-4b27-9b10-3fee4b68dc87 |  | signoff | Nominated Authority Sign off
checkpoint-status | 47721ee1-6d57-4286-91dc-40e814555767 |  | checkpoint | Define LOT Area
checkpoint-status | 896dc0df-d4c7-4898-b979-13f2ffadc826 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 757ce2ac-661c-4581-925e-374e4bb88ba6 |  | checkpoint | Ensure materials available
checkpoint-status | c739262a-e7e2-4863-ad25-2836bceb8dba |  | checkpoint | Site inspection and SWMS
checkpoint-group | dd815f87-5515-47e4-a82c-1eee919f9e3e |  | section | GPO & Electrical Install
checkpoint-status | f4f4f7d0-1fd0-44b9-a2ee-44b31214e23e |  | checkpoint | Pre-start meeting
checkpoint-status | 4d252f2d-faec-4b35-ac9e-601462c37c98 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 7b764189-0fab-4b29-b5ba-78b6ddea605b |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | 4c86c0d7-804f-4076-811f-a36effba9fa7 |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | 9235cef5-cfd4-471f-9ed2-841c3bf7fc2c |  | checkpoint | QA Electrical Equipment Check Sheet Completed as needed.
checkpoint-status | 0430aeb7-feab-40cf-bf51-878eabe2e805 |  | checkpoint | All test sheets completed as per AS/NZS 3000:2007 as required.
checkpoint-status | c62b37b9-9028-4b9f-8411-b025d9eede9d |  | checkpoint | All refuse removed from work area.
checkpoint-status | b76c7364-4a4b-49d1-9791-33b305eeb501 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | f9001195-0200-4baf-90fc-28a0d4b85f2a |  | section | Completion Inspections and Tests
checkpoint-status | 77db140a-56e8-405c-af73-266edfde6c60 |  | checkpoint | Inspection by supervisor
checkpoint-status | 34d34ae7-67dd-46fa-9fc4-f03aea075e40 |  | checkpoint | Notice of Completion
holdpoint | 3104aa27-6ad6-4c4d-85d1-941cf1efe319 |  | signoff | Nominated Authority Sign off
checklist-sectioned | c8911bed-2e10-454d-8ade-a2f50a77e2d5 |  | checklist | 0009 Cables and Conduit Underground |  |  |  |  | Yes | 0009 Cables and Conduit Underground | 46e4cd90-936a-4a56-95c5-2e9749de6746
checkpoint-group | 03e7709c-25b4-4ee4-9f77-a08eb28d156b |  | section | Preliminary Inspections and Tests
checkpoint-status | b5fb0c60-e9d7-441a-a433-1fc1d6507709 |  | checkpoint | RDM & Consent Approval
holdpoint | d0612a07-42a2-4adf-97ab-70d53281f912 |  | signoff | Nominated Authority Sign off
checkpoint-status | 471f66dc-cefc-4238-ae5c-51035ce61e00 |  | checkpoint | Define LOT Area
checkpoint-status | 5dc6e35d-4579-4ca6-a050-9377daf99bdf |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 8f45468c-3c79-4867-8ba2-ac9000c8dd68 |  | checkpoint | Ensure materials available
checkpoint-status | e2446ff4-cd5b-4313-a95e-e6610d0ac760 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 4e7b933a-2a40-495b-822a-63742ce71672 |  | section | Conduit & Cable Works
checkpoint-status | 8bd28aca-1b1e-49ff-8bf8-7205b3d27d12 |  | checkpoint | Pre-start meeting
checkpoint-status | 4fcfcb4b-996b-43cf-b701-fb6dc461e6aa |  | checkpoint | Ensure HD conduits are used
checkpoint-status | 4b1349d8-f1e8-4310-8a7a-fddecbf61029 |  | checkpoint | Each length of duct is to be fully inserted into the next and glued
checkpoint-status | f18315f8-7d4e-4a26-8571-34c097d2550d |  | checkpoint | Ensure separation of Low Voltage cables from Telecommunication cables is as AS/NZ 3000 2007
checkpoint-status | 11a1761b-ca97-45ad-bd25-fa7575d72dcc |  | checkpoint | Entry and exit of ducts are at the correct location as per set out
checkpoint-status | 17242a0d-9a86-4c51-834b-57f270aac5b6 |  | checkpoint | Conduits to be finished to allow further works to continue.
checkpoint-status | de924f34-737c-46c4-a662-2e1bde0b694d |  | checkpoint | Push snake through fully completed duct install and pull through draw wire (string)
checkpoint-status | 71921311-c4af-4276-bd96-18772ad5b448 |  | checkpoint | Seal off open ends of ducts with tape
checkpoint-status | f928561d-e8ce-460a-9674-ae1254939d7a |  | checkpoint | Photos to be taken of critical elements above as evidence of QA
checkpoint-group | ef4f1b8f-fd35-4589-a084-822f2ae87630 |  | section | Completion Inspections and Tests
checkpoint-status | 97ae88ce-7fa7-4bb2-b5bb-194d246bca00 |  | checkpoint | Inspection by supervisor
checkpoint-status | f7b99e2b-7472-42c9-b58f-3caa1a4c78e0 |  | checkpoint | Notice of Completion
holdpoint | 05898d27-3bbe-4903-9a9e-8ca3a5625d80 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 585cb687-44ae-477b-85cd-c929edc7b665 |  | checklist | 0003 Containment |  |  |  |  | Yes | 0003 Containment (V4.2) | 5865c30e-67ee-4224-9ace-e89df108cc02
checkpoint-group | 19342d71-7cd2-4b92-96f9-8b8c2627ea7d |  | section | Containment
checkpoint-status | 3923872d-832e-4067-a5ce-24425f26e29c |  | checkpoint | Drawings referenced. (3)
checkpoint-status | 1bc929c3-b388-46f8-8478-01e4fc8759cf |  | checkpoint | Define LOT Area. (2)
checkpoint-status | b33f867b-8380-4720-8418-f56b09a1e7e4 |  | checkpoint | Ensure cable ladders and trays are provided to support cable. (6)
checkpoint-status | 0b7eec3d-9a4a-487a-9f29-201da09a7921 |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity. (50% spare capacity as per original design.) (6)
checkpoint-status | 64f21cfa-beaf-46e6-9d4f-c6f114d57f58 |  | checkpoint | Ensure cable ladder and tray is installed to manufacturer’s instructions, complete with all necessary splice plates, bends, and fixings. (6)
checkpoint-status | 04292fd4-ae7e-46d9-ab9b-6e8d8dfc1310 |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable. (as at time of install.) (6)
checkpoint-status | 6bf38176-5e31-4a98-acab-eba56462a34d |  | checkpoint | Ensure seismic supports and bracing installed according to KCL design.) (7)
checkpoint-status | 13035bf5-dac2-40a8-ab6f-dcbeb400e6b5 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA. (6)
checkpoint-group | 1eff88ca-eb7d-46ce-a10a-d4d3afa5cf04 |  | section | Completion Inspections and Tests
checkpoint-status | b32e14da-245b-4805-8efb-87553d3e2762 |  | checkpoint | Notice of Completion. (9)
holdpoint | b53030b2-4e5e-4477-bc0e-79f0e4512b0b |  | signoff | Nominated Authority Sign off
checklist-sectioned | 70ecc46e-9ffa-4629-9722-eec077f26e45 |  | checklist | 0002 Cable Installation |  |  |  |  | Yes | 0002 Cable Installation | 5fdb80f3-972b-482d-b511-3c68045f9f9e
checkpoint-group | a46375af-101b-4fee-a816-33e32874875d |  | section | Preliminary Inspections and Tests
checkpoint-status | 26f0e257-ec09-4e0d-9fce-92ce4652bb21 |  | checkpoint | RDM & Consent Approval
holdpoint | de50b9e8-372b-428a-97f3-72b0df0b2273 |  | signoff | Nominated Authority Sign off
checkpoint-status | 6784e15f-52b3-4e7b-8901-a8c437f637dc |  | checkpoint | Define LOT Area
checkpoint-status | 4fc3690e-8d37-44d0-931b-a3ee6605bc8a |  | checkpoint | Understanding of the Scope of works
checkpoint-status | a2bca548-9e11-4f21-99d2-62b523a27143 |  | checkpoint | McKay SHD proposed cable route
checkpoint-status | 3ee90554-9bec-4b41-b1b1-1915efd30082 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 8fa70af6-819e-4056-909e-9bfad9d090dc |  | section | Cable Installation
checkpoint-status | b394d08b-efb6-4741-9e52-ffad77990eb2 |  | checkpoint | Pre-start meeting
checkpoint-status | 8efbb5c2-d2a4-48e5-b5d4-09b16c4a2534 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 4a68bc87-5498-4b7d-9a85-fc70f5cdd81f |  | checkpoint | Provide logical cable management and reticulation system coordinated with other trades.
checkpoint-status | a837a3d7-f195-47af-96e1-f7be5a544515 |  | checkpoint | All cable routes rationalised where possible.
checkpoint-status | 9ea8bfd1-442d-45b9-b3cc-3d405710bd83 |  | checkpoint | Maintain Minimum Separation Distances
checkpoint-status | 8e96e57c-4e1a-4cf9-a8b5-d6e6d99b69aa |  | checkpoint | All wiring systems adequately protected.
checkpoint-status | cb8f8be9-ceb5-40ba-8d63-1dce428c6e5e |  | checkpoint | All cables and supports concealed.
checkpoint-status | 78d44ad1-7dad-430f-89af-1f70fd6508b2 |  | checkpoint | Cables installed as per manufacturer's instructions.
checkpoint-status | 463dccd0-889b-4bee-9c95-a2267ca689e6 |  | checkpoint | Complete �dead� testing, As per �McKay Form 19A and 19D - Cable Inspection and Test�
checkpoint-status | cc9d690f-bbc0-4b45-830e-4d06aa9d18c0 |  | checkpoint | Complete �dead� testing as per �McKay Form 19A/19D/19B - Cable Inspection and Test�.
checkpoint-status | 9010488a-5066-4be6-9faf-51c1a73a1dd2 |  | checkpoint | Insert as Required: McKay I&T Form 24: Earthing and Resistance Test.
checkpoint-status | d1711040-cd1c-4858-a89b-1677a0ea85f8 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 936f56b3-7c1f-4599-a9fd-8b2a177629f5 |  | section | Completion Inspections and Tests
checkpoint-status | 3c5ca132-5660-4dbf-8cd9-1ff425cdc14b |  | checkpoint | Inspection by supervisor
checkpoint-status | 2d5c7ab5-99a5-413a-b99d-6046643938ac |  | checkpoint | Dead Testing
checkpoint-status | fad4ed3b-f6c7-42af-a470-2f65336d4511 |  | checkpoint | Notice of Completion
holdpoint | 09e22a95-6df8-4200-b02e-bf541f043fef |  | signoff | Nominated Authority Sign off
checklist-sectioned | 30da7a31-b19e-4630-b627-4fa79d4d3365 |  | checklist | 0002 Cable Installation |  |  |  |  | Yes | 0002 Cable Installation (V3.1) | 704efd8d-80cc-4063-959e-4b8966ff98eb
checkpoint-group | 75c0a5a5-a7b2-4117-9eaf-2874a2577a79 |  | section | Cable Installation
checkpoint-status | 066e46ea-2534-4dc9-bb34-8cdb2ff4ffff |  | checkpoint | Drawings referenced. (3)
checkpoint-status | 75a8e19a-c14c-417a-bc53-a71f5d0adbcd |  | checkpoint | The LOT is not defined by an area/zone, it is defined by the cables listed in the Summary Report. (2)
checkpoint-status | 7a5d3467-3e37-4634-8253-22eb73b02334 |  | checkpoint | Provide logical cable management and reticulation system coordinated with other trades. (6)
checkpoint-status | dc675be1-0345-4601-a520-59e6ff97c947 |  | checkpoint | All cable routes rationalised where possible. (6)
checkpoint-status | 31b42514-37c0-4b83-b588-6d2e3f79787e |  | checkpoint | Maintain Minimum Separation Distances as per 22.2.3. (6)
checkpoint-status | db18d5ef-8fda-414e-9c25-dc59932a476e |  | checkpoint | Catenary Installed. 6 cables/cat wire max. No excessive sag. Cable tied regularly. (6)
checkpoint-status | 60bd696c-3539-4af4-9c29-9d1257ee5c69 |  | checkpoint | Conduit installed. 22.5.2-fix conduit saddles at a maximum of 1m intervals in horizontal runs and 2m intervals in vertical runs. (6)
checkpoint-status | 4c8fa3dd-4ebf-4be3-aff9-26e35852e967 |  | checkpoint | Containment. 22.2.8-Fixing with nylon ties to slab or roof structure at max intervals of 1500mm. (6)
checkpoint-status | 4aaac39e-eae9-4d10-a24f-dadb7c4e5613 |  | checkpoint | All wiring systems adequately protected as per 22.2.4 (6)
checkpoint-status | 307778f8-621a-4517-baea-01db54fa822a |  | checkpoint | All cables and supports concealed as per 22.2.6 (6)
checkpoint-status | 99b784f5-2cee-4030-8a46-e3670b2d804a |  | checkpoint | Cables installed as per manufacturer’s instructions. (6)
checkpoint-status | 9f2532d5-b61b-41c8-ad87-c35531a4d61b |  | checkpoint | As required: Acoustic sealing completed for the cables included in the ITP. (6)
checkpoint-status | 96e77b73-1e25-40e5-a4e9-c313853e3589 |  | checkpoint | Written approval obtained where cables/conduits must be run surface mounted as per 22.2.7 & 22.6.1. (6)
checkpoint-status | cf6cfcee-bbe0-4858-8d36-cd16cca1f3a4 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA. (6)
checkpoint-group | 3e811288-36c6-43db-833f-bf546f40770f |  | section | Completion Inspections and Tests
checkpoint-status | a1e0c054-98dc-438f-9436-70041ec34eae |  | checkpoint | Notice of Completion (8)
holdpoint | d38c5410-babb-47bd-938b-5bc04b4e5e94 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 52475c25-93b6-40be-9a42-906c31d3d3f1 |  | checklist | 0012 Street Pole Foundation and Erection |  |  |  |  | Yes | 0012 Street Pole Foundation and Erection | 75c9c974-5fa6-40b0-bc09-82a7fbc9eee3
checkpoint-group | 4a4408b2-97a5-4b7d-aac8-ebba0d5cc4ed |  | section | Preliminary Inspections and Tests
checkpoint-status | e8a38908-0c15-4821-80aa-01806bd8f1eb |  | checkpoint | RDM & Consent Approval
holdpoint | 52694d30-115f-43c1-916e-2dd79b991bdb |  | signoff | Nominated Authority Sign off
checkpoint-status | 4f40fc66-18eb-4e8f-ae5b-9cea69218d19 |  | checkpoint | Define LOT Area
checkpoint-status | 948845cd-620b-4757-88c2-5400d412d56d |  | checkpoint | Understanding of the Scope of works
checkpoint-status | cbaf833e-e4f6-43aa-acdf-32a2e29d89a9 |  | checkpoint | Ensure materials available
checkpoint-status | 896f9801-360f-4ab3-a8d7-a0cae9a52686 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 8cece0cf-94ee-4b94-b46c-ef08b788df56 |  | section | Street Light Foundation & Erection
checkpoint-status | e7f88983-e0cd-4e9d-8a93-b867f28a4e92 |  | checkpoint | Pre-start meeting
checkpoint-status | 0cecbe81-70f7-400c-8d9a-08c05927e79f |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 57190c4f-1c62-48ed-bad4-f6923a35223f |  | checkpoint | Layout and location drawing confirmed as current and accurate
checkpoint-status | f77e4a5c-ee8c-47d7-a41a-0e7527d26030 |  | checkpoint | Excavation Completed and Checked (Photos to be taken)
checkpoint-status | 4c074b90-822b-4b35-b414-2e96dbd65cf6 |  | checkpoint | Foundation Installed and Checked (Photos to be taken)
checkpoint-status | 1b9985d0-fb60-4f5d-9184-6629072c6180 |  | checkpoint | Pole Installation and equipment (Luminaire, Fusing and Earthing) as per AS/NZS 3000:2007.
checkpoint-status | b9a53c37-94c9-4b04-aefe-13cb96f040ad |  | checkpoint | Grouting completed within 7 days of installing the pole as per Specification references 26.
checkpoint-status | eb496257-d21f-4abc-b6fc-e6a4a6f6e00b |  | checkpoint | All test sheets completed as per AS/NZS 3000:2007.
checkpoint-status | 2ef2a172-a8ce-4323-a01c-ac601804d1db |  | checkpoint | All refuse removed from work area.
checkpoint-status | 29e63ad5-62ab-4015-90ee-e6416a3c347e |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 6b503c39-8c25-47a5-b770-6b9ee41927b9 |  | section | Completion Inspections and Tests
checkpoint-status | c42ae7fb-9e2d-4fbe-bed6-403ddc24a15a |  | checkpoint | Inspection by supervisor
checkpoint-status | 726a039c-4ec4-47c5-a4bb-015e3a3c28fa |  | checkpoint | Notice of Completion
holdpoint | 2692dde8-3251-47aa-ba9a-6462b0f9648f |  | signoff | Nominated Authority Sign off
checklist-sectioned | f5d1d466-5c21-4850-8b1d-6bac760e6755 |  | checklist | 0003 Containment |  |  |  |  | Yes | 0003 Containment (V1) | 812c9609-fc3f-4905-8b25-f5d0ac4eed36
checkpoint-group | 3a3f5a7b-2b03-43fd-9963-1fd2265274dd |  | section | Preliminary Inspections and Tests
checkpoint-status | 9923794f-2c74-47f4-a438-ec963a542fc9 |  | checkpoint | RDM & Consent Approval
holdpoint | 41886f0f-6651-4d05-8761-4b9419c5620e |  | signoff | Nominated Authority Sign off
checkpoint-status | 2f2f7e7d-2d26-40cc-b5fb-fc4218e11da6 |  | checkpoint | Define LOT Area
checkpoint-status | 106e5980-5f4a-444b-954b-d3743fa6caf0 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 0320a901-dcbf-40a8-8980-0f55d47af0b2 |  | checkpoint | Draw up proposed route of Cable Containment
checkpoint-status | f81a3584-1d50-4327-a566-85563ad01d18 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 905d2017-9ffc-4308-acac-112916aceb5e |  | section | Containment
checkpoint-status | abff0ba9-d7b5-43f0-8dda-3098bc462e5f |  | checkpoint | Ensure reference Drawings are listed in Reference Documentation.
checkpoint-status | 41bc58f6-e344-4c9f-b394-5504c4a45dc2 |  | checkpoint | Ensure cable ladders and trays are provided to support cable runs (where necessary).
checkpoint-status | f9a226ae-b268-4621-9546-124cc96c4b4b |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity.
checkpoint-status | c9da8a62-2d58-48d1-9d87-37b76f350e13 |  | checkpoint | Ensure cable ladder and tray is installed as manufacturer's instructions, complete with all necessary splice plates, bends and fixings.
checkpoint-status | 33b6b847-547b-46bf-90f4-3ea84ab8e163 |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable.
checkpoint-status | 69c55ad5-0c9f-400b-9f36-7ea728bd1324 |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009.
checkpoint-status | 2ee533c5-f736-410a-a795-6afb425e05e2 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 57dec178-8a76-4787-b4f9-00c637ef6545 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 7aa267c2-25f2-44a8-b853-77b058e35c8a |  | section | Completion Inspections and Tests
checkpoint-status | 3732299a-9e5d-440f-a130-4839a8261e49 |  | checkpoint | Inspection by supervisor
checkpoint-status | 7d9c5654-005d-4c56-b5bc-e4586a8b0824 |  | checkpoint | Seismic Bracing
holdpoint | 8f0dfa39-3dc4-43f1-84aa-5fb70423b7d2 |  | signoff | Nominated Authority Sign off
checkpoint-status | 74843da8-0a7c-404d-85b3-16d36eaed806 |  | checkpoint | Notice of Completion
holdpoint | f08509f0-5bf5-4954-8fba-be1f8fcc5fc3 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 57eda14e-a678-4c7b-891f-109f7d623919 |  | checklist | Test Training |  |  |  |  | Yes | Test Training | 8ea145b8-372a-48d8-a2b5-0914f761d231
checkpoint-group | 48485d2a-2d88-4b21-83a4-7b21797f03b0 |  | section | Preliminary Inspections and Tests
checkpoint-status | 0cbe9a6c-4f4d-48f6-8af8-04c1f510c2e6 |  | checkpoint | RDM & Consent Approval
holdpoint | d7b438ae-865b-4a9d-a80d-ef9e1fb35f3f |  | signoff | Nominated Authority Sign off
checkpoint-status | 23678401-3e0a-43bc-8009-7630ec4ef888 |  | checkpoint | Define LOT Area
checkpoint-status | b4480fa1-8104-4973-8a97-d4e291161994 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | f7865e5c-c8ba-42b3-b4d1-ba3f579c9ce6 |  | checkpoint | Draw up proposed route of Cable Containment
checkpoint-status | 0a6046eb-71cf-4a8b-8510-c58438d96fc1 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 71650ec2-d153-4e8e-ab8d-efbb1f55eb7f |  | section | Containment
checkpoint-status | 0016b197-0f62-4710-8c26-0439088ae9ea |  | checkpoint | Ensure reference Drawings are listed in Reference Documentation.
checkpoint-status | 8bf18ddb-5b9b-4237-aab7-90c0a8ed4a70 |  | checkpoint | Ensure cable ladders and trays are provided to support cable runs (where necessary).
checkpoint-status | fbbcfc49-dcb1-4f4b-aedb-1cabfeb186e8 |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity.
checkpoint-status | 523d9c29-cd5d-4cdc-b7cd-5c269c63f275 |  | checkpoint | Ensure cable ladder and tray is installed as manufacturer's instructions, complete with all necessary splice plates, bends and fixings.
checkpoint-status | 9d402841-581d-4a5d-8e4d-ab8973d601b4 |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable.
checkpoint-status | 8c1cb552-b7b7-44ab-8d96-e9f5afde6dbb |  | checkpoint | All refuse removed from work area.
checkpoint-status | 3ffa5058-5017-437f-a3d5-a445f5d8f190 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | cb6adc21-c2f5-4a8d-850e-4283d2056fe7 |  | section | Completion Inspections and Tests
checkpoint-status | 366912b1-0b24-4f6b-aad9-43f8793f0c54 |  | checkpoint | Inspection by supervisor
checkpoint-status | fe88c675-e6fa-4965-9ddf-cacb67d4318e |  | checkpoint | Seismic Bracing
holdpoint | df1ca132-2410-4ad1-af7f-6a24ee86db5b |  | signoff | Nominated Authority Sign off
checkpoint-status | bbfab5df-fd03-471c-9ac5-f4a7956e8e2f |  | checkpoint | Notice of Completion
holdpoint | aefac292-178d-4c9b-8b65-4cf1e11c4034 |  | signoff | Nominated Authority Sign off
checklist-sectioned | a485cb20-e236-4472-ab1a-1578d971d0f0 |  | checklist | 0004 Lighting Install |  |  |  |  | Yes | 0004 Lighting Install (V3) | 9009d25f-ed0c-4506-9219-95c341635e60
checkpoint-group | 913800e7-a395-40e1-93c4-a11c274eb2b1 |  | section | Preliminary Inspections and Tests
checkpoint-status | 37ef562d-a4fb-40ce-ae28-3003f31877ce |  | checkpoint | RDM & Consent Approval
holdpoint | f0a51ede-3ea4-46f3-a978-4f3b61a82ba9 |  | signoff | Nominated Authority Sign off
checkpoint-status | f50da074-c0fe-44bd-bdda-2201a8429173 |  | checkpoint | Define LOT Area
checkpoint-status | 35790696-9e4d-4f5d-bea6-8673deab2509 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 978631bc-3c76-4fe3-89dc-8920f9b2b2ea |  | checkpoint | McKay SHD proposed Lighting Layout
checkpoint-status | bc2a88a2-9b9f-410d-98f3-79ac56839a9b |  | checkpoint | Site inspection and SWMS
checkpoint-group | 459bf40f-7ebc-47bd-af43-2fe744cc66e8 |  | section | Lighting Install
checkpoint-status | 88fd8571-7582-4a7c-a55e-aa7e1849481f |  | checkpoint | Pre-start meeting
checkpoint-status | a993afd6-6c3c-46be-baf9-8283555bd86b |  | checkpoint | Site Inspection and JRA.
checkpoint-status | 8315cc4e-0874-4f07-8d70-85933669faac |  | checkpoint | Drawings referenced in Reference Documentation
checkpoint-status | ba6a9fb3-5a2f-4251-b52d-0a8816a6130f |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | 3e8bf7c8-96a1-4774-a763-8fd761458f2a |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | 9b52aa8b-45a3-4d5e-afd4-01dd404b2317 |  | checkpoint | Seismic Restraints installed as required.
checkpoint-status | e2b9d02c-a191-47f3-ae9c-2848fbc3bcf5 |  | checkpoint | As required: McKay I&T Form 17 or 17A– Lighting/Street Lighting Installation Inspection completed.
checkpoint-status | a82946bd-70ce-47ae-844d-ec76c72488da |  | checkpoint | As required: Test sheets completed as per AS/NZS 3000:2007.
checkpoint-status | d6d2e0e0-a8f3-4f30-be4e-b7feaebc57e0 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 4186a01c-9b0f-4eda-b42d-93afd46beb7d |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | f11a9bd5-64ed-4fb2-ba2a-850d634c651d |  | section | Completion Inspections and Tests
checkpoint-status | 3ea0d9a0-8112-4a5c-a1bc-d2d12a68fb01 |  | checkpoint | Inspection by supervisor
checkpoint-status | 8f6dcf9d-5086-44a1-a918-dc103cb44e51 |  | checkpoint | Notice of Completion
holdpoint | 93aee765-f5c2-4f5b-908f-70f0cc62526a |  | signoff | Nominated Authority Sign off
checklist-sectioned | a0ac81b2-d14c-4e12-8da4-9a7b613f0968 |  | checklist | 0001 In Slab Conduit |  |  |  |  | Yes | 0001 In Slab Conduit (V3) | 9f2da48c-8488-4307-a0a5-98901b8fcfd3
checkpoint-group | 5ef9bf66-0ef2-4187-9b8c-0f7f5992acfb |  | section | Preliminary Inspections and Tests
checkpoint-status | 294848ac-2c93-452a-8d8e-01cb1f8a3257 |  | checkpoint | RDM & Consent Approval
holdpoint | 102988fc-50d4-4b28-b764-079c25e2867f |  | signoff | Nominated Authority Sign off
checkpoint-status | 1e498803-f777-401f-a87d-93cffc042201 |  | checkpoint | Define LOT Area
checkpoint-status | 74a8efbc-462d-4749-9a6e-ebc13771d7a3 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 490d7e12-99bf-4486-b29e-98ee47da4e50 |  | checkpoint | Draw up proposed route of conduit
checkpoint-status | 294aab5d-a8f0-4f49-a3df-e6e9378abc0b |  | checkpoint | Site inspection and SWMS
checkpoint-group | ca6eceb2-f98c-4b94-84cc-e3f0a0832945 |  | section | In Slab Conduit Install
checkpoint-status | 9f748cea-5434-4fc8-ba41-29e8d5d48086 |  | checkpoint | Pre-start meeting
checkpoint-status | 4423853e-cf0a-4aed-a4de-ef1c4ec403e1 |  | checkpoint | Site Inspection and JRA.
checkpoint-status | e85f9785-16bc-49f7-a275-31754da28187 |  | checkpoint | Ensure at least 50mm thick continuous poured concrete above conduit (ASNZS 3000:2007)
checkpoint-status | c67f8e28-1be5-497a-9ac5-93b085cb408e |  | checkpoint | Each length of duct is to be fully inserted into the next and glued
checkpoint-status | 2bd9223d-5709-47d4-bb36-f6656ec4e0ac |  | checkpoint | Space conduit/duct at a minimum of twice the diameter apart of conduit/duct used horizontally (32mm=64mm Etc)
checkpoint-status | 83d38db4-84fa-4592-b607-3856e60c96eb |  | checkpoint | Entry and exit of ducts are at the correct location as per set out
checkpoint-status | f40e5178-78c3-498a-a3d5-20e23be98bf0 |  | checkpoint | Ensure conduits/ducts are securely fixed and cable tied to the reo bottom mat, in middle not parallel (hard up) to reo.
checkpoint-status | 937234cc-d4cd-414a-8e5a-dfca183e5eca |  | checkpoint | Extend duct to a minimum of 300mm past FFL
checkpoint-status | d7412e84-d538-452b-924b-5dd9e008d543 |  | checkpoint | Push snake through fully completed duct install and pull through draw wire (string)
checkpoint-status | ac7b7a97-f933-488f-9067-dc67b77e387e |  | checkpoint | Seal off open ends of ducts with tape
checkpoint-status | b41a35e6-28ba-4410-b67e-8b13d06d1333 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA
checkpoint-group | 50397535-650c-4355-baa4-ceef469f8c03 |  | section | Completion Inspections and Tests
checkpoint-status | f1f1e7b4-5f97-4e15-9ce2-da32d5dde766 |  | checkpoint | Inspection by supervisor
checkpoint-status | 22c2d8a1-0bcd-4645-afd7-6e2126a3b1ed |  | checkpoint | Notice of Completion
holdpoint | 69d9e2bc-0f7a-48ec-a835-c56b80fedf04 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 07ee10a2-5484-426a-932d-48bdbbc17063 |  | checklist | 0009 Cables and Conduit Underground (V2) |  |  |  |  | Yes | 0009 Cables and Conduit Underground | a0c315e8-a9fb-4a4a-b8a5-6dddfcb54018
checkpoint-group | a798ea2d-8932-4c0a-8e84-85b408732697 |  | section | Preliminary Inspections and Tests
checkpoint-status | 9c6125c3-34f8-44ec-9bd8-53bbbadf6c38 |  | checkpoint | RDM & Consent Approval
holdpoint | d7b88643-81b2-4d11-a14d-83e37519131c |  | signoff | Nominated Authority Sign off
checkpoint-status | b97d6788-31ca-4355-89ba-9aa1f6fc6331 |  | checkpoint | Define LOT Area
checkpoint-status | 676b9552-060e-4628-80c7-dfcbf165ec74 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 25d30646-65ff-4143-8e78-fa9d64750314 |  | checkpoint | Ensure materials available
checkpoint-status | 3bb49a59-d61c-4611-8427-6a8ec31b7b5a |  | checkpoint | Site inspection and SWMS
checkpoint-group | a6f01adb-d43f-4c71-924d-b0ff99016c36 |  | section | Conduit & Cable Works
checkpoint-status | cfdf60fd-34d3-4e4c-975c-7b484a61f2ca |  | checkpoint | Pre-start meeting
checkpoint-status | d9e0ff5a-344e-4f7f-8288-8c5d22117df6 |  | checkpoint | Site Inspection, JRA .
checkpoint-status | c76a8aaf-2b65-4469-be96-c271b695e30d |  | checkpoint | Ensure HD conduits are used
checkpoint-status | db5bb278-7536-4ed7-98c4-67fffe1b409b |  | checkpoint | Each length of duct is to be fully inserted into the next and glued
checkpoint-status | 1258fb54-133b-444b-8838-a358a40b8be2 |  | checkpoint | Ensure separation of Low Voltage cables from Telecommunication cables is as AS/NZ 3000 2007
checkpoint-status | c4346834-5150-470e-a63f-e2831e1d910c |  | checkpoint | Entry and exit of ducts are at the correct location as per set out
checkpoint-status | 67de3896-1425-40ba-a9ac-ff7b15e8aba6 |  | checkpoint | Conduits installed
checkpoint-status | c65fc3fa-02bd-4d32-b709-d38c42a53e70 |  | checkpoint | Cable installed
checkpoint-status | 71f10e17-a4e7-4136-bc8f-8c5cdbf129a9 |  | checkpoint | Push snake through fully completed duct install and pull through draw wire (string)
checkpoint-status | c0316206-1592-4bb9-a573-25baa60d397d |  | checkpoint | Seal off open ends of ducts with tape
checkpoint-status | e69cd797-7376-4337-8f47-0a180f5c0b2e |  | checkpoint | Photos to be taken of critical elements above as evidence of QA
checkpoint-group | 556e73a1-6e7f-4fb4-b694-13c19e6ff25c |  | section | Completion Inspections and Tests
checkpoint-status | 6363b694-0769-40b6-9fd6-9c09d9a5b04a |  | checkpoint | Inspection by supervisor
checkpoint-status | 65372bfe-fc32-41eb-9068-3ae1cb81d1d5 |  | checkpoint | Notice of Completion
holdpoint | 227bc081-36c0-4429-ab9c-760ba44ba5b2 |  | signoff | Nominated Authority Sign off
checklist-sectioned | cc1f0cf6-f293-4911-a271-c373efa54d40 |  | checklist | 0007 Switchboards |  |  |  |  | Yes | 0007 Switchboards (V2) | a1ca54e5-57b9-4c4e-8a4b-a43d6436b56e
checkpoint-group | 7bbdf459-d739-4b5d-8489-582bb6a026a9 |  | section | Preliminary Inspections and Tests
checkpoint-status | e161e3c2-ea98-4d81-bc59-d36aa513a032 |  | checkpoint | RDM & Consent Approval
holdpoint | 73b7e97a-2238-4bbf-a0ed-9bc0571a9e3b |  | signoff | Nominated Authority Sign off
checkpoint-status | 9b5c7019-080f-4119-9783-3ef30e722523 |  | checkpoint | Define LOT Area
checkpoint-status | abe0033f-f4a5-425e-a959-3aa817743edc |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 15fafdd6-69ef-43b4-89a9-deae0711800c |  | checkpoint | Confirm Position
checkpoint-status | 3996bb63-04dd-48a5-b8bd-366b72cf6762 |  | checkpoint | Site inspection and SWMS
checkpoint-group | 529599f5-5c72-45c9-91fa-ba31b9691ff1 |  | section | Switchboard Installation
checkpoint-status | a775104c-4d4b-474f-aeb7-285ba601b0d6 |  | checkpoint | FAT.
checkpoint-status | 9a9c1961-fd05-4a4b-8237-b09a25ca34de |  | checkpoint | Arrived and checked.
checkpoint-status | 3d811f74-542c-42a1-bb14-9d84ded8dfd9 |  | checkpoint | Pre-start meeting
checkpoint-status | 79b6ff14-b789-467c-820c-6189ee99d22e |  | checkpoint | Site Inspection, JRA .
checkpoint-status | 93114088-1f9c-4cee-9e20-3caa02f66c33 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | cd6b42bc-688a-4858-8eee-d2b003df1e07 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | efdc3469-2c28-4357-ba2b-100fe3307447 |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | 75f2883f-599c-4190-9926-97c147cf7e8a |  | checkpoint | Terminations checked.
checkpoint-status | 8bbd78cc-48fc-469e-bd0b-4b4c0a89a299 |  | checkpoint | CTT labelling completed.
checkpoint-status | dc3d8dd3-09f9-45c4-bf7a-4358c3f1adda |  | checkpoint | All Cable glands compressed.
checkpoint-status | 188d2aa8-802e-4fc8-b159-4459fec4bf6f |  | checkpoint | Seismic Restraints installed as required
checkpoint-status | 91d941d9-6e95-4a39-aae5-37e6da4665c0 |  | checkpoint | Incoming submain terminated and photographed.
checkpoint-status | 9f7fa06e-8391-40e5-a7ae-396bad3e3bca |  | checkpoint | Complete McKay Test Forms as required: McKay I&T Form 0 - Visual Inspection McKay I&T Form 19A - Single Phase Power Cable: Inspection and Test McKay I&T Form 19B-1 - Local DB Power Cable: Inspection and Test McKay I&T Form 19B-2 - Local DB Power Cable: Inspection and Test - Live McKay I&T Form 19D - 3 Phase Power Cable: Inspection and Test McKay I&T Form 20 - Earthing Resistance Test Sheet
checkpoint-status | 77c6fef9-e83c-4e79-8be4-76165101b2d4 |  | checkpoint | All ASNZS 3000:2007 tests sheets completed.
checkpoint-status | 09546dd0-7837-4f12-b293-98f734c80399 |  | checkpoint | All Refuse removed from work area.
checkpoint-status | c8a14207-54e0-4964-ae89-3c53d309ddbb |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 6657ebe8-6f1e-4182-b782-87952070feb7 |  | section | Completion Inspections and Tests
checkpoint-status | 4a5fc577-7e9d-44c7-9309-d47062e5d716 |  | checkpoint | Inspection by supervisor
checkpoint-status | ff54724f-68ed-4bd1-aa7e-4b0b887c72be |  | checkpoint | Notice of Completion
holdpoint | 9483e170-9d2c-47c0-b88e-6ad5d1f2c4ac |  | signoff | Nominated Authority Sign off
checklist-sectioned | ddc95d59-0951-45f0-a876-6545a646f183 |  | checklist | 0001 In Slab Conduit |  |  |  |  | Yes | 0001 In Slab Conduit V2 | aa51bd67-38a9-4bec-9354-6ee093d6dbde
checkpoint-group | 45341759-84ac-4f3a-8bfd-cbd22021d5db |  | section | Preliminary Inspections and Tests
checkpoint-status | a81c510f-46be-4f85-b531-a6c1b4c039af |  | checkpoint | RDM & Consent Approval
holdpoint | bc32e207-fa92-46c9-9dec-53416a2fdfca |  | signoff | Nominated Authority Sign off
checkpoint-status | 24010288-3709-4353-b243-cc78281ea8ce |  | checkpoint | Define LOT Area
checkpoint-status | 2e246a45-d5da-47ea-9470-dc68dd96bcf8 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | db3e4123-4bb0-420c-8eeb-0f29e3f7e698 |  | checkpoint | Draw up proposed route of conduit
checkpoint-status | 8356a972-479b-433b-b50f-d05086610911 |  | checkpoint | Site inspection and SWMS
checkpoint-group | b1a5cfaa-e07c-471d-bf9f-a2a76b6109a0 |  | section | In Slab Conduit Install
checkpoint-status | 6a04efd9-6063-4682-a3c3-8fe22b756e2a |  | checkpoint | Pre-start meeting
checkpoint-status | ed9368ca-fecf-4006-bc60-735da9810f21 |  | checkpoint | 50mm thick continuous poured concrete above conduit (ASNZS 3000:2007)
checkpoint-status | b15d719d-2f3d-421b-83ce-dd9f4f59d262 |  | checkpoint | Each length of duct is to be fully inserted into the next and glued
checkpoint-status | 352dd04b-544e-455f-90be-510a1f8747ba |  | checkpoint | Space conduit/duct at a minimum of twice the diameter apart of conduit/duct used horizontally (32mm=64mm Etc)
checkpoint-status | d5c0f45e-1c35-4bee-9ebc-b7a2167fef65 |  | checkpoint | Entry and exit of ducts are at the correct location as per set out
checkpoint-status | 677da465-90c4-4034-bba6-91123137b0dc |  | checkpoint | Ensure conduits/ducts are securely fixed and cable tied to the reo bottom mat, in middle not parallel (hard up) to reo.
checkpoint-status | 27a61133-09e4-4869-a2b8-38d0a155556a |  | checkpoint | Extend duct to a minimum of 300mm past FFL
checkpoint-status | 465bdd97-d2c0-44e9-9581-68492cfa02e9 |  | checkpoint | Push snake through fully completed duct install and pull through draw wire (string)
checkpoint-status | c40a7098-917f-4dd0-b3ad-050fad484cc6 |  | checkpoint | Seal off open ends of ducts with tape
checkpoint-status | 3dbb828b-c7ca-418d-a1d0-2adeb317fd1a |  | checkpoint | Photos to be taken of critical elements above as evidence of QA
checkpoint-group | 3ae08250-4e6b-4a94-99b4-fda3b78d488a |  | section | Completion Inspections and Tests
checkpoint-status | 79cee048-4a69-4be6-b25d-36a4d3127cff |  | checkpoint | Inspection by supervisor
checkpoint-status | e9528fb3-01d1-4883-81ee-a1c813a9be67 |  | checkpoint | Notice of Completion
holdpoint | 29b1a18a-957f-43c6-a2fa-b1dce22852a1 |  | signoff | Nominated Authority Sign off
checklist-sectioned | c76a2e7e-816f-4845-b264-e5a98706683d |  | checklist | 0006 Seismic Checklist |  |  |  |  | Yes | 0006 Seismic Checklist (V3) | baaee9c6-e859-4b35-8b16-a53716148d54
checkpoint-group | d8f673cf-0d17-46ef-9ae1-a72d382fb493 |  | section | Preliminary Inspections and Tests
checkpoint-status | 561fe346-3d01-4be5-aab1-3c55ad154f4a |  | checkpoint | RDM & Consent Approval
holdpoint | 4c1b37a6-b408-411d-a9b8-f469d72dad73 |  | signoff | Nominated Authority Sign off
checkpoint-status | c69e4ba6-dc8e-4fbf-bed4-1b7350e1fc9c |  | checkpoint | Define LOT Area
checkpoint-status | ec1e6a87-b224-46a3-aa79-abb97359dca7 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 86f96877-cfe2-4ffb-979a-1f31d9edb52c |  | checkpoint | Site inspection and SWMS
checkpoint-group | 6aec6bd6-61ae-498b-a117-9a0203c1648a |  | section | Seismic
checkpoint-status | b2bf2f66-c022-42d8-b68a-47a33de6c3f2 |  | checkpoint | Pre-start meeting
checkpoint-status | 4a89086b-b953-44b6-804f-f1e23446bedb |  | checkpoint | Site Inspection, JRA .
checkpoint-status | c4de7717-951d-4070-9117-17f8bc9fc677 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | a273149d-fcc9-467b-8dc3-5f1321afc434 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | ad10982e-562c-4875-9fb7-47a5a726c923 |  | checkpoint | Installation as per Referenced Drawings.
checkpoint-status | af2709d1-a328-452f-817c-f4b77b74073b |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009.
checkpoint-status | 21d6bef6-109a-477b-9a4c-5b90e34e9085 |  | checkpoint | Installation on cable trays only if below 400 mm from ceiling.
checkpoint-status | f5d2b80b-c513-49f0-a263-decfd10cc4c4 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | c1617767-2f2f-4272-84d0-0eff21e7bb6e |  | section | Completion Inspections and Tests
checkpoint-status | 90461d4c-330b-41d5-8bcf-f26f4956b516 |  | checkpoint | Inspection by supervisor
checkpoint-status | 5f450d77-29cb-4e98-a781-f5c626acbd2a |  | checkpoint | Notice of Completion
holdpoint | 0328ad76-4f66-4628-acd2-7dde695a7551 |  | signoff | Nominated Authority Sign off
checklist-sectioned | f0514c59-2b88-4739-b8b8-9dc2a2e21cd6 |  | checklist | 0008 Underground Submains |  |  |  |  | Yes | 0008 Underground Submains (V3) | bc8f2f76-d631-491e-aa9d-f8761208c34f
checkpoint-group | 3c01f27a-1114-4e82-9072-85259a17e918 |  | section | Preliminary Inspections and Tests
checkpoint-status | 0b895769-122c-42b3-b868-494c91a8a1ea |  | checkpoint | RDM & Consent Approval
holdpoint | 00260159-8bb0-4270-ba4d-3ad255983b55 |  | signoff | Nominated Authority Sign off
checkpoint-status | 616597d4-2f46-4c4d-8219-74366473c5f5 |  | checkpoint | Define LOT Area
checkpoint-status | 6e6a867b-faa3-44f7-8e51-bb81ade026ec |  | checkpoint | Understanding of the Scope of works
checkpoint-status | bbc9cdac-8c11-45fc-bba6-6c9a57b81ae3 |  | checkpoint | Trench Inspection
checkpoint-status | 6736cdcf-e443-43a1-8632-94438dd98f11 |  | checkpoint | Drum Delivery Test Certificate
holdpoint | c43c72d0-5217-4e2b-bb50-84dde8acb09c |  | signoff | Nominated Authority Sign off
checkpoint-status | 7b1e228f-6bf6-4395-b5ed-9a92408b19f0 |  | checkpoint | Site inspection and SWMS
checkpoint-status | 5cd89973-cbe3-4cef-af70-a4e5f67ca0d3 |  | checkpoint | Trench inspection
checkpoint-status | c58701d4-ead9-4d32-ac56-4693852a7e4e |  | checkpoint | Cables for Route installed in trench
checkpoint-status | 4bd264ac-4a44-4351-bb57-80a35d93902c |  | checkpoint | Install cables into buildings and contain to prevent damage
checkpoint-status | f1d6f193-25b7-4fff-b331-682454483963 |  | checkpoint | MAG Slab installed
checkpoint-status | ceefe5ce-828d-4ade-bc6c-7aec1acb3cbe |  | checkpoint | Test cables installed when installed in trench and building containment
checkpoint-group | bbb2c1bb-2887-478b-a7a9-becd3824fdde |  | section | Underground Submains
checkpoint-status | 2712202c-e4e5-4954-8bcc-d5638d5a8ce4 |  | checkpoint | Pre-start meeting
checkpoint-status | 0face4b8-bce4-4f45-af63-bb6eb5aa7503 |  | checkpoint | Site Inspection, JRA .
checkpoint-status | 3d87bf35-455b-41c0-83d8-d872bd5e66ba |  | checkpoint | Drawings referenced in Reference Documentation
checkpoint-status | 72824c5b-2da6-49b0-87b6-af177ac60395 |  | checkpoint | Drawing and Schedule confirmed as current.
checkpoint-status | 829a8cdf-2b4d-43c7-a7e0-6e9eb41cc501 |  | checkpoint | Installed to AS/NZS 3000:2007 and AS/NZS 3008:2007.
checkpoint-status | d6a087c3-0471-4946-90ef-5790aba3c89c |  | checkpoint | CCT labelling completed.
checkpoint-status | 37380ff3-df66-4809-a959-e4c5d66308b1 |  | checkpoint | McKay I&T Form 19A – Single Phase Power Cable Inspection and Test McKay I&T Form 19B-1 - Local DB Power Cable: Inspection and Test Pre-Livening McKay I&T Form 19D – Three Phase Power Cable Inspection and Test completed as required.
checkpoint-status | b5a57db1-1c5a-4c6b-befc-dee65c36f709 |  | checkpoint | Seismic Loops installed as required.
checkpoint-status | adb1e6ac-6c54-46f4-a5b0-9fe95e24e94f |  | checkpoint | All AS/NZS 3000:2007 tests sheets completed as required.
holdpoint | 4ca482eb-468a-4414-9f1a-b6939940a254 |  | signoff | Nominated Authority Sign off
checkpoint-status | 219496bf-bbbc-482e-9892-3898401de745 |  | checkpoint | All refuse removed from work area.
checkpoint-status | a0d97cf8-29bf-4f5e-9549-2b10141cf78b |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | d78e78b6-b126-4ea5-954a-30f0081e98c6 |  | section | Completion Inspections and Tests
checkpoint-status | 884362d6-36f2-4ddc-a50b-fadaa922a8a6 |  | checkpoint | Inspection by supervisor
checkpoint-status | b032ddf6-e0d1-4c8e-a051-e836bdb45b4b |  | checkpoint | Notice of Completion
holdpoint | 15db91a5-70bf-4791-8448-a686ec5e5b13 |  | signoff | Nominated Authority Sign off
checklist-sectioned | e53641e8-e526-4ea5-bfb3-36987b0c125f |  | checklist | 0001 In Slab Conduit |  |  |  |  | Yes | 0001 In Slab Conduit V1 | c164d7c6-8507-4831-93f3-b42f27f2f18e
checkpoint-group | 8389e317-2d99-4151-982e-9338c62450ce |  | section | Preliminary Inspections and Tests
checkpoint-status | 976ab7ad-d38a-4926-84bf-589f8c6031b7 |  | checkpoint | RDM & Consent Approval
holdpoint | 4e1cc9c8-3f9c-468a-b86d-49ac3631b383 |  | signoff | Nominated Authority Sign off
checkpoint-status | 5b2b0811-a06b-4f06-bb8d-c5c5e9206136 |  | checkpoint | Define LOT Area
checkpoint-status | d45c06d2-2f01-41c5-b40a-daad2f201ef9 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 0a9eb254-9acd-43a8-940f-17eafcfbb492 |  | checkpoint | Draw up proposed route of conduit
checkpoint-status | c981e5d3-bf75-4bd1-a895-1f067e15880c |  | checkpoint | Site inspection and SWMS
checkpoint-group | fc970924-b799-4fdb-bd17-ee92513ea1a3 |  | section | In Slab Conduit Install
checkpoint-status | 7260b9bb-0a47-45eb-a487-6ade896d0bbc |  | checkpoint | 50mm thick continuous poured concrete above conduit (ASNZS 3000:2007)
checkpoint-status | b0e034d6-372a-48ee-a381-2f6b9ca7c36a |  | checkpoint | Each length of duct is to be fully inserted into the next and glued
checkpoint-status | 7630bb2a-2139-4b31-8c63-287284cd017a |  | checkpoint | Space conduit/duct at a minimum of twice the diameter apart of conduit/duct used horizontally (32mm=64mm Etc)
checkpoint-status | 9353365b-c39e-457e-a23a-1bb2df6f318f |  | checkpoint | Entry and exit of ducts are at the correct location as per set out
checkpoint-status | d1f2a618-3174-46e4-bb4a-05cda0331da3 |  | checkpoint | Ensure conduits/ducts are securely fixed and cable tied to the reo bottom mat, in middle not parallel (hard up) to reo.
checkpoint-status | 3ebdfe6e-8428-4b05-ad7d-269eb01bac41 |  | checkpoint | Extend duct to a minimum of 300mm past FFL
checkpoint-status | b1540acc-82c7-4f09-ba75-6033ef7bb9f6 |  | checkpoint | Push snake through fully completed duct install and pull through draw wire (string)
checkpoint-status | 4847bbd6-417e-4db4-b9e7-ebfefe91bf56 |  | checkpoint | Seal off open ends of ducts with tape
checkpoint-status | 18ca83f3-43a5-4a9a-a2c0-24bb581df1e2 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA
checkpoint-group | ac362e2b-1129-46c6-a6e1-7863bb36c8b5 |  | section | Completion Inspections and Tests
checkpoint-status | 8f050071-fe04-41b7-a3c0-58d5ce80edbd |  | checkpoint | Inspection by supervisor
checkpoint-status | d07f20c1-3e3a-4afc-bd49-1da24d9edbec |  | checkpoint | Notice of Completion
holdpoint | d74c0c8b-5952-4ce1-b782-8308421d604b |  | signoff | Nominated Authority Sign off
checklist-sectioned | 4cd17713-8a4f-4823-abd6-10088cca2f07 |  | checklist | 0004 Lighting Install |  |  |  |  | Yes | 0004 Lighting Install (V3.1) | dc8c0825-3668-4e8b-a525-111a8425b7e8
checkpoint-group | 4e98e3be-0927-4132-a079-5dbbbc7149a0 |  | section | Lighting Install
checkpoint-status | 6bff9fe0-1ad0-4dae-9a43-00c9d666511c |  | checkpoint | The LOT is not defined by an area/zone, it is defined by the lights listed in the ITP Summary Report. (2)
checkpoint-status | 1abf3824-a12b-4078-b4ad-8ed639bc3c9d |  | checkpoint | Drawings referenced.
checkpoint-status | aaef0859-841c-49bb-8760-215ecd6388d9 |  | checkpoint | Installed as per AS/NZS 3000:2007. (6)
checkpoint-status | 50e652a5-1646-4f54-88c3-1ef04266934e |  | checkpoint | As required: Seismic Restraints installed. (6)
checkpoint-status | 90e7ae7c-e91a-4723-bd2d-4996ce959860 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA. (6)
checkpoint-group | 446ead77-cf44-433f-a493-b92df949fe7a |  | section | Completion Inspections and Tests
checkpoint-status | 41db3ef5-6824-425c-a32b-817da147c672 |  | checkpoint | Notice of Completion (8)
holdpoint | 24290d78-9547-45b8-81ae-6ef25c3fdeea |  | signoff | Nominated Authority Sign off
checklist-sectioned | d00d50e1-dbff-4f1b-a8aa-6b5185d8d356 |  | checklist | 0004 Lighting Install |  |  |  |  | Yes | 0004 Lighting Install | ddb512ac-2d4c-4ea0-b8cf-b827653d16c2
checkpoint-group | 69cc4371-fe44-47a2-951a-9fca3a73641d |  | section | Preliminary Inspections and Tests
checkpoint-status | c174b324-4511-4ea1-bf82-d02f2e322ada |  | checkpoint | RDM & Consent Approval
holdpoint | 78798ae3-9cf0-4359-80bc-827f2b143936 |  | signoff | Nominated Authority Sign off
checkpoint-status | 9b13869c-f47c-43ff-9481-9c7d6f9b7585 |  | checkpoint | Define LOT Area
checkpoint-status | 54710e5d-ef3f-44a3-89ca-54e914df59ab |  | checkpoint | Understanding of the Scope of works
checkpoint-status | f906c785-b783-493f-8dc3-025001a359c8 |  | checkpoint | McKay SHD proposed Lighting Layout
checkpoint-status | f3391a51-7a75-4dee-bc8f-9ebb849897d5 |  | checkpoint | Site inspection and SWMS
checkpoint-group | fdaff545-c92a-4bfa-aa18-ec7b9b2bab60 |  | section | Lighting Install
checkpoint-status | 05e6614a-e13d-4c44-b583-3355dfd4a173 |  | checkpoint | Pre-start meeting
checkpoint-status | 3e8b0880-03b6-40bf-b173-b64cb6093ab4 |  | checkpoint | Drawings referenced in Reference Documentation
checkpoint-status | 44c22569-4e08-43b0-85e2-b7d48ac30f54 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | 4f4692f9-2e2d-4b14-84ea-9ac1cbe7e084 |  | checkpoint | Installed as per AS/NZS 3000:2007.
checkpoint-status | 422466cf-e9f9-4ca3-8fa1-a2a8f808073c |  | checkpoint | Seismic Restraints installed as required.
checkpoint-status | 11860be9-910f-4e70-ba4f-b9e511ba6def |  | checkpoint | McKay I&T Form 17 � Lighting Installation Inspection completed.
checkpoint-status | 68548d93-7481-4f21-b507-f2a9dde1e2db |  | checkpoint | All test sheets completed as per AS/NZS 3000:2007.
checkpoint-status | d8852150-8ec2-4174-bf80-11d48e0ad6d5 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 2d76e031-e544-4a3d-94a2-e99a385c857e |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 17e00c55-c391-4b94-abb9-054627dadeb8 |  | section | Completion Inspections and Tests
checkpoint-status | ac7268a5-e4d2-4ea9-9f61-9c3fd72459b9 |  | checkpoint | Inspection by supervisor
checkpoint-status | 33824951-9676-404c-8d5a-088cb6572176 |  | checkpoint | Notice of Completion
holdpoint | 002ece60-026e-499e-82ae-858c44bc7cf0 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 84e6a992-3440-4cd8-8a75-7f9672e3f99e |  | checklist | 0006 Seismic Checklist |  |  |  |  | Yes | 0006 Seismic Checklist | ddd8bafc-54e8-4e27-bd74-76d81b699417
checkpoint-group | dacc4b8d-248e-442f-b575-ceeac04b8147 |  | section | Preliminary Inspections and Tests
checkpoint-status | 3af42fd9-aef7-4715-8abe-f88789b6b050 |  | checkpoint | RDM & Consent Approval
holdpoint | a947c8b5-535d-438f-bbb5-c8011a115f25 |  | signoff | Nominated Authority Sign off
checkpoint-status | c073aea3-3520-4384-8706-befa2194b015 |  | checkpoint | Define LOT Area
checkpoint-status | 7922c71f-77b3-4ad8-84ff-4b8306e34abe |  | checkpoint | Understanding of the Scope of works
checkpoint-status | de3a7c7a-b397-4936-b75d-59ee17a5f64f |  | checkpoint | Site inspection and SWMS
checkpoint-group | c148eded-cd72-4e0f-a1c9-cae8e6afbe2c |  | section | Seismic
checkpoint-status | df16c4fe-83b3-41d9-b6fb-054d0a27e391 |  | checkpoint | Pre-start meeting
checkpoint-status | 010c02d6-6a15-450a-a9c8-9aa56c7c1fe3 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | 50cb4cff-203d-4e69-a726-196441142f11 |  | checkpoint | Layout drawing confirmed as current.
checkpoint-status | efe78cac-8281-4f11-8325-8662a14d4b83 |  | checkpoint | Installation as per Referenced Drawings.
checkpoint-status | 086224b4-bc9a-4b9a-a086-b82232bbdcf0 |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009.
checkpoint-status | 5cdb662e-e413-481e-ad27-9d62d72761f2 |  | checkpoint | Installation on cable trays only if below 400 mm from ceiling.
checkpoint-status | 036938b2-e69c-42f3-87a8-bcda744c72b4 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | fb9d3015-703b-4ce2-bd89-7348e21fdd33 |  | section | Completion Inspections and Tests
checkpoint-status | 0ac0c476-3a03-499e-bdad-58a4aff21fda |  | checkpoint | Inspection by supervisor
checkpoint-status | eadc69c1-c6ea-45e3-bb7b-e4bdd5b29ccc |  | checkpoint | Notice of Completion
holdpoint | 8c21b79e-f3a0-484f-ad21-f76f7e086075 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 69e68e24-a74f-42db-9941-23f9f30dbbec |  | checklist | 0005 Earthing/Bonding |  |  |  |  | Yes | 0005 Earthing/Bonding (V3) | e6e4ab62-1934-4deb-a4f8-b60929ce626b
checkpoint-group | 1e7ef467-e71a-440e-8116-10ebeafefc1f |  | section | Preliminary Inspections and Tests
checkpoint-status | 037624c6-956f-4bdb-8c45-74d1bd2f8b53 |  | checkpoint | RDM & Consent Approval
holdpoint | 8bd0b859-e342-4de1-8f27-54f75572ae84 |  | signoff | Nominated Authority Sign off
checkpoint-status | 8f9f01cf-eca6-44d8-98cf-621e2c2ad79d |  | checkpoint | Define LOT Area
checkpoint-status | c7fd581a-3540-42a2-af9d-0f69a5767756 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 4ee6472d-e7d6-43d3-8df2-90db9f2b2c5c |  | checkpoint | Site inspection and SWMS
checkpoint-status | db9ed440-5325-4ea5-9dec-82db63d28e40 |  | checkpoint | Hot works permit
checkpoint-group | 80b71b3d-18d7-480f-8424-e75f5302666e |  | section | Earthing & Bonding
checkpoint-status | 24e71efe-106a-4ddf-9159-da70403e3467 |  | checkpoint | Pre-start meeting
checkpoint-status | c34c4c67-1b56-439a-a5bb-e376e538b80d |  | checkpoint | Site Inspection, JRA and where applicable a Hot Works Permit.
checkpoint-status | 290bff3a-4df7-486d-864d-e4f8ac1fa177 |  | checkpoint | Weld copper wire to steel pile as specified on pile plan as required.
checkpoint-status | cab5a1e2-5eca-4d8c-87c8-9c568ed9ef31 |  | checkpoint | Feed and cable tie copper earth wire to correct point.
checkpoint-status | ab2155fb-fd8a-4815-8071-f7fcbdefd746 |  | checkpoint | All Earth, Bonding and Equipotential Bonding to AS/NZS 3000:2007
checkpoint-status | 4c0f8d55-e102-47ff-a46d-cd51aa3a611f |  | checkpoint | Complete McKay I&T Form 20 - Earthing Resistance Test sheet.
checkpoint-status | adcfbafb-eca1-4c8b-b398-dd1210194d27 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 477fe20f-9929-4e8b-966d-1ce1250e153e |  | section | Completion Inspections and Tests
checkpoint-status | de432f40-3cd2-4a9c-a5d7-5c9ad7f9832a |  | checkpoint | Inspection by supervisor
checkpoint-status | 3fcf41b2-edff-4559-8e2d-eaddf1bac408 |  | checkpoint | Notice of Completion
holdpoint | c00ceb60-c0f2-4842-9342-6d608d37a3ec |  | signoff | Nominated Authority Sign off
checklist-sectioned | 02bf69c7-f6e5-4b0c-abb6-eaed13d8e4d1 |  | checklist | 0002 Cable Installation |  |  |  |  | Yes | 0002 Cable Installation V2 | ebd8de6e-76c8-4f9b-aa5a-d444120724d6
checkpoint-group | b100f600-fd63-46e8-86a6-e01d52972a1d |  | section | Preliminary Inspections and Tests
checkpoint-status | 236da56e-796c-449d-8022-e839494ae62d |  | checkpoint | RDM & Consent Approval
holdpoint | 7594a375-bc00-4554-acff-32ef3577cfcd |  | signoff | Nominated Authority Sign off
checkpoint-status | 288e2440-1257-481b-9c00-5fece36fc3c0 |  | checkpoint | Define LOT Area
checkpoint-status | 8e5e7ae3-c923-469a-a41a-ed1b3969d7c4 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 575ab059-b027-4c9d-99d9-b269aa54c7c9 |  | checkpoint | McKay SHD proposed cable route
checkpoint-status | 022b3c72-6319-48d8-bc14-7920e7b32a75 |  | checkpoint | Site inspection and SWMS
checkpoint-group | d8dedb1b-5c78-41fe-8157-5c4dd12c53cc |  | section | Cable Installation
checkpoint-status | 326d33fd-dc90-4299-a951-fd1b6bc06d97 |  | checkpoint | Pre-start meeting
checkpoint-status | 259a47aa-b209-495a-a58a-2d0e0a8d0695 |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | a274d924-b66a-44ac-b907-717e72a2ecc0 |  | checkpoint | Provide logical cable management and reticulation system coordinated with other trades.
checkpoint-status | 5593ba01-6a33-4d8b-9c30-5c5aaeef1ca9 |  | checkpoint | All cable routes rationalised where possible.
checkpoint-status | 28acc56d-5441-41cb-aea7-42c1024518f6 |  | checkpoint | Maintain Minimum Separation Distances
checkpoint-status | 7cbb6846-339d-487d-b1c4-0b844801d4e0 |  | checkpoint | All wiring systems adequately protected.
checkpoint-status | a558af28-769d-4be0-8ebc-cc8550ef7c9f |  | checkpoint | All cables and supports concealed.
checkpoint-status | 27417448-6a32-46b4-a8f9-24989bc64f18 |  | checkpoint | Cables installed as per manufacturer's instructions.
checkpoint-status | 2dd83d97-f31c-4cf0-ac48-8aeff1cea7d0 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 24182e0f-38ef-421f-858f-a32f36bbc7d5 |  | section | Completion Inspections and Tests
checkpoint-status | ba3a5ae6-479e-4d4a-8ff4-b562ba163328 |  | checkpoint | Inspection by supervisor
checkpoint-status | 17c63752-f7f7-4556-8209-14f90376ad4f |  | checkpoint | Notice of Completion
holdpoint | 1081063f-9c60-44aa-b1ab-a301a6f6633e |  | signoff | Nominated Authority Sign off
checklist-sectioned | 85b95fa0-9ac1-4dd2-b2b6-434bdbd907d8 |  | checklist | 0003 Containment |  |  |  |  | Yes | 0003 Containment (V2) | f513e5ec-e8bf-4834-b1b4-1ca6acb2be64
checkpoint-group | 645bd739-8e61-40d4-8415-5901e401c9f2 |  | section | Preliminary Inspections and Tests
checkpoint-status | 356bd0f9-ee00-45ce-8113-190afa266cd7 |  | checkpoint | RDM & Consent Approval
holdpoint | 8d86c7ff-eac2-4891-b21f-47be36bfca2c |  | signoff | Nominated Authority Sign off
checkpoint-status | 077ad76e-f728-47b0-ad94-417a51145b94 |  | checkpoint | Define LOT Area
checkpoint-status | ca9f0a9c-5f6a-4168-8b0a-b7c6137581b8 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | b354c5ae-b468-4470-8f0c-2b68095d6ebe |  | checkpoint | Draw up proposed route of Cable Containment
checkpoint-status | 260834fd-888c-4eeb-a30e-364b27e814eb |  | checkpoint | Site inspection and SWMS
checkpoint-group | f0c7501f-ac28-40ee-b643-f78ccca901d0 |  | section | Containment
checkpoint-status | cca4292a-dc31-4261-88eb-2c3680b20167 |  | checkpoint | Pre-start meeting
checkpoint-status | d463709a-f0fe-44ce-9176-12c81b94fb69 |  | checkpoint | Ensure reference Drawings are listed in Reference Documentation.
checkpoint-status | 7364f17f-53e1-46a1-8b09-e536c34e6da3 |  | checkpoint | Ensure cable ladders and trays are provided to support cable runs (where necessary).
checkpoint-status | 74a96aa8-6a1d-4860-9444-f735126b9748 |  | checkpoint | Ensure cable ladders and trays have enough support, and 50% spare capacity.
checkpoint-status | 21fdd772-6de0-450f-a3af-511f1abfeb57 |  | checkpoint | Ensure cable ladder and tray is installed as manufacturer's instructions, complete with all necessary splice plates, bends and fixings.
checkpoint-status | c2de1982-0493-4903-b84c-80aec33d0c0b |  | checkpoint | Ensure adequate access for replacing, inspecting, or adding cable.
checkpoint-status | 2d87ab98-40b8-467c-ab67-b8dc1fea8c7d |  | checkpoint | Ensure seismic supports and bracing installed as per NZS 4219:2009.
checkpoint-status | 3e86c728-c9bc-416b-a5f7-5babb29a9e21 |  | checkpoint | All refuse removed from work area.
checkpoint-status | 01282d89-4122-41b0-835c-eb7a658419fa |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | 3cbcc0cc-6e7a-497f-ba75-0cfd6fff5e38 |  | section | Completion Inspections and Tests
checkpoint-status | a2d68459-9a26-4965-8925-d62b79fc1095 |  | checkpoint | Inspection by supervisor
checkpoint-status | e5b290f3-e58a-4a0f-9a30-abc473545a79 |  | checkpoint | Seismic Bracing
holdpoint | 1ce679b7-fc3a-41f1-9ff1-6f57940e4b53 |  | signoff | Nominated Authority Sign off
checkpoint-status | 2932cba1-2501-4d31-bae2-b202d691378e |  | checkpoint | Notice of Completion
holdpoint | 9065ab5a-a530-4835-a4ce-59ebe7e0b744 |  | signoff | Nominated Authority Sign off
checklist-sectioned | 9d0cead0-16ad-4ee3-9e15-7b198fe0d1b8 |  | checklist | 0002 Cable Installation |  |  |  |  | Yes | 0002 Cable Installation (V3) | fea185eb-2891-40cf-bf56-c401ea46418b
checkpoint-group | 9a957b4b-2df6-43e8-aec9-05536bddd57b |  | section | Preliminary Inspections and Tests
checkpoint-status | 6144d9ce-f7f7-4d2a-874b-2dbe5feb9200 |  | checkpoint | RDM & Consent Approval
holdpoint | 777b596d-1a7f-405c-9576-2bf4457d0d5f |  | signoff | Nominated Authority Sign off
checkpoint-status | 2f8038d9-fd94-4d88-9f0d-2346086fd909 |  | checkpoint | Define LOT Area
checkpoint-status | 8e9d477d-ea0d-44fc-96ae-a0cc170752e3 |  | checkpoint | Understanding of the Scope of works
checkpoint-status | 302ba2fc-3236-4237-8bd7-043e55e28e79 |  | checkpoint | McKay SHD proposed cable route
checkpoint-status | 97bcbce8-3f98-424b-8bb7-44f5219b49ba |  | checkpoint | Site inspection and SWMS
checkpoint-group | 928a566b-5c41-46b0-b12c-77c09b492732 |  | section | Cable Installation
checkpoint-status | a45c8791-6f66-47c7-ba47-55b404a6342a |  | checkpoint | Pre-start meeting
checkpoint-status | 5c85288b-377c-4253-8ef0-2a30e5917a58 |  | checkpoint | Site Inspection and JRA.
checkpoint-status | 74873475-f91d-46fb-937b-2ae0474a14cc |  | checkpoint | Drawings referenced in Reference Documentation.
checkpoint-status | fe4c1f21-096e-41c4-8547-cd6cfe3495ff |  | checkpoint | Provide logical cable management and reticulation system coordinated with other trades.
checkpoint-status | a065e798-4016-4d33-911e-615c63ec6b57 |  | checkpoint | All cable routes rationalised where possible.
checkpoint-status | 755646dd-92ea-4a8c-b8d4-fbdc562e6710 |  | checkpoint | Maintain Minimum Separation Distances as per 22.2.3.
checkpoint-status | b66399a0-5c17-4abd-af51-bc030541a075 |  | checkpoint | Catenary Installed. 6 cables/cat wire max. No excessive sag. Cable tied regularly.
checkpoint-status | d4db99bf-c7a1-498c-876b-e56a07b72b35 |  | checkpoint | Conduit installed. 22.5.2-fix conduit saddles at a maximum of 1m intervals in horizontal runs and 2m intervals in vertical runs.
checkpoint-status | e7fcaf09-366c-4769-9fc2-3d3602bce2fc |  | checkpoint | Containment. 22.2.8-Fixing with nylon ties to slab or roof structure at max intervals of 1500mm.
checkpoint-status | 771c3516-7df1-48b0-82cf-e55d43ff4cbc |  | checkpoint | All wiring systems adequately protected.
checkpoint-status | 90df71f1-432e-4d39-8e45-6d962d4499d3 |  | checkpoint | All cables and supports concealed as per 22.2.6
checkpoint-status | 9f773777-0585-42bc-a376-dc62c4593601 |  | checkpoint | Cables labelled correctly.
checkpoint-status | 0541199e-b1bf-4831-9097-da3041342b44 |  | checkpoint | Cables installed as per manufacturer's instructions.
checkpoint-status | 38510c4c-2004-4583-9527-2295e113bab6 |  | checkpoint | Written approval obtained where cables/conduits must be run surface mounted as per 22.2.7 22.6.1
checkpoint-status | 8f5a2ac3-4fdb-4a5d-9269-224cb1ad0325 |  | checkpoint | Photos to be taken of critical elements above as evidence of QA.
checkpoint-group | f47f1006-4f30-4037-b9cd-757ffc831b11 |  | section | Completion Inspections and Tests
checkpoint-status | 8e5bc055-5dcc-490f-a0d8-6bf0e3a7a46d |  | checkpoint | Inspection by supervisor
checkpoint-status | 4d7b41c1-00f7-437d-ac61-5d99769964e5 |  | checkpoint | Notice of Completion
holdpoint | 5efce90c-c9da-413a-9f13-c4fd2feb29b9 |  | signoff | Nominated Authority Sign off