## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-070-CIV-CAMMS-Tactile Installation | itp |  |  |  |  | ITP-070-CIV-CAMMS-Tactile Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-070-CIV-CAMMS-Tactile Installation
label | ITP Description: CAMMS-Tactile Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 070-CIV
label | Revision Number: 0
label | Revision Date: 28/02/2023
label | ITP created by: Chloe Mitchell
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: AS1428.4.1
label | 1.2 Non Dependent
label | Reference: VicRoads Section 160.A9
label | 1.3 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries - Materials
checkpoint | 2.1 Material Conformance
label | REFERENCE: AS1428.4.1 Section 2.2 & 2.3.1
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
label | Attach: TeamBinder Material Approval Ref No
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Conqa HP Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP