## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
2d5bd5d3-906c-40b6-a6cf-05e1006e81f5 | checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation
48bfa6d9-ce1d-4390-8645-ed450f57238b | section | Details
28415b61-5954-4629-9b39-60fa1fbe30e5 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
f54de1d9-8640-5396-a521-400891167ddb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ec4d2b3a-cb37-51ff-bffb-fd7f9d93c1b8 | note | Check Item - Hold Point 4
acf169bb-c7f8-5f2e-a822-a1f405912982 | note | Reference - MRTS04 Cl. 9.4
a0732c2b-0cda-4fd0-8d7a-229dc44f1fa3 | signoff | HOLD POINT
32851a91-8f48-425b-ab8a-57373af282f8 | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
0a30f99d-b6d1-50b9-9a80-ba0d9908d61b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1210b5fa-088a-5df2-b16d-0d02a60ba5d4 | note | Check Item - Hold Point 8
d86f4a61-66ad-5730-9abf-932fec1ed5e4 | note | Reference - MRTS04 Cl. 13.3.2.1
af0d53e4-4c41-4842-8496-33866b6d3f4d | signoff | HOLD POINT
c541d40c-7500-4c48-a889-20068e9426ed | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
252138e5-e1f3-5cdd-9f38-5aec11bcd5d3 | note | Acceptance Criteria & Frequency (Project Specific) - Survey
b2d125ab-9f38-5dbb-a85c-3cb6918dbf4e | note | Check Item - Check Item
14f23a0d-549b-5435-9e55-8dba04897601 | note | Reference - MRTS04 Cl.13.3.1, Cl. 6
14b67eea-aab8-4878-abb1-016c4cc61f53 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
a6db5755-3dba-584e-9ab7-bc3002f21b9d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7658379b-1d50-5372-821c-0ef2f5b0da82 | note | Check Item - Check Item
1a927129-51f6-53f2-84dd-634d0a7d7460 | note | Reference - MRTS04 Cl. 13.3.3.3
40db74ca-300e-4d5f-a50e-6f37c469c026 | checkpoint | Dewatering of excavations shall comply with requirements of EMP
5d4f130e-2e4b-505a-9260-c2f16c5d668f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
449f8118-da56-5101-819b-509ec3b8b167 | note | Check Item - Check Item
cba6a234-cdd8-5c28-8816-70778133ad48 | note | Reference - MRTS04 Cl. 13.3.8
3c53ecbd-9457-40d2-89d4-24f656db2002 | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
1971c731-33b3-5515-9180-1a830c4cf4b7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d61836bb-43e8-5b6f-8fec-81de484ce177 | note | Check Item - Check Item
27b05482-6aa2-5351-8a62-f02fc56e2302 | note | Reference - MRTS04 Cl. 16.1
c183cc22-155e-4b0e-8597-3d42c541909c | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
ed616e33-6341-545c-85c9-4bb7487745c9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3a228b8e-dcaf-5f36-937d-920d253567aa | note | Check Item - Check Item
810333d5-42ba-5a23-a2b3-f9f036f2b718 | note | Reference - MRTS04 Cl. 13.3.2.4
| checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
| note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
| note | ○ 10,000L water tanker with 600kPa tyre pressure.
| note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
| note | Check Item - Witness Point
| note | Reference - MRTS04 Cl18.3.2 RMS T198
| signoff | HOLD POINT
1ce22f46-f0f0-4483-8338-7d8a73134f20 | checkpoint | Final Verification
8e878198-0df9-5283-baee-4f1aaf509c00 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
f7c1c71f-3dc9-5546-a159-6fecb75bd3ea | textbox | Print Name:
b67ab0c3-3982-5a09-9fb8-1b51823030cd | date | Date:
f852b222-fc1a-5654-a558-d88c1467f5cf | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
dfe3015b-699d-517a-b071-ebbf7330d724 | textbox | Print Name:
6dd12327-5f49-57bf-96ab-5e22e96e2d52 | date | Date:
50349dac-b12d-42c4-95ac-0e1a7e8f4278 | signoff | Sign ITP
daf5b1f6-cb35-48fb-8960-9b86f31e3940 | section | Final Sign Offs (to be completed at closure of Lot)
ff70bd08-67da-4191-ab2e-58ad410fbc3d | checkpoint | Agreed Quantities
e31b5272-a5ba-4dbc-9722-59042c8d7ba5 | signoff | Agreed Quantities Sign Off
a58b1194-16dc-4572-8794-88d340ee49df | checkpoint | Closure of Lot
dd50da82-4fb8-4eed-b791-82c111524994 | signoff | Closure of Lot Sign Off