## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
ec9a0299-7a08-4d97-9c12-044ab23fb545 | checklist | 04.09 - Subgrade Level | itp | 04.09 - Subgrade Level
3d723306-cc44-4119-8231-3185654cbcee | section | Details
f4f96f2d-c580-4ec0-b38e-464067ae91e5 | checkpoint | Define Lot
d1bdb2c6-9bae-50c1-9a0c-89ce49083ec1 | note | Acceptance Criteria & Frequency (Project Specific) - Normal : Max Lot Size : 4000m2
2d89da01-0fdd-5d4f-a52f-0e682d32128d | note | ○ Reduced : Max Lot Size : 2000m2
39e5d46a-904b-5951-b44a-19953744885d | note | Check Item - Lot Records
b975c840-9633-55a2-9c94-0a648a57ec84 | note | Reference - MRTS04 App A
e24ac0e3-1890-4a97-b12d-5da0d88be613 | checkpoint | Reporting Pavment Design Requirements - For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
96a3769c-1223-58de-94e0-55e72c5ec4b7 | note | a) test pit logs
6c617b87-0720-5cc8-bff0-d1705497845e | note | b) all test results for each layer encountered within the test pit, including certified test certificates, and
3d0c4a7d-a674-5086-8ed1-83240a6b8245 | note | c) marked-up drawings accurately showing all test locations within the Lot.
391bc26b-10f0-53ec-99bd-3f9199a05f06 | note | The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
600e2f0e-04a3-550e-9635-10d8d97522f3 | note | Acceptance Criteria & Frequency (Project Specific) - Submission to Administrator
22eb03bf-8d62-57a5-bab5-f578f64f5a57 | note | Check Item - Hold Point 16
96001efa-4a54-50fa-be49-9d1006783297 | note | Reference - MRTS04 App B.6.2
386c5468-a81f-433f-bc7d-5ef45009d3a0 | signoff | HOLD POINT
616a6d56-cb63-45d3-b8fb-7c0cc9026317 | checkpoint | Bottom of Excavation for Cuttings - Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
540c7db1-288c-56a9-9c00-4a7bd523807f | textbox | Subgrade Treatment Type Directed:
c6b0e461-2edc-5513-85ac-85a21769664c | note | Acceptance Criteria & Frequency (Project Specific) - As directed by Administrator
dab916eb-450a-54b1-bdd3-2c24bfd31ce4 | note | Check Item - Hold Point 8
1e93eab2-6a1f-5093-8e3b-1fcac3026851 | note | Reference - MRTS04 Cl13.3.2.1 Cl 18.3.3
fde1afd0-cd47-4812-b341-b2e2fcb72bf6 | signoff | HOLD POINT
bbee0ca2-ad58-49ef-bc61-d9083cea4a09 | checkpoint | Subgrade Treatment Type A - As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
389ac352-7107-51ae-9ea9-34eca1e434ef | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm
6d347084-7278-5512-be15-40d170214cfc | note | ○ Compaction Standard: min 97%
42b2c252-e434-59d9-aa5b-f798c1fdfb64 | note | ○ Normal: 1 per 500m2, 4 per lot
957cd673-7302-528c-969d-f5e4d4806d20 | note | ○ Reduced: 1 per 1000m2, 1 per lot
7b5ef9d6-6736-5c1b-99d0-a09f2a179418 | note | Check Item - Test Reports
204561b8-5c64-5533-a081-4fc84a125c51 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
616b8a63-9a2e-4523-a933-8e6bd4b66ada | checkpoint | Subgrade Treatment Type B - As ordered by the Administrator at subgrade level on all section. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and to various depths, as directed by Administrator, typically between 150mm and 250mm.
9ae768e5-3257-57f3-8abf-e885898af932 | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm-250mm
7335bee1-0d1c-5f12-8f5b-46250d6f2477 | note | ○ Compaction Standard: min 97%
b891be08-3565-5a04-be14-f76e172fbc06 | note | ○ Normal: 1 per 500m2, 4 per lot
58ceff71-e53b-5b94-a18e-5fb279e58fce | note | ○ Reduced: 1 per 1000m2, 1 per lot
e176b736-1c52-5e14-a4bd-33a8222a2e04 | note | Check Item - Test Reports
f29c2b74-93ba-5f0c-b4b0-b7187e977998 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
2d6ea3ce-c7ac-41c0-94d8-14c443bc0062 | checkpoint | Subgrade Emabankment - Material to be compacted to requirements not less than that specified in Table 15.3(b). Subgrade relative density tested to Q140A.
70ad41b9-f62c-59f6-b337-3af2cb3a1378 | textbox | Material Source Stockpile Lot Ref:
94bd78f1-4feb-546e-8772-5b80b7f91073 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
9777d834-9b00-5b9b-a925-772813e06176 | note | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material: min 97%
ace5d19f-d406-5625-add5-4afc261e18b4 | note | ○ Normal: 1 per 500m2, 4 per lot
8e347876-8de5-5ada-8ef0-157d94ca9769 | note | ○ Reduced: 1 per 1000m2, 4 per lot
c8b2c09f-1c81-5964-948b-c659a68c3198 | note | Check Item - Test Reports
e16be81d-f21b-57c2-bd41-2ab228878254 | note | Reference - MRTS04 Cl15.3(b) App A
31fd2a2c-350e-4ddc-99a0-23ab673cb686 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
3d168943-8300-52f8-98ac-d179f50ad515 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
a93428a7-8770-5570-a575-7f0d4d48266e | note | ○ 10,000L water tanker with 600kPa tyre pressure.
1b2409af-9ea1-591d-b93b-07e3bfaf1305 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
7ab40af2-6128-5ed6-88ee-2413d10e6d8a | note | Check Item - Witness Point
033c658e-679b-54ed-b5b4-00fd98a24806 | note | Reference - MRTS04 Cl18.3.2 Q723
| signoff | HOLD POINT
9e14a4a9-f3a1-4611-a4dd-d281411231bf | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
48b684b0-12f7-55e7-ae75-a6f4239e35de | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
651949f5-bca8-5e18-90e5-5dadde3610d9 | note | Check Item - Dip Sheet Records MRTS04
303c3cf7-8d21-5eec-b0a2-8897e726e33d | note | Reference - Cl. 6, Cl.13.3.1 Table 6.3.1
d2e26e7d-d109-418e-b742-160581afdc37 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
982be595-9c29-5b15-8d27-5cbadb741684 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
3141cc04-84a9-5692-b00b-8971ed8224a2 | note | Check Item - Dip Sheet Records
5879072c-11f6-58e6-8787-49fd72fc5e89 | note | Reference - MRTS04 Cl. 6.3.2
cc9a47d8-2c18-4328-b2ad-aa52df062a50 | checkpoint | Subgrade shall not pond water and be free draining.
3c902505-9096-519f-a95c-9c6f85ed1692 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d1d4a3b0-999b-5d9d-a4ba-c762700bc4f7 | note | Check Item - Check Item
681d14db-a2f1-50ab-8b71-cece1ec87e46 | note | Reference - MRTS04 Clause 6.3.2
f7925881-fb34-4970-b0d2-2117d957dbcb | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
f0391b69-ae24-573b-924e-4c1d477142f1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
00cde754-6f6b-5731-8089-322c462729cf | note | Check Item - Hold Point 12
28621052-deed-5cae-8f19-06891d7b689b | note | Reference - MRTS04 Cl. 18.3.1
79aafb6f-83bf-493f-87f7-5cad841dd336 | signoff | HOLD POINT
63b91a1d-06a3-4598-b881-e5ea9a6e1939 | checkpoint | Final Verification
18836e4b-2081-53bd-b6cd-c42944801302 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
262e1018-9948-557e-b2bf-a0a72395f97c | textbox | Print Name:
02d3ba9b-b107-5b0f-82d3-bdf5ec352b62 | date | Date:
4ad3c645-b80f-50d6-9803-42283c1d5daf | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
e290ee1f-d495-5a5c-b1a3-efb3b4d10048 | textbox | Print Name:
0a2f1804-ae12-5211-8bef-b6b236d1988a | date | Date:
d436d7ea-d5f9-46ff-8623-335585130994 | signoff | Sign ITP
5baf8a78-adec-4e7a-9c23-a5ec98a56488 | section | Final Sign Offs (to be completed at closure of Lot)
5033d2ab-97db-43ea-999c-4abcf0f7303d | checkpoint | Agreed Quantities
a9bdd6e2-773a-49d1-be10-30bc067a5fa0 | signoff | Agreed Quantities Sign Off
0cb2deed-a818-4f54-821c-4fc6b8a342c4 | checkpoint | Closure of Lot
9969e3c6-14db-433c-a956-a86159329991 | signoff | Closure of Lot Sign Off
c0eb53fb-4184-482f-9892-53c8ceac964e | checklist | 04.091 - Subgrade Treatment Type A | itp | 04.091 - Subgrade Treatment Type A
65c8368e-5519-4c84-922f-53208dd447d0 | section | Details
2ae0e122-16e3-448d-b053-19ebddefbf89 | checkpoint | Define Lot
1ef94f60-0448-5783-a9ba-690a8041e33d | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
c8987aea-eaa9-50fa-92a5-e082aeb1c39d | note | Check Item - Lot Records
507aecbf-3ee0-57eb-82f5-f173aa1af9aa | note | Reference - MRTS04 App A
6b2cba09-76f0-4fc5-a13b-dda1b917b6e3 | checkpoint | Trim and compact existing - Subgrade Density requirements Q140A -Material to be compacted to a density of not less than that stated in Table 15.3(b)
3fc5a642-e02d-525e-a9bd-d32b757ac359 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
3fb30cd5-8554-5411-bda1-a09dcc776449 | note | ○ Existing material in cuttings: min 97%
feb54ad4-53d2-5538-b4ae-ab2dc53c0067 | note | ○ Normal: 1 per 500m2, 1 per lot
6262d666-455e-5deb-a672-a3a863f32623 | note | ○ Reduced: 1 per 1000m2, 1 per lot
0dc9661b-4a42-5bb1-abf3-1a88d3f126f3 | note | Check Item - Test Reports
b57ff1d7-ee12-5ca2-966d-c15b43792206 | note | Reference - MRTS04 Cl15.3(b) App A
ac856e2a-2657-46dd-873b-88d27513cb70 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
c3cbb032-0fdf-54b4-82be-ac985b845839 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
6cc8a129-3335-501c-a789-94a66fa0d899 | note | ○ 10,000L water tanker with 600kPa tyre pressure.
b151abeb-4573-5158-9dea-d2911e35754d | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
b94ab110-545c-5389-85d2-fdec3f315c80 | note | Check Item - Witness Point
9ff1f352-5c31-57af-924f-494594d85a0e | note | Reference - MRTS04 Cl18.3.2 RMS T198
| signoff | HOLD POINT
619e60bb-830a-45ab-87d9-d10a9c250f43 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
1c4c5a36-e5b2-5126-ab73-decfe10034cd | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
b0e486e4-e478-556c-96be-32edfbfc2356 | note | Check Item - Dip Sheet Records
4390e6be-48d6-5a49-a3e9-af401f302a9b | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
5d036c7a-425a-405b-a2a1-2b75b724e839 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
7f7ad6de-2f57-50f0-84f7-4901b6ad865a | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
2b7d106d-2be3-5793-b2b7-8cdfd37f7353 | note | Check Item - Dip Sheet Records
f56100fd-145d-5540-9417-d368b7d369bf | note | Reference - MRTS04 Cl. 6.3.2
13bed220-bb1a-43ec-afe1-92073796a4d8 | checkpoint | Subgrade shall not pond water and be free draining.
87709fbc-e8b7-591e-9464-9214d49dcea8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c61e64c7-28b9-52f4-84cf-f0c9e95ee425 | note | Check Item - Check Item
e69f0a87-3063-589d-9b47-eb1163355a24 | note | Reference - MRTS04 Clause 6.3.2
005cffd9-b580-49d3-b950-1c242415d5ec | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
d20c28c9-ab91-558c-bc73-d9b51736d2a5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
aa5487c4-3005-5df0-a2ca-a36b05b5c123 | note | Check Item - Hold Point 10
a56b27ec-13fa-5c87-9594-ef10d92b6eea | note | Reference - MRTS04 Cl. 18.3.1
7b5feced-987b-4c97-8ce2-2148f5c46ca0 | signoff | HOLD POINT
fb9002c4-db38-4d36-8375-a9c7fc9511b3 | checkpoint | Final Verification
02dde255-dcb3-5f9c-92b9-9aa3aafe40dc | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
89d159d7-8853-50fe-8f50-2574102a83f9 | textbox | Print Name:
921d3fcd-bf54-5406-8e47-2c02fc2581dc | date | Date:
c27ac476-3026-5bae-9cc6-1d0ae705db10 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
f9579594-b7c3-5028-8c64-86499edaf2eb | textbox | Print Name:
c0e02062-9ebb-5fa4-9173-2369af6665fa | date | Date:
da92892c-1a6f-4dde-b1dc-f38d010db8b4 | signoff | Sign ITP
23ba9913-8b9d-4b33-b234-7326458af098 | section | Final Sign Offs (to be completed at closure of Lot)
9a7d66dd-505b-4dff-b805-63af88fe27f5 | checkpoint | Agreed Quantities
98bc84b5-82b4-4173-80fa-1f48dfee780a | signoff | Agreed Quantities Sign Off
a1fd8e0d-3f56-4daa-ad62-50220534eb92 | checkpoint | Closure of Lot
622ec525-beb8-482a-b147-628f431f6466 | signoff | Closure of Lot Sign Off
8df6920e-3711-4c7e-8cc0-94dc0a6ecb93 | checklist | 04.092 - Subgrade Treatment Type C | itp | 04.092 - Subgrade Treatment Type C
226e1ae6-a9fc-4370-bd35-875b37f332d5 | section | Details
79669948-8a98-4ba3-b6e1-3fffd8f12886 | checkpoint | Define Lot
fe7fb26b-3dd6-589a-a3d4-57251c7abdf3 | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
ef400e12-7c86-574d-8276-85d045936aab | note | Check Item - Lot Records
76d56de4-e49c-5ca4-bb8f-990e5cb678a0 | note | Reference - MRTS04 App A
f3dff0a9-4a8a-4004-810b-34637039d139 | checkpoint | Unbound Granular Material incorporated into unbound treatment shall be as specified in MRTS04.1 Cl. 12.1 and meet the material requirements specified in MRTS05 Cl. 7.
0a15ca94-a180-5198-9a4f-fd2146397315 | textbox | Material Type:
ca5c4c7b-be09-5330-9f30-3f3afee85562 | textbox | Material Source Stockpile Lot Ref:
db6592a0-ca9b-5df6-8d45-f54a7de62fc7 | note | Acceptance Criteria & Frequency (Project Specific) - Unbound Granular Material Stockpile Lot
f2c08ed6-6b43-5cab-9de0-7cb544b6c097 | note | Check Item - Check Item
dd155413-0252-56e6-98d4-fdb1c42608f7 | note | Reference - MRTS04.1 Cl 12.1, MRTS05 Cl 7
f215275f-9c7b-46f1-90f3-8d2b07e9348e | checkpoint | Subgrade Density requirements - Material to be compacted to a density of not less than that stated in Table 15.3(b)
0531d8c8-6a6f-5176-958c-f567fc9acc47 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
297fd154-6707-5a62-9d2c-3021b6b98cd4 | note | ○ Existing material in cuttings: min 97%
96c899d2-ec18-5802-af65-2b86fffde895 | note | ○ Normal: 1 per 500m2, 1 per lot
0d9b9415-4e9f-53ec-ac48-62f6797f67aa | note | ○ Reduced: 1 per 1000m2, 1 per lot
bd98b7c8-447e-513d-92f2-bcc12324172b | note | Check Item - Test Reports
dc96323f-5c37-5baa-8bd6-8e49e47ba6fa | note | Reference - MRTS04 Cl15.3(b) App A
4ba8ab5e-7533-4f13-a45c-3d72f1f127f9 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
5423f85d-c33f-5fac-a277-7e36665237b4 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
465c65e7-37cb-5818-8e87-e04323bd7cd9 | note | ○ 10,000L water tanker with 600kPa tyre pressure.
8a338ae4-7b0a-5c4a-99de-5d48eb89f729 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
cbd3b5f7-1f39-51f5-ad2d-ba6a376942db | note | Check Item - Witness Point
13b81c99-7f89-5baa-a316-7287c937c657 | note | Reference - MRTS04 Cl18.3.2 RMS T198
| signoff | HOLD POINT
23e18093-81c9-42ae-bf69-0c180b539760 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
55bc053c-b47d-5fe5-a1f9-13515423f820 | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
ca6e97a7-c2ff-5165-84cb-8a0c16b9ee17 | note | Check Item - Dip Sheet Records
65c06375-9eb2-511c-aeea-f3b5ea2d432b | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
ca6834ae-1f48-4630-b55b-0f8b350dbd65 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
a5f79162-680a-5a83-8019-0bb94e0fa4b8 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
dc0d43c2-987a-5dbb-9391-878f21eca4ba | note | Check Item - Dip Sheet Records
59ccbed9-2c0a-5a9e-ba0f-584c5cca3744 | note | Reference - MRTS04 Cl. 6.3.2
16cecebb-15e6-4c54-9889-7fb5c169465b | checkpoint | Subgrade shall not pond water and be free draining.
473b992d-7fa6-5af0-90cf-377572b82b3b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
292e2662-5ad1-5f49-bb43-62263c0f93a5 | note | Check Item - Check Item
d2f22fc2-21b4-5a42-a216-b9bd45ad6042 | note | Reference - MRTS04 Clause 6.3.2
f27ae47a-af9b-4716-ae91-42b6b6aaacf2 | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
8f82313c-899b-5e20-a810-e957de41057a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fc752bec-6518-5334-a023-18e0b0085ce6 | note | Check Item - Hold Point 10
0a3ca54c-c003-5706-83d9-311b20ae26f6 | note | Reference - MRTS04 Cl. 18.3.3.1
a98e640d-2290-4ab6-a73a-9e2e2bab219a | signoff | HOLD POINT
0aa78ca5-6ad6-4140-96bf-fbef14589c42 | checkpoint | Final Verification
b3648b15-f7f5-5073-b6d1-f2301ce8bb83 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
06ec6481-c464-5820-9db3-88ef8c716de7 | textbox | Print Name:
b348a896-6be5-50e4-a36d-893787c09b58 | date | Date:
e8406fb9-6d53-5f01-b058-2d1aa4f03cc0 | note | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
547d18b4-5b5e-5b48-ae93-c72203b4db8e | textbox | Print Name:
ffa52136-b99b-5a29-a2fc-0f8ee478b52a | date | Date:
a59f0c62-90b8-401b-b9d2-828b9ea03782 | signoff | Sign ITP
112cc4a0-a4f5-40a1-b428-ccaa3dbc2655 | section | Final Sign Offs (to be completed at closure of Lot)
be853ccc-36bd-4072-a2bb-023608e3d29a | checkpoint | Agreed Quantities
ad8b6949-d411-4082-9445-738b1621fd6a | signoff | Agreed Quantities Sign Off
92d0739c-dcff-4820-a984-978ccdf2de12 | checkpoint | Closure of Lot
b1bdb9d1-63f1-4ef5-bed0-d723d3c703ee | signoff | Closure of Lot Sign Off