## Table 1
[8 empty] | Inspection and Test Plan – Control and Supervision of the Works | [11 empty] | Doc ID: FH-ZU2-QU-ITP022 Rev: 0
| Principal’s: Melbourne Airport (APAM) | [8 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Abdul Saad
| Project: Taxiway Zulu 2.0 | [13 empty] | Reviewed By: Faiyaaz Ahmed | [6 empty] | Date: 16/09/2024
| Construction Process: HaTelit C Placement | [13 empty] | Approved By: Angela Julianto | [6 empty] | Date: 16/09/2024
Specifications: ZULU-BECA-001-SPC-00002 - Revision C04 (07 June 2024)
Structure / Component: HaTelit C
| Lot No: |  |  | Lot Details: |  | Lot size/Quantity: | [10 empty] | Date:
Item No. |  |  | Task/Activity Description | Inspection/Test | [11 empty] | HP/ WP/ AP/IP/TP/S CP | Responsibility |  |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  | Reference Documents |  | Inspection/ Test Method |  | Record of conformity | [6 empty] | Principal’s Representative |  |  | Fulton Hogan | Date
1 |  |  | Preliminary Activities
1.1 |  |  | Check for correct documentation | Prior to commencing works |  | Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors. Current revisions of these documents to be obtained via Aconex or ACC. |  |  | Current Revisions in Aconex, ACC |  | Verify |  | This ITP signed |  |  | HP* | Project / Site Engineer
1.2 |  |  | Implementation of all measures and controls | Prior to commencing works |  | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS |  |  | PSP, EMP, TMP, SWMS, WMS |  | Visual Inspection |  | This ITP signed |  |  | HP* | Project / Site Engineer Site Supervisor
1.3 |  |  | Equipment | Prior to Commencing works |  | All plant and equipment to be used in the constructed of the works must be deemed acceptable to use by the Principal’s Representative. |  |  | Huesker HaTelit C Specifications 1.4.1 |  | Site Inspection |  | This ITP signed |  |  | HP | Project / Site Engineer Site Supervisor Principal’s Representative
2 |  |  | Materials
2.1 |  |  | Tack Coat Material Acceptance | Prior to commencing works, not less than 10 days prior to commencement of delivery |  | Proposed tack coat material and test certificates shall be submitted to the Principal’s Representative for review. |  |  | Huesker HaTelit C Specifications 1.10.1 |  | Verify |  | Aconex Corresponde nce |  |  | HP | Project / Site Engineer Principal’s Representative
2.2 |  |  | HaTelit C Material Acceptance | Prior to commencing works, not less than 20 days prior to scheduled commencement of application |  | Information on proposed HaTelit C manufacturer and test certificates to be submitted to the Principal’s Representative. |  |  | Huesker HaTelit C Specifications 1.10.2 |  | Verify |  | Aconex Corresponde nce |  |  | HP | Project / Site Engineer Principal’s Representative
3 |  |  | Surface Preparation & Tack Coat
3.1 |  |  | Surface Preparation | Prior to Works |  | All loose and foreign materials must be removed from the surfaces to a distance not less than 150 mm beyond the edge of the area to be tack-coated All treatments within area to be tack coated to be inspected by the Principal’s Representative. |  |  | Huesker HaTelit C Specifications 1.6.1 |  | Site Inspection |  | This ITP signed |  |  | HP | Project / Site Engineer Principal’s Representative
3.2 |  |  | Spraying of Tack Coat | Each Shift |  | The tack coat shall be sprayed evenly at the required spray rate of 0.4 - 0.55 L/m2 to achieve target residual bitumen as per guide. Rate may be adjusted based on site-specific conditions ensuring HaTelit C is bonded to underlying surface. |  |  | Huesker HaTelit C Specifications 1.6.2 |  | Visual Inspection |  | This ITP signed |  |  | IP | Project / Site Engineer Site Supervisor
4 |  |  | Placement
4.1 |  |  | Prior to placing HaTelit | Each Shift |  | A minimum of 48 hours’ notice shall be given to the Principal’s Representative prior to the commencement of placing the HaTelit. |  |  | Huesker HaTelit C Specifications 1.7.3 |  | Visual Inspection |  | This ITP signed |  |  | WP | Project / Site Engineer Principal’s Representative
4.2 |  |  | HaTelit installation | Each Shift |  | HaTelit to be installed to Manufacturers Specification. Where placing multiple rolls, an overlap of 250mm transversely and 150mm longitudinally is required. The overlaps shall be treated with tack coat and rolled to bond to one another. For small areas, manual installation is acceptable provided a fully flat and crease free installation is achieved. |  |  | Huesker HaTelit C Specifications 1.7.2 |  | Visual Inspection |  | This ITP signed |  |  | HP* | Project / Site Engineer Principal’s Representative
4.3 |  |  | HaTelit Rolling | Each Run |  | Rolls applied to tack coated surface without wrinkles, creases and folds. HaTelit to be rolled with 2 passes using pneumatic tyred rollers following application. |  |  | Huesker HaTelit C Specifications 1.7.3 |  | Verify |  | This ITP signed |  |  | HP* | Project / Site Engineer Site Supervisor
4.4 |  |  | Surface Finish Inspection | Each Shift |  | Installed HaTelit surface to be inspected and areas recorded where required for flatness and saturation. Surface to be free from any loose or deleterious material. |  |  | Huesker HaTelit C Specifications 1.7.3 |  | Visual Inspection |  | This ITP signed |  |  | WP | Project / Site Engineer Principal’s Representative
4.5 |  |  | Spring Balance Adhesion Testing | 1 every 50 to 150m2 |  | Test locations to show adequate bond between HaTelit and tack coated surface. |  |  | Huesker HaTelit C Specifications 1.7.4 |  | Test Point |  | This ITP signed |  |  | WP | Project / Site Engineer Principal’s Representative
4.6 |  |  | Asphalt paving over HaTelit | Each Shift |  | Ensure that the surface of the installed HaTelit and the underlying asphalt layer is dry, clean, undamaged and free from loose material until the completion of paving over the installed HaTelit. |  |  | Huesker HaTelit C Specifications 1.7.5 |  | Visual Inspection |  | This ITP signed |  |  | IP | Project / Site Engineer Site Supervisor
5 |  |  | Quality Assurance
5.1 |  |  | HaTelit Surface Conformance | Each Lot |  | The Contractor shall assess the conformance of the surface flatness and saturation of the installed HaTelit surface |  |  | Huesker HaTelit C Specifications 1.12.1 |  | Survey Report & Visual Inspection |  | This ITP signed |  |  | HP | Project / Site Engineer Principal’s Representative
5.2 |  |  | Nonconforming HaTelit Lot areas | Each Lot |  | If required, any sections deemed nonconforming shall be removed and replaced according to Manufacturer’s Specifications - FH NCR Procedure to be adopted when lot area is deemed nonconforming. |  |  | Huesker HaTelit C Specifications 1.13.1 |  | Visual Inspection |  | Nonconform ance Report |  |  | HP | Project / Site Engineer Principal’s Representative
[7 empty] | Inspection and Test Plan – Control and Supervision of the Works | [12 empty] | Doc ID: FH-ZU2-QU-ITP022 Rev: 0
Principal’s: Melbourne Airport (APAM) | [9 empty] | Contract No: CP14038 | [7 empty] | Prepared By: Abdul Saad
Project: Taxiway Zulu 2.0 | [13 empty] | Reviewed By: Faiyaaz Ahmed | [6 empty] | Date: 16/09/2024
Construction Process: HaTelit C Placement | [13 empty] | Approved By: Angela Julianto | [6 empty] | Date: 16/09/2024
Specifications: ZULU-BECA-001-SPC-00002 - Revision C04 (07 June 2024)
Structure / Component: HaTelit C
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
|  | HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent | [6 empty] | IP | Inspection point |  |  |  | Formal Inspection to be done and recorded
|  | HP* | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
|  | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent | [6 empty] | SCP | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
|  | AP | Approval Point |  | Written or verbal approval given by the Superintendent
Notes