## Table 1
[7 empty] | Inspection and Test Plan - Control and Supervision of the Works | [13 empty] | Doc ID: FH-ZU2-QU-ITP023 Rev: 1
Client: Melbourne Airport (APAM) | [8 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Abdul Saad
Project: Taxiway Zulu 2.0 | [14 empty] | Reviewed By: Angela Julianto | [7 empty] | Date: 08/07/2024
Construction Process: RBB Joint Sealing | [14 empty] | Approved By: Angela Julianto | [7 empty] | Date: 16/09/2024
Specifications: ZULU-BECA-001-SPC-00002 – Revision C04 (07 June 2024)
Structure / Component: Joint Sealing in Bituminous Pavements
Lot No: Lot Details: Lot size/Quantity: Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [12 empty] | HP / WP/ AP / IP/ TP / SCP |  |  | Responsibility |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  |  |  |  | Reference Documents |  | Inspection/ Test Method | Record of Conformity | [7 empty] | Principal’s Representative |  |  | Fulton Hogan | Date
1 |  | Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
1.1 |  | Check for correct documentation |  | Prior to commencing works |  | Current revision drawing is being used including the Subcontractor’s copy. Current revision to be obtained via Aconex. |  |  |  |  | Current Revisions in Aconex or ACC |  | Visual inspection | This ITP signed |  |  | HP* |  |  | Project / Site Engineer
1.2 |  | Implementation of all measures and controls |  | Prior to commencing works |  | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS. |  |  |  |  | PSP, EMP, TMP, SWMS, WMS |  | Visual Inspection | This ITP signed |  |  | HP* |  |  | Project / Site Engineer
1.3 |  | Definition of the work area |  | Prior to commencing works |  | Work area has been cleared and surveyed (marked on site). Limits of work clearly defined. |  |  |  |  | Drawings |  | Visual Inspection | This ITP signed |  |  | HP* |  |  | Project / Site Engineer
2 |  | Materials
2.1 |  | Rubberised Bituminous Sealant |  | Prior to commencing any activity |  | RBB must be a proprietary polymer modified bitumen (PMB) crack and joint bandage product and have the following properties: - Minimum softening point to be 95°C - Penetration at 25°C between 20 and 50 - Flow at 60°C at 5 hours to be maximum 5mm - Viscosity at 180°C to be maximum 3Pa.s |  |  |  |  | Beca Spec 002 – 10.7 |  | Verify | Manufacturer’s Datasheet |  |  | HP* |  |  | Project / Site Engineer |  | BecaCPL-GCOR-001062
2.2 |  | Material Sources – Conformance Test Certificates/Reports |  | Prior to commencing works |  | Test certificates and matching production batch numbers are to be provided for each product used |  |  |  |  | Beca Spec 002 – 10.7 |  | Test Certificates | Aconex Reference |  |  | HP* |  |  | Project / Site Engineer
3 |  | Sealing
3.1 |  | Applying Sealant |  | During joint sealing works |  | Sealant bandage is to be between 50mm and 75mm wide or as per drawings. |  |  |  |  | Beca Spec 002 – 10.7 |  | Visual Inspection | This ITP signed |  |  | IP |  |  | Project / Site Engineer
3.2 |  | Protection of Applied Sealant |  | During joint sealing works |  | Installed sealant must be protected from damage by traffic (and possible pick up on construction vehicles and aircraft tyres) until it has cooled to ambient temperature. |  |  |  |  | Beca Spec 002 – 10.7 |  | Visual Inspection | This ITP signed |  |  | IP |  |  | Project / Site Engineer
3.3 |  | Cleaning up |  | After sealing works |  | Any sealant split on surface of pavements must be cleaned off immediately. |  |  |  |  | Beca Spec 002 – 10.7 |  | Visual Inspection | This ITP signed |  |  | IP |  |  | Project / Site Engineer
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [13 empty] | Doc ID: FH-ZU2-QU-ITP023 Rev: 1
| Client: Melbourne Airport (APAM) | [8 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Abdul Saad
| Project: Taxiway Zulu 2.0 | [13 empty] | Reviewed By: Angela Julianto | [8 empty] | Date: 08/07/2024
| Construction Process: RBB Joint Sealing | [13 empty] | Approved By: Angela Julianto | [8 empty] | Date: 16/09/2024
Specifications: ZULU-BECA-001-SPC-00002 – Revision C04 (07 June 2024)
Structure / Component: Joint Sealing in Bituminous Pavements
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent | [6 empty] | IP Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point |  | An inspection which must be witnessed by the Superintendent | [6 empty] | SCP Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point |  | Written or verbal approval given by the Superintendent