## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP015 - High Early Strength Lean Concrete Placement | itp |  |  |  |  | FH-ZU2-QU-ITP015 - High Early Strength Lean Concrete Placement - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex, ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Plant and equipment items used in the Works shall be appropriate for the intended purpose and shall be maintained in good and serviceable condition at all times during which they are operating.
label | Reference Documents - Beca Spec 002 13.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
section | 2.0 - Production and Construction Trials
checkpoint | 2.1 - Mix Design
label | Frequency - Prior to works
label | Acceptance Criteria - Theoretical mix design and preliminary trial mix results to be submitted to the Principal’s Representative for review and acceptance prior to full trial mixing.
label | Reference Documents - Beca Spec 002 13.5.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed / test reports
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Mix Design Report
label | Frequency - Prior to works
label | Acceptance Criteria - The theoretical mix design and preliminary trial mix results to be submitted not less than seven (7) working days prior to full trial mixing.
label | Reference Documents - Beca Spec 002 13.5.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed / test reports
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Mixer Uniformity Test
label | Frequency - Prior to works
label | Acceptance Criteria - Mixer uniformity tests shall be undertaken on the fully operational mixing plant at least seven (7) days prior to undertaking production trial and submitted to the Principal’s Representative.
label | Reference Documents - Beca Spec 002 13.6.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.4 - Production Trial
label | Frequency - Prior to works
label | Acceptance Criteria - A production trial must be completed as per the requirements in the specification.
label | ○ The results and control procedures to be presented for review and approval by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 13.6.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Compliance
label | Frequency - Prior to works
label | Acceptance Criteria - Provide evidence to Principal’s Representative of concrete supplier demonstrating compliance to AS 1379 or is a third party accredited to AS 1379.
label | Reference Documents - Beca Spec 002 13.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed / evidence documents
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Pre-Placement Activities
checkpoint | 3.3 - Surface preparation
label | Frequency - Prior to works
label | Acceptance Criteria - The surface must be clean and inspected by the Principal’s Representative prior to placing.
label | Reference Documents - Beca Spec 002 13.8.1.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Weather Conditions
label | Frequency - Prior to commencing works
label | Acceptance Criteria - HESLC shall not be placed when the shade temperature is below 5°C or above 35°C.
label | Reference Documents - Beca Spec 002 13.15
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
section | 4.0 - Placing Concrete
checkpoint | 4.1 - Place, Spread and Compact Concrete
label | Frequency - After completion of works
label | Acceptance Criteria - Compaction of HESLC shall commence immediately after placing and shall be by internal vibration.
label | Reference Documents - Beca Spec 002 13.10
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 4.2 - Slump
label | Frequency - 1 test every 2 trucks
label | Acceptance Criteria - 100mm +/- 20mm
label | Reference Documents - Beca Spec 002
label | Inspection/Test Method - AS 1012.3.1
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.3 - Temperature
label | Frequency - 1 test every 2 trucks
label | Acceptance Criteria - Minimum 10°C Maximum 30°C
label | Reference Documents - Beca Spec 002 13.15
label | Inspection/Test Method - AS 1012.3.1
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.4 - Density of Cylinders
label | Frequency - 6 cylinders per Lot (same cylinders used for compressive strength)
label | Acceptance Criteria - Results for information only. To be used to determine density of cores.
label | Reference Documents - Beca Spec 002 13.17.3.6
label | Inspection/Test Method - AS
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.4 - Compressive Strength (7-day)
label | Frequency - 4 cylinders per Lot (same cylinders used for Density)
label | Acceptance Criteria - Mean of the 4 cylinders to be minimum 10MPa and maximum 15MPa.
label | Reference Documents - Beca Spec 002 13.5.1, 13.17.3.6
label | Inspection/Test Method - AS 1012.1, AS 1012.8, AS 1012.9
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 4.5 - Compressive Strength (28-day)
label | Frequency - 2 cylinders per Lot (same cylinders used for Density)
label | Acceptance Criteria - Each sample to be minimum 20MPa.
label | Reference Documents - Beca Spec 002 13.17.3.6
label | Inspection/Test Method - AS 1012.1, AS 1012.8, AS 1012.9
label | Record of conformity - NATA Test Certificate
label | TP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
section | 5.0 - Post-Placement
checkpoint | 5.1 - Construction Joints
label | Frequency - Each Concrete Pour
label | Acceptance Criteria - At the end of the day’s works, the HESLC to be feathered out and cut back before work restarts to give a straight, vertical face for full depth of layer.
label | ○ Edges of construction joints shall be painted or sprayed with bituminous emulsion.
label | Reference Documents - Beca Spec 002 13.11.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Saw Cut Joints
label | Frequency - Each Concrete Pour
label | Acceptance Criteria - HESLC to be sawcut into maximum slab spacing of 5m x 5m. Where pavement width is less than 5m the spacing shall be reduced to obtain slab dimension ratio of maximum 1:1.25.
label | ○ Sawcut to be approximately one third of the layer depth.
label | Reference Documents - Beca Spec 002 13.11.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.3 - Layer Thickness
label | Frequency - Each Concrete Pour
label | Acceptance Criteria - Finished surface of the HESLC to be picked up by a surveyor to determine the thickness of the layer.
label | Reference Documents - Beca Spec 002 13.17.3.4
label | Inspection/Test Method - Verify
label | Record of conformity - Survey Report
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Core Analysis – Density
label | Frequency - Refer to markup in notes section
label | ○ Aconex: BecaCPL- GCOR- 001038
label | Acceptance Criteria - Cores shall be 120mm diameter.
label | ○ Calculate the field density by comparing the density of individual cores with the average density of four (4) compressive strength cylinders taken.
label | ○ Field density to be not less than 98%. If the density is less than 98% then a Hold Point to be raised for the nonconforming Lot.
label | Reference Documents - Beca Spec 002 13.10.1, 13.17.3.6
label | Inspection/Test Method - AS 1012.12
label | Record of conformity - NATA Test Certificate
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Testing Records
label | Frequency - During works
label | Acceptance Criteria - Within three (3) weeks of completion of the Works, the Contractor shall supply two (2) copies of a report detailing the results of all quality control and testing undertaken.
label | Reference Documents - Beca Spec 002 13.17.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Protection of Layer
label | Frequency - Prior to placing subsequent layer
label | Acceptance Criteria - The Contractor shall protect the HESLC from damage until surface layers are placed. The layer shall not be covered by any further pavement layers under it has been accepted by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 13.16
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Removal and Replacement of Defective Pavement Areas
label | Frequency - After completion of works
label | Acceptance Criteria - If required, defective pavement areas shall be removed and replaced as specified herein with pavements of thickness and quality required by the specifications.
label | Reference Documents - Beca Spec 002 13.13
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP022 - Hatelit Install | itp |  |  |  |  | FH-ZU2-QU-ITP022 - Hatelit Install - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex, ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Equipment
label | Frequency - Prior to Commencing works
label | Acceptance Criteria - All plant and equipment to be used in the constructed of the works must be deemed acceptable to use by the Principal’s Representative.
label | Reference Documents - Huesker HaTelit C Specifications 1.4.1
label | Inspection/Test Method - Site Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Site Supervisor, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Materials
checkpoint | 2.1 - Tack Coat Material Acceptance
label | Frequency - Prior to commencing works, not less than 10 days prior to commencement of delivery
label | Acceptance Criteria - Proposed tack coat material and test certificates shall be submitted to the Principal’s Representative for review.
label | Reference Documents - Huesker HaTelit C Specifications 1.10.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Corresponde nce
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - HaTelit C Material Acceptance
label | Frequency - Prior to commencing works, not less than 20 days prior to scheduled commencement of application
label | Acceptance Criteria - Information on proposed HaTelit C manufacturer and test certificates to be submitted to the Principal’s Representative.
label | Reference Documents - Huesker HaTelit C Specifications 1.10.2
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Corresponde nce
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Surface Preparation & Tack Coat
checkpoint | 3.1 - Surface Preparation
label | Frequency - Prior to Works
label | Acceptance Criteria - All loose and foreign materials must be removed from the surfaces to a distance not less than 150 mm beyond the edge of the area to be tack-coated
label | ○ All treatments within area to be tack coated to be inspected by the Principal’s Representative.
label | Reference Documents - Huesker HaTelit C Specifications 1.6.1
label | Inspection/Test Method - Site Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Spraying of Tack Coat
label | Frequency - Each Shift
label | Acceptance Criteria - The tack coat shall be sprayed evenly at the required spray rate of 0.4 - 0.55 L/m2 to achieve target residual bitumen as per guide.
label | ○ Rate may be adjusted based on site-specific conditions ensuring HaTelit C is bonded to underlying surface.
label | Reference Documents - Huesker HaTelit C Specifications 1.6.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
section | 4.0 - Placement
checkpoint | 4.1 - Prior to placing HaTelit
label | Frequency - Each Shift
label | Acceptance Criteria - A minimum of 48 hours’ notice shall be given to the Principal’s Representative prior to the commencement of placing the HaTelit.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.3
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 4.2 - HaTelit installation
label | Frequency - Each Shift
label | Acceptance Criteria - HaTelit to be installed to Manufacturers Specification. Where placing multiple rolls, an overlap of 250mm transversely and 150mm longitudinally is required. The overlaps shall be treated with tack coat and rolled to bond to one another. For small areas, manual installation is acceptable provided a fully flat and crease free installation is achieved.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.2
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 4.3 - HaTelit Rolling
label | Frequency - Each Run
label | Acceptance Criteria - Rolls applied to tack coated surface without wrinkles, creases and folds. HaTelit to be rolled with 2 passes using pneumatic tyred rollers following application.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 4.4 - Surface Finish Inspection
label | Frequency - Each Shift
label | Acceptance Criteria - Installed HaTelit surface to be inspected and areas recorded where required for flatness and saturation.
label | ○ Surface to be free from any loose or deleterious material.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.3
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 4.5 - Spring Balance Adhesion Testing
label | Frequency - 1 every 50 to 150m2
label | Acceptance Criteria - Test locations to show adequate bond between HaTelit and tack coated surface.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.4
label | Inspection/Test Method - Test Point
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 4.6 - Asphalt paving over HaTelit
label | Frequency - Each Shift
label | Acceptance Criteria - Ensure that the surface of the installed HaTelit and the underlying asphalt layer is dry, clean, undamaged and free from loose material until the completion of paving over the installed HaTelit.
label | Reference Documents - Huesker HaTelit C Specifications 1.7.5
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
section | 5.0 - Quality Assurance
checkpoint | 5.1 - HaTelit Surface Conformance
label | Frequency - Each Lot
label | Acceptance Criteria - The Contractor shall assess the conformance of the surface flatness and saturation of the installed HaTelit surface
label | Reference Documents - Huesker HaTelit C Specifications 1.12.1
label | Inspection/Test Method - Survey Report & Visual Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Nonconforming HaTelit Lot areas
label | Frequency - Each Lot
label | Acceptance Criteria - If required, any sections deemed nonconforming shall be removed and replaced according to Manufacturer’s Specifications - FH NCR Procedure to be adopted when lot area is deemed nonconforming.
label | Reference Documents - Huesker HaTelit C Specifications 1.13.1
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - Nonconform ance Report
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP044 - AGL Luminaires | itp |  |  |  |  | FH-ZU2-QU-ITP044 - AGL Luminaires - Rev 0
section | 1.0 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents - IFC Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activities
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - Site and office Inspection
label | HP*
label | Responsibility - Project Engineer / Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Material/equipment approvals
label | Frequency - Prior to start
label | Acceptance Criteria - All materials shall be proven to meet contractual requirements prior to acceptance.
label | – MAGS shall be from ATG Airfield guidance signs range
label | – Taxiway centre lights shall be
label | – from the ADB Safegate range only
label | – Runway guard lights shall be from ADB Safegate only.
label | – Intermediate hold position lights shall be from the ADB Safegate range only
label | – Stop Bar Lights shall be from the ADB Safegate
label | – IWDI shall be from ALS
label | ○ Any deviation from the above suppliers shall be submitted to the Contract Administrator for approval prior to ordering.
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl 2.3
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference(s)
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.4 - Setting out for airfield luminaires
label | Frequency - Each Lot
label | Acceptance Criteria - HOLD POINT
label | ○ The Contractor shall survey the proposed light locations in conjunction with the new and existing line-marking to set out the proposed lights. A schedule of the proposed lights shall be produced and submitted to the Contract Administrator.
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl 5.4
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference
label | HP
label | Responsibility - Project Engineer / Beca
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Installation of AGL Luminaires
checkpoint | 2.1 - Elevated Light Installation
label | Frequency - Each Lot
label | Acceptance Criteria - Components of elevated lights shall:
label | – Be less than 360mm above the pavement level including the frangible coupling.
label | – Be suitable for installation on a threaded connection when installed.
label | Reference Documents - ZULU-BECA-001-SPC-00003 Cl 4.4.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 2.2 - Inset Light Installation
label | Frequency - Each Lot
label | Acceptance Criteria - Components of inset lights shall:
label | – Be less than 13mm height above the surrounding surface.
label | – Have a slope of surface of the unit to be less than 20 degrees (not including any recesses).
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl 4.4.4.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, ADBSG Installation of Inset Light Fittings checklist
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 2.3 - Series Isolation Transformer (SIT)
label | Frequency - Each Lot
label | Acceptance Criteria - SITs shall be installed in specified deep base cans or pits
label | Reference Documents - ZULU-BECA-001-SPC-00003 Cl 4.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, ADBSG Installation of Series Isolating Transformer (SIT)
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 2.4 - Luminaire Circuit
label | Frequency - Each lot
label | Acceptance Criteria - Each luminaire fitting shall be installed on the appropriate circuit as specified in the AGL schedule.
label | Reference Documents - ZULU-BECA-024-DWG-09001-16
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, As-Built Documentation
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
section | 3.0 - Post Construction
checkpoint | 3.1 - As-Built
label | Frequency - Each lot
label | Acceptance Criteria - Submission of surveyed luminaire position to superintendent prior to practical completion
label | Reference Documents - WP-001-09
label | Inspection/Test Method - Verify
label | Record of conformity - SCP
label | SCP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: