## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP012 - High Early Strength Lean Concrete Pavement Production | itp |  |  |  |  | FH-ZU2-QU-ITP012 - High Early Strength Lean Concrete Pavement Production - Rev 0
section | 1) Plant
checkpoint | 1.1 - Batch tolerances
label | Code / Spec Ref - AS1379 4.2.1
label | Acceptance Criteria - AS1379 Table 4.1
label | Frequency - Each Batch
label | Initiated by - PS
label | Approved by - PS
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Electronic
label | Record Location - Batch computer
date | Date Completed:
checkpoint | 1.2 - Record Plant Malfunctions
label | Code / Spec Ref - HOL QMS PN6.1
label | Acceptance Criteria - All plant mulfunctions are to be documented
label | Frequency - Each Time
label | Initiated by - PS
label | Approved by - AOM
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Register
label | Record Location - AOM office
date | Date Completed:
checkpoint | 1.3 - Weigh Hopper (Cem & Agg)
label | Code / Spec Ref - AS1379.3.3.2
label | Test / inspection method - AS1379
label | Acceptance Criteria - ± 0.4% of the Max. Scale Value
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Calibration Report
label | Record Location - Google
date | Date Completed:
checkpoint | 1.4 - Water Meters (Plant, Slump Stands & Trucks)
label | Code / Spec Ref - AS1379.3.4.2
label | Test / inspection method - TRBE652973
label | Acceptance Criteria - ± 2%
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Calibration Report
label | Record Location - Google
date | Date Completed:
checkpoint | 1.5 - Admixtures
label | Code / Spec Ref - AS1379.3.4.2
label | Test / inspection method - BASF TM033
label | Acceptance Criteria - ± 5%
label | Frequency - VicRoads Min. 3 Monthly
label | Initiated by - PS
label | Approved by - AOM
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Calibration Report
label | Record Location - Google
date | Date Completed:
section | 2) Cementitous materials
checkpoint | 2.1 - Type GP cement
label | Code / Spec Ref - AS1379.2.2
label | Test / inspection method - AS2350
label | Acceptance Criteria - AS3972 Table 2
label | Frequency - Cement Australia Supplied (as per AS3972 Clause 5.2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company - H
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Reference Sample
label | Code / Spec Ref - BECA Cl 11.4.7, 11.24.5
label | Frequency - Plant Sample : 10kg / 1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier -
label | Verification / witness: Company - W
label | Verifying document - Record only
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 2.2 - Flyash
label | Code / Spec Ref - AS1379.2.2
label | Test / inspection method - AS3583
label | Acceptance Criteria - AS/NZS3582.1 Table 1 - Grade 1
label | Frequency - Cement Australia Supplied (as per AS/NZS3582.1 Table 2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company - H
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Slag
label | Code / Spec Ref - AS1379.2.2
label | Test / inspection method - AS3583
label | Acceptance Criteria - AS3582.2 Table 1
label | Frequency - Cement Australia Supplied (as per AS3582.2 Table 2)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company - H
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3) Coarse Aggregate
checkpoint | 3.1 - Particle Size Distribution
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.11.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.2 - Flakiness Index
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.15
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per month
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.3 - Particle Density & Water Absorbtion
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.6.1, AS1141.5
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 3 months
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.4 - Los Angeles Abrasion Index Value
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.23
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.5 - Weak Particles
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.32
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.6 - Wet/Dry Strength Variation
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.22, AS2758.7
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.7 - Petrographic Analysis
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - ASTM C295
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 2 years
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.8 - Sodium Sulphate Soundness
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.24
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 3.9 - Reference Sample
label | Code / Spec Ref - BECA Cl 11.4.6.2
label | Frequency - Once Only : 2 x 25kg samples of each coarse aggregate fraction
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier -
label | Verification / witness: Company - W
label | Verifying document - Record only
label | Record Location - Tech Mgr office
date | Date Completed:
section | 4) Fine Aggregate
checkpoint | 4.1 - Particle Size Distribution
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS 1141.11.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.2 - Sodium Sulphate Soundness
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.24
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.3 - Particle Density & Water Absorbtion
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.6.1, AS1141.5
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 3 months
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.4 - Petrographic Analysis
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - ASTM C295
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per 2 years
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.5 - Sugar Content
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.35
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.6 - Clay & Fine Silts
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.33
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1/1000 tonnes
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.7 - Organic Impurities
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1141.34
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per month
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.8 - pH Value
label | Code / Spec Ref - AS1379.2.3
label | Test / inspection method - AS1289.4.3.1
label | Acceptance Criteria - AS1379.2.3
label | Frequency - 1 per year
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 4.9 - Reference Sample
label | Code / Spec Ref - BECA Cl 11.4.6.2
label | Frequency - Once Only : 2 x 25kg samples of fine aggregate
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier -
label | Verification / witness: Company - W
label | Verifying document - Record only
label | Record Location - Tech Mgr office
date | Date Completed:
section | 5) Water
checkpoint | 5.1 - Mains water
label | Code / Spec Ref - AS1379.2.4
label | Acceptance Criteria - Main complies
label | Frequency - Nil
label | Verification / witness: Supplier -
label | Verification / witness: Company -
date | Date Completed:
checkpoint | 5.2 - Non mains water
label | ~ Sugar
label | ~ Oil & grease
label | ~ pH
label | ~ Chlorides
label | ~ Sulfates
label | ~ Total suspended solids
label | Code / Spec Ref - AS1379.2.4
label | Test / inspection method - AS1141.35 APHA 5520 AS1580.505.1
label | Acceptance Criteria - 100 mg/L max
label | ○ 50 mg/L max
label | ○ > 5
label | ○ 500 mg/L max
label | ○ 500 mg/L max
label | ○ 2000 mg/L max
label | Frequency - 1 / 6 months
label | Initiated by - AOM
label | Approved by - Tech Mgr
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Lab report
label | Record Location - Tech Mgr office
date | Date Completed:
section | 6) Admixtures
checkpoint | 6.1 - WR Admixture general acceptance
label | Code / Spec Ref - AS1379.2.5
label | Test / inspection method - AS1478.2
label | Acceptance Criteria - AS1478.1 Table 2.1
label | Frequency - Initial
label | Initiated by - Tech Mgr
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 6.2 - WR Admixture Uniformity test
label | Code / Spec Ref - AS1379.2.5
label | Test / inspection method - AS1478.2
label | Acceptance Criteria - AS1478 Cl 2.1.3 [Supplier specs for pH (+/- 1), Relative density (+/- 0.02), Non-volitle content (+/- 2%)]
label | Frequency - MBCC Supplied (Each Batch)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Test Reports
label | Record Location - Plant
date | Date Completed:
checkpoint | 6.3 - AEA Admixture general acceptance
label | Code / Spec Ref - AS1379.2.5
label | Test / inspection method - AS1478.2
label | Acceptance Criteria - AS1478.1 Table 2.1
label | Frequency - Initial
label | Initiated by - Tech Mgr
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Supplier report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | 6.4 - AEA Admixture Uniformity test
label | Code / Spec Ref - AS1379.2.5
label | Test / inspection method - AS1478.2
label | Acceptance Criteria - AS1478 Cl 2.2.3 [Supplier specs for pH (+/- 1), Relative density (+/- 0.01), Non-volitle content (+/- 1%)]
label | Frequency - MBCC Supplied (Each Batch)
label | Initiated by - Supplier
label | Approved by - Tech Mgr
label | Verification / witness: Supplier - W, R
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Test Reports
label | Record Location - Plant
date | Date Completed:
section | 7) Transport
checkpoint | 7.1 - Agitator blade inspection
label | Code / Spec Ref - HOL QMS PN6.1
label | Acceptance Criteria - Concrete Barrel Solution - No excess buildup, No excess wear
label | Frequency - 1 / 3 months
label | Initiated by - PS
label | Approved by - AOM
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Inspection report
label | Record Location - Plant
date | Date Completed:
checkpoint | 7.2 - Mixer uniformity test
label | Code / Spec Ref - AS1379 3.5.1 (a)
label | Test / inspection method - AS1012
label | Acceptance Criteria - AS1379 Appendix A Table A1
label | Frequency - Initial for agi type
label | Initiated by - Trans
label | Approved by - Tech Mgr
label | Verification / witness: Supplier -
label | Verification / witness: HOL - W
label | Verification / witness: Company -
label | Verifying document - Manufacturer report HOL test report
label | Record Location - Tech Mgr office
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: