## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP019 - Spray Seal Placement | itp |  |  |  |  | FH-ZU2-QU-ITP019 - Spray Seal Placement - Rev 1
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for Correct Documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All equipment shall comply with VicRoads Section 408 and VicRoads Bituminous Sprayed Surfacing Manual.
label | Reference Documents - Beca Spec 002 - 12.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Materials
checkpoint | 2.1 - Material Approval
label | Frequency - Prior to Works
label | Acceptance Criteria - The binder used shall be class 170 residual bitumen complying with AS 2008.
label | ○ All aggregates used shall comply with VicRoads section 801 and 831. Material and Test Reports to be submitted to the Principal’s Representative prior to commencement of works.
label | Reference Documents - Beca Spec 002 - 12.6.1.1 to 12.6.1.3
label | Inspection/Test Method - Verify
label | Record of conformity - Test Reports, This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
label | Principal’s Representative - DCWC Mgt-GCOR-009596
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Construction
checkpoint | 3.1 - Underlying Surface
label | Frequency - Prior to works
label | Acceptance Criteria - The pavement surface should be cleaned to remove all mud, carried on material, dirt and dust.
label | ○ After cleaning the surface should be swept with a suction sweeper, supplemented by hand brooms where required. Seal coat should only be applied to a sound clean dry surface.
label | ○ Preparation of the underlying surface shall be approved by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 - 12.4.1 to 12.4.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Binder and Aggregate Application
label | Frequency - During works
label | Acceptance Criteria - Application rates shall be:
label | ○ Binder: 0.8 – 1.2 L/m2
label | Refer Aconex: DCWC Mgt-RTRFI- 001272
label | ○ Aggregate: 8 – 10 kg/m2
label | Reference Documents - Beca Spec 002 - 12.6.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Aggregate Spreading
label | Frequency - During works
label | Acceptance Criteria - All aggregate spreading shall be undertaken using forward aggregate spreading and discharge plant.
label | Reference Documents - VicRoads Section 408 – 408.13(e) to 408.13(f)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.4 - Rolling of Aggregate
label | Frequency - During Works
label | Acceptance Criteria - Rolling of aggregate shall be undertaken over the full width of the pavement being sealed. Works to be undertaken by static rubber tyred rollers or otherwise approved by the Principal’s Representative.
label | Reference Documents - VicRoads Section 408 – 408.13(g)
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.5 - Removal of Loose Aggregate
label | Frequency - During Works
label | Acceptance Criteria - At completion of sprayed seal treatment, the Contractor shall remove and dispose of all loose aggregate.
label | Reference Documents - VicRoads Section 408 – 408.14
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP020 - Prime Coat | itp |  |  |  |  | FH-ZU2-QU-ITP020 - Prime Coat - Rev 1
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications, permits as required for excavation and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall provide equipment for heating and uniformly applying the bituminous material and blotter material.
label | ○ The bitumen distributor shall comply with the requirements of NAS 70: ‘Bitumen Sprayers’
label | Reference Documents - Beca Spec 002 - 7.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.4 - Weather Conditions
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Prime coat shall not be applied on a wet surface, or when the surface temperature is below 10°C, or when the weather conditions would prevent the proper application or adhesion of the prime coat
label | Reference Documents - Beca Spec 002 - 7.9
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Materials
checkpoint | 2.1 - Cut-back Bitumen
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Cut-back bitumen for prime coat shall comply with AS 2157 and shall be class AMC0, AMC00 or AMC1.
label | Reference Documents - Beca Spec 002 – 7.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.2 - Cutter
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The cutter for use in cutback bitumen shall be a suitable petroleum-based material complying with the requirement of AS 3569.
label | Reference Documents - Beca Spec 002 – 7.4.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.3 - Bitumen Emulsion
label | Frequency - Prior to commencing works
label | Acceptance Criteria - If directed by the Principal’s Representative, bitumen emulsion complying to AS 1160 shall be used as a prime coat.
label | Reference Documents - Beca Spec 002 – 7.4.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
label | Principal’s Representative - BecaCPL-GCOR-001036
checkpoint | 2.4 - Blinding Sand
label | Frequency - Prior to commencing works
label | Acceptance Criteria - If required, blinding sand to be used for absorbing excess primer shall comply with the following PSD.
label | – – – – – – – – –
label | AS Sieve Size (mm) ¦¦ Percent Passing Sieve by Mass
label | – – – – – – – – –
label | 6.7 ¦¦ 100
label | 4.75 ¦¦ 85-100
label | 1.18 ¦¦ 40-100
label | 0.425 ¦¦ 10-50
label | 0.075 ¦¦ 0-5
label | – – – – – – – – –
label | Reference Documents - Beca Spec 002 – 7.4.5
label | Inspection/Test Method - Verify
label | Record of conformity - Test Report
label | TP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 2.5 - Test Certificates
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The Contractor shall submit a Test Certificate for each material proposed for use in the Works indicating compliance of those materials with the properties or requirements specified.
label | Reference Documents - Beca Spec 002 – 7.11.2
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
label | Principal’s Representative - BecaCPL-GCOR-000967
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Construction
checkpoint | 3.1 - Trial Application
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A trial application, to be conducted as part of permanent works, shall be conducted on an area of the Works agreed and witnessed by the Principal’s Representative
label | Reference Documents - Beca Spec 002 – 7.5
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.2 - Surface Preparation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Immediately before applying the prime coat, the full width of the surface to be primed shall be swept to removal all loose dirt and material. The prepared surface is to be inspected by the Principal’s Representative.
label | Reference Documents - Beca Spec 002 – 7.6
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Application of Bituminous Material
label | Frequency - During works
label | Acceptance Criteria - The prime coat shall be applied at a uniform rate and shall be between 1.0 and 1.4 litres/m². The depth of penetration shall be a minimum of 6mm and maximum of 10mm
label | Reference Documents - Beca Spec 002 - 7.7.1
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.4 - Job Samples
label | Frequency - During works
label | Acceptance Criteria - Samples of each bituminous material shall be obtained from the delivery vehicle at not less than one sample per 10,000 litres of bituminous material sprayed.
label | Reference Documents - Beca Spec 002 – 7.11.3
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.5 - Spray Rates
label | Frequency - During works
label | Acceptance Criteria - The Contractor shall submit records of spray application rates at completion of each mobilisation
label | Reference Documents - Beca Spec 002 - 7.11.4
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP023 - RBB Install | itp |  |  |  |  | FH-ZU2-QU-ITP023 - RBB Install - Rev 1
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision drawing is being used including the Subcontractor’s copy.
label | ○ Current revision to be obtained via Aconex.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS.
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.3 - Definition of the work area
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of work clearly defined.
label | Reference Documents - Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 2.0 - Materials
checkpoint | 2.1 - Rubberised Bituminous Sealant
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - RBB must be a proprietary polymer modified bitumen (PMB) crack and joint bandage product and have the following properties:
label | – Minimum softening point to be 95°C
label | – Penetration at 25°C between 20 and 50
label | – Flow at 60°C at 5 hours to be maximum 5mm
label | – Viscosity at 180°C to be maximum 3Pa.s
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Verify
label | Record of conformity - Manufacturer’s Datasheet
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
label | Principal’s Representative - BecaCPL-GCOR-001062
checkpoint | 2.2 - Material Sources – Conformance Test Certificates/Reports
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Test certificates and matching production batch numbers are to be provided for each product used
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Test Certificates
label | Record of conformity - Aconex Reference
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 3.0 - Sealing
checkpoint | 3.1 - Applying Sealant
label | Frequency - During joint sealing works
label | Acceptance Criteria - Sealant bandage is to be between 50mm and 75mm wide or as per drawings.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Protection of Applied Sealant
label | Frequency - During joint sealing works
label | Acceptance Criteria - Installed sealant must be protected from damage by traffic (and possible pick up on construction vehicles and aircraft tyres) until it has cooled to ambient temperature.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 3.3 - Cleaning up
label | Frequency - After sealing works
label | Acceptance Criteria - Any sealant split on surface of pavements must be cleaned off immediately.
label | Reference Documents - Beca Spec 002 – 10.7
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: