## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | SYM-ITP-019 - CLADDING (Rev A) |  |  |  |  | Yes | SYM-ITP-019 - CLADDING (Rev A) | 13a2340d-4ee1-410f-8f3a-5c2c7e6e58dc
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Has the structure been surveyed, including any fixing inserts, before commencement?
checkpoint-status |  |  | checkpoint | • Is the structure clear of dirt and blemishes?
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 7211fece-f1e2-5986-aa51-2e1e8dbd332b |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 8a35aeca-1321-5d1b-9fb5-183f4b2be5e1 |  | textbox | • Zone Reference
text | d809d8da-086f-5fc5-aa04-3548581f60c4 |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 3.0 Installation
checkpoint-status |  |  | checkpoint | • Have stone cladding fixings been provided as required, sufficient to support, restrain and resist the structural design loads on each cladding panel, as specified?
checkpoint-status |  |  | checkpoint | • Have adhesives been applied where required, as specified?
checkpoint-status |  |  | checkpoint | • Has cladding been installed as described in specification, considering given tolerances?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d3864764-396b-5b26-9196-36790ad03a52 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 41abf612-842b-5df3-af1c-b846125a98fb |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-001 - Subgrade (Rev A) |  |  |  |  | Yes | SYM-ITP-001 - Subgrade (Rev A) | 179aece3-74fc-4a9a-ad70-9bbacfbe0e91
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-no-status |  |  | checkpoint | • What is the lot size? Maximum lot size = 1 days production or 4000m2 (Attach markup if Available)
text | 66aa066e-618a-5a61-82e3-e4d8bc2470f1 |  | textbox | Lot Size
checkpoint-status |  |  | checkpoint | • Has the work area been set out for line and level?
checkpoint-status |  |  | checkpoint | • Has the material being excavated been inspected with category agreed upon by Superintendent?
checkpoint-status |  |  | checkpoint | •Attach Imported material test report (If Available)
checkpoint-status |  |  | checkpoint | •Is Material Approved By CYP D&C JV
checkpoint-status |  |  | checkpoint | • Attach latest IFC Drawings
checkpoint-status |  |  | checkpoint | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
text | 9857bb6b-e569-5c41-8197-139ef540183d |  | textbox | • Zone Reference
text | 01ca2151-c719-5265-8235-671f408caca5 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | •Is the area in cut / fill / both?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | a1663f75-23ff-5775-bb7f-15f2900d0320 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | a193fa1d-5350-5645-8e1b-4936c067bee9 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Bulk earthworks - cut
checkpoint-status |  |  | checkpoint | • Has the cut surface been trimmed to an even surface free from loose material?
checkpoint-status |  |  | checkpoint | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action.
checkpoint-status |  |  | checkpoint | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
checkpoint-status |  |  | checkpoint | • Has all approvals to proceed acquired?
checkpoint-status |  |  | checkpoint | • Is Dewatering permit Completed (if applicable)
checkpoint-status |  |  | checkpoint | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
checkpoint-status |  |  | checkpoint | • Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard? AttaTest reports (If required).
checkpoint-status |  |  | checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
checkpoint-status |  |  | checkpoint | • Complete Proof roll report, attach or add to lot.
text | 69ab4abf-0134-5ded-bf9f-d2e110ed2d86 |  | textbox | • What quantity of soft, wet or unstable material is present?
checkpoint-status |  |  | checkpoint | • Attach Survey report of area
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to the Superintendent for review?
text | 45eb6c11-eb56-5782-824d-e14911119568 |  | textbox | • What was the rectification process used?
checkpoint-status |  |  | checkpoint | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water.
checkpoint-status |  |  | checkpoint | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 2b5ac0ff-327f-5a2e-9fbb-7b72dac340f4 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 26618230-777a-5c7a-bf39-bbd4d738963b |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Bulk earthworks - fill
checkpoint-status |  |  | checkpoint | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
checkpoint-status |  |  | checkpoint | •Attach fill Material test report.
checkpoint-status |  |  | checkpoint | • Complete Proof roll report, attach or add to lot.
text | 6ff152e8-39a7-5ddb-a2c9-a1daf2194958 |  | textbox | • What quantity of soft, wet or unstable material is present?
checkpoint-status |  |  | checkpoint | • Attach Survey report of the area of works.
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to the Superintendent for review? (If Required).
checkpoint-status |  |  | checkpoint | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
checkpoint-status |  |  | checkpoint | • Has fill been placed in maximum 200mm compacted layer thickness?
checkpoint-status |  |  | checkpoint | • Attach as built report of the area of works.
checkpoint-status |  |  | checkpoint | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction? Attach Test Report
checkpoint-status |  |  | checkpoint | • Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard? Attach Test Report
checkpoint-status |  |  | checkpoint | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041?
checkpoint-status |  |  | checkpoint | •Confirm If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested (Attach Test Reports)
checkpoint-status |  |  | checkpoint | • Does the layer withstand test rolling without visible deformation or springing?
text | 0ad1635f-226c-5d16-a94d-1a20fa4d91c7 |  | textbox | • What quantity of soft, wet or unstable material is present?
checkpoint-status |  |  | checkpoint | • Attach Survey report of area
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 8e6e33af-7eab-5061-a5bf-8e73e2c245e2 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 1d0187b8-400a-569a-8ea7-91fa29edf0f0 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Conformance check
checkpoint-status |  |  | checkpoint | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
checkpoint-status |  |  | checkpoint | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
checkpoint-status |  |  | checkpoint | • Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
checkpoint-status |  |  | checkpoint | • Attach as built report
checkpoint-status |  |  | checkpoint | • All Test reports received and reviewed.
label | 7329f7e6-e924-558e-8dba-19beeb566606 |  | note | • NATA Endorsed Test Reports
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
label | 4ac0d293-326f-5b1b-9872-15dffdf43935 |  | note | • Completed NCR form
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9b603fab-6625-5a40-a031-16abf1490a47 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 1f2881a9-94cf-52c2-9b1d-eddc68765099 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-018 - Public Lighting (Rev A) |  |  |  |  | Yes | SYM-ITP-018 - Public Lighting (Rev A) | 18e38c9c-e4f6-432d-b8c7-6516dbed5eec
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the lot been defined and marked up on lot map?
checkpoint-status |  |  | checkpoint | • Has the work area been set out as per IFC drawings?
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | b37faa27-9f1c-5225-8208-643b42b6f6d3 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 27fb5956-fd19-540f-8b65-17e1deeb3355 |  | textbox | • Zone Reference
text | 0e3b6fce-297c-5b80-8324-53afc2adc19b |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 2.0 Public lighting Installation
checkpoint-status |  |  | checkpoint | • Has the public lighting been constructed in accordance with the IFC Drawings?
checkpoint-status |  |  | checkpoint | • Has the public lighting passed all commissioning and testing?
checkpoint-status |  |  | checkpoint | • Powercor inspection & approval provided?
checkpoint-status |  |  | checkpoint | • Attach Subcontractor ITP's
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 3736061a-82b0-5347-91c2-e51b692b0259 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2137e5f9-f851-5a40-92f2-a35bf9872f0c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Conformance check
checkpoint-status |  |  | checkpoint | • All Test reports and as builts received and reviewed? Attach Test reports
checkpoint-status |  |  | checkpoint | • Attach As-builts
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checkpoint-status |  |  | checkpoint | • Completed NCR form
checklist-sectioned |  |  | checklist | SYM-ITP-011 - LANDSCAPING (Rev A) |  |  |  |  | Yes | SYM-ITP-011 - LANDSCAPING (Rev A) | 193623b7-64e5-479b-b3b6-6f57a6f7b639
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
text | d0db377c-a34a-53c2-bd0e-8598458c9916 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 1d990ff7-cfec-523a-9611-c926b70bf8ba |  | textbox | • Zone Reference
text | 44e2b280-9995-5c2b-b07c-b4f514158aef |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
label | 1d423441-a81a-5cc5-a5e0-b4ff17cf79ff |  | note | • Test results to be provided prior to bulk deliveries
checkpoint-status |  |  | checkpoint | • Have all plants been set out in garden beds prior to planting?
checkpoint-status |  |  | checkpoint | • Has cultivation of sub-grade been undertaken as specified?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d975ef72-f727-5a0c-aae6-8adb02208ade |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 36352786-ec83-57e2-a40d-15c9aa7cdc19 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 - Installation of imported topsoil / subsoil / structural soil
checkpoint-status |  |  | checkpoint | • Has topsoil been placed in the manner specified, alongside to the depth specified in detail on drawing set?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | ec10dec6-f4bc-53fc-aeab-a932b6516284 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | f3c1be0d-746e-52ff-bad9-e5997a4c691e |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 - Installation of imported organic / inorganic mulch
checkpoint-status |  |  | checkpoint | • Has mulch been placed in the manner specified, alongside to the depth specified in detail on drawing set?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 57d7eafa-f0a9-5840-8603-58896c8e76b5 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 08e50800-187e-530a-ab19-8b30ad20a031 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 - Installation of edging
checkpoint-status |  |  | checkpoint | • Has edging been placed in the manner specified, referencing both design standards, drawing details and manufacturers recommendations (where relevant)?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 95e5300e-fc58-5f33-80e7-d1c18c37256f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2cce89d7-c9c9-546d-9a39-d8899a972354 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 - Installation of plants
checkpoint-status |  |  | checkpoint | • Have all plants been placed / installed as per project specifications and drawings?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9437066e-b044-526f-90bf-b7d2cfbf1cfe |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | bee7c52a-350e-552f-b69b-4c4ea778aa9a |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 6.0 - Installation of turf
checkpoint-status |  |  | checkpoint | • Has turf been installed as per method described in section 3.17 ‘turfing’?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | ea65dbde-e519-5995-8760-242115621e65 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | a5bb78c9-e659-58f6-b965-d3e2ca487dd6 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | SYM-ITP-024 - Handrails & Balustrades (Rev A) |  |  |  |  | Yes | SYM-ITP-024 - Handrails & Balustrades (Rev A) | 409767f7-5366-4d5d-8eae-d4f79239921e
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | 2c1e2af2-114f-5bc2-bef0-06b1a584f684 |  | textbox | • Handrail/Balustrade Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 0178a06d-005d-50c6-8f3b-fd2ce4547e34 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 77a20862-c30b-5c04-91ca-e81bd7d8e5eb |  | textbox | • Zone Reference
text | 311b55d7-d3c3-5cc9-b656-e4d5092314fc |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? Attach completed Permit
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • Are handrails and Balustrades compliant with DDA standards.
checkpoint-status |  |  | checkpoint | • Have the subcontractor ITP’s been completed and attached
checkpoint-status |  |  | checkpoint | • Have handrail and Balustrades been installed as per approved shop drawings?
checkpoint-status |  |  | checkpoint | • All edges smoothed and final finish provided as per project specs?
checkpoint-status |  |  | checkpoint | • Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | • Attach survey Report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 5f5e84c7-ffeb-52d2-bf94-75b9f4fa43c7 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | e6fba20f-287b-555d-a6bd-0a3d95025e6b |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-021 - Precast Concrete Elements (Rev A) |  |  |  |  | Yes | SYM-ITP-021 - Precast Concrete Elements (Rev A) | 52dbd8d3-4ff6-4db8-9a54-921c78be5d4c
checkpoint-group |  |  | section | 1.0 Preliminaries, Pre-delivery
checkpoint-status |  |  | checkpoint | • Has the pre-pour check been completed by manufacturer?
checkpoint-status |  |  | checkpoint | • Has the certificate of compliance been completed? Attach certificate of compliance.
checkpoint-status |  |  | checkpoint | • Attach Precast element Supplier ITP (If applicable)
checkpoint-status |  |  | checkpoint | • Has the concrete reached its 28-day compressive strength Prior to Transport and not transported before 7 days after casting?
checkpoint-status |  |  | checkpoint | • Any defects (Cracks, chips, honeycomb etc) identified? (Attach Pictures of Element)
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 8bf10114-c9b2-5b5e-b300-e8a063741853 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | bbd909a6-0607-52ac-8a19-082eead5c166 |  | textbox | • Zone Reference
text | c97722d0-7e80-5386-8970-48f6fc8499ea |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 2.0 Installation of Precast Element
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
checkpoint-status |  |  | checkpoint | • Has survey set out points identified and existing condition of location checked to ensure suitability of install.
checkpoint-status |  |  | checkpoint | • Has the Precast element been constructed in accordance with the IFC drawings?
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b29d1dcb-f135-519e-95b3-fedfe3c9c416 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 7c43022c-c926-565b-97d9-222aa9196fdc |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Document Upload Checklist |  |  |  |  | Yes | Document Upload Checklist | 53059a19-6c3d-4269-9379-28c3e49a2d77
checkpoint-status |  |  | checkpoint | Document uploaded below
checklist-sectioned |  |  | checklist | SYM-ITP-016 - Gross Pollutant Trap & Diversion Structure PV-GPT-2 (RevA) |  |  |  |  | Yes | SYM-ITP-016 - Gross Pollutant Trap & Diversion Structure PV-GPT-2 (RevA) | 542a610f-f151-410b-9458-4042ed3b5018
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Prepare the excavation for the Vortceptor separation chamber first.
checkpoint-status |  |  | checkpoint | • Did the excavation for the Diversion Chamber (the rectangular precast concrete chamber) follow afterwards the Vortceptor.
checkpoint-status |  |  | checkpoint | • Was the inlet pipe run would installed, within one or two pipe lengths prior to the diversion chamber.
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? Attach Completed Permits.
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
checkpoint-status |  |  | checkpoint | • Attach manufacturer Installation manual
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 1c595598-232d-513e-9199-2d987bb1ac92 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 52b030a4-ded7-5cf3-b2fd-dbf31ed44dce |  | textbox | • Zone Reference
text | a00ac345-ccec-53ff-9b98-93e021198669 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e2b6cbad-d2dd-5b0a-bc5a-f1627d9be1f5 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | e91de99c-7e58-5d7b-b56b-6de4311d764c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Vortceptor Installation
checkpoint-status |  |  | checkpoint | • Were measurements checked on the Vortceptor prior to installation, and confirmed as per approved IFC
checkpoint-status |  |  | checkpoint | • The Vortceptor excavation should be no greater than required, this would be 1000mm oversized or to suit shield sizing. This is with due regard to the amount of backfill to be used under and around the tank.
checkpoint-status |  |  | checkpoint | • Were 150mm thick, compacted base of either a concrete blinding or compacted crushed rock layer installed.
checkpoint-status |  |  | checkpoint | • Was the Vortceptor lowered into the excavation with no rocks or sharp objects falling into the hole and no damage to the tank
checkpoint-status |  |  | checkpoint | • Were the levels of the Vortceptor adjusted to suit pipeworks and diversion chamber inlet void?
checkpoint-status |  |  | checkpoint | • Fill the tank with water up to the invert of the inlet
checkpoint-status |  |  | checkpoint | • Encase & backfill the outside of Vortceptor as per project backfilling specs
checkpoint-status |  |  | checkpoint | • Is the take located in an area subject to high water table or trapped underground water?
checkpoint-status |  |  | checkpoint | • If yes, the tank must be completely encased in unreinforced concrete, up to the specified height above the Vortceptor base, and at the minimum specified width beyond the perimeter of the Vortceptor base. Refer to SPEL Stormwater for recommended concrete dimensions and volumes to withstand buoyancy forces.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 3.0 - Diversion Chamber Installation
checkpoint-status |  |  | checkpoint | • Were measurements checked on the Diversion Chamber prior to installation, and confirmed as per approved IFC
checkpoint-status |  |  | checkpoint | • Has the diversion chamber excavation pit been prepared as per Construction drawings
checkpoint-status |  |  | checkpoint | • Is sufficient room left to install inlet pipe and pipe is angled to be fed into the diversion chamber?
checkpoint-status |  |  | checkpoint | • Was the Diversion Chamber adjusted to a correct level so the rectangular opening matches the Vortceptor with the inlet and outlet block outs are to match the drainage line.
checkpoint-status |  |  | checkpoint | • Use the template provided with the Vortceptor to drill the bolt holes into the diversion chamber rectangular void.
checkpoint-status |  |  | checkpoint | • Use Sikaflex or silicone to seal the Vortceptor to the Diversion Chamber, use 8.5mm 4 cutter SDS bit to drill the bolt holes.
checkpoint-status |  |  | checkpoint | • Use M8 x 100mm Galvanised screw bolts to fix the Vortceptor to the Diversion Chamber.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | aea3127e-411f-565d-993e-707a01a2a5f0 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 164c3614-2702-526e-b280-16f2a75b0977 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 - Associated Drainage & Finishing Works.
checkpoint-status |  |  | checkpoint | • Were upstream and downstream drainage pipework Installed?
checkpoint-status |  |  | checkpoint | • Connect the pipework to the Diversion Chamber, concrete bandage the inlet and outlet pipes to the Diversion Chamber.
checkpoint-status |  |  | checkpoint | • Internally render the inlet and outlet pipework
checkpoint-status |  |  | checkpoint | • Use low slump concrete to mass infill and bench the base of the diversion chamber and weir. This is to direct the flow and remove any dead zones in the diversion chamber.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | ebf44a03-a57b-5909-91f3-34b47a21ab75 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d3ab1f1a-adaf-54b0-b0e0-e341d3c8fe78 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 - Cover Slab Installation
checkpoint-status |  |  | checkpoint | • Use a Sikaflex bead around the rebate on the top of the Diversion Chamber to ensure a satisfactory seal between cover slab (Lid) and chamber.
checkpoint-status |  |  | checkpoint | • Lift and install cover slab, ensure manhole void / cover is on Vortceptor side of the chamber.
checkpoint-status |  |  | checkpoint | • Use Sikaflex and screw bolts to secure fibreglass manhole riser to cover slab
checkpoint-status |  |  | checkpoint | • Tie in the manhole covers as per lid manufacturers installation guidelines, to achieve Finished Surface level.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 0928390f-6b6f-59dc-83a2-ca3678ee6c43 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8f24f6f5-71a9-5c93-9769-7258e1d0d43f |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-003 - Asphalt Placement 1 (Rev A) |  |  |  |  | Yes | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 578ae5f8-5649-4073-bea6-ceff71694f72
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-no-status |  |  | checkpoint | Details
text | c506f1ef-b383-5396-8449-6a6ed65a677f |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 5a409bdd-6ba9-5976-8afe-f22986cdf165 |  | textbox | • Zone Reference
text | bd64fec5-97bc-501d-8a58-e46003eb0314 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV?
label | 2a811c45-e956-5161-9257-3cd0bac36407 |  | note | • is the Mix Design Approved
checkpoint-status |  |  | checkpoint | • Has the previous layer passed acceptance criteria?
checkpoint-status |  |  | checkpoint | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater than 10 degrees Celsius. Has the above criteria been met?
checkpoint-status |  |  | checkpoint | • Have the existing pits been raised/lowered to meet the surface level of Asphalt?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d006bf66-0b41-5a9a-a3e6-65a0f08772b8 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 9251b352-3926-54ef-a204-0d5a768d8dbb |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Hot Mix Asphalt Installation
checkpoint-status |  |  | checkpoint | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
checkpoint-status |  |  | checkpoint | • All transverse joints shall be offset from layer to layer by at least 2 m.
checkpoint-status |  |  | checkpoint | • Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
checkpoint-status |  |  | checkpoint | • Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
checkpoint-status |  |  | checkpoint | • Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
label | f3fa4e76-3ce5-57a1-82d2-e01d27145ccf |  | note | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
checkpoint-status |  |  | checkpoint | • Does new Asphalt Layer match the existing pavement surface with chases cut?
label | 1e0b5deb-b894-588e-b6d0-e4120718bb38 |  | note | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified.
label | 12af3633-39b5-557f-8487-8dc7508db9df |  | note | • Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b20cc6cf-abe3-5a47-b9e1-9b63def23510 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | f888d0f5-655d-551f-b0b8-423553326a2c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Completion and Compliance
checkpoint-status |  |  | checkpoint | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
checkpoint-status |  |  | checkpoint | • Thickness > 50mm: 96.0% Characteristic Density Ratio
checkpoint-status |  |  | checkpoint | • Has testing been completed and report received? Do results match requirements?
checkpoint-status |  |  | checkpoint | • Attach NATA Test Report: Compaction Tests
checkpoint-status |  |  | checkpoint | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
checkpoint-status |  |  | checkpoint | • Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
checkpoint-status |  |  | checkpoint | • Is finished surface level acceptable and survey conformance report received? Attach Reports.
checkpoint-status |  |  | checkpoint | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
checkpoint-status |  |  | checkpoint | • Kerb & Channel - Flush or not more than 5mm above lip of channel
checkpoint-status |  |  | checkpoint | • Shape – For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively.
checkpoint-status |  |  | checkpoint | • Alignment - Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside.
checkpoint-status |  |  | checkpoint | • Width - Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 1beced25-e5cd-57a8-a29c-75056622d6fe |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 67182ea4-91ce-59bd-b905-c5699fb84398 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-012 - Stratavaults (Rev A) |  |  |  |  | Yes | SYM-ITP-012 - Stratavaults (Rev A) | 625dfbe1-ea0f-4af6-936c-cdc737ab3295
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • is the excavation for the Stratavaults as per specifications and drawings?
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? Attach completed permits.,
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings
text | 80f34cf9-a521-512a-b991-cf8350b762a6 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | c6f29d45-a1ad-5241-a93e-c89e868a4c7f |  | textbox | • Zone Reference
text | 49c4867c-0f82-5bd9-8853-6565bdeed2dc |  | textbox | • Stage Reference
text | d2981d86-db6e-5f77-a171-812ba934dcc3 |  | textbox | • Stratavault number
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 96289d34-fe9a-5b90-9298-6fc9020c046c |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | ae3f5fed-daa7-5ce9-8ebb-4e4b817b1617 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Stratavault Installation and soil testing
checkpoint-status |  |  | checkpoint | • Are all stratavaults installed as per manufacturer specifications
checkpoint-status |  |  | checkpoint | • Are all pipes extended for the startavault installed?
checkpoint-status |  |  | checkpoint | • Attach Supplier ITPs
checkpoint-status |  |  | checkpoint | • Attach manufacturer warranty
checkpoint-status |  |  | checkpoint | • Soil testing and sampling completed as per manufacturer specification
checkpoint-status |  |  | checkpoint | • Attach test report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 610de58e-4034-598d-8621-82411d62c95e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | feb6fae0-2271-5288-b2ea-649da5e022a3 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-013 - Retaining walls and wall footings (Rev A) |  |  |  |  | Yes | SYM-ITP-013 - Retaining walls and wall footings (Rev A) | 6a028896-cec7-475f-9e74-6c268fd4e74d
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Is Mix design approved prior to placement and material properties meet project specification, AS 3600, AS 1379.
text | 337448c0-b3fa-5533-8301-1f9dcb9852f5 |  | textbox | • Concrete Strength
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | 60f71b3c-05c9-5a32-8e33-75ae60e35180 |  | textbox | • Wall/Footing Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings
text | a6a097f9-488a-50d8-b8b2-a83db4407b23 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | e05d9ed7-77bc-52d3-99ea-ac171f3a3356 |  | textbox | • Zone Reference
text | c425fa31-40eb-5c60-9e8e-dbdb3646e60f |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? Attach Completed Permits.
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
text | 7e317ece-5e1a-5639-af93-abaeca70d81a |  | textbox | • Excavation to a total depth of
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e1fb8af5-4bcc-5989-b06e-6a8d23f6b785 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 27a36224-e32d-5ad9-8aff-f333f6044a3f |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Wall Footings Installation
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
checkpoint-status |  |  | checkpoint | • Formwork set out has been done as per latest design drawings and specifications
checkpoint-status |  |  | checkpoint | • Were Construction joints/Expansion Joints/Isolation Joints Installed
checkpoint-status |  |  | checkpoint | • Any Backfill/ Underlay Material as per drawings & specifications
checkpoint-status |  |  | checkpoint | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified
checkpoint-status |  |  | checkpoint | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval?
checkpoint-status |  |  | checkpoint | • Attach formwork design and approvals
checkpoint-status |  |  | checkpoint | • Reinforcement Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
checkpoint-status |  |  | checkpoint | • Steel is free of excess corrosion, loose millings, oil or other contaminants
checkpoint-status |  |  | checkpoint | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars
checkpoint-status |  |  | checkpoint | • Correct concrete cover and chairs on sides, bottom and top Verified
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
checkpoint-status |  |  | checkpoint | • Have tie bars and expansion joints been installed at the correct intervals?
checkpoint-status |  |  | checkpoint | • Pour area is free of loose debris, oils, water
checkpoint-status |  |  | checkpoint | • Have any services located within the slab been installed, surveyed and pinned down
checkpoint-status |  |  | checkpoint | • Concrete Testing Lab Representative will be available during concrete pour
checkpoint-status |  |  | checkpoint | • CYP D&C JV informed of concrete pour date and start time
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 3c5c3ac9-4be1-5e1f-b3c1-1a1f9cd411b3 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8f1f2690-10fb-5ded-b096-9b8c254e2767 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 - Wall Footings Concrete Placement
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials.
checkpoint-status |  |  | checkpoint | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
checkpoint-status |  |  | checkpoint | • Has a minimum of one of vibrator used at all times while the concreting is in operation
checkpoint-status |  |  | checkpoint | • Ensure monitoring forms/cast in items during the pour
checkpoint-status |  |  | checkpoint | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy
checkpoint-status |  |  | checkpoint | • Concrete Dockets Received, Attach last Docket
text | 58f4fbb3-ae6d-5052-908a-60b03646809b |  | textbox | • Pour date
text | 9868ecd6-0984-5dc6-9683-6d4c0237d6bb |  | textbox | •Total pour Concrete quantity
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 7f391253-b110-54e8-9f0f-3a59ff980930 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | b8c43646-0326-51bf-85fb-befcb66ddea4 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 - Wall Footings Post Pour
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork
checkpoint-status |  |  | checkpoint | • Any identified defects after striping rectified
checkpoint-status |  |  | checkpoint | • Attach Subcontractor’s QA
checkpoint-status |  |  | checkpoint | • Does Backfill material comply with Vicroad specs, Project specs and drawings?
label | e997910d-cb0b-51ec-9d98-7adf96ef7e8c |  | note | • Concrete Strength Report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 23d0fb8a-6ce9-5061-9f9a-7fa61c28fd1b |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | eb2534e2-1596-5acb-af74-6e233b455192 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 Wall Installation
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
checkpoint-status |  |  | checkpoint | • Formwork set out has been done as per latest design drawings and specifications
checkpoint-status |  |  | checkpoint | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
checkpoint-status |  |  | checkpoint | • Any Backfill/ Underlay Material as per drawings & specifications
checkpoint-status |  |  | checkpoint | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified
checkpoint-status |  |  | checkpoint | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval?
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
checkpoint-status |  |  | checkpoint | • Steel is free of excess corrosion, loose millings, oil or other contaminants
checkpoint-status |  |  | checkpoint | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars
checkpoint-status |  |  | checkpoint | • Correct concrete cover and chairs on sides, bottom and top Verified
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
checkpoint-status |  |  | checkpoint | • Have tie bars and expansion joints been installed at the correct intervals?
checkpoint-status |  |  | checkpoint | • Pour area is free of loose debris, oils, water
checkpoint-status |  |  | checkpoint | • Have any services located within the slab been installed, surveyed and pinned down
checkpoint-status |  |  | checkpoint | • Concrete Testing Lab Representative will be available during concrete pour
checkpoint-status |  |  | checkpoint | • CYP D&C JV informed of concrete pour date and start time
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | ce24f0df-7330-5e3d-955f-e8de20045c39 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 7663c43c-b635-5c66-9cbc-fc005a824cf3 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 6.0 - Wall Concrete Placement
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials.
checkpoint-status |  |  | checkpoint | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
checkpoint-status |  |  | checkpoint | • Has a minimum of one of vibrator used at all times while the concreting is in operation
checkpoint-status |  |  | checkpoint | • Ensure monitoring forms/cast in items during the pour
checkpoint-status |  |  | checkpoint | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy
checkpoint-status |  |  | checkpoint | • Concrete Dockets Received, Attach last Docket
text | 08d6824e-d1fc-50df-af55-165de83677d3 |  | textbox | • Pour date
text | 0d5fe759-0346-556f-9859-cda0c049cb8d |  | textbox | •Total pour Concrete quantity
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b64d5011-0459-57bc-aaf9-ebb4b3caeddf |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 0d34b4b7-ca2a-533e-afd8-eb6f7511bc3f |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 7.0 - Wall Post Pour
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork
checkpoint-status |  |  | checkpoint | • Any identified defects after striping rectified
checkpoint-status |  |  | checkpoint | • Attach Subcontractor’s QA
checkpoint-status |  |  | checkpoint | • Does Backfill material comply with Vicroad specs, Project specs and drawings?
checkpoint-status |  |  | checkpoint | • Were as Built completed? Attach report if applicable
checkpoint-status |  |  | checkpoint | • Attach Concrete Test Report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 6ef2de4f-a10a-517b-a3df-8867c884f81e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8f584c1c-0452-5a72-b25e-aa9374e168b4 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 8.0 -Wall Backfilling
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
checkpoint-status |  |  | checkpoint | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checklist-sectioned |  |  | checklist | SYM-ITP-006 - STORMWATER (Rev A) |  |  |  |  | Yes | SYM-ITP-006 - STORMWATER (Rev A) | 6ceafb34-bda7-4f77-8753-e4ca5018a12d
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-no-status |  |  | checkpoint | Details
text | e1fba68c-ea43-564d-9801-cdb3540f472b |  | textbox | • What is the lot size? ( Lot shall be defined from pit to pit (or endwall, where applicable). Specify Lot Details in Text.
text | 3bac7f94-1af7-5a31-a830-3a24378b67b0 |  | textbox | • Zone Reference
text | dc075436-5fde-5e55-aa8f-8378a96b8c47 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Do survey boundaries clearly define the Underground Drainage Construction works?
checkpoint-status |  |  | checkpoint | • Is the Box Culvert free of defects and to drawing dimensions?
checkpoint-status |  |  | checkpoint | • Is the Pipes free of defects and to drawing dimensions?
checkpoint-status |  |  | checkpoint | • Have proposed precast Covers, Grates, Lids and Pits been approved for use?
checkpoint-status |  |  | checkpoint | • Attach Shop Cards. (If Applicable)
checkpoint-status |  |  | checkpoint | • Is Bedding and Backfill Materials material free from perishable matter and lumps?
checkpoint-status |  |  | checkpoint | • Bedding and Backfill Material Conformance
text | 30b36323-9455-59cc-8e47-79eda6ef7254 |  | textbox | • Specify Pipe/Box Culvert/ Sizes & Classes
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 1de8297b-ee5b-54be-b937-94f7eac4db73 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 7968babe-a172-5e08-bc0c-9b0b39b1419c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Excavation and bedding
checkpoint-status |  |  | checkpoint | • Is the trench clearance width between 300mm to 600mm?
checkpoint-status |  |  | checkpoint | • Is the excavation at a sufficient depth for pipe/box culvert bedding?
checkpoint-status |  |  | checkpoint | • Is the pit excavation not less than 400mm from external pit wall to side of excavation?
checkpoint-status |  |  | checkpoint | • Is the excavation at a sufficient depth for pit bedding?
checkpoint-status |  |  | checkpoint | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed?
checkpoint-status |  |  | checkpoint | • Is the Pipe Diameter greater than 1500mm? If so, has 200mm of bedding been placed?
checkpoint-status |  |  | checkpoint | • Has bedding for pits been placed and compacted to a thickness not less than 80mm on clay foundation?
checkpoint-status |  |  | checkpoint | • Has bedding for pits been placed and compacted to a thickness not less than 150mm on a rock foundation?
checkpoint-status |  |  | checkpoint | • Bedding and Backfill Material Conformance
checkpoint-status |  |  | checkpoint | • Has bedding been compacted to refusal?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 8323b68d-3dff-586b-a76b-55630d24f27f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 06571c34-99ed-58b5-a407-a8716628c5e7 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Installation of Pipes
checkpoint-status |  |  | checkpoint | • Are pipes being laid from downstream end?
checkpoint-status |  |  | checkpoint | • Are socket ends of pipes being placed facing upstream and fully entered?
checkpoint-status |  |  | checkpoint | • Is the pipe in full contact with the bedding for the full length of each section?
label | e3bd2a88-15bc-576f-8682-50b8a6ead515 |  | note | • The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
checkpoint-status |  |  | checkpoint | • Are rubber rings to be used on rubber ring joint pipes clean and free of debris?
checkpoint-status |  |  | checkpoint | • Have all interlocking joint reinforced concrete pipes been jointed or wrapped with 200mm wide external joint rubber band? Has the rubber band been placed between the spigot and socket?
checkpoint-status |  |  | checkpoint | • Have pipes with lifting holes been placed with lifting holes uppermost? Have lifting holes been plugged after pipe installation?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 717e43a4-7e31-51ca-bda5-53873c45eac5 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 91a2bbdd-bc47-50ab-a713-548a35b0afef |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 - Installation of Pits
checkpoint-status |  |  | checkpoint | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
checkpoint-status |  |  | checkpoint | • Have subsurface drainage connections been cored at appropriate dimensions?
checkpoint-status |  |  | checkpoint | • Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier)
checkpoint-status |  |  | checkpoint | • Have pits greater than 1.0 meter been fitted with step irons?
checkpoint-status |  |  | checkpoint | • Step irons shall not obstruct openings or be fitted to a wall which has openings.
checkpoint-status |  |  | checkpoint | • Have step Irons shall be installed in accordance with the manufacturer’s instructions and are an approved proprietary type?
checkpoint-status |  |  | checkpoint | • Material Conformance Certificates
checkpoint-status |  |  | checkpoint | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
checkpoint-status |  |  | checkpoint | • Surfaces shall be finished uniform in appearance with a Class 2 surface finish in accordance with the Specifications.
checkpoint-status |  |  | checkpoint | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 332f6d88-d108-50f0-8e42-86b683c44a53 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 2c308814-868f-5a34-b222-92e153aaaaf7 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | 5.0- Fitting of Covers
checkpoint-no-status |  |  | checkpoint | Details
text | e2900888-509c-58ce-aa36-041d8e790d40 |  | textbox | Pit Downstream
text | d6712a29-25dc-5000-821f-d4ed1a611e8c |  | textbox | Pit Number
text | 3153d318-0f4f-5e9e-8024-c77986ad3f29 |  | textbox | Lid Class
text | 63b03f74-b16f-5bb4-aaa7-e245be2fb0f3 |  | textbox | Lid Type
checkpoint-no-status |  |  | checkpoint | Details
text | 463d137b-caec-5cfe-8889-34e04e06c830 |  | textbox | Pit Downstream
text | 69303317-2088-58db-b465-fd4ead74436e |  | textbox | Pit Number
text | 87ae71f8-6d22-5620-9b7e-9846b524d3c3 |  | textbox | Lid Class
text | 09b5060b-371b-53fa-9976-1a82aecf0f96 |  | textbox | Lid Type
checkpoint-status |  |  | checkpoint | • Attach Survey Conformance Report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | f2d81415-3ee3-5f6d-accc-bf44073217e1 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5cf06d84-f969-5224-9883-f18fff878f58 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 5.0 Installation of Box Culverts
checkpoint-status |  |  | checkpoint | • Have consecutive sections of box culverts been firmly butted together?
checkpoint-status |  |  | checkpoint | • Does the mortar have a minimum 28 day compressive strength of not less than 40MPa? Is it at least Type C Class?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e53f5bfb-7fbc-598d-9e8e-82518c564039 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 77734c61-fc34-58e6-91e2-7355968c8e96 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 6.0 - Backfill – Pipes/Culverts/Pits
checkpoint-status |  |  | checkpoint | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer.
checkpoint-status |  |  | checkpoint | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material?
checkpoint-status |  |  | checkpoint | • Is the pipe to be backfilled in under an area to be paved? If so, has excavation below design subgrade level been backfilled with select backfill material? And within the pavement layer backfilled with appropriate pavement material?
checkpoint-status |  |  | checkpoint | • Is the pipe to be backfilled in under an area not to be paved? If so, has the trench been backfilled with select backfill material to a level 0.3m above the top of the culvert? Ordinary backfill may be used above that level.
checkpoint-status |  |  | checkpoint | • Has the backfill material been backfilled in max 150mm layers?
checkpoint-status |  |  | checkpoint | NATA Test Report: Compaction
checkpoint-status |  |  | checkpoint | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | c06359a9-c631-5e0f-bf3f-9f2fa6f3e280 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 62160653-b01d-59bb-a1f4-d6cbe26eeab0 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 7.0 Completion
checkpoint-status |  |  | checkpoint | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design?
checkpoint-status |  |  | checkpoint | • Is the invert level of pipes at pipes ±50mm of design?
checkpoint-status |  |  | checkpoint | • Is the line of the pit cover been installed ±10mm of the design kerb line?
checkpoint-status |  |  | checkpoint | • Is the pit cover level ±10 mm of the design level for that point?
checkpoint-status |  |  | checkpoint | • Is the offset of entry pits within ±20 mm of kerbs/barriers?
checkpoint-status |  |  | checkpoint | • Is the offset of entry pits within ±20 mm of kerbs/barriers?
checkpoint-status |  |  | checkpoint | • Is the plan location of pits other than offsets to kerb lines or barriers ±100 mm?
checkpoint-status |  |  | checkpoint | • Survey Conformance Certificate
checkpoint-status |  |  | checkpoint | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction?
label | 646d6f8d-d43e-5a18-ae8e-251f58267a0b |  | note | • Attach Compaction Reports | Pass,Flag ,N/A
checkpoint-status |  |  | checkpoint | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement?
checkpoint-status |  |  | checkpoint | • Attach CCTV Inspection Report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | a4bd490a-7425-5810-9bde-ff8284d8c27e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 0d19b368-d890-54f4-83fd-7cdc3acfe0be |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-007 - Subsurface Drainage (Rev A) |  |  |  |  | Yes | SYM-ITP-007 - Subsurface Drainage (Rev A) | 816e5765-dd6d-45c4-9236-da7a2394feee
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-no-status |  |  | checkpoint | Details
text | d633e85f-376c-5a0b-a1fe-3a0801c7d9fb |  | textbox | • What is the lot size? Maximum Lot Size = per days production or Pit to Pit
text | ebf728d8-65da-5360-a684-923fe60c65d9 |  | textbox | • Zone Reference
text | 89875006-c786-5d15-b4a8-06f25172d2cc |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
checkpoint-status |  |  | checkpoint | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved?
checkpoint-status |  |  | checkpoint | • Has no fines concrete been used as a filter material?
checkpoint-status |  |  | checkpoint | • Has no fines concrete been placed and compacted within 1 hour of mixing?
checkpoint-status |  |  | checkpoint | • Is the subsurface drainage pipe or the geocomposite invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length.
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? (Attach completed Permits)
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
checkpoint-status |  |  | checkpoint | • Has the trench been excavated to allow 300mm between top of capping and top of subsoil pipe?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 8bfc205c-dd7a-5339-8ddf-e7e06d6ab49c |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 4efae99c-650a-53bc-82cc-989d0d0c2599 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 - subsurface Pipes (AG)
checkpoint-status |  |  | checkpoint | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs?
checkpoint-status |  |  | checkpoint | • Has the slotted pipe been placed centrally in the trench?
checkpoint-status |  |  | checkpoint | • Have plastic pipes been kept away from sunlight and undamaged during delivery and installation?
checkpoint-status |  |  | checkpoint | • Is the subsurface drainage pipe invert level not exceeding 25 mm from the specified level and not more than 50 mm from the specified line. With changes of grade not at a rate exceeding 10 mm in any 3 m length.
checkpoint-status |  |  | checkpoint | • Is the pipe grade not flatter than 1m in 250m?
checkpoint-status |  |  | checkpoint | • Attach Compliance Certificates.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | fc4a7e6f-31f0-5648-b58a-6b7a9d19dea2 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | d42f4485-d277-52a1-bafa-2db50d8e67ef |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 - Subsurface Geotextiles
checkpoint-status |  |  | checkpoint | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified?
checkpoint-status |  |  | checkpoint | • Has the geotextile been placed without punctures or tears?
checkpoint-status |  |  | checkpoint | • In expansive clays does the geotextile material extend to directly below the kerb line?
checkpoint-status |  |  | checkpoint | • is the Geotextile material supplied and installed as per latest IFC drawings and project specifications?
checkpoint-status |  |  | checkpoint | • Manufactures Compliance Certificates
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 4.0 - Subsurface Filter material
checkpoint-status |  |  | checkpoint | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls?
checkpoint-status |  |  | checkpoint | • Has no fines concrete ratios and specifications applied as per Table 702.051 and VR702.05(e)
checkpoint-status |  |  | checkpoint | • Has crushed rock/concrete ratios and specifications applied as per Table 702.052 and VR702.05(d)
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 5.0 - Access points
checkpoint-status |  |  | checkpoint | • Have access points installed at intervals of between 100m and 150 m?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 6.0 - Flushing
checkpoint-status |  |  | checkpoint | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checklist-sectioned |  |  | checklist | SYM-ITP-008 - Insitu Concrete Elements (Rev A) |  |  |  |  | Yes | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 8337c5ef-4d10-4637-8c0a-1549a353679b
checkpoint-group |  |  | section | 1.0 General Details
checkpoint-status |  |  | checkpoint | • Is Mix design approved prior to placement and material properties meet project specification, AS 3600, AS 1379.
text | cd240276-6531-5714-a6c9-43d9d6c1a563 |  | textbox | • Concrete Strength
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | dccf488d-b95a-5cb7-bafa-3356a5c2e565 |  | textbox | • What is the lot size?
text | d42501aa-3ab7-5e0e-9470-3ea008cdf937 |  | textbox | • Zone Reference
text | 734c493f-bb0e-5f89-9987-154d773023d6 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
text | e1d11645-1083-59d0-9483-a2280e0fce97 |  | textbox | • Element Description
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved? Attach completed Permit
checkpoint-status |  |  | checkpoint | • Extents and levels correct to relevant drawings
checkpoint-status |  |  | checkpoint | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
text | 229339c4-241b-5855-b8b5-141921c5531b |  | textbox | • what is the excavation depth?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 967b3516-efca-52e3-9c6e-2769f0209429 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 8207070f-346c-504c-814f-ead3b5786d89 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Insitu concrete Element Installation
checkpoint-status |  |  | checkpoint | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
checkpoint-status |  |  | checkpoint | • Has the surface shall be thoroughly moistened with water and excess surface water removed prior to placing concrete.
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
checkpoint-status |  |  | checkpoint | • Formwork set out has been done as per latest design drawings and specifications
checkpoint-status |  |  | checkpoint | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
checkpoint-status |  |  | checkpoint | • Any Backfill/ Underlay Material as per drawings & specifications
checkpoint-status |  |  | checkpoint | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified
checkpoint-status |  |  | checkpoint | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval?
checkpoint-status |  |  | checkpoint | • Attach formwork design and approvals
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
checkpoint-status |  |  | checkpoint | • Steel is free of excess corrosion, loose millings, oil or other contaminants
checkpoint-status |  |  | checkpoint | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars
checkpoint-status |  |  | checkpoint | • Correct concrete cover and chairs on sides, bottom and top Verified
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
checkpoint-status |  |  | checkpoint | • Have tie bars and expansion joints been installed at the correct intervals?
checkpoint-status |  |  | checkpoint | • Pour area is free of loose debris, oils, water
checkpoint-status |  |  | checkpoint | • Have any services located within the slab been installed, surveyed and pinned down
checkpoint-status |  |  | checkpoint | • Concrete Testing Lab Representative will be available during concrete pour
checkpoint-status |  |  | checkpoint | • CYP D&C JV informed of concrete pour date and start time
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9a83b447-68ea-5744-b673-e8b080f578e3 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 94170aa5-ff53-55a2-b477-cb5dfd6b7218 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 - Concrete Placement
checkpoint-status |  |  | checkpoint | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
checkpoint-status |  |  | checkpoint | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
checkpoint-status |  |  | checkpoint | • Has a minimum of one of vibrator used at all times while the concreting is in operation
checkpoint-status |  |  | checkpoint | • Ensure monitoring forms/cast in items during the pour
checkpoint-status |  |  | checkpoint | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy
checkpoint-status |  |  | checkpoint | • Concrete Dockets Received, Attach last Docket
text | 8d0157c7-1090-56da-a894-47d8f8e8b8c0 |  | textbox | • Pour date
text | f638ed7f-d4ec-5312-a6ed-18688c4eb402 |  | textbox | • Total pour Concrete quantity
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e351c124-bc3c-58e3-8b44-78cd9a26ca1c |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 40a73f87-9ae3-5f1e-bb16-cbb6f00bec1a |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 - Post Pour
checkpoint-status |  |  | checkpoint | • Was Curing agent applies as per project specifications
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork
checkpoint-status |  |  | checkpoint | • Any identified defects after striping rectified
checkpoint-status |  |  | checkpoint | • Attach Subcontractor’s QA
checkpoint-status |  |  | checkpoint | • Does Backfill material comply with Vicroad specs, Project specs and drawings?
checkpoint-status |  |  | checkpoint | • Were as Built completed? Attach report if applicable
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork. (Attach test results)
checkpoint-status |  |  | checkpoint | • Were expansion joints placed at intervals less than 10m.
checkpoint-status |  |  | checkpoint | • Attach concrete Test Report
checkpoint-status |  |  | checkpoint | • Attach As built report
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b3147c7d-a170-5e69-9d72-ec47757fcbe6 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | e2f1be72-110a-55a1-a76c-9b34b0cbb7e8 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.6 - Backfilling
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
checkpoint-status |  |  | checkpoint | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checklist-sectioned |  |  | checklist | SYM-ITP-017 - Traffic Signals (Rev A) |  |  |  |  | Yes | SYM-ITP-017 - Traffic Signals (Rev A) | 91013f82-3092-48db-904e-f8f2639f61d1
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the lot been defined and marked up on lot map?
checkpoint-status |  |  | checkpoint | • Has the work area been set out as per IFC drawings?
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 75a00de0-2465-5670-93ab-d592df729e37 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | b6c6c5b6-aca5-50eb-a079-19245265519a |  | textbox | • Zone Reference
text | 8cffeec4-8649-5b25-9e9b-a5ebfb5781f5 |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 2.0 Traffic Signals Installation
checkpoint-status |  |  | checkpoint | • Has signalised crossing been constructed in accordance with the IFC Drawings?
checkpoint-status |  |  | checkpoint | • Attach Subcontractor ITP's
checkpoint-status |  |  | checkpoint | • Has Signalised crossing passed all commissioning and testing?
checkpoint-status |  |  | checkpoint | • DOT inspection & approval provided?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 69ed2ddc-bee2-569f-b79f-386d98e0d0b0 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 0af9f5ae-acb3-5840-b648-278dad6ed057 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Conformance check
checkpoint-status |  |  | checkpoint | • All Test reports and as builts received and reviewed? Attach Test reports
checkpoint-status |  |  | checkpoint | • Attach As-builts
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checkpoint-status |  |  | checkpoint | • Completed NCR form
checklist-sectioned |  |  | checklist | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) |  |  |  |  | Yes | SYM-ITP-005 - Insitu Kerb and Channel (Rev A) | 958164a5-20ff-450f-8e66-73b0046b3761
checkpoint-group |  |  | section | 1.0 Pre-start activities
checkpoint-no-status |  |  | checkpoint | Details
text | 3e037ba4-3dce-5ac9-9945-95baeabc8486 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 3dca7124-1197-5eaa-b877-72ed9fd75630 |  | textbox | • Zone Reference
text | 0643d844-fd25-55ca-9ea3-0d71d0abf28b |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Concrete used in kerb extrusion machines shall have a minimum cementitious material content in the finished concrete as follows: ○ A minimum of 320 kg of cementitious material for traffic routes ○ A minimum of 280kg of cementitious material for local streets
checkpoint-status |  |  | checkpoint | • Concrete mix designs approved by CYP D&C JV?
checkpoint-status |  |  | checkpoint | • All works shall be set out in accordance with the drawings and as specified.
checkpoint-status |  |  | checkpoint | • The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 4d17c347-5b3f-5017-9090-0a6747837152 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 384d8f71-9961-5473-a6ea-79a6f6851f9f |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Construction
checkpoint-status |  |  | checkpoint | • Concrete shall be fed to the machine at a uniform rate. Surfaces shall be free from surface pitting larger than 5 mm diameter.
checkpoint-status |  |  | checkpoint | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. Transitions between different profiles shall be made in accordance with the drawings.
checkpoint-status |  |  | checkpoint | • Are the profile transitions acceptable?
checkpoint-status |  |  | checkpoint | • All edgings shall be rendered and have a steel trowel finish. Visible concrete surfaces to have class 3 finish. Hidden surfaces may have a class 4 finish.
checkpoint-status |  |  | checkpoint | • Is the surface finish acceptable?
checkpoint-status |  |  | checkpoint | • Transverse joints shall be constructed at regular intervals not exceeding 2.5 m. The resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces.
checkpoint-status |  |  | checkpoint | • Expansion joints shall be placed at junctions with bridges and shall be 15 mm wide and filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the edging.
checkpoint-status |  |  | checkpoint | • Are joints installed and comply with all specifications?
checkpoint-status |  |  | checkpoint | • Freshly finished exposed concrete surfaces shall be protected from rain or damage from other sources, until hard set has occurred.
checkpoint-status |  |  | checkpoint | • All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
checkpoint-status |  |  | checkpoint | • Are finished curbs protected and free from damage?
checkpoint-status |  |  | checkpoint | • For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be: (a) constructed on compacted bedding; (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections
checkpoint-status |  |  | checkpoint | • Attach Concrete Delivery Docket.
checkpoint-status |  |  | checkpoint | • Attach Concrete Test Report.
checkpoint-status |  |  | checkpoint | • Is all damage to Kerbs repaired in line with specifications? (If required)
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 53848633-f2c5-5388-a133-df9bb65f0841 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 019aac8f-1443-5a49-bdf3-a13af3eeb196 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Completion
checkpoint-status |  |  | checkpoint | • Concrete paving including footpaths, edgings, other surfaces and shared use paths shall be shaped to match existing fixtures, e.g. pit covers, edgings and vehicle crossings, within 5 mm.
checkpoint-status |  |  | checkpoint | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
checkpoint-status |  |  | checkpoint | • All Product Non-Conformance(s) recorded and closed (if applicable)
checkpoint-status |  |  | checkpoint | • Attach NCR reports
checklist-sectioned |  |  | checklist | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) |  |  |  |  | Yes | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) | b2a9380c-e80d-426f-8a5c-b60dc3ac5d56
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications
text | f928eef2-c61b-5a78-9001-1284f38ba633 |  | textbox | • Concrete Strength
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
checkpoint-status |  |  | checkpoint | • Is edging constructed over Pavement layer?
checkpoint-status |  |  | checkpoint | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
checkpoint-status |  |  | checkpoint | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise.
checkpoint-status |  |  | checkpoint | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise.
checkpoint-status |  |  | checkpoint | • Bedding shall be moist but shall have no free water on the surface before concrete is placed
checkpoint-status |  |  | checkpoint | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
checkpoint-status |  |  | checkpoint | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304.
checkpoint-status |  |  | checkpoint | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85%
checkpoint-status |  |  | checkpoint | • Is fill material used below bedding tested to Table Compaction Requirements
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
text | 5a671427-2622-556a-95d0-308c169be66d |  | textbox | • Excavation to a total depth of
text | 9338bc95-89b6-5476-9664-143023f85944 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 38dec746-1b48-5731-9406-1be9ba2fc694 |  | textbox | • Zone Reference
text | 6aa8e073-1af2-5369-9919-2bbe3d2a9669 |  | textbox | • Stage Reference
text | e12c6a99-8f25-5861-99bd-e29cd3c0bf70 |  | textbox | • What is the Sub-Base Course layer Thickness
text | 16d5ad7d-117a-5b1b-ac28-8cc0ec357cac |  | textbox | • what is the Class of crushed rock or crushed concrete placed?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 3bc219a1-4795-5be8-948e-f201056dfae2 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | c5d135a1-e1b8-57d4-99aa-0a0912207a4e |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Under screed/Concrete Pavement Installation
checkpoint-status |  |  | checkpoint | • Formwork has been installed correctly and sufficiently braced.
checkpoint-status |  |  | checkpoint | • Formwork set out has been done as per latest design drawings and specifications
checkpoint-status |  |  | checkpoint | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
checkpoint-status |  |  | checkpoint | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets
checkpoint-status |  |  | checkpoint | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover
checkpoint-status |  |  | checkpoint | • Tolerance - As per specifications and Australian Standard
checkpoint-status |  |  | checkpoint | • Steel is free of excess corrosion, loose millings, oil or other contaminants
checkpoint-status |  |  | checkpoint | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified
checkpoint-status |  |  | checkpoint | • Correct concrete cover and chairs on sides, bottom and top Verified
checkpoint-status |  |  | checkpoint | • Has steel reinforcement been placed correctly with adequate cover?
checkpoint-status |  |  | checkpoint | • Have tie bars and joints been installed at the correct intervals?
checkpoint-status |  |  | checkpoint | • Pour area is free of loose debris, oils, water
checkpoint-status |  |  | checkpoint | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down
checkpoint-status |  |  | checkpoint | • Concrete Testing Lab Representative will be available during concrete pour
checkpoint-status |  |  | checkpoint | • Sufficient vibrators are available during concrete pour
checkpoint-status |  |  | checkpoint | • CYP D&C JV informed of concrete pour date and start time
checkpoint-status |  |  | checkpoint | • Attach subcontractor ITPs
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 87519695-d50f-5128-95ed-609b13b7eb3e |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 7bb940ab-4c46-52ff-8b4c-f7eabef28c2a |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 - Placing, compacting and finishing concrete
checkpoint-status |  |  | checkpoint | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C.
checkpoint-status |  |  | checkpoint | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes.
checkpoint-status |  |  | checkpoint | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications
checkpoint-status |  |  | checkpoint | • Are concrete samples taken in accordance with 610.16(b).
checkpoint-status |  |  | checkpoint | • Is specified slump tolerance within 610.16(c).
checkpoint-status |  |  | checkpoint | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge.
checkpoint-status |  |  | checkpoint | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour
checkpoint-status |  |  | checkpoint | • A minimum of one of vibrator used at all times while the concreting is in operation
checkpoint-status |  |  | checkpoint | • Were forms/cast in items monitored during the pour.
checkpoint-status |  |  | checkpoint | • Concrete Dockets Received
text | 5c46f1da-11e3-5b23-9047-8aab40492b8a |  | textbox | • Concrete quantity
text | deb9ae55-0ca2-54eb-b46e-ef0a2f3000d7 |  | textbox | • Pour date
checkpoint-status |  |  | checkpoint | • Concrete Fall achieved as per latest IFC drawings
checkpoint-status |  |  | checkpoint | • Concrete pour record attached
checkpoint-status |  |  | checkpoint | • Concrete test results attached.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | fe22c762-062d-5e42-8dd6-938e37eb26dc |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 10924544-b308-5816-84ae-7fbf9ec2f0ab |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Post Pour/ Finishing
checkpoint-status |  |  | checkpoint | • Did concrete achieve the required finish as per specifications
checkpoint-status |  |  | checkpoint | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610.
checkpoint-status |  |  | checkpoint | • Curing agent applies as per project specifications
checkpoint-status |  |  | checkpoint | • Concrete reached design strength to strip formwork. (Attach test results)
checkpoint-status |  |  | checkpoint | • Any identified defects after stripping rectified
checkpoint-status |  |  | checkpoint | • Were expansion joints placed at intervals less than 10m.
checkpoint-status |  |  | checkpoint | • As Built Survey completed and report attached.
checkpoint-status |  |  | checkpoint | • Concrete test results attached.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-group |  |  | section | 5.0 - Backfilling
checkpoint-status |  |  | checkpoint | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
checkpoint-status |  |  | checkpoint | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checklist-flat |  |  | checklist | SYM-Proof Roll Record |  |  |  |  | Yes | SYM-Proof Roll Record | bbee9def-c005-4635-8b35-3e323c8d24a3
checkpoint-no-status |  |  | checkpoint | Details
text | fa50faab-eed8-5982-8ecd-eb113a0b4b76 |  | textbox | Lot ID:
text | 5fa62e1a-4915-5ed3-8415-0afa6a2b8834 |  | textbox | Stage/ Zone:
text | cec5b3ad-b9a6-508e-a00e-6d6e8b895d07 |  | textbox | Material Type:
text | 62b1bd6f-cb38-51bd-a9b0-43483e901261 |  | textbox | Plant/ Vehicle:
text | 5db54670-9023-5047-96ea-3b8154270b50 |  | textbox | Date:
text | cabb3314-0002-533b-950c-ccaad18068c3 |  | textbox | Road Name:
text | 8db7e848-0181-5906-acb9-057a1ce2e15b |  | textbox | Zone Reference:
text | 05ca693f-0478-510a-986d-af7c153b10dd |  | textbox | Stage Reference:
text | 40ad35ab-8bb1-56ad-9d9a-e0b9a50689ae |  | textbox | Layer Name:
text | 4c5d2043-5075-5602-bf0c-e2e5877bd7d1 |  | textbox | No. Passes:
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e3d4e33b-7582-5369-ae90-78362638118f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | a16a271f-091a-5c42-8b8e-4ec19cf2bc1c |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-020 - PAVING (Rev A) |  |  |  |  | Yes | SYM-ITP-020 - PAVING (Rev A) | bc0bf3ad-28b8-4bfb-960d-c07d1f02b845
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Have pavers been set-out as per current drawings?
checkpoint-status |  |  | checkpoint | • Is the concrete slab free of any deposits or rubbish, projections/voids?
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current? Attach IFC drawings& Manufacturer shop drawings
text | 16a53ceb-9d07-500c-9193-670d0b96892c |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | a23540f3-e49e-5af3-8d2f-91b43014130d |  | textbox | • Zone Reference
text | 112eb5aa-570b-5073-96ba-cc3c190e3c6c |  | textbox | • Stage Reference
checkpoint-group |  |  | section | 3.0 Paving Installation
checkpoint-status |  |  | checkpoint | • Has mortar been placed using type/method described in specification?
checkpoint-status |  |  | checkpoint | • Where required, have been pavers been cut as described in specification?
checkpoint-status |  |  | checkpoint | • Have pavers been laid as described in specification, considering specified tolerances?
checkpoint-status |  |  | checkpoint | • Have joints been sealed as described in specification?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | fd760f24-0223-5af9-a2a4-9406d9afe406 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 772326cf-3fe3-5fc1-911f-a7b49ca978ae |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-025 - Structural Soil (Rev A) |  |  |  |  | Yes | SYM-ITP-025 - Structural Soil (Rev A) | d02e7ff8-c8d2-4dd2-8ceb-9a09cb3a62a1
checkpoint-group |  |  | section | 1.0 Excavation and Setouts
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?
checkpoint-status |  |  | checkpoint | • Have all relevant samples been provided to CYP and approved?
checkpoint-status |  |  | checkpoint | • prepare the excavation for the Structural Soil (Setout) as per latest IFC drawings specified dimensions
checkpoint-status |  |  | checkpoint | • Were all identified underground services marked and potholed to confirm location and depth.
checkpoint-status |  |  | checkpoint | • Relevant permits have been signed and approved.
checkpoint-status |  |  | checkpoint | • Is the work area clearly pegged out for line and level?
text | 55dcc56e-7be8-5e83-aa62-9ea3a12be221 |  | textbox | • Zone Reference
text | f6e6033f-645c-5dbf-b339-1aa849a6c275 |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | d597ee62-c970-5c42-88a3-04dfe451520d |  | button | HOLD POINT - Signature by by CYP D&C JV | Yes,No
button | 60c52509-388f-58a4-a192-a15a4ba46b59 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Construction Activities
checkpoint-status |  |  | checkpoint | • Are all pipes extended for the structural Soil install?
checkpoint-status |  |  | checkpoint | • Granular layer installed as per drawings?
checkpoint-status |  |  | checkpoint | • Structural Soil fill completed as per specified levels and quantities.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 9d1e7031-a8fd-5635-9ee2-a2486343c597 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | e98c9752-408e-5548-9041-69e62319feb7 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-009 - TACTILES (Rev A) |  |  |  |  | Yes | SYM-ITP-009 - TACTILES (Rev A) | d201215e-cd8f-4797-a145-a01db6ecd9f0
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-no-status |  |  | checkpoint | Details
text | 011a9106-503a-561a-bbf7-344d7d1abfb6 |  | textbox | • What is the lot size? Maximum Lot Size = per days production
text | 84f85251-437f-5a2f-a992-88e09daacf69 |  | textbox | • Zone Reference
text | 99d0cc22-6553-576f-b4ce-55ef373b15ec |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | • Are the drawings, complete & current?Attach Recent IFC Drawings
checkpoint-status |  |  | checkpoint | • Have tactiles/pavers been set-out as per current drawings?
checkpoint-status |  |  | checkpoint | • Is the concrete slab free of any deposits or rubbish, projections/voids?
checkpoint-status |  |  | checkpoint | • Does the area include stone TGSI’s?
checkpoint-status |  |  | checkpoint | • Does the area include regular tactiles?
checkpoint-status |  |  | checkpoint | • Does the area include both types of tactiles?
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 7903e3ab-5422-5a55-8ddf-2089237a0a75 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5f3ac8a9-57fc-5f53-9265-cf2164683bfb |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Stone TGSI's (pavers)
checkpoint-status |  |  | checkpoint | • Has mortar been placed using type/method described in specification?
checkpoint-status |  |  | checkpoint | • Does the section require directional or horizontal TGSI’s, or both?
checkpoint-status |  |  | checkpoint | • Have pavers been laid as described in specification, considering specified tolerances?
checkpoint-status |  |  | checkpoint | • Have joints been sealed as described in specification?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | b4fc89c8-b307-55f3-ae1d-3f84eb8a7ba5 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 5dfcacbf-fbd3-5c62-8e3d-3a7b2f7b6736 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 4.0 Regular Tactiles
checkpoint-status |  |  | checkpoint | • Have tactiles been installed in accordance with manufacturer specifications?
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 4587d48f-9b5c-5a4e-9a27-565fc9aae6ae |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 3217097e-7d64-5430-8f29-3f211b4b8df1 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | SYM-ITP-002 - Flexible Pavements (Rev A) |  |  |  |  | Yes | SYM-ITP-002 - Flexible Pavements (Rev A) | f47cbdd9-64b5-4d08-b4ea-664eb475560f
checkpoint-group |  |  | section | 1.0 Preliminaries
checkpoint-status |  |  | checkpoint | • Has the work area been set out for line and level?
checkpoint-status |  |  | checkpoint | • Has the previous layer passed acceptance criteria?
checkpoint-status |  |  | checkpoint | • Attach Survey Conformance Certificate (If applicable)
checkpoint-status |  |  | checkpoint | • Is the correct material being used?
text | 3f99979a-892b-57b7-a739-066a514ba726 |  | textbox | • Material used
checkpoint-status |  |  | checkpoint | • Has the material to be used been approved for use (Material certificates to be provided)?
text | 76240f9a-2582-588b-8b2c-348417e4d98f |  | textbox | • What is the lot size? Noting Maximum lot size = 1 days production or 4000m2
text | 80b3c010-a7e5-51f8-950a-ac0648108bbc |  | textbox | • Zone Reference
text | cf1bef6d-bd9e-5c4f-b3fb-f71d039df1db |  | textbox | • Stage Reference
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | f5fbc90c-f942-5d28-b6b4-8f158e11823f |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | b584baa8-63c0-5916-b594-506b8fbace81 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 2.0 Pavement Construction
checkpoint-no-status |  |  | checkpoint | • Is the pavement intended to be Lower Subbase or Upper Subbase?
text | c230e599-3292-5261-aa96-c2963e9cf72f |  | textbox | Lower or upper subbase
checkpoint-status |  |  | checkpoint | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
checkpoint-status |  |  | checkpoint | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
checkpoint-status |  |  | checkpoint | • Place and compact layers so that the surface finish is smooth and uniform.
checkpoint-status |  |  | checkpoint | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
checkpoint-status |  |  | checkpoint | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction? Attach Test Report
checkpoint-status |  |  | checkpoint | • Area shall withstand test rolling without visible deformation or springing.
checkpoint-status |  |  | checkpoint | • Has all of the above been completed correctly, to a high standard and approved by relevant authority?
checkpoint-status |  |  | checkpoint | • Complete Proof roll report, attach or add to lot.
text | b7e43950-bd41-59dc-b21e-54543f73da8a |  | textbox | • What quantity of soft, wet or unstable material is present? (m2) | m2
text | 875a1c6b-2052-5acf-b739-bb711a74b310 |  | textbox | • What quantity of soft, wet or unstable material is present? (m3) | m3
checkpoint-status |  |  | checkpoint | • Attach Survey report
checkpoint-status |  |  | checkpoint | • Has rectification process been submitted to Related authority for Review?
text | ece0cf81-67d1-53f0-b935-3816ade5d592 |  | textbox | • What was the rectification process used?
checkpoint-status |  |  | checkpoint | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
checkpoint-status |  |  | checkpoint | • Attach site photos for all stages of works.
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | e64497a1-561c-5c10-ac09-62117d26b8c6 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 67d6b317-4198-53c1-bd0a-082bf162dfaf |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | 3.0 Testing
checkpoint-status |  |  | checkpoint | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
checkpoint-status |  |  | checkpoint | • Characteristic Density Ratio % (six tests per lot): Not less than 97.0% Modified (Scale B)
checkpoint-status |  |  | checkpoint | • For layer directly beneath bituminous surface, not less than 100.0 for scale A and 98.0 for scale B
checkpoint-status |  |  | checkpoint | • Attach NATA Test Report
checkpoint-status |  |  | checkpoint | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
checkpoint-status |  |  | checkpoint | • For Subbase, one Characteristic Density Ration % (six tests) will be completed for every second lot.
checkpoint-status |  |  | checkpoint | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency
checkpoint-status |  |  | checkpoint | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
checkpoint-status |  |  | checkpoint | • Surface level checked for compliance with 304.06 ○ Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A) ○ Min 80 measurements per lot (Scale A) ○ Mean +8 mm to -16 mm with a max std deviation of 15 mm (Scale B) ○ Min 40 measurements per lot (Scale B)
checkpoint-status |  |  | checkpoint | •Attach Survey Conformance Certificate
checkpoint-status |  |  | checkpoint | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
checkpoint-status |  |  | checkpoint | • NATA Endorsed Test Reports
label | a7871b20-aa2c-591a-b675-39aea1038144 |  | note | • All Product Non-Conformance(s) recorded and closed (if applicable)
checkpoint-status |  |  | checkpoint | • NCR reports
checkpoint-status |  |  | checkpoint | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
button | 288c88a1-bead-5585-baa0-38242f2fb989 |  | button | HOLD POINT - Signature by CYP D&C JV | Yes,No
button | 28e1c323-baba-5f83-9fe6-d72e8fcd84c2 |  | button | Symal Infrastructure Signature Sign-Off added below | Yes,No
holdpoint |  |  | signoff | Request Sign Off