## Matrix
Package | Customer | Trade Type | WBS Tiers - (Optional, but Ideal) Added Checklist | Ability to Add Checklist Required? | Add Requirement Explained | Fed Matrix 1 | Fed Matrix 1 Columns | Fed Matrix 2 | Fed Matrix 2 Columns | Specific Sections/Checkpoints Required
Structure
| PXF Steel | Steel Fixer | Level | Yes | Everywhere | Structure | Reinforcement Work(s) completed to specification/drawings & Area left clean/tidy |  |  | Yes
| Form Group | Formworker | Level | Yes | Everywhere | Structure | Formwork(s) completed to specification/drawings & Area left clean/tidy |  |  | Yes
Services-Rough In
| IPS | Plumbing | Level, Apartment | Yes | Everywhere | Services Rough In | Rough-In completed to specification/drawings (Plumbing Rough-In Water/Gas/Sewer Checklist ) |  |  | Yes
| GM Electircal | Electrical | Level, Apartment | Yes | Everywhere | Services Rough In | Verify all inspections complete (Electrical Rough-in) |  |  | Yes
| United Fire | Wet Fire | Level, Apartment | Yes | Everywhere | Services Rough In | Pipework installed as per drawing & completed in area (ITR-001 Sprinkler System – Rough in)
| Sydney Fire | Dry Fire | Level, Apartment | Yes | Everywhere | Services Rough In | Rough-in cables for speakers (SOU Rough in ITP)
Services Fit Out
| IPS | Plumbing | Level, Apartment | Yes | Everywhere | Services Fit Out | Verify all inspections complete, Check Status and collate records (Fit Off Checklist) |  |  | Yes
| GM Electircal | Electrical | Level, Apartment | Yes | Everywhere | Services Fit Out | Verify all inspections complete, Check Status and collate records (Fit Off & Testing ) |  |  | Yes
| United Fire | Wet Fire | Level, Apartment | Yes | Everywhere | Services Fit Out | Pipework installed as per drawing & completed in area (ITR-003 Sprinkler System – Fit Off)
| Sydney Fire | Dry Fire | Level, Apartment | Yes | Everywhere | Services Fit Out | Fit-out of speakers/ detectors (SOU Fit Out ITP)