## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 1e41987d-4df5-4e7b-a13d-e48dca009a0e
checkpoint-status |  |  | checkpoint | Project details entered below
text | bc4a0823-b279-5923-953c-bc595508a8cb |  | textbox | Job Number
text | 160e97a1-566e-5108-a6b7-b2b3c70f639c |  | textbox | Project Name
text | b373959a-7e48-53e1-9bc6-2cda54e6c378 |  | textbox | Site Address
text | 89ba1af6-4e9b-5857-bf34-8b397e3feb14 |  | textbox | Builder
text | 854264ef-e25a-539c-a747-347eec1ebc54 |  | textbox | Euro Precast Project Manager
text | 8909309d-7b03-5c68-bbf4-24bd37a81318 |  | textbox | Euro Precast Lead Draftsperson
text | 0ffffe63-cea1-5e70-9625-7fe68b5906a0 |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | ab62791b-6e64-41df-a915-dbfebf3780c5
checkpoint-status |  |  | checkpoint | Details complete
text | abb08659-914e-5939-8385-bb6666376ee9 |  | textbox | Date:
text | f631cf62-ede5-59c3-b583-0da3638291ee |  | textbox | Time truck arrived at Factory:
text | a8a721f5-61c3-5f91-8b71-905b04d0c226 |  | textbox | Time truck departed Factory:
text | f5d5b5ec-efb6-5b0b-94fb-f54892a29fff |  | textbox | Project Name:
text | b3a4c639-214e-5396-8ad3-2f4c44ba2d4e |  | textbox | Delivery Address:
text | 27d98810-1d9e-5a35-833d-057acf9428b0 |  | textbox | Transport Company:
text | 8d642f0d-fbc2-5193-8958-3a55940778ac |  | textbox | Truck Registration #
text | 33863c76-b0f7-5b8c-867b-934da075c45b |  | textbox | Trailer Registration
select | 20a688a2-78eb-5b81-9e7a-eb64177cbbf0 |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | 0c12d926-aea0-5cfe-a35a-d32ce06234dd |  | note | In signing below, you agree and acknowledge that:
label | 36c05e88-67c0-5e08-b998-35a297a5aa72 |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | 59e6fb14-6fc2-5327-8508-6b78ffadb51e |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | 33f720fe-9e45-5a24-83f1-f78cf85630de |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | a81d86ff-767f-5272-8c2a-e6c29250d8cd |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | dcaf70ef-c61c-5226-bb66-adb5999d9435 |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | b86daada-4859-4a12-bf99-0c9704d5cacd
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | 1e7ab9c2-7050-59c1-b78d-ac0964c1457e |  | tickbox | Bedding grout (trowellable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 739d33ce-88d2-5dad-ad4a-40da1a3b50ee |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | cedd3cbe-a1d4-50ea-bcf8-88b20bb6a25f |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 19f12ae1-088b-5943-a6ad-0031f3cf8969 |  | tickbox | Survey Pins
boolean | 6b6eb9db-53b2-5075-b14f-df685943c943 |  | tickbox | Within 5mm of vertical plumb
boolean | 90ddf82b-a134-51aa-a4b1-e5abf496f90d |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | 79ce2fd0-a5de-5a05-bd98-c5d7df5cbd56 |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 3790f5b4-052d-5e11-bbe6-2aebadb1d86e |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 583e15d2-fb74-591f-8322-5a690e360983 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 308237ed-ac03-5085-a753-127d06fb69fa |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Were there any delays or Site Instructions given. If yes, please comment below and have builder sign
label | 4e40a119-8232-5b23-bc60-342a03135929 |  | note | If site instruction was given or delays experienced, mark as FAIL so Euro Precast Project Manager can review. Once reviewed, Euro Precast Project Manager will change the status to PASS with appropriate comments.
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | b2d694b0-5769-53f1-8b63-36b45bce88a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | Element Caulking
checkpoint-status |  |  | checkpoint | Element caulked as per project requirements
boolean | e791e0f2-b055-5adc-8d4a-59a91ce27a62 |  | tickbox | Caulking product used as per element/project requirements (PHOTO REQUIRED of caulking product used)
boolean | 3561a16b-3aee-5573-9277-e88e504f5c0b |  | tickbox | Open or closed cell backing rod used? (SPECIFY in comments section below)
boolean | 3c8d0be9-da22-5409-92b1-dfb1b52c0161 |  | tickbox | Caulking installed and checked (PHOTO REQUIRED of caulked joint/s)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checkpoint-group |  |  | section | Basic Patch
checkpoint-status |  |  | checkpoint | Have the lifting anchors been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the prop points been patching as per project requirements
checkpoint-status |  |  | checkpoint | Have the grout tubes been patching as per project requirements
checkpoint-group |  |  | section | Final Finish
checkpoint-status |  |  | checkpoint | Has all outstanding patching been completed (PHOTO REQUIRED of all visible faces of element)
checkpoint-status |  |  | checkpoint | Has the builder signed off on the element? (ATTACH signature box below)
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | c7ab256b-a428-42c0-8a59-92bf994a4916
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | eb722c43-9578-5232-9b65-00f759be767e |  | textbox | Date:
text | cfe0abd9-00bd-5536-a57e-e165bb3a3691 |  | textbox | Project Name:
text | eebe3498-74bf-5f44-a1f2-5cc3617db90a |  | textbox | Time of test:
text | 2b95881c-50fb-51f2-8815-dd03f5eab2aa |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | d1756d60-89dd-4d8e-baf8-86b9dcae0423
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 000dd3bd-d72c-5a64-901f-65a8c0204eef |  | tickbox | Mould clean with release oil applied correctly
boolean | 571d189d-3a7a-5dc4-9313-d59bc9dc7919 |  | tickbox | Primary & diagonal dimensions checked
boolean | 1af4e617-5401-5430-82d7-cc9643fc9536 |  | tickbox | Openings Checked and Correct
boolean | 273d6ac4-1825-559c-82c9-5b21fbd2a630 |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | c5272591-3631-53b8-9dba-d24a34e167cf |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | a4c51ff9-c2ce-591d-8a41-ce93353e54e9 |  | tickbox | Correct Size and Type
boolean | af95c4ce-6684-50ec-8c90-17faa08f30fe |  | tickbox | Laps and Splices correct
boolean | 9ca7e454-b188-547e-aa6b-ae5b0b4928b8 |  | tickbox | Cover Checked
boolean | faef533e-cda1-56dc-b308-6f083a0b686a |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | 8d3d1d6c-9cb2-530e-9e7d-fc78e4dd5fb7 |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 52ac4b3f-d254-5e03-8bb1-3877ca2b207e |  | tickbox | Starter Bars inserted, checked and correct
boolean | 32c65f13-a4aa-54a1-9c38-60511feb6e15 |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | 3ce8ef6c-7889-53cd-8a23-c7f5a06a2102 |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | ad54e238-fee7-5b7c-82f9-9374394c7957 |  | tickbox | All Concrete Dockets Attached
text | e6d0110a-6e5d-52a6-b73a-658055423857 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | eb6a8c30-3823-59c4-952a-c13d8bcde08b |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | c07024c4-ce5b-5cd1-b844-d008e113dff6 |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 610b6a45-1265-57f6-9a9a-9ce06157d616 |  | tickbox | Lifting anchors checked and approved
boolean | 22404935-db8e-5cb3-97f0-7bf42af97e8f |  | tickbox | Critical fitments / fixtures checked and approved
boolean | 10dc50f7-f3f9-54c6-8e84-f743b5df8bbd |  | tickbox | Openings (formwork removed)
boolean | 6c6258a7-c898-5dda-90b4-4f391a32795a |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | f19e2ad0-b2d3-5349-9220-1603b08ecfbf |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 1e0ede64-9047-542d-80dd-d7045210d0d3 |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | 92bd5360-383c-5301-a04e-131dd9c27cdb |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | ffea7682-6083-45bb-aa44-4f424504a229
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | 5324faf2-c369-5f1d-a2a0-6ac974456248 |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-status |  |  | checkpoint | Element details
select | b856c5f5-7e94-5254-9f97-e1fea0dc7d57 |  | dropdown | Number of elements installed (COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations) | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,39,40