## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fences & Retaining Walls (Brickwork) Cleaning |  |  |  |  | Yes | Fences & Retaining Walls (Brickwork) Cleaning | 11a5874b-1bab-4f3a-aa99-60d16bd504db
checkpoint-status |  |  | checkpoint | Scope area & notes
label | f0b7e955-90df-4ffa-8674-3d7b69ae7312 |  | note | All Brickwork Surfaces to Fences and Retaining walls
label | 35f88c47-213f-482a-a787-a11ca3278bf2 |  | note | Retaining walls can be subject to significant amounts of Moss build up on Mortar joints as they often have not been waterproofed from behind. Pressure cleaning can damage the mortar, and as such cleaning by wet and leave cleaning is preferred in these areas.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould removed
label | 20f63cb5-6c04-4220-a646-3c5384442604 |  | note | Avoid if heavy infestation where it is deemed the surface could be damaged by continuing with pressure washing. This situation a ‘wet and leave’ treatment will be used. Note this can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material.
label | 2c06cf54-c7f9-4967-9938-2f393670ef0b |  | note | The mortar lines may well exhibit permanent staining from poor mortar quality on older villages
label | b3dea38e-9f1c-42ce-be1e-59b085dcee10 |  | note | The ‘whiting’ of brick work most notably in Christchurch and the newer villages is a result of Salt deposits from the mortar.
label | c0e6c794-6e4a-4935-93d7-f7df3c78c661 |  | note | The washdown will initially remove this, but it will return very quickly as the water dries out of the brickwork.
checklist-flat |  |  | checklist | Project Variation Form |  |  |  |  | Yes | Project Variation Form | 007ce741-0252-4256-98d4-d8f2675feb30
checkpoint-status |  |  | checkpoint | Details
text | 22420a31-1172-4b59-b8a1-71002ce80668 |  | textbox | Project Name
text | f36a99b7-2f16-40f9-8b7e-d924c9185985 |  | textbox | Project Location
text | 6ec49581-72e7-4245-8657-cfd7334631c6 |  | textbox | Project Manager
text | 6753777d-f76a-4372-bc6b-f0c5f73ad80e |  | textbox | Site Supervisor/Foreman
text | 944bc424-4eec-40c9-88f2-3a41bdca011b |  | textbox | Form of Instruction
text | 2ab960cd-3d7a-4d1e-b67b-98a94030b7cc |  | textbox | Instructed By
checkpoint-status |  |  | checkpoint | Description of Work
checkpoint-status |  |  | checkpoint | Labour 1
text | 3a490890-9474-495a-a9b6-3b8b346dc028 |  | textbox | Date
text | 97a859d4-0939-45ae-8506-80e19e267402 |  | textbox | Name
text | fd9b2871-7112-4d3d-b6d4-1abac35d281e |  | textbox | Hours
text | 19869ee4-5087-439e-9572-d86a30e16ae0 |  | textbox | Rate
text | e242de31-eeaf-49dc-9bcf-6d240aab3b38 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 2
text | 3430be09-75a2-4232-9a94-a4ce24233dd4 |  | textbox | Date
text | 961f6991-df69-43ea-8da6-556a7f9115c9 |  | textbox | Name
text | a0296beb-c35d-490e-9416-b5f53509366f |  | textbox | Hours
text | d0cce0d4-a909-4ea9-940d-8cab0cbfecec |  | textbox | Rate
text | fb4eafd6-2aa0-47a9-9149-7d14da810af6 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 3
text | 023abb11-b41a-425f-982a-fbc053c14f64 |  | textbox | Date
text | 8c8f1521-acba-4aa7-b6b9-644c683e2bb7 |  | textbox | Name
text | 9bc04888-268d-45cb-bb0e-c95d2ce46afe |  | textbox | Hours
text | 6bc34494-883a-401b-b09b-fac6ed94aae4 |  | textbox | Rate
text | b33d579c-4bed-4c93-a756-f9442aa8b51d |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 4
text | 8f7e029e-f957-45d6-9c58-708874ae19b8 |  | textbox | Date
text | b0301b69-151c-43dd-aeb2-47294906b755 |  | textbox | Name
text | 30c9a4da-34d6-4337-8a7d-7b0862613755 |  | textbox | Hours
text | e566955f-c3dc-481c-8ae9-8c6e8b42e389 |  | textbox | Rate
text | ef3a96f5-fb7e-41d8-aede-43e4d0926a6b |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 5
text | 5fd7fff3-b525-415c-ab83-9341d9ebbca9 |  | textbox | Date
text | f9f0146b-4953-4f79-bbb8-956a1b114b15 |  | textbox | Name
text | 5b310cc7-2da2-48d4-9b54-28c6fa785437 |  | textbox | Hours
text | 3fcdb9c5-97a5-433a-963b-40ae6363e7b3 |  | textbox | Rate
text | b45cf3e4-7155-4065-b32d-7ff629054e27 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 6
text | b2add89f-9ef6-44a0-bd81-1f254724c18a |  | textbox | Date
text | c8e6dc2b-a7de-4d08-b789-0339d8450c52 |  | textbox | Name
text | 82def784-34d0-4f9d-adeb-0d994e41f60d |  | textbox | Hours
text | 215f612d-41f2-4b17-aa3a-0aec6f2430e2 |  | textbox | Rate
text | cbdfe8a3-7b98-4799-9cba-cf2f1bd051fc |  | textbox | Total
checkpoint-status |  |  | checkpoint | Labour 7
text | 7be8c10e-46d1-445e-860e-ec4954437998 |  | textbox | Date
text | a4f9a05b-ce8b-4b50-9987-0c5b40ebcb58 |  | textbox | Name
text | f2dc07fa-369c-4424-9784-d2f295b3da1f |  | textbox | Hours
text | 687ffa89-d094-4704-b335-84aa52162cbe |  | textbox | Rate
text | 526c0d29-27f8-43b3-bb93-9be0ae594b92 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 1
text | e8799cef-8850-46fa-985b-1e8b8d966643 |  | textbox | Date
text | 2911fb6f-a3dd-405e-bade-c12ed2d91803 |  | textbox | Description
text | 06718f29-249e-48cb-81a3-8086242424b3 |  | textbox | Qty
text | a53da602-be57-4848-b4f4-189333280f68 |  | textbox | Rate
text | e1e92185-08c5-4ac9-960a-211b409d3328 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 2
text | 3508625f-dde8-40f2-9e4b-8f4b4c10698a |  | textbox | Date
text | 568de11c-4448-448c-ab1c-30dd27953610 |  | textbox | Description
text | aa101270-d2ad-413e-8f44-733337489c30 |  | textbox | Qty
text | 8b723636-eaf6-4fab-8977-9a2c513d4259 |  | textbox | Rate
text | 9ab547b4-0224-429e-b451-df8b0619b4e9 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 3
text | 54e73bec-58c7-43ba-8ec7-f95e2115cbe1 |  | textbox | Date
text | 08e8fbc7-dd1e-419c-a35c-9a342cd978ba |  | textbox | Description
text | 90684c23-d46c-4a24-9ebf-a8be08136b3d |  | textbox | Qty
text | b5efb8fc-be6d-4f23-86b3-dd347bf09c06 |  | textbox | Rate
text | 9ddafff6-f4c8-4ce9-92bf-540cfd7f6cde |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 4
text | b1c09c24-d419-478a-87f2-61e91f2c4c58 |  | textbox | Date
text | 448d772e-626a-406c-9aab-b3e5ab3a8929 |  | textbox | Description
text | 863e6b40-0cd0-4bb8-8887-04ee282db398 |  | textbox | Qty
text | 58b9d5fc-2365-4fdf-93b2-55f899426be1 |  | textbox | Rate
text | dd830f62-b130-4237-a1b8-c01c70d6d68d |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 5
text | 1be7933f-163a-48be-b2da-410781bd576c |  | textbox | Date
text | 7b982557-cf5d-4835-ba44-4f90bfb44bef |  | textbox | Description
text | ff6d6de3-4c1f-41c3-94bd-699f4fdf54c1 |  | textbox | Qty
text | aab4f449-3097-4db0-b246-229c8ae51bfd |  | textbox | Rate
text | 7886e002-7181-4960-808f-a6c9c0dbab92 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 6
text | 61f2d676-ccb2-40b3-8f65-ca0246e12e2f |  | textbox | Date
text | 612ee67a-3287-4723-a1f6-07d04f0e98df |  | textbox | Description
text | 4569a50b-35df-46d2-94ab-19a84bd98cb8 |  | textbox | Qty
text | 74667c0a-e256-47c3-88fe-50062b6dc6ba |  | textbox | Rate
text | 4401a704-f6be-48dc-bcab-c1e0c0815d0a |  | textbox | Total
checkpoint-status |  |  | checkpoint | Material 7
text | ec59aed1-83bd-4e53-a4d3-5dcebfa2abc8 |  | textbox | Date
text | 274a7ec5-1f84-422f-baf2-735ffd4bf2a3 |  | textbox | Description
text | d9828845-d22d-46bb-8315-e874541435df |  | textbox | Qty
text | 71451074-b34f-48e3-95c6-b7d7b2f66ad0 |  | textbox | Rate
text | 7a9bdb46-c277-4085-9313-0b2b80f0634c |  | textbox | Total
checkpoint-status |  |  | checkpoint | Plant 1
text | c7e2c798-7361-438b-bfde-ce37ea0c068f |  | textbox | Date
text | f7237e2b-f056-46ef-bea5-8514823e7959 |  | textbox | Description
text | 5db50dba-1e91-4a65-ab09-76d3a15ea7ab |  | textbox | Qty
text | 068673a8-d218-4747-88c7-91aacc723c9d |  | textbox | Rate
text | 7397fa55-988c-4ad8-84c7-8443897f6616 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Plant 2
text | f1085039-39d3-4b6e-a844-d752b7949603 |  | textbox | Date
text | 0c48f767-8679-4fc3-98f5-77578a4ccb17 |  | textbox | Description
text | 448dfc36-12ef-4777-aed9-7121c04b4bfc |  | textbox | Qty
text | 9f125d42-1e97-428d-bbe8-a1e00412c89a |  | textbox | Rate
text | 3c2323b0-0409-4657-ba62-4e0a6290b2fb |  | textbox | Total
checkpoint-status |  |  | checkpoint | Plant 3
text | 64afa82f-f328-4e3a-8971-464ccc42c3dc |  | textbox | Date
text | f2ceb245-07b9-4f66-9e42-f1d00e674563 |  | textbox | Description
text | 684575d1-a556-4522-8b2d-7cde3439f5e6 |  | textbox | Qty
text | d985fe08-fe91-4d75-ae2a-d9ea6a1b5b0c |  | textbox | Rate
text | b00972ec-93e9-4078-aa47-09b665083ad0 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Variation Total
checkpoint-status |  |  | checkpoint | Client Name & Signature
checkpoint-status |  |  | checkpoint | Euroclad Name & Signature
checklist-flat |  |  | checklist | External Gutter Fascia |  |  |  |  | Yes | External Gutter Fascia | 67639cdb-23d9-4176-ae67-9f66e0f9774e
checkpoint-status |  |  | checkpoint | Exterior of gutters, soffits and fascia’s to be clean and free of loose detritus material, mould and moss should be cleaned away.
checklist-flat |  |  | checklist | Building Clean | itp |  |  |  | Yes | Building Clean Checklist | c89b497f-6f69-4c5d-9001-2f36fb63741b
checkpoint-status |  |  | checkpoint | Check all frames are free of debris
checkpoint-status |  |  | checkpoint | All glass to be streak free
checklist-flat |  |  | checklist | Townhouse Plaster Walls Washdown |  |  |  |  | Yes | Townhouse Plaster Walls Washdown | 96e27bfb-a4f9-40f4-b4f2-716cbbe7d2f4
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 2ee36c76-c730-4aef-9e39-849918f75a26 |  | note | All Plaster Surfaces to wall, deck faces, and columns.
label | 13104406-75fc-4010-9878-04791580147c |  | note | When completing work to a full plaster Village, i.e Edmund Hillary, Evelyn Page, Princess Alexandra, and Francis Hodgkin, the fascia, soffit and guttering is to be washed down also.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould cleaned away
checklist-flat |  |  | checklist | Main Building Brickwork Washdown |  |  |  |  | Yes | Main Building Brickwork Washdown | 7e0d7a42-170a-4b04-ab6e-f4d34ee6bcf0
checkpoint-status |  |  | checkpoint | Scope area & notes
label | a681186c-9c91-4e45-8b19-e4c401818a34 |  | note | All Brickwork Surfaces, walls and Columns.
label | 800be771-4f6b-4d8f-a2fa-fe26278ff4ad |  | note | Fascia, soffit and guttering washed down
label | 7f064ee7-5d75-46ff-a4fb-bd3a2701c8a0 |  | note | It is understood that some brick Village walls are washed down every two to four years. The fascia soffit and guttering would also reflect this cycle.
label | 95690fb3-75ee-4c05-afd5-3c91830cb33b |  | note | Decks are rinsed down when the adjacent walls are done, so for those decks in brick Villages this may be every two to four years.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould removed
label | 48fa224f-6c5c-4a89-bca9-350fb4969b47 |  | note | Avoid if heavy infestation where it is deemed the surface could be damaged by continuing with pressure washing. This situation a ‘wet and leave’ treatment will be used. Note this can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material.
label | 5d53da71-874c-4ddb-98e7-6a985fe38e74 |  | note | The mortar lines may well exhibit permanent staining from poor mortar quality on older villages
label | dd54323a-e416-4440-a38d-b0fa37deec89 |  | note | The ‘whiting’ of brick work most notably in Christchurch and the newer villages is a result of Salt deposits from the mortar.
label | 5410a908-7cd9-47e5-b1c7-14054d9b3579 |  | note | The washdown will initially remove this, but it will return very quickly as the water dries out of the brickwork.
checklist-flat |  |  | checklist | Townhouse Gutter Debris Removal |  |  |  |  | Yes | Townhouse Gutter Debris Removal | a4a38301-913c-4831-8666-5192c9a80628
checkpoint-status |  |  | checkpoint | Scope area & notes
label | d0a1c8dc-b09d-4c89-ba6b-98f09f73a83d |  | note | Inspect all townhouses.
label | b91347f4-1962-48a3-8134-b65c647aed55 |  | note | Clean out all areas identified as requiring debris removal
checkpoint-status |  |  | checkpoint | Post completion the gutters should be clear and free of all loose material i.e grass, leaves, and other debris.
checkpoint-status |  |  | checkpoint | Wet dirt may remain in gutters with inadequate fall.
checkpoint-status |  |  | checkpoint | Gutters sections with leaf guards cannot be cleared, and water may be used in these areas
label | 8f0723ec-8a7e-4b67-b9fe-860733793172 |  | note | NOTE: THE SCOPE OF WORK DOES NOT ALLOW FOR CLEANING TO THE EXTERIOR AND UNDERSIDE OF THE GUTTER, AND ASSOCIATED FASCIA. THIS WORK IS DONE AS PART OF THE WALL CLEANING.
checklist-flat |  |  | checklist | Signoff |  |  |  |  | Yes | Signoff | 50c61d98-8e10-4553-bddc-bf18c9c3fabc
checkpoint-status |  |  | checkpoint | Relevant photos and documentation completed
checkpoint-status |  |  | checkpoint | All variations recorded
checkpoint-status |  |  | checkpoint | Work completed as per spec
checkpoint-status |  |  | checkpoint | Report sent to Village office
checklist-flat |  |  | checklist | Visits |  |  |  |  | Yes | Tracking Visits | b87e8807-2171-42bd-b268-4aa078532829
checkpoint-status |  |  | checkpoint | Visit 1
checkpoint-status |  |  | checkpoint | Visit 2
checkpoint-status |  |  | checkpoint | Visit 3
checklist-flat |  |  | checklist | Fences & Retaining Walls (Plaster) Cleaning |  |  |  |  | Yes | Fences & Retaining Walls (Plaster) Cleaning | b7e61e37-a8ce-4d75-92b6-d3fbc6406d92
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 9dfe425b-d27d-4fa1-8ae4-2f44d92d1941 |  | note | All Plaster Fences and Retaining Walls
label | 26053776-5f51-480a-9a81-fce8f441165e |  | note | Retaining walls can be subject to significant amounts of Moss build up on Mortar joints as they often have not been waterproofed from behind. Pressure cleaning can damage the mortar, and as such cleaning by wet and leave cleaning is preferred in these areas.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould cleaned away
checklist-flat |  |  | checklist | Main Building Gutter Debris Removal |  |  |  |  | Yes | Main Building Gutter Debris Removal | fc2f8bbb-2a48-4541-bdf3-845ae6856122
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 8ebbf69d-a436-491a-92ab-b9921f11b4de |  | note | Inspect all areas to main building, admin. blocks, hospitals and apartments.
label | d73f17a3-dc06-4a8a-8380-98d57248663e |  | note | Clean out all areas identified as requiring debris removal.
checkpoint-status |  |  | checkpoint | Post completion the gutters should be clear and free of all loose material i.e grass, leaves, and other debris.
checkpoint-status |  |  | checkpoint | Wet dirt may remain in gutters with inadequate fall.
checkpoint-status |  |  | checkpoint | Gutters sections with leaf guards cannot be cleared, and water may be used in these areas
label | 089d37dd-a790-49b8-a499-bf49d3f860d9 |  | note | NOTE: THE SCOPE OF WORK DOES NOT ALLOW FOR CLEANING TO THE EXTERIOR AND UNDERSIDE OF THE GUTTER, AND ASSOCIATED FASCIA. THIS WORK IS DONE AS PART OF THE WALL CLEANING.
checklist-flat |  |  | checklist | Main Building Roof Treatment |  |  |  |  | Yes | Main Building Roof Treatment | 9fcf9ac8-f224-4075-aff6-47e491891b75
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 7de39a37-12ec-44a0-b75f-800769558dc1 |  | note | Coat all roof areas of main building, admin. blocks, hospitals, and apartments.
label | bc7e058e-36d8-4942-b8f7-92e65d0432bb |  | note | Surfaces could be concrete tiles, metal roofing, butanyl, or membrane.
checkpoint-status |  |  | checkpoint | The surface should be fully coated in the Wet and leave product.
label | 9efeac6d-e47e-4614-809d-66ef03f6ac85 |  | note | Care is to be taken with ensuring adequate coverage to Parging, pointing and leading edge of tiles.
label | e0953e5d-bb2d-473f-bb3a-e7bf8030dc89 |  | note | The ‘wet and leave’ treatment can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material after one month
checklist-flat |  |  | checklist | Main Building & Townhouse Spiderproofing |  |  |  |  | Yes | Main Building & Townhouse Spiderproofing | 43f03a01-8b0a-41ac-a247-f13a16678b42
checkpoint-status |  |  | checkpoint | Scope area & notes
label | cf8310fb-1f5b-48bb-998d-c0b8e9709e15 |  | note | Only to be applied to ground floor areas.
label | 6655ee1f-7f36-4e45-9d20-ba3051acf108 |  | note | Does not include decks to areas above ground level.
label | b6ee21a6-33e0-4bda-a2ad-460910e0be88 |  | note | Wall/soffit junctions of single-level buildings only.
label | cb00f05c-c959-48e6-bea1-35420dd5b0f1 |  | note | Window heads.
label | 8cedc1df-5343-4473-b602-d3aafbf32a81 |  | note | Brick weep holes.
label | a15e23a1-5dcc-4381-9750-367cac0053ee |  | note | Junctures where spiders accumulate, i.e. behind flashings, etc.
checkpoint-status |  |  | checkpoint | Continuous application of the spiderproofing product by Sprayer to the areas as described
label | 88379732-0871-4858-86c0-854ff24e1664 |  | note | The product is a contact killer and remains active for 7 days or until a significant rainfall.
label | b799055e-3ee2-4442-bb48-24af548f6415 |  | note | The product does not remove spider webs, and kills the spiders that are present in those locations, or those that walk across the applied area within the active period.
checklist-flat |  |  | checklist | Townhouse Brickwork Washdowns |  |  |  |  | Yes | Townhouse Brickwork Washdowns | 0ee92c47-2e27-4f25-aee3-43dd4266a04e
checkpoint-status |  |  | checkpoint | Scope area & notes
label | a75c1d26-bae8-41e7-b20b-7fe15c669077 |  | note | All Brickwork Surfaces walls and Columns.
label | 772ce0cc-ce32-4396-a632-82228144efeb |  | note | When completing a Brickwork Washdown the fascia, soffit and guttering is to be washed down also.
label | e6628a0c-e03e-4029-8589-58ba1f476dbc |  | note | It is understood that some brick Village walls are washed down every two to four years. The fascia soffit and guttering would also reflect this cycle.
label | c05ace15-4423-4de2-b659-0c65e0d01f4a |  | note | Decks are rinsed down when the adjacent walls are done, so for those decks in brick Villages this may be every two to four years.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould removed
label | 114da14c-1f87-4d2a-ab9c-ab9106152650 |  | note | Avoid if heavy infestation where it is deemed the surface could be damaged by continuing with pressure washing. This situation a ‘wet and leave’ treatment will be used. Note this can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material.
label | 561dff27-782a-419d-b877-591498f3c187 |  | note | The mortar lines may well exhibit permanent staining from poor mortar quality on older villages
label | f5e1ef9d-22bc-44c8-866c-c14873132cd9 |  | note | The ‘whiting’ of brick work most notably in Christchurch and the newer villages is a result of Salt deposits from the mortar.
label | 9fc941df-a750-43fd-af4f-398a49e1f755 |  | note | The washdown will initially remove this, but it will return very quickly as the water dries out of the brickwork.
checklist-flat |  |  | checklist | Path Treatments & Lamp Cleaning |  |  |  |  | Yes | Path Treatments & Lamp Cleaning | 3163fd91-dcd7-4256-9314-e260047cbf57
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 98722462-47bf-4c8e-be3d-33a82854e655 |  | note | To all concrete and cobblestone paths, both common and/or individual to townhouses and apartments.
label | ec455203-c4c3-4dd2-8146-17357c2c894e |  | note | Clothes line patios
label | 65bf3373-37b8-49bc-8dde-f3336e6cefe8 |  | note | Lamps are to be treated each year.
checkpoint-status |  |  | checkpoint | Paths should be fully cover with the Wet and Leave Product
label | e0a13acd-94e9-49be-ada9-a4f56802e58c |  | note | The ‘wet and leave’ treatment can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material after one month.
checkpoint-status |  |  | checkpoint | Lamps cleaned with a wet broom to remove spider webs and dirt
label | a4454696-77d5-4bec-b3f6-725232e0a8ee |  | note | The lamp Lens is NOT to be removed to remove insects. This must be done by an electrician
checklist-flat |  |  | checklist | Prestart checks |  |  |  |  | Yes | Prestart checks | 6e156e23-da6e-402a-8e8d-ad379411198e
checkpoint-status |  |  | checkpoint | PPE
checkpoint-status |  |  | checkpoint | Signage available
checkpoint-status |  |  | checkpoint | Paperwork reviewed and understand scope
checkpoint-status |  |  | checkpoint | All relevant materials available
checkpoint-status |  |  | checkpoint | any other observations
checklist-flat |  |  | checklist | Oamaru Stone Inspection |  |  |  |  | Yes | Oamaru Stone Inspection | 4357d1f3-9edd-40a4-a43f-980e18f68e9a
checkpoint-status |  |  | checkpoint | Has the Oamaru Stone been cleaned?
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | b0a56fd1-441b-4951-970e-f32f9a17da36
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Main Building Plaster Wall Washdowns |  |  |  |  | Yes | Main Building Plaster Wall Washdowns | 86126201-abfc-4203-afa6-1f39e115045e
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 95294432-fa37-4b14-961a-98ef4bf64ec1 |  | note | All Plaster Surfaces to wall, deck nibs, and columns
label | 2d9d4913-6ad5-4e5c-af66-317a58df37b6 |  | note | Note for Full Plaster Villages: When completing work to a full Plaster Village the fascia, soffit and external guttering is to be washed down also.
label | a96856e1-b470-4068-b76d-7218dedc3db4 |  | note | Note for Predominantly Brick Villages: If this is a predominantly Brick village with only plaster sectionsthe fascia, soffit and guttering is washed down in conjunction with the brick wash NOT the plaster wash.
checkpoint-status |  |  | checkpoint | Surface clean and free of loose detritus material
checkpoint-status |  |  | checkpoint | Moss and Mould removed
checkpoint-status |  |  | checkpoint | On a Full Plaster Village (please see scope/notes) the fascia, soffit and external guttering
checklist-flat |  |  | checklist | Add Site Map |  |  |  |  | Yes | Add Site Map | 9b7c9cb2-c7db-4a4d-b770-eaa8e6972e96
checkpoint-no-status |  |  | checkpoint | Add Site Map (attach to this checkpoint)
checklist-flat |  |  | checklist | Townhouse Roof Treatments |  |  |  |  | Yes | Townhouse Roof Treatments | f38e9ea1-f4ac-499b-83ea-3942e02db6a0
checkpoint-status |  |  | checkpoint | Scope area & notes
label | 5ba1658e-39b6-4c29-992e-d5118e04e0d3 |  | note | Coat all roof areas townhouses.
label | 6100153b-7942-420a-97f3-9293a0dd1a19 |  | note | Surfaces could be concrete tiles, metal roofing, butanyl, or membrane.
checkpoint-status |  |  | checkpoint | Surface has been fully coated in the Wet and leave product.
checkpoint-status |  |  | checkpoint | Care is to be taken with ensuring adequate coverage to Parging, pointing and leading edge of tiles.
label | 122b3736-ce48-44d6-adca-4722b1e61a98 |  | note | The ‘wet and leave’ treatment can take 6-8 weeks to produce results. Indications that the process has worked is the browning off and lifting of the material after one month.
checklist-flat |  |  | checklist | Oamaru Stone Treatment |  |  |  |  | Yes | Oamaru Stone Treatment (KMG) | 82518890-5fec-41f5-8068-ebf895b8df16
checkpoint-status |  |  | checkpoint | Has the Oamaru Stone received the treatment?