## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Structural Steel for Area: |  |  |  |  | Yes | QA - Structural Steel | 02177a37-e3bb-4a19-a0f6-44120304482c
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Structural steel items checked
label | f7725ee9-d154-53c3-8cab-67d95f3171fd |  | note | Type/Size Checked
label | 667eab58-51c6-5b15-be9a-23ccb81a5d0e |  | note | Finishing checked (ie. Painted, Galvanised, etc)
checkpoint-status |  |  | checkpoint | Cast in/anchor bolts and plates installed
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels checked/correct
checkpoint-status |  |  | checkpoint | All dry packing completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
boolean | d1ac5ab6-9e1c-5d89-a74f-a53a5e4028f3 |  | tickbox | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | QA - Exterior Finishes |  |  |  |  | Yes | QA - Exterior Finishes | 0c72854b-5e56-4bf3-b9c0-2488c20a9a35
checkpoint-group |  |  | section | Exterior wall framing
checkpoint-status |  |  | checkpoint | Window opening dimension (check agreed sizes with NZ windows)
checkpoint-status |  |  | checkpoint | Bottom plate H3.2 (All other timber frame H1.2)
checkpoint-status |  |  | checkpoint | DPC
checkpoint-status |  |  | checkpoint | Stud , Nog spacing & Bracing
checkpoint-status |  |  | checkpoint | Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Connectors (type & fixing)
label | ed12916d-9414-5f7d-bd5b-a6e3dfd2049c |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Building Wrap
checkpoint-status |  |  | checkpoint | RAB board (thickness & gaps)
checkpoint-status |  |  | checkpoint | RAB board fixings
checkpoint-status |  |  | checkpoint | RAB board taping
checkpoint-status |  |  | checkpoint | All cuts primed
checkpoint-status |  |  | checkpoint | Penetration detailed
checkpoint-status |  |  | checkpoint | Sealant
checkpoint-status |  |  | checkpoint | Vaproshield (when required)
label | f846fc22-2bff-5fbc-9fbd-ab3b6f62462e |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Cavity System
checkpoint-status |  |  | checkpoint | Head flashings
checkpoint-status |  |  | checkpoint | Cavity battens
checkpoint-status |  |  | checkpoint | Cavity batten fixings
checkpoint-status |  |  | checkpoint | Verman strips
checkpoint-status |  |  | checkpoint | Flashing tapes
label | 6e16eb5a-8266-5314-88e9-fc9eb0475b3d |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Joinery
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct jamb sizes
checkpoint-status |  |  | checkpoint | AT façade sealant
checkpoint-status |  |  | checkpoint | PEF backing rod
checkpoint-status |  |  | checkpoint | Flashings
label | 8d8e5ec3-5e85-52a8-817a-6dd9595b23d0 |  | note | Trades QA received & attached as applicable
label | 3a538b5b-e273-554b-ac70-f57fa4099739 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior 1st fix
checkpoint-status |  |  | checkpoint | Plumbing drains for deck
checkpoint-status |  |  | checkpoint | Fire colars (when required)
checkpoint-status |  |  | checkpoint | Lights wiring
checkpoint-status |  |  | checkpoint | Mechanical ducts
checkpoint-status |  |  | checkpoint | Hose taps pipework
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations
label | 9d50468d-ac2a-561a-be74-e24d730209c0 |  | note | Trades QA received & attached as applicable
label | dbb1db95-6c8c-5ce2-8f9b-b71722413b95 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior soffit framing & lining
checkpoint-status |  |  | checkpoint | Framing - DPC
checkpoint-status |  |  | checkpoint | Framing - Stud , Nog spacing & Bracing
checkpoint-status |  |  | checkpoint | Framing - Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Building paper
checkpoint-status |  |  | checkpoint | Lining - Type & Joins
checkpoint-status |  |  | checkpoint | Lining - Fixing
label | 0cfef9de-d5f1-5e27-b584-0a575ebbf21b |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior cladding Linea Oblique Weatherboard
checkpoint-status |  |  | checkpoint | Correct layout
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Correct fixing spacing
checkpoint-status |  |  | checkpoint | Boards plumb
checkpoint-status |  |  | checkpoint | Boards level
checkpoint-status |  |  | checkpoint | All joints acceptable/sealed
checkpoint-status |  |  | checkpoint | All cuts primed with 2 coats of stain
checkpoint-status |  |  | checkpoint | Correct moldings/flashings
label | 263a8c14-27e6-5646-a042-6b08b207113b |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Balustrades
checkpoint-status |  |  | checkpoint | Correct type
checkpoint-status |  |  | checkpoint | Correct sizes
label | bc461e4a-adf8-5c8f-bdc1-7ef395db3616 |  | note | Trades QA received & attached as applicable
label | d2fecb7c-f3d5-5ce7-87bb-eb23b45bf559 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Fins
checkpoint-status |  |  | checkpoint | Correct type
checkpoint-status |  |  | checkpoint | Correct sizes
label | 130c23eb-a528-52bb-9e9f-42ae7199a9da |  | note | Trades QA received & attached as applicable
label | 723b3ccf-4d47-54a3-8557-547ad8dcebf4 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Gutters/downpipes
checkpoint-status |  |  | checkpoint | Correct size gutters
checkpoint-status |  |  | checkpoint | Correct downpipe sizes
checkpoint-status |  |  | checkpoint | Correct colours
checkpoint-status |  |  | checkpoint | Gutters straight
checkpoint-status |  |  | checkpoint | Downpipes straight
label | 7cb93dbd-f295-58c8-85fd-5d20567506ca |  | note | Trades QA received & attached as applicable
label | 3a18d688-e48d-50ca-be1e-84d75e3173a4 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior painting
checkpoint-status |  |  | checkpoint | Concrete repairs
checkpoint-status |  |  | checkpoint | Join sealant
checkpoint-status |  |  | checkpoint | Window preparation
checkpoint-status |  |  | checkpoint | Ecotone stain
checkpoint-status |  |  | checkpoint | Dulux White on white
checkpoint-status |  |  | checkpoint | Soffit colours
label | d03d2d70-4477-5e2c-82db-cab0967bfee1 |  | note | Trades QA received & attached as applicable
label | 3422d97a-775c-528a-b0d5-827aa48fd4e9 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Deck membrane
checkpoint-status |  |  | checkpoint | Correct membrane
checkpoint-status |  |  | checkpoint | Correct laps
checkpoint-status |  |  | checkpoint | Correct upstands
checkpoint-status |  |  | checkpoint | No damage
label | beb0b08f-be02-551e-b64a-f5b50fd2061c |  | note | Trades QA received & attached as applicable
label | d44d96f1-0ef1-564b-a337-5175fc811bf7 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Decking
checkpoint-status |  |  | checkpoint | Correct timber (treatment)
checkpoint-status |  |  | checkpoint | Timber on correct jacks
checkpoint-status |  |  | checkpoint | Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Even gaps @ wall / balustrade
checkpoint-status |  |  | checkpoint | Request Sign Off
checkpoint-group |  |  | section | Exterior 2nd fix services
checkpoint-status |  |  | checkpoint | Plumbing drains for decks
checkpoint-status |  |  | checkpoint | Downpipes
checkpoint-status |  |  | checkpoint | Lights
checkpoint-status |  |  | checkpoint | Hose taps
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations complete
checkpoint-status |  |  | checkpoint | Clothes line
label | 728b5bf1-2096-515b-9581-5245a259d5c9 |  | note | Trades QA received & attached as applicable
label | 38dbec20-2f90-5c74-bcd0-f2c18fcc72c6 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Masonry (Ground level only)
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Straight
checkpoint-status |  |  | checkpoint | Plumb
label | b860f90b-950a-5978-84f6-62573c7eaae6 |  | note | Trades QA received & attached as applicable
label | 0994a12f-5bab-57f3-bc9f-caefbf4ae840 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Underslab for Area: |  |  |  |  | Yes | QA - Underslab Services Install | 1257f1c4-d6aa-4eac-a1fd-cfd2e7c67e4f
checkpoint-status |  |  | checkpoint | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | GAS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any other services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
checklist-flat |  |  | checklist | Concrete Slab on Grade for Area: |  |  |  |  | Yes | QA - Concrete Slab on Grade | 13dc4c18-7a4c-45b1-bd13-fd3173cc4c7c
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | Slab on grade – top of metal RL.
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Holding bolts in place.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checkpoint-status |  |  | checkpoint | Control joints / saw-cuts and depth.
checklist-flat |  |  | checklist | Comfloor for Area: |  |  |  |  | Yes | QA - Comfloor | 158d6ccc-bed3-44b9-a751-f5ba3979f6c6
checkpoint-status |  |  | checkpoint | Relevant falsework/propping, netting & edge protection installed, checked and acceptable
checkpoint-status |  |  | checkpoint | Setout and heights checked
checkpoint-status |  |  | checkpoint | All perimeter/edges installed & any penetrations correctly formed
checkpoint-status |  |  | checkpoint | Comfloor installation completed, reviewed and approved
checklist-sectioned |  |  | checklist | QA - Interior Fitout - TEST |  |  |  |  | Yes | QA - Interior Fitout - TEST | 579ddd04-4525-463d-81bf-caf87de34979
checkpoint-group |  |  | section | Plumbing First Fix
checkpoint-status |  |  | checkpoint | Plumbing first fix complete
boolean | 1654cbd1-0789-5ffc-ad12-d14b6f7cb887 |  | tickbox | Mixers are in correct position (hole allowance to work with tiles)
boolean | 185abf47-c78e-5b32-8802-809b2e6c9218 |  | tickbox | All water & gas risers are complete
boolean | e1b5b1de-4cae-54c5-b3d6-dd9a0f45b116 |  | tickbox | All stacks are level/plumb
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | dd66b7c2-ba2a-5371-a21e-5d5b30e99a5a |  | tickbox | Power points have been installed as per the electrical plans
boolean | 0a843057-ea49-58d5-a044-d118ad9a6044 |  | tickbox | All comms are installed to allow for good detailing around
boolean | 1e62d797-b72d-582d-ab18-fc82db2e787d |  | tickbox | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Mechanical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | 1c1eb34d-d231-5430-9e99-d95ef81ed4ae |  | tickbox | All aircon has been roughed in & tested
boolean | f04de3dd-424a-5917-84f8-60ebdf4d90f0 |  | tickbox | All mech has been roughed in & completed
boolean | 9008efbc-9f4c-5307-a418-8366cc5ab5b8 |  | tickbox | All services that go through fire rated walls to be treated with collars/fire rated sealant
boolean | 36fc68d3-128c-5331-8496-8e94728d64c4 |  | tickbox | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Passive Fire
checkpoint-status |  |  | checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Post Wall Linings
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for insulation
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for fire rated walls
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Bathroom & Laundry Waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Joinery Fit Out
checkpoint-status |  |  | checkpoint | All bathroom joinery installed as per specifications
checkpoint-status |  |  | checkpoint | All kitchen joinery installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Services Fit Out
checkpoint-status |  |  | checkpoint | Plumbing fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Electrical fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Internal Painting, Framing & Carpet
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint-status |  |  | checkpoint | Painting completed as per specs, correct paint product and colour used
checkpoint-status |  |  | checkpoint | Carpet installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Fire System
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinkler rough fit off completed
checkpoint-status |  |  | checkpoint | Sprinklers commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Scarbro Final Sign - Off
checkpoint-status |  |  | checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
boolean | 15feaecc-8625-586b-916a-eaf9750efe28 |  | tickbox | Scarbro - apartment final sign off
label | c5938551-b8d1-54b0-a61e-f54d508c18c2 |  | note | Click to attach signature sign off below
checklist-sectioned |  |  | checklist | Precast for Area: |  |  |  |  | Yes | QA - Precast Walls/Stairs/Balconies/Floors | 5abac006-ffb7-4c07-9fe3-4283a8913818
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast walls manufacturing completed and transported safely to the site
boolean | bfc1de35-9617-535d-b533-cf8865f87ec1 |  | tickbox | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Site Setout completed
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked
checkpoint-status |  |  | checkpoint | Checked rebar requirements for any insitu stich joints
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
checklist-flat |  |  | checklist | Grout for Area: |  |  |  |  | Yes | QA - Grout | 665c7347-7f32-4ac2-89ed-90acf537b4fc
checkpoint-status |  |  | checkpoint | Grouting works completed
label | d0caebbb-52b7-5d3c-b58f-ed830cf968e9 |  | note | Photos
checklist-flat |  |  | checklist | Waterproofing for Area: |  |  |  |  | Yes | QA - Waterproofing | 6e64fc1b-833e-408c-876a-66e758175de8
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist-sectioned |  |  | checklist | QA - Exterior Finishes - TEST |  |  |  |  | Yes | QA - Exterior Finishes - TEST | 93fcfe2e-39a7-496a-bff7-e1511279d47a
checkpoint-group |  |  | section | Building Wrap
checkpoint-status |  |  | checkpoint | Weatherline
checkpoint-status |  |  | checkpoint | Weatherline fixings
checkpoint-status |  |  | checkpoint | Weatherline taping
checkpoint-status |  |  | checkpoint | AT façade sealant
label | c36de85d-ad54-5264-8d83-2c37251e3563 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Cavity System
checkpoint-status |  |  | checkpoint | Head flashings
checkpoint-status |  |  | checkpoint | Cavity battens
checkpoint-status |  |  | checkpoint | Cavity batten fixings
checkpoint-status |  |  | checkpoint | Verman strips
checkpoint-status |  |  | checkpoint | Flashing tapes
label | 3763435b-84b1-5862-a063-590c7efb7ec1 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Joinery
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct jamb sizes
checkpoint-status |  |  | checkpoint | AT façade sealant
checkpoint-status |  |  | checkpoint | PEF backing rod
checkpoint-status |  |  | checkpoint | Flashings
label | 8a6123d9-4041-525a-8c92-0ad0117a2358 |  | note | Trades QA received & attached as applicable
label | 27953e34-15fe-5548-a464-5c2fbb4ef830 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior 1st fix
checkpoint-status |  |  | checkpoint | Plumbing drains for deck
checkpoint-status |  |  | checkpoint | Lights wiring
checkpoint-status |  |  | checkpoint | Hose taps pipework
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations
label | 59d8b792-ae19-52f8-85dd-2cfe90c23951 |  | note | Trades QA received & attached as applicable
label | 91db4804-3d76-5037-9214-375af88141ad |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Balustrades
checkpoint-status |  |  | checkpoint | Correct type
checkpoint-status |  |  | checkpoint | Correct sizes
label | f2ed91ac-4bb3-5c21-b73e-7bcdb2f990d3 |  | note | Trades QA received & attached as applicable
label | acbf949d-e8c1-5f35-8d13-e3775d389ea9 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior aluminium strouds
checkpoint-status |  |  | checkpoint | Strouds fixings/brackets
label | a47fa55e-1d53-54f7-983c-b4643c7003d7 |  | note | Trades QA received & attached as applicable
label | d74ef219-0909-53d0-9145-93792baa88c3 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior cladding Abodo
checkpoint-status |  |  | checkpoint | Correct colour
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Correct fixing centres
checkpoint-status |  |  | checkpoint | Boards plumb
checkpoint-status |  |  | checkpoint | Boards level
checkpoint-status |  |  | checkpoint | All joints acceptable/sealed
checkpoint-status |  |  | checkpoint | All cuts primed with 2 coats of stain
checkpoint-status |  |  | checkpoint | Correct moldings/flashings
label | fbfe2a60-fc03-5941-8647-99393d0c2f6e |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior plaster system
checkpoint-status |  |  | checkpoint | Exterior plaster
checkpoint-status |  |  | checkpoint | Colour exterior plaster colour
label | 8deb86d0-bf81-5bf6-b82f-03bc6e4fbd33 |  | note | Trades QA received & attached as applicable
label | fc432396-cb81-5dbb-b3a7-01d7692392a7 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Masonry
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Straight
checkpoint-status |  |  | checkpoint | Plumb
label | bf09a245-3d16-588b-8604-ad3d0b5c1e32 |  | note | Trades QA received & attached as applicable
label | 063c1ed9-e2cb-5dcf-8521-ce91020d2a1c |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior cladding espan cladding
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Correct colours
checkpoint-status |  |  | checkpoint | Straight
checkpoint-status |  |  | checkpoint | Correct flashing sizes
checkpoint-status |  |  | checkpoint | Correct flashing types
label | 79b6e392-b4b0-5219-8791-fed37abb0d91 |  | note | Trades QA received & attached as applicable
label | f8a5ba6a-175d-59f0-bbc1-db1ac2f4ea4e |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Correct colours
checkpoint-status |  |  | checkpoint | Straight
checkpoint-status |  |  | checkpoint | Correct flashing sizes
checkpoint-status |  |  | checkpoint | Correct flashing types
checkpoint-status |  |  | checkpoint | Roof penetrations sealed
checkpoint-status |  |  | checkpoint | Roof penetrations back flashed
label | 97428069-554a-5369-be2e-6a5a7d57b3cf |  | note | Trades QA received & attached as applicable
label | 975e3b80-b2e4-5c75-913a-bd27725490c1 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Gutters/downpipes
checkpoint-status |  |  | checkpoint | Correct size gutters
checkpoint-status |  |  | checkpoint | Correct downpipe sizes
checkpoint-status |  |  | checkpoint | Correct colours
checkpoint-status |  |  | checkpoint | Gutters straight
checkpoint-status |  |  | checkpoint | Downpipes straight
label | 28494b39-cb05-554a-b3b9-824d3339b9a4 |  | note | Trades QA received & attached as applicable
label | 19091612-08b6-5dbe-bd0a-f47cbeddbae9 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior painting
checkpoint-status |  |  | checkpoint | Abodo stain
checkpoint-status |  |  | checkpoint | Soffit colours
label | 6541c954-d9e9-5eb5-afd5-14d455f34017 |  | note | Trades QA received & attached as applicable
label | 5f110152-8b13-5805-9afa-dc4a17910ee5 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Letterboxes
checkpoint-status |  |  | checkpoint | Correct colour
checkpoint-status |  |  | checkpoint | Correct size
checkpoint-status |  |  | checkpoint | Correct position
label | 79d2e23c-d7c7-5572-8e7a-8ae4a266c882 |  | note | Trades QA received & attached as applicable
label | 6d8dd19b-dcfa-58a5-9828-cd67546146c3 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Deck membrane
checkpoint-status |  |  | checkpoint | Primer coat to plywood
checkpoint-status |  |  | checkpoint | Correct membrane
checkpoint-status |  |  | checkpoint | Correct laps
checkpoint-status |  |  | checkpoint | Correct upstands
checkpoint-status |  |  | checkpoint | No damage
label | 735b7d92-1c22-5276-a67b-30383763fcfd |  | note | Trades QA received & attached as applicable
label | 527ff990-bec1-52bc-8f3a-86fbb5b39ecd |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior 2nd fix services
checkpoint-status |  |  | checkpoint | Plumbing drains for decks
checkpoint-status |  |  | checkpoint | Downpipes
checkpoint-status |  |  | checkpoint | Lights
checkpoint-status |  |  | checkpoint | Hose taps
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations complete
label | 4e294456-2f64-5daf-a031-6812604d687f |  | note | Trades QA received & attached as applicable
label | 57055a20-5c0e-5b79-b6f8-1b2bd512d3c2 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Fins
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | End caps installed
label | cfa905c3-7586-5d94-acfb-8138d5f5817c |  | note | Trades QA received & attached as applicable
label | 92dd64e3-7eee-5218-99e2-38a3f887968b |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | QA - Roof Framing TEST |  |  |  |  | Yes | QA - Roof Framing TEST | a07646be-3cef-4c40-8192-a810557e4a7f
checkpoint-status |  |  | checkpoint | Correct rafter sizes
checkpoint-status |  |  | checkpoint | Correct timber treatment
checkpoint-status |  |  | checkpoint | Correct rafter centres
checkpoint-status |  |  | checkpoint | Bracing correct
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Hold down fixings
checkpoint-status |  |  | checkpoint | Connections to masonry
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
label | 001b62bd-b7a5-546d-bdbf-5d96b85075bf |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Roof Framing |  |  |  |  | Yes | QA - Roof Framing | dc9b4a75-5433-4526-9479-8e7affdfeb2f
checkpoint-status |  |  | checkpoint | Correct timber treatment
checkpoint-status |  |  | checkpoint | Correct fixings (incl spacing)
checkpoint-status |  |  | checkpoint | Hold down fixings
checkpoint-status |  |  | checkpoint | Connections to masonry
checkpoint-status |  |  | checkpoint | Correct flashing sizes
checkpoint-status |  |  | checkpoint | Correct flashing types
checkpoint-status |  |  | checkpoint | Roof penetrations sealed
checkpoint-status |  |  | checkpoint | Roof penetrations back flashed
checkpoint-status |  |  | checkpoint | Vaproshield (when required)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
label | 2f28bb0e-d969-5220-917b-9455ec4a6185 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request holdpoint
checklist-sectioned |  |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pours and Slabs | e0f8db5e-d9ad-44c4-9a8e-2e5d5fdb7691
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | 4746d3b9-af2c-53ca-bef1-03ee77a1ca28 | DataPoint is missing 'button' values | button | Size and type correct to specification
boolean | 5a82f304-aa6d-52b5-8051-0b99323d6b07 |  | tickbox | Reinforcing spacing and location correct | Yes, N/A
boolean | 58c77393-dc2a-5040-980d-768868150d77 |  | tickbox | Specified covers checked/correct | Yes, N/A
boolean | 9e4607b0-3b82-590a-bdcc-0b9196917776 |  | tickbox | Splice laps checked/correct | Yes, N/A
boolean | cbb2eab7-e151-5daa-a6bc-bb31854a3942 |  | tickbox | Any starter bars are installed correctly (location, size and spacing ) | Yes, N/A
boolean | adf8a497-c74c-5c93-9be5-159ec1c39e17 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed | Yes, N/A
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | 7a06dc70-161f-556e-9a20-4389d8d58e21 |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | ea588747-a9a4-503b-bcd1-22c8b54eb4c9 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | 17d87d49-05d5-50b8-a371-7b32e01c9423 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Footings for Area: |  |  |  |  | Yes | QA - Footings | e46f039a-1870-4649-a54a-f4c2d9d7d8ec
checkpoint-status |  |  | checkpoint | Drawings photo with location
checkpoint-status |  |  | checkpoint | Set out correct
checkpoint-status |  |  | checkpoint | Boxing correct
checkpoint-status |  |  | checkpoint | Reinforcing
checkpoint-status |  |  | checkpoint | Starter setout
checkpoint-status |  |  | checkpoint | Inspect
checkpoint-status |  |  | checkpoint | Pour