## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Add Variation (V.180821) |  |  |  |  | Yes | Add Variation (V.180821) | 14ad46fb-c6aa-413b-b6ee-a5e2e8a807ec
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 08c12357-d6f0-5bf7-9fd1-b1994f90d34a |  | textbox | Reference/Drawing/Instruction Number
text | aaadf8e3-5426-587c-852f-82af4fb01750 |  | textbox | Variation Area
text | 25593235-0700-5add-a4ae-cd11fe53baf9 |  | textbox | Materials & labour breakdown (Names, Hours & Material(s)/Quantities)
checkpoint-status |  |  | checkpoint | Variation Completed
label | 168db01d-2cb1-5967-a5e3-d03ea5d4f8d5 |  | note | Once variation information is completed - Please SEND report to Builder OR request Sign-off below
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Spray ITP (V.180821) |  |  |  |  | Yes | Spray ITP (V.180821) | 63e76685-bd34-4098-b0bd-1098d141e1ca
checkpoint-group |  |  | section | Preparation of Substrate Prior to Application
checkpoint-status |  |  | checkpoint | All concrete grout or mortar spills have been removed
checkpoint-status |  |  | checkpoint | All protruding tie wire, nails and or bolt removed from surface
checkpoint-status |  |  | checkpoint | All bony and defective concrete finishes have been repaired with approved repair materials
checkpoint-status |  |  | checkpoint | All diesel or oil spills have been removed and the area degreased prior to application
checkpoint-status |  |  | checkpoint | Substrate wet blast cleaned using 3000 PSI Water Blaster and allowed to air dry prior to priming
checkpoint-status |  |  | checkpoint | Substrate prepared prior to application of concresive
checkpoint-status |  |  | checkpoint | Polyurethane fillets to be installed into all junctions between horizontal and vertical surfaces
checkpoint-status |  |  | checkpoint | Cracks in concrete over 3mm have been ground out and sealed with polyurethane sealant
checkpoint-status |  |  | checkpoint | Expansion joints to be treated have been pretreated as per detail
checkpoint-status |  |  | checkpoint | Have all sources of dust/debri like power saws cutting timber etc been controlled prior to our application
checkpoint-status |  |  | checkpoint | Have all sources of water, mist or spray been investigated and controlled prior to application
checkpoint-status |  |  | checkpoint | Are all penetrations in place that are needed for services to this area
checkpoint-status |  |  | checkpoint | Is the area barricaded and signed to prevent workers transiting across our prepared surfaces
checkpoint-group |  |  | section | Application of Membrane System
checkpoint-status |  |  | checkpoint | AM Readings Recorded
text | e7ca1d02-e823-5b22-a72e-b5c6161cdd30 |  | textbox | Air Temp
text | ffa29c4f-831d-5187-9f12-93578b60c29c |  | textbox | Humidity
text | 1b83b19a-0f93-5e57-8e4a-e4a915f3f1f0 |  | textbox | Dewpoint
text | 1b567c88-b4b7-5ee9-98a2-011a7a7b5459 |  | textbox | Moisture Content
text | ef6fcf55-264c-519b-a25f-024b35f60e32 |  | textbox | Weather Forecast
checkpoint-status |  |  | checkpoint | PM Readings Recorded
text | 2c17cfd2-8927-5318-aa60-44827264a455 |  | textbox | Air Temp
text | 8d31e1df-d5b7-5a52-bb4e-90d41d0cff02 |  | textbox | Humidity
text | accf159d-11d8-5a3f-a44e-d6555b9aef60 |  | textbox | Dewpoint
text | 472908fc-e73c-5e40-8535-151090ca41c3 |  | textbox | Moisture Content
text | 63f4876f-98ac-57a8-b31e-a58754dbf8c0 |  | textbox | Weather Forecast
checkpoint-status |  |  | checkpoint | Chemspray 117 Primer
text | 335a9dd9-6f8b-5eb1-921c-1e4a27c6211f |  | textbox | Area
text | 7fa8dff5-3da9-565d-80ca-7f160e8670c6 |  | textbox | Coverage
text | 4de97e58-ac6d-5989-a24a-8e1e3bee08fe |  | textbox | QTY A |  |  | Kg
text | c717412e-9d78-5495-903c-92858be1eb78 |  | textbox | QTY B |  |  | Kg
text | d92392a8-89aa-5fdf-9e71-6f9180d24676 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Chemspray 790 Part A
text | e3ccdb61-e66b-5b23-a672-ae185f3291a5 |  | textbox | Area
text | f27a6dca-cbf5-5dda-8d9b-bdc037de1129 |  | textbox | Coverage
text | 91256849-29c5-5284-b160-f0ba34b5e262 |  | textbox | QTY A |  |  | Kg
text | 5e069658-e751-5bca-9acb-b8cbd4c071b1 |  | textbox | QTY B |  |  | Kg
text | d9600150-37a5-5f0b-959c-ea4dda934f11 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Chemspray 790 Part B
text | db67e6e7-a4fd-5954-813f-495b0beb836d |  | textbox | Area
text | fffef92b-d819-5eab-99ec-707e798d89b1 |  | textbox | Coverage
text | 502d4f40-b820-595b-be50-6b6afe69bae6 |  | textbox | QTY A |  |  | Kg
text | 2c903e27-8e4d-579a-bf6b-820592619123 |  | textbox | QTY B |  |  | Kg
text | e910085d-bea6-5f46-ad88-f9d8a7c7a127 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Ultraure Top Coat
text | 100b99e9-9a21-50df-b9b6-54239d439396 |  | textbox | Area
text | 50c7c2a8-de07-59fc-bea5-f638937df468 |  | textbox | Coverage
text | 655a1061-65c6-50d9-9cf2-3825f49395c8 |  | textbox | QTY A |  |  | Kg
text | 3f7056f4-4c9f-5639-b306-770efca93c60 |  | textbox | QTY B |  |  | Kg
text | c4937f3c-e7c5-58a6-846d-db2805334690 |  | textbox | Total
checkpoint-status |  |  | checkpoint | Aquaguard Top Coat
text | 600b4297-99c4-5b78-b27a-fc78e3f997c4 |  | textbox | Area
text | 7edc066f-b132-5cf8-9ae6-ee23aae66225 |  | textbox | Coverage
text | 807629d5-69c8-5029-b419-08eb2388918c |  | textbox | QTY A |  |  | Kg
text | dfe00cfa-10c8-5af6-beb1-4485f4e8395a |  | textbox | QTY B |  |  | Kg
text | 72a649f6-5e4d-57ae-9e46-5b59493b52e1 |  | textbox | Total
folder-normal |  |  | checklist | Project - |  |  |  |  | Yes | Add Project Template | 664e587b-0470-4f62-8dd1-69f40f4592e8
checklist-flat |  |  | checklist-flat | Job Details
folder-normal |  |  | folder-normal | QA
folder-normal |  |  | folder-normal | OH&S
folder-normal |  |  | folder-normal | Variations
folder-normal |  |  | folder-normal | Site Issues/Delays
checklist-sectioned |  |  | checklist | ITP Liquids (V.071223) |  |  |  |  | Yes | ITP Liquids V2 | 684c9f19-f22b-4578-8b80-8a27a0391c5f
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | f7379baa-1819-5fd5-a9de-a11979479665 |  | textbox | Area/Grid Reference
text | 563dc4e9-7eb0-5678-894a-7dbc06e2454c |  | textbox | Level
text | 97dfa1b7-5c99-5289-a959-78e62a2182ec |  | textbox | Description of Works Performed
text | c8201e77-a24c-5d18-9d1a-3875267ce2d6 |  | textbox | Product supplier
text | e21b4032-03e5-5799-868d-43d56a48e969 |  | textbox | Products used
checkpoint-group |  |  | section | Substrate inspection
checkpoint-status |  |  | checkpoint | Is the substrate suitable for application
checkpoint-status |  |  | checkpoint | All concrete grout or mortar spills have been removed
checkpoint-status |  |  | checkpoint | All protruding tie wire, nails and or bolt removed from surface
checkpoint-status |  |  | checkpoint | All bony and defective concrete finishes have been repaired with approved repair materials
checkpoint-status |  |  | checkpoint | Moisture content in the concrete lower than 4.5% are required by Manufacturer using Tramex CME moisture meter
checkpoint-status |  |  | checkpoint | HOLD POINT MANUFACTURER INSPECTION
holdpoint |  |  | signoff | Manufacturers Representative Sign-Off (attach signature)
checkpoint-group |  |  | section | Membrane Installation
checkpoint-status |  |  | checkpoint | Is the area barricaded and signed to prevent workers transiting across our prepared surfaces
checkpoint-status |  |  | checkpoint | Have all sources of dust/debris like power saws cutting timber etc been controlled prior to our application
checkpoint-status |  |  | checkpoint | Cracks in concrete over 3mm have been ground out and sealed with polyurethane sealant
checkpoint-status |  |  | checkpoint | Install 10mm radius Polyurethane coves been installed to all intersections
checkpoint-status |  |  | checkpoint | Install a minimum of 100mm turnup above finished floor level as per Manufacturers requirements
checkpoint-status |  |  | checkpoint | Install Tremco Vulkem 171 primer @7-10L/m2 and allow to cure 30-60 minutes or until tacky
checkpoint-status |  |  | checkpoint | Install Tremco Vulkem 350 base coat to manufacturers requirements @.81-1.08m2/L and allow to cure for 12 hours
checkpoint-status |  |  | checkpoint | Install Tremco Vulkem 951 top coat(if required) to manufacturers requirements @ 3.23m2/L and allow to cure for 24 hours
checkpoint-status |  |  | checkpoint | Check for each of the below and detail as per Tremco Standard details. Attach photos/comments where applicable
boolean | d4238faf-b2e6-50e7-9c5d-33607ee8ad8d |  | tickbox | Penetrations
boolean | 6539bd1a-8ace-5e02-976b-1b7d7cd8a293 |  | tickbox | Outlets
boolean | ad8ffd69-dbb4-5770-9914-fe39a2e591b2 |  | tickbox | Upstands
boolean | a421fbf5-5d36-5bac-b81d-9e6b9d3c2fd8 |  | tickbox | Expansion joints
checkpoint-group |  |  | section | Membrane Testing
checkpoint-status |  |  | checkpoint | Flood test areas for a minimum of 24hrs
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | Has membrane been installed in accordance with AS4654.1&4654.2 (waterproof membranes for external above ground use)
checkpoint-status |  |  | checkpoint | Application as per manufacturer’s instructions
checkpoint-status |  |  | checkpoint | Waterproofing works completed - Area left clean & tidy
label | 93115484-109a-5187-b626-7cdf91675069 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-status |  |  | checkpoint | Release to next Trade
checkpoint-status |  |  | checkpoint | Bicon Representative Sign-Off (attach signature)
checkpoint-status |  |  | checkpoint | Builders Representative Sign-Off (attach signature)
checkpoint-status |  |  | checkpoint | Manufacturers Representative Sign-Off (attach signature)
checklist-flat |  |  | checklist | Add Site Issue (V.180821) |  |  |  |  | Yes | Add Site Issue (V.180821) | 84840cb4-5150-4dfd-a929-f0127beff914
checkpoint-status |  |  | checkpoint | Site Issue Logged - Pass once detailed entered
text | d670ae17-84a0-5947-9dd8-5b0528c7d575 |  | textbox | Details
label | c12ff5ca-b95e-5186-9ba8-d769658a6512 |  | note | Photos/Comments added below as applicable
checklist-sectioned |  |  | checklist | ITP Sheet (V.180821) |  |  |  |  | Yes | ITP Sheet (V.180821) | 8d289a04-096a-45c3-b58f-71c82d000096
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 0e478b34-367b-5754-9fc2-8b516af62b45 |  | textbox | Area/Grid Reference
text | a5f4d70d-2d37-513f-87ee-7deaf59d8d6f |  | textbox | Level
text | 88ffbc29-3cea-5f2e-ba6b-29439670d86a |  | textbox | Room
text | 53b78dd4-9eef-55ec-9808-52b5f3609bf4 |  | textbox | Description of Works Performed including Materials Used
checkpoint-group |  |  | section | Membrane Inspection
checkpoint-status |  |  | checkpoint | Is the substrate suitable for application
checkpoint-status |  |  | checkpoint | Has cement or paragranular coves been installed at all intersections
checkpoint-status |  |  | checkpoint | Is there a minimum of 100mm turnup above finished floor level
checkpoint-status |  |  | checkpoint | Has the minimum sheet overlap been achieved and have all overlaps been trowelled off or seam taped
checkpoint-status |  |  | checkpoint | Has termination bar been installed
checkpoint-status |  |  | checkpoint | Is protection board required - Pass=Yes / Fail=No
label | d8e64903-c894-529b-b6fa-a5b67da64f9d |  | note | If so, has it been supplied/installed upon completion
checkpoint-status |  |  | checkpoint | Has membrane been installed to Australian standards
label | 9c11342d-1e58-5689-a1bb-d89ec759e1b0 |  | note | Check details at each of the below and attach photos/comments as applicable
boolean | 0eb84068-1793-5f35-9db7-fb2b8dd44685 |  | tickbox | Penetrations
boolean | 32d6c2e1-82ba-5b40-9024-f723db459005 |  | tickbox | Outlets
boolean | cde7008c-ad7b-5bdc-bf1c-ee6ee79b7613 |  | tickbox | Upstands
boolean | 403fd480-0a74-5bd1-b1a3-9adf04bee514 |  | tickbox | Expansion joints
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | Waterproofing works completed to specification/drawings - Area left clean & tidy
label | 2e18593e-9bfb-5e3a-ae36-e953bb627faa |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
select | c0cd9c6b-9a3c-5c1f-99ef-9b4c1769e478 |  | dropdown | Release to next Trade | Yes, No
text | b07eae50-d11a-5419-b55e-859b4e0f22f8 |  | textbox | Inspection By
boolean | 9a9871e3-2dfb-5bed-b06b-154680be6da3 |  | tickbox | Bicon Representative Signature sign-off added
boolean | 6fcfb252-aa73-5972-8844-5e922961b6de |  | tickbox | Builders Representative Signature sign-off added
label | 5526b915-dcc1-5e53-b1c0-165ab4135625 |  | note | Attach Signature Sign-offs below
checklist-sectioned |  |  | checklist | ITP Liquids (V.180821) |  |  |  |  | Yes | ITP Liquids (V.180821) | c263c0ac-ed66-467d-9c13-e50f624927e9
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 7c187e32-fd87-5e69-8fc2-adbe92e7bdab |  | textbox | Area/Grid Reference
text | f5616f16-639c-50ba-90d1-8207d983908a |  | textbox | Level
text | e38490d6-5111-5620-af20-b1d9e15a05da |  | textbox | Room
text | 011ae90e-f60a-571e-96b2-d8f0f5c5b346 |  | textbox | Description of Works Performed including Materials Used
checkpoint-group |  |  | section | Membrane Inspection
checkpoint-status |  |  | checkpoint | Is the substrate suitable for application
checkpoint-status |  |  | checkpoint | Have Polyurethane coves been installed to all outlets & intersections
checkpoint-status |  |  | checkpoint | Is there a minimum of 100mm turnup above finished floor level
checkpoint-status |  |  | checkpoint | Has membrane been installed to manufacturer's specified thickness
checkpoint-status |  |  | checkpoint | Has membrane been installed to Australian standards
label | dc230e13-611b-55f1-8842-89357e14db66 |  | note | Check details at each of the below and attach photos/comments as applicable
boolean | eb3c57dc-93c4-5ad8-b0df-3171908bb657 |  | tickbox | Penetrations
boolean | 678c9527-7eac-5653-af79-311c9ee3bfdf |  | tickbox | Outlets
boolean | 6393ffc2-4a46-5f78-9228-b30b55ff6666 |  | tickbox | Upstands
boolean | cf34effa-96aa-5c49-99f3-749c478ca9b5 |  | tickbox | Expansion joints
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | Application as per manufacturer’s instructions
checkpoint-status |  |  | checkpoint | Waterproofing works completed to specification/drawings - Area left clean & tidy
label | 4e8012e1-78f3-5eca-8731-baa195413b50 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
select | 5946037e-95be-59d8-b4be-749eece65950 |  | dropdown | Release to next Trade | Yes, No
text | 1572d4b2-07ea-5381-8f98-036939e8ba51 |  | textbox | Inspection By
boolean | f4634eb9-6feb-5f09-9fbb-3a8321e90cf0 |  | tickbox | Bicon Representative Signature sign-off added
boolean | e1affe1f-5459-55f0-ae47-fc4e177d66c8 |  | tickbox | Builders Representative Signature sign-off added
label | 4232613c-4d98-56d3-8ea6-e9bed93493c2 |  | note | Attach Signature Sign-offs below
checklist-sectioned |  |  | checklist | Waterproofing ITP (V.180821) |  |  |  |  | Yes | Waterproofing ITP (V.180821) | fd8af85c-c6db-4c72-b4de-c773c6dcbc07
checkpoint-group |  |  | section | Measure up Details
checkpoint-status |  |  | checkpoint | Works Undertaken Recorded - As per below
text | adad3c6c-72b3-564b-9aa1-e3ee1ab85581 |  | textbox | Prep |  |  | m2
text | 847a8573-3c92-596a-9a3b-ae7ca64fc6ec |  | textbox | Cove |  |  | LM
text | e871e530-3c94-5a7d-bbe6-5d5c6a730f0a |  | textbox | Prime |  |  | m2
text | ab9fd1f9-4157-5513-a437-377bc33c7f05 |  | textbox | Mem 1 |  |  | m2
text | 321b3e1d-fd1d-5ebb-a657-c4e5f7834e21 |  | textbox | Mem 2 |  |  | m2
text | 8f38c092-263d-597e-9fa7-5578ffd3929d |  | textbox | Coat 1 |  |  | m2
text | 26527c84-83c2-5c19-9d53-c0ff412638e6 |  | textbox | Coat 2 |  |  | m2
text | 021e6e05-3f02-59e1-bc2e-d4f656802e3f |  | textbox | Coat 3 |  |  | m2
text | e5275fce-15c3-5e4b-9d30-3fa068d9ebc3 |  | textbox | N/Slip |  |  | m2
text | 1a74b88c-3b46-502c-9b78-f72c802a717f |  | textbox | T/Up |  |  | LM
text | ec33cbe3-f8a5-5c8a-972c-1b46354c4c4a |  | textbox | Flashing |  |  | LM
text | 678a84bc-9746-57ad-9aff-c7fa382160f9 |  | textbox | P/Board |  |  | M2
text | 2d90e747-c2ed-51aa-a48a-775b761b7316 |  | textbox | D/Cell |  |  | m2
text | 23aaddd8-474a-5dea-93de-c46525ed1a04 |  | textbox | Outlets |  |  | NO
text | 2fada568-9ff8-55b4-acaf-55532f989a00 |  | textbox | Leak/CF |  |  | NO
text | 4f1124ac-10db-5e9f-9030-fe96cdc204b1 |  | textbox | Spindles |  |  | NO
text | a922b9e8-00ec-517a-9017-c082b70058d9 |  | textbox | S/Rose |  |  | NO
text | 64f308d4-0143-5023-9166-20580ed7a429 |  | textbox | E/Joint |  |  | LM
checkpoint-group |  |  | section | Substrate & Preparation Checks
checkpoint-status |  |  | checkpoint | Is substrate suitable for the application of the system
checkpoint-status |  |  | checkpoint | Does substrate fall to outlets without ponding water
checkpoint-status |  |  | checkpoint | Have all nails or bolts been removed and holes filled
checkpoint-status |  |  | checkpoint | Is substrate dry? (Dampened if required by specification)
checkpoint-status |  |  | checkpoint | Did you (sweep) (vacuum) (pressure wash) substrate
checkpoint-status |  |  | checkpoint | Have you installed coves at intersections
select | 9f1b95cb-664b-518b-80ee-9983c82eaf89 |  | dropdown | Coves | S/C, P/U
checkpoint-status |  |  | checkpoint | Have you primed the area including turn up to height
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Have you installed sheet system
select | a239cda6-7eb7-5cf4-b121-ea6cab76ab8a |  | dropdown | No of Layers | 1 Layer, 2 Layer
checkpoint-status |  |  | checkpoint | Did you turn sheet system up walls 150mm above FFL
checkpoint-status |  |  | checkpoint | Did you overflash the turn up
select | 1791fd24-4892-5cb7-b4c3-1538bcf428f9 |  | dropdown | Options | P/Seal, T/Bar, Chased
checkpoint-status |  |  | checkpoint | Do floor outlets have clamping bands to restrain membrane
checkpoint-status |  |  | checkpoint | Have metal flanges been installed for all PVC pipe installs
checkpoint-status |  |  | checkpoint | Have expansion joints been treated as per design required
checkpoint-status |  |  | checkpoint | Are protection boards installed over system in this area
checkpoint-status |  |  | checkpoint | Has drainage cell been a requirement and is it installed
checkpoint-status |  |  | checkpoint | Are there Concrete or screeds to be placed over our system - Pass=Yes / Fail=No
checkpoint-status |  |  | checkpoint | Have you advised builder about slip sheets under screeds
checkpoint-status |  |  | checkpoint | Have you installed coating system
select | 5388509d-0cdf-55f2-b99c-10ba16036105 |  | dropdown | Coats | 1 Coat, 2 Coats, 3 Coats
checkpoint-status |  |  | checkpoint | Have you reinforced the floor wall/wall wall junctions
checkpoint-status |  |  | checkpoint | Are leak control flanges or outlets in place in the area
checkpoint-status |  |  | checkpoint | Have you turned up a minimum of 100mm above FFL
checkpoint-status |  |  | checkpoint | Have you terminated a minimum 200mm above s/rose
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Waterproofing works completed to specification/drawings - Area left clean & tidy
label | 679b2349-b3d7-58f6-ba24-8743f6dda4e4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
text | 20603d47-d135-5473-aff0-b0103b497608 |  | textbox | Applicators Name
boolean | 00b01b34-6a88-5e1f-923e-1c54ebc38d48 |  | tickbox | Bicon Representative Signature sign-off added
boolean | b70ef0ab-40a4-5ad5-a4a7-7bbcd6711bec |  | tickbox | Builders Representative Signature sign-off added
label | 3aec5156-25cc-5292-a1ae-ebd3badaab52 |  | note | Attach Signature Sign-offs below