## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Earthworks - 101 - Rev A | itp |  |  |  |  | ITP - Earthworks - 101 - Rev A
section | 3.01 General
checkpoint | 3.01.01 - Precondition Surveys
label | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
label | Standard / Specification - PS 2.13
label | Verifying Document - Precondition Survey
label | Frequency - Prior to the Contractor taking possession of the Site.
label | Verification Activity: Activity - H
label | Verification Activity: By - PM
section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
checkpoint | 4.01.01 - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
label | Standard / Specification - PS 15.7.3 Appendix XIII
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.03 - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
label | Standard / Specification - PS 15.7.3 Appendix XIII
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0-400 M3 – 2 Tests
label | ○ 400-1,500M3 – 3 Tests
label | ○ 1,500-4,000M3 – 4 Tests
label | ○ >4,000M3 - 1 Test For Each Additional 1,000M3
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | 4.02 Type A2 (Cohesive Site Won Material Fill)
checkpoint | 4.02.01 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02.02 - Insitu Property Test Sampling
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Peak Hand Vane, Peak Shear Strength, Liquid Limit, Maximum and Optimum Moisture Content, and inspected for containing allophane, organics or other deleterious materials.
label | Standard / Specification - PS 15.7.3 Appendix XIII
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - Frequency TBC as not provided
holdpoint | AUTHORITY HOLDPOINT
section | 4.03 Type A2 (Granular Site Won Material Fill)
checkpoint | 4.03.01 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03.02 - Insitu Property Test Sampling
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
label | Standard / Specification - PS 15.7.3 Appendix XIII
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
label | Comments / Closeout Details - Frequency TBC as not provided
holdpoint | AUTHORITY HOLDPOINT
section | 4.04 Type A3 (Site Won Landscaping Fill)
checkpoint | 4.04.01 - On Site track-able Testing
label | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
label | Standard / Specification - PS 15.7.3
label | Verifying Document - Visual Site Record
label | Frequency - Prior to Sampling
label | Verification Activity: Activity - W
label | Verification Activity: By - PE
checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
label | Standard / Specification - PS 15.7.3, PS 15.13
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04.03 - Insitu Property Test Sampling
label | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
label | Standard / Specification - PS 15.7.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.05 Topsoil
checkpoint | 4.05.01 - Topsoil
label | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus.
label | ○ The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
label | Standard / Specification - PS 15.7.3
label | Verifying Document - Site Record
label | Frequency - During Stripping
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | 4.06 Stabilisation
checkpoint | 4.06.01 - Stabilising Agent and Source
label | Acceptance / Conformance Criteria - The Engineer shall approve the stabilising agent source and the quality. The producer shall certify the grade of the stabilising agent at least two weeks before commencement of the works.
label | Standard / Specification - PS 15.9 NZTA B/5 NZTA M/15
label | Verifying Document - Producer Certification or Testing Certificate
label | Frequency - At least two weeks before commencement of the works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.06.02 - Water
label | Acceptance / Conformance Criteria - The water quality and suitability must be approved by the Engineer at least two weeks before commencement of the works.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Source Details
label | Frequency - At least two weeks before commencement of the works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Settlement Levelling Materials
label | Acceptance / Conformance Criteria - Settlement levelling pins shall be as specified in the drawings and include 15MPa concrete with 12x100mm stainless steel benchmark pins.
label | Standard / Specification - PS 15.12.4
label | Verifying Document - Datasheet / Mix Design
label | Frequency - Prior to installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.06 Earthworks General
checkpoint | Geotextile on Undercut to Waste and Backfill
label | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
label | Standard / Specification - PS 15.10.9
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 5.01 Site Clearance
checkpoint | 5.01.01 - Site Clearance
label | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
label | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
label | Verifying Document - Site Record
label | Frequency - Prior to excavation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.01.02 - Dump Site Approval
label | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
label | Standard / Specification - NZTA F/1 - 9.4
label | Verifying Document - Site Record
label | Frequency - Prior to Stockpiling
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.03 - Mulching
label | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
label | Standard / Specification - PS 14.1.1
label | Verifying Document - Site Record
label | Frequency - During Clearing
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 6.01 General Earthworks
checkpoint | 6.01.01 - Earthworks Methodology
label | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
label | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
label | Verifying Document - Approved Methodology
label | Frequency - Prior to Earthworks
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.02 - Temporary Excavation Approval
label | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Excavation.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.03 - Temporary Works Design
label | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
label | Standard / Specification - PS 15.13
label | Verifying Document - Approved Design
label | Frequency - Prior to Excavation.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.04 - Temporary Stockpiles
label | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
label | Standard / Specification - PS 15.6.5
label | Verifying Document - Engineers Approval
label | Frequency - Prior to stockpiling
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.05 - Surplus Material
label | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
label | Standard / Specification - PS 15.1
label | Verifying Document - Engineers Approval
label | Frequency - Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.06 - As-Builts
label | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Standard / Specification - PS 15.11.7
label | Verifying Document - Survey Records
label | Frequency - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
section | 6.02 Borrow Site and Haul Roads
checkpoint | 6.02.01 - Borrow and Filling Sites
label | Acceptance / Conformance Criteria - The contractor shall submit the details for review and approval of Borrow or Filling Sites.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Borrow or Filling
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02.02 - Haul Road Approval
label | Acceptance / Conformance Criteria - The Contractor shall construct and maintain all temporary haul roads as required to carry out the works.
label | ○ Haul Roads located within the existing farm shall be designed to allow farm operation movements through/over the haul road.
label | ○ The proposed haul road plan shall be submitted to the Engineer for prior acceptance.
label | Standard / Specification - 15.6.3
label | Verifying Document - Approval Haul Road Plan
label | Frequency - Prior to Hall Road Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02.03 - Haul Road Asbuilts
label | Acceptance / Conformance Criteria - The Contractor shall provide to the Engineer as built drawings of the constructed haul road within 2 weeks after placement of the haul road. The as-built plan is to show the road location, extent of batter slopes and temporary and permanent structures.
label | Standard / Specification - 15.6.3
label | Verifying Document - Haul Road Asbuilts
label | Frequency - 2 weeks after placement of the haul road
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02.04 - Borrow Site Trial Methodology
label | Acceptance / Conformance Criteria - The Contractor will be responsible for the selection of plant for the site trials. The Contractor shall submit their details of their plant and also methodology for the site trials at least 1 week prior to commencement on site.
label | Standard / Specification - PS 15.8
label | Verifying Document - Borrow Site Trial Methodology
label | Frequency - At least 1 week prior to commencement on site.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02.05 - Borrow Site Trial
label | Acceptance / Conformance Criteria - Prior to the establishment of the onsite borrow site the following trial shall be completed to confirm the viability of the proposed borrow site.
label | Standard / Specification - PS 15.8, PS 15.13
label | Verifying Document - Approval Trial Results
label | Frequency - Prior to the establishment of the onsite borrow site
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.02.06 - Stabilising Agent - Trial
label | Acceptance / Conformance Criteria - The rate of lime application shall be determined during the borrow site trials. This is determined as the quantity of stabilising agent in kilograms/m².
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Approved Application Rate
label | Frequency - Prior to the establishment of the onsite borrow site
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.03 Stabilisation
checkpoint | 6.03.01 - Hand Spreading
label | Acceptance / Conformance Criteria - When using bagged stabilising agent, check and record the distribution of bags.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - During Spreading
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.02 - Mechanical Spreading
label | Acceptance / Conformance Criteria - Check the rate of spread by placing either a canvas cover or tray with an area of 1m² in the path of the spreader and weighing the quantity of stabilising agent deposited thereon or by counting and recording the number and spacing of bags when laid out.
label | ○ The percentage rate of spread must not differ by more than 0.5% by mass from the specified stabilising agent content.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Mat Test
label | Frequency - Every 400m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.03 - Constructed Thickness
label | Acceptance / Conformance Criteria - The thickness of the compacted stabilising agent treated layer will be within plus 40mm to minus zero for 90% of the sample.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.04 - Preparation Of Formation
label | Acceptance / Conformance Criteria - Scarify soil full width to a depth of 10mm greater than that required for the stabilising agent treatment.
label | ○ Remove granular particles larger than 100mm in any dimension.
label | ○ Check the depth of scarification by comparing the level at a point on the ground surface prior to scarification to the level on the unscarified soil at that point beneath scarified material.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.05 - Stabilising - Weather
label | Acceptance / Conformance Criteria - Do not spread or mix stabilising agent treated material when the ground temperature is less than 3°C or during heavy rain.
label | ○ Spread bulk stabilising agent with a suitably calibrated distributor.
label | ○ Fit a curtain to the distributor when using stabilising agent to minimise it being blown by the wind.
label | ○ Do not spread stabilising agent when the mean wind velocity exceeds 15 knots.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Day
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.03.06 - Spreading Bagged Stabilising Agent3
label | Acceptance / Conformance Criteria - Carry out by spotting individual bags at spacing's appropriate to the application rate. The Engineer to inspect and approve the spacing's before the bags are emptied on the formation.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.07 - Spreading Quicklime
label | Acceptance / Conformance Criteria - Quicklime shall only be supplied in granulated form.
label | ○ When spreading quicklime, use a water cart fitted with a fine mist spray bar or other suitable device to slake the quicklime.
label | ○ Water must be applied to the quicklime until complete slaking has occurred.
label | ○ Do not commence mixing and pulverising until the quicklime has fully slaked.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.08 - Traffic
label | Acceptance / Conformance Criteria - After spreading, do not allow traffic to pass over the spread stabilising agent until mixing has been completed.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.03.09 - Pulverisation And Mixing
label | Acceptance / Conformance Criteria - Mixing of hydrated lime should follow immediately behind the spreader and in no case should there be a delay of more than one working day.
label | ○ If a delay longer than one working day cannot be avoided, add lime at not less than 4% of the dry weight of the soil and ensure that mixing is carried out immediately.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.03.10 - Initial Curing
label | Acceptance / Conformance Criteria - Depending on conditions allow 1 - 4 hours before compaction, for soils in which conditioning is required. During any period of conditioning, keep the surface lightly rolled to camber and watertight, and add water as necessary to prevent the surface drying.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut before compaction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.03.11 - Compaction
label | Acceptance / Conformance Criteria - Commence compaction of the stabilised mix after the necessary water has been added and the conditioning period has elapsed.
label | ○ The Engineer to specify the amount of water to be added.
label | ○ Use a sheep's foot roller for the initial compaction on massive clay sub-grades, exerting pressures of not less than 2,800 MPa from the feet.
label | ○ Finish with a steel wheeled roller providing not less than 50kg mass/10mm length of the roller driving wheel.
label | ○ Use conventional compaction equipment appropriate to the soil type for compaction of material other than massive clay sub-grades.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.12 - Compaction - Inaccessible Areas
label | Acceptance / Conformance Criteria - Compact areas inaccessible to rollers to the required density by other suitable means.
label | ○ If compaction planes occur in the compacted layer, adequately scarify, re-lay and compact the affected area.
label | ○ Acceptance of the stabilising agent treated layer to be determined by the Engineer after consideration of appropriate test results which show an adequate strength gain with time.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.13 - Joints
label | Acceptance / Conformance Criteria - Take care at longitudinal joints to knit materials and provide an overlap during the mixing operation.
label | ○ Make all transverse and construction joints in thoroughly compacted material, either with a vertical face or by overlapping with the next mixing operation. Remove all loose material from the joint before the next mix is compacted in place.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Each Cut
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.03.14 - Handover Straightedge Check
label | Acceptance / Conformance Criteria - No point of the finished compacted surface shall vary by more than 12mm from a 3.0m straightedge laid parallel to either the centre line or across the camber of the surface perpendicular to the centreline or by more than 10mm from the design level.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Straight Edge Results
label | Frequency - Prior to any traffic or further fill placement on the lime stabilised areas
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 6.03.15 - Final Curing
label | Acceptance / Conformance Criteria - After mixing, pulverisation and compaction of the stabilising agent soil sub-grade, nominate the method of curing for approval.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Site Records
label | Frequency - Prior to Backfilling
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 6.03.16 - Final Inspection And Testing
label | Acceptance / Conformance Criteria - Prior to any traffic or further fill placement on the lime stabilised areas, make due allowance and make plant and other facilities available for the Engineer to carry out tests.
label | ○ Generally, but not exclusively, Scala Penetrometer tests.
label | ○ A minimum CBR value of 15% is required.
label | Standard / Specification - PS 15.9.3
label | Verifying Document - Scala Report
label | Frequency - Prior to any traffic or further fill placement on the lime stabilised areas
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.04 Cutting and Subgrade
checkpoint | 6.04.01 - Cut slope inspections
label | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages.
label | ○ Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils.
label | ○ Results will be submitted to the Engineer.
label | Standard / Specification - PS 15.10.2, PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.04.02 - Dewatering
label | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
label | Standard / Specification - PS 15.10.18
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 6.04.03 - Subgrade CBR Testing (Road and Embankment)
label | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions.
label | ○ Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
label | ○ This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level.
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
label | – Shear Vane Average minimum su: > 60kpa
label | – Shear Vane Single test minimum su: > 50kpa
label | – SCALA: Minimum 3 blows per 100mm penetration
label | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
label | Verifying Document - Shear Vane or Scala Report
label | Frequency - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.04.04 - Undercut Subgrade Compaction
label | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
label | Standard / Specification - PS 15.10.4
label | Verifying Document - Site Records
label | Frequency - Prior to Backfilling
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 6.04.05 - Soft Road Subgrade Areas
label | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
label | Standard / Specification - PS 15.10.4
label | Verifying Document - Notice
label | Frequency - When Encountered
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 6.04.06 - Daily Earthwork Grading and Rolling
label | Acceptance / Conformance Criteria - Earthwork materials on site are sensitive to overworking in wet conditions. It is critical that all fill surfaces are graded and rolled at the end of each day’s work to prevent any ponding, erosion and potential softening of the structural fill.
label | Standard / Specification - PS 15.6.4
label | Verifying Document - Site Records
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.04.07 - Finished Surfaces
label | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
label | Standard / Specification - PS 15.6.8
label | Verifying Document - Survey Records
label | Frequency - Each Finished Surface
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 6.04.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
label | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll.
label | ○ No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials.
label | ○ Visual Observation Across The Stripped Area Displacement < 15mm.
label | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
label | Verifying Document - Engineers Approval
label | Frequency - Prior to filling with 24h notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.05 Filling General
checkpoint | 6.05.01 - Compaction Trials
label | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers).
label | ○ The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements.
label | ○ The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
label | Standard / Specification - PS 15.10.15
label | Verifying Document - Trial Results
label | Frequency - During Works before placement of each material.
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 6.05.02 - Daily Earthwork Grading and Rolling
label | Acceptance / Conformance Criteria - Earthwork materials on site are sensitive to overworking in wet conditions. It is critical that all fill surfaces are graded and rolled at the end of each day’s work to prevent any ponding, erosion and potential softening of the structural fill.
label | Standard / Specification - PS 15.6.4
label | Verifying Document - Site Records
label | Frequency - Daily
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.05.03 - Surface Scarifying
label | Acceptance / Conformance Criteria - Prior to commencement of filling operations, the previously graded and rolled surface shall be scarified or worked to prevent the formation of sub-standard, or weak layers within the fill.
label | Standard / Specification - PS 15.6.4
label | Verifying Document - Site Records
label | Frequency - Prior to commencement of filling operations
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.05.04 - Geotextile on Undercut to Waste and Backfill
label | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped to in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
label | Standard / Specification - PS 15.10.9
label | Verifying Document - Site Records
label | Frequency - Prior to Backfilling undercuts
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.05.05 - Conditioning
label | Acceptance / Conformance Criteria - Prior to compaction, the fill materials shall be spread uniformly in horizontal layers and, if necessary, uniformly conditioned to an appropriate water content by aeration and drying or wetting and/or by blending and mixing suitable "wet" and "dry" materials and/or by lime and/or cement treated.
label | ○ Where drying of the soils is required, the Contractor shall disc the soil and allow it to dry uniformly to its full depth before compaction.
label | Standard / Specification - PS 15.10.13
label | Verifying Document - Survey Records
label | Frequency - Prior to compaction
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.05.06 - Weaving or Pumping
label | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted.
label | ○ If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
label | Standard / Specification - PS 15.10.16
label | Verifying Document - Site Records
label | Frequency - When encountered
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | 6.05.07 - Finished Surfaces
label | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings.
label | ○ Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
label | Standard / Specification - PS 15.6.8
label | Verifying Document - Survey Records
label | Frequency - Each Finished Surface
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | 6.05.08 - Final Trimmed Shape Inspection
label | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Prior to placing topsoil or track rolled fill.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.06 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
checkpoint | 6.06.01 - Imported Structural Fill Layers
label | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
label | Standard / Specification - PS 15.10.14
label | Verifying Document - Site Records
label | Frequency - Each Layer
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.06.02 - Surface Scarifying
label | Acceptance / Conformance Criteria - When the fill operation has ceased in any area for more than 8 hours, then immediately before recommencing the fill operation, the fill surface shall be scarified to a depth of 100mm, conditioned and compacted to achieve the required standard of compaction.
label | Standard / Specification - PS 15.10.14
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.06.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
label | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
label | ○ Minimum CIV = 18
label | ○ Average CIV= 20
label | Standard / Specification - Appendix XIII
label | Verifying Document - Clegg Results
label | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.06.04 - Non-Structural Fill Zone - Strength – Clegg Impact Value (CIV)
label | Acceptance / Conformance Criteria - A1 Imported Non-Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
label | ○ Minimum CIV = 10
label | ○ Average CIV = 12
label | Standard / Specification - Appendix XIII
label | Verifying Document - Clegg Results
label | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.06.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
label | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
label | ○ Average >95% Of In-Situ MDD
label | ○ Minimum >92% Of In-Situ MDD
label | Standard / Specification - Appendix XIII
label | Verifying Document - NDM Results
label | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.06.06 - Solid Density
label | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source).
label | ○ Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
label | Standard / Specification - Appendix XIII
label | Verifying Document - Solid Density Lab Report
label | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.06.07 - Organic Content
label | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.06.08 - Completed Fill Approval
label | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineer Approval
label | Frequency - Prior to Pavement Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.07 TYPE A2 (COHESIVE SITE WON MATERIAL FILL)
checkpoint | 6.07.01 - Cohesive Fill Layers
label | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work with rubber tyre plant to reduce erosion and protect the fill.
label | Standard / Specification - PS 15.10.16
label | Verifying Document - Site Records
label | Frequency - Each Layer
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.07.02 - Fill surfaces Sealing
label | Acceptance / Conformance Criteria - All fill surfaces shall be sealed at the end of each day’s work with rubber tyre plant to reduce erosion and protect the fill.
label | Standard / Specification - PS 15.10.16
label | Verifying Document - Site Records
label | Frequency - Each Day
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.07.03 - Surface Scarifying
label | Acceptance / Conformance Criteria - For cohesive fills only, when the fill operation has ceased in any area for more than eight hours, then immediately before recommencing the fill operation, the fill surface shall be scarified to a depth of 150mm, conditioned and re-compacted to achieve the required standard of this specification.
label | Standard / Specification - PS 15.10.16
label | Verifying Document - Site Records
label | Frequency - Each Occurrence
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.07.04 - Structural fill zone strength – Shear Strength (SU)
label | Acceptance / Conformance Criteria - A2 Cohesive Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 100m3 per area per day per lift of fill placed.
label | ○ Average Minimum Su > 100kPa
label | ○ Single Test Minimum Su > 80kPa
label | ○ Scala: Minimum 4 Blow Per 100mm
label | Standard / Specification - Appendix XIII
label | Verifying Document - Shear Vane or Scala Results
label | Frequency - 1 Set (5 Test) Per 100m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.07.05 - Non-structural fill Zone Strength – Shear Strength (SU)
label | Acceptance / Conformance Criteria - A2 Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
label | ○ Average Minimum Su > 60kPa
label | ○ Single Test Minimum Su > 50kPa
label | ○ Scala: Minimum 2 Blow Per 100mm
label | Standard / Specification - Appendix XIII
label | Verifying Document - Shear Vane or Scala Results
label | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.07.06 - Structural fill zone insitu density
label | Acceptance / Conformance Criteria - A2 Cohesive Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
label | ○ Average Maximum Air Voids < 6%
label | ○ Single Test Maximum Air Voids< 7%
label | Standard / Specification - Appendix XIII
label | Verifying Document - NDM Results
label | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
checkpoint | 6.07.07 - Non-Structural fill zone insitu density
label | Acceptance / Conformance Criteria - A2 Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
label | ○ Average Maximum Air Voids < 8%
label | ○ Single Test Maximum Air Voids< 10%
label | Standard / Specification - Appendix XIII
label | Verifying Document - NDM Results
label | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
checkpoint | 6.07.08 - Water content
label | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Water Report
label | Frequency - Every NDM
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.07.09 - Bulk Density, Dry Density, Air Voids
label | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Lab Report
label | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.07.10 - Organic Content
label | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.07.11 - Completed Fill Approval
label | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineer Approval
label | Frequency - Prior to Pavement Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.08 TYPE A2 (NON COHESIVE SITE WON MATERIAL FILL)
checkpoint | 6.08.01 - Fill Layers
label | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
label | Standard / Specification - PS 15.10.14, PS 15.10.9
label | Verifying Document - Site Records
label | Frequency - Each Layer
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 6.08.02 - Structural fill zone - Strength
label | Acceptance / Conformance Criteria - A2 Non-Cohesive Structural Fill Strength shall be tested by Scala every 100m3 per area per day per lift of fill placed.
label | ○ Scala: Minimum 5 Blow Per 100mm
label | Standard / Specification - Appendix XIII
label | Verifying Document - Scala Results
label | Frequency - 1 Set (5 Test) Per 100m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | Comments / Closeout Details - Frequency TBC
checkpoint | 6.08.03 - Non-structural fill Zone - Strength
label | Acceptance / Conformance Criteria - A2 Non-Cohesive Non-Structural Fill Strength shall be tested by Scala every 100m3 per area per day per lift of fill placed.
label | ○ Scala: Minimum 3 Blow Per 100mm
label | Standard / Specification - Appendix XIII
label | Verifying Document - Scala Results
label | Frequency - 1 Set (5 Test) Per 100m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | Comments / Closeout Details - Frequency TBC
checkpoint | 6.08.04 - Bulk Density, Dry Density, Air Voids
label | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Lab Report
label | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.08.05 - Structural fill zone insitu density
label | Acceptance / Conformance Criteria - A2 Non-Cohesive Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
label | ○ Average >95% OF IN-SITU MDD
label | ○ Minimum >92% OF IN-SITU MDD
label | Standard / Specification - Appendix XIII
label | Verifying Document - NDM Results
label | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.08.06 - Non-Structural fill zone insitu density
label | Acceptance / Conformance Criteria - A2 Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
label | ○ 90% Minimum Dry Density (MDD)
label | Standard / Specification - Appendix XIII
label | Verifying Document - NDM Results
label | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.08.07 - Organic Content
label | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
label | Standard / Specification - Appendix XIII
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.08.08 - Completed Fill Approval
label | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineer Approval
label | Frequency - Prior to Pavement Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 6.09 Settlement Monitoring
checkpoint | 6.09.01 - Settlement Monitoring Methodology
label | Acceptance / Conformance Criteria - The Contractor shall submit details of their proposed monitoring equipment and installation methodology within their Earthworks Management Plan for the Engineer’s Approval.
label | Standard / Specification - PS 15.12.5
label | Verifying Document - Approved EMP
label | Frequency - Prior to Works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.09.02 - Supply, Install, Survey and Remove and Monitoring Equipment
label | Acceptance / Conformance Criteria - The Contractor shall install geotechnical instrument systems in the positions shown in the Contract Drawings unless otherwise instructed by the Engineer.
label | Standard / Specification - PS 15.12
label | Verifying Document - Site Records
label | Frequency - Prior to Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | 6.09.03 - Instrument Reading Notice
label | Acceptance / Conformance Criteria - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
label | Standard / Specification - PS 15.12.5
label | Verifying Document - Site Records
label | Frequency - Prior to Survey
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.09.04 - Base Readings, Responsibility and Ownership
label | Acceptance / Conformance Criteria - Following installation, the Contractor shall undertake testing to demonstrate the instruments are working properly.
label | ○ The Contractor shall submit records of each of the instruments showing location, soil conditions encountered, installation details and initial readings.
label | ○ Construction will not be permitted until the Engineer is satisfied that the instruments are working correctly.
label | Standard / Specification - PS 15.12.2
label | Verifying Document - Site Records
label | Frequency - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.09.05 - Pin Protection
label | Acceptance / Conformance Criteria - The Contractor shall ensure the Pins are protected and not disturbed in any way once constructed. The Contractor shall also install settlement survey stations at locations protected from Construction traffic and works.
label | Standard / Specification - PS 15.12.5
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 6.09.06 - Monitoring
label | Acceptance / Conformance Criteria - Following the active fill of the embankment, the Contractor shall read all monitoring pins bi weekly. Monitoring frequency may be reduced to weekly intervals when there is no active earthworks in that area, and while waiting for embankment to settle.
label | Standard / Specification - PS 15.12.5
label | Verifying Document - Survey Records
label | Frequency - Bi Weekly following Embankment Filling
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 6.09.07 - Engineers Review
label | Acceptance / Conformance Criteria - The Engineer will review the results of the settlement monitoring to assess completion of the preconsolidation period. This period is anticipated to be less than 3 months.
label | Standard / Specification - PS 15.12.5
label | Verifying Document - Survey Records
label | Frequency - Ongoing
label | Verification Activity: Activity - R
label | Verification Activity: By - SV
checkpoint | 6.09.08 - Pore Water Dissipation
label | Acceptance / Conformance Criteria - Review of settlement pins data to confirm sufficient pore water dissipation has occurred in the soft soil layer.
label | Standard / Specification - PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Prior to completing Monitoring
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.09.09 - Settlement Monitoring Termination
label | Acceptance / Conformance Criteria - The criteria for terminating the embankment preload are either:
label | ○ Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed.
label | ○ The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
label | Standard / Specification - PS 15.12.7, PS 15.13
label | Verifying Document - Engineers Approval
label | Frequency - Prior to completing Monitoring
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT