## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Preliminary Activities and Materials Approval |  |  |  |  | Yes | Preliminary Activities and Materials Approval | 0cb0326b-bd57-40b2-af2b-81b4d3f94e00
checkpoint-group |  |  | section | Preliminary Activities (Approved by Client)
checkpoint-status |  |  | checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint-status |  |  | checkpoint | HSE Management Plan
checkpoint-status |  |  | checkpoint | Permacast Project Quality Management Plan
checkpoint-status |  |  | checkpoint | Inspection & Test Plan
checkpoint-status |  |  | checkpoint | MDR Index
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Prestress
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Curing
checkpoint-status |  |  | checkpoint | Concrete Repair Methodology
checkpoint-status |  |  | checkpoint | Shop Drawings
checkpoint-status |  |  | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | S65 Concrete Mix Design Approved by Client
label | 33b6cdb2-b160-5f7e-9ac9-6d02d7f9d343 |  | note | Supplier : Holcim
label | 8223150c-f306-5fa2-b141-18eb98bd804e |  | note | Mix Code: WS654TC04 (S65/14/200)
label | 5bd07ac6-dc5e-5c3b-9565-d52a7f942343 |  | note | Slump : 200 ± 40
checkpoint-group |  |  | section | Steel Reinforcement
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
checkpoint-group |  |  | section | Prestressing Tendons
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Ensure that all Coil Numbers are recorded
checkpoint-status |  |  | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint-status |  |  | checkpoint | Stressing Jack Calibration Certificates
checkpoint-group |  |  | section | Lifting Anchors
checkpoint-status |  |  | checkpoint | Lifting Design Approved by Client
checkpoint-status |  |  | checkpoint | Lifting Devices Approved by Client
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checkpoint-group |  |  | section | Cast-in Items and Ferrules
checkpoint-status |  |  | checkpoint | All Cast in Materials Approved
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned |  |  | checklist | Precast Piers |  |  |  |  | Yes | Precast Piers | cb90df23-b0f0-40b6-86cc-f2e9d5ab59f3
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-status |  |  | checkpoint | Pre-Pour Checklist completed
text | 4e7afe8a-b8d9-5737-beb2-8f0c651cc3db |  | textbox | Cast Number
text | 6382421e-9011-5979-a5cf-caa01c812d0b |  | textbox | Bridge Name
text | 1b405b9f-fce4-5f29-9ad7-cf8b7830b312 |  | textbox | Precast Pier 1
text | 803beb40-e5e5-5a44-bf24-76a5a1c5a84f |  | textbox | Precast Pier 2
text | fb3f9880-435f-58dc-ba52-1d45aa4273ff |  | textbox | Precast Pier 3
text | b5911e03-de0e-5993-a1e9-93e08c119355 |  | textbox | Mould Beam 1
text | a4f9d4ba-07f4-5b06-bca4-80ad1be63b42 |  | textbox | Mould Beam 2
text | 6a1dce4b-d24c-541b-97b7-7306d8f795a6 |  | textbox | Mould Beam 3
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | 4a541877-249f-545d-bc97-6617f72a285b |  | note | Length
label | 997dfb26-56c3-59ac-bb51-ddf4f1c6b76c |  | note | Width
label | d2ed374d-ed18-5380-b9ea-baf4de7a17d0 |  | note | Height
label | b89e4592-7c2a-5ccb-b943-59e89ff86ee1 |  | note | Straightness
label | abf4fef2-0533-577c-838c-14a84beb59a0 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | 7c8696d3-1934-566d-bed6-c8e865fa0df7 |  | note | Cleaned
label | 51dd88d9-c039-5d77-af83-fd32c458ca8e |  | note | Sealed
label | 0f80e1ae-97a8-5e62-b15c-65be62b256df |  | note | Rubbers in Place
label | 91d250fa-0054-5fce-84be-f611ddba06ba |  | note | Oiled
label | 068cb4c4-bbc1-5e41-a1bf-1edcf1214016 |  | note | Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | c64a314c-7abf-54af-8075-0933650c8688 |  | note | Reinforcement size
label | 4c6c8d01-7687-5eaa-8cf5-773557da8666 |  | note | Lap Length
label | 7846081a-7480-5750-9e9c-3fbc6005a7b8 |  | note | Splicing
label | 93650da2-93fd-5101-bc8a-21fc7d2d7bf5 |  | note | Bar Chairs
checkpoint-status |  |  | checkpoint | Earthing and Bonding
label | aafa5a88-24c1-54e2-9789-9d78c0e4c8b1 |  | note | Weld Locations
label | a9dc0e15-fc25-5f74-af3a-340bb7c4acf2 |  | note | Rebar Ties
label | a96b0f67-c42e-5bfb-862f-145daaab421b |  | note | Continuity. E&B requirements ≤ 20 mΩ per continuous reinforcing section
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
checkpoint-status |  |  | checkpoint | All Cast-in Items are installed in accordance with Drawings
label | 1686e113-f8aa-5180-980b-7889804e3fc3 |  | note | Cast-in Items
label | 3a3203fa-dac2-55b5-b13d-2e768acad43c |  | note | Fittings
label | e8a3a7a6-1145-558f-b368-2d6d053245e6 |  | note | Cooling pipes
label | ea81cea0-825c-5685-af89-cfb43cfc41ba |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
label | 1e08fcf4-f01f-5281-8fd2-a8f0e3753065 |  | note | Every 25m
label | 00584b31-b35b-5a86-a5c5-dcde4a1a6961 |  | note | 1 x Core
label | a9b9cb9b-ff4b-57a1-a886-7c653cc08f62 |  | note | 1 x Within Cover Zone
label | a91d09e6-62d0-5753-9e47-7a7fa831ae1b |  | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
label | 266be85a-b264-5821-89b4-d15bbab95090 |  | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
checkpoint-status |  |  | checkpoint | Ensure All temperature Loggers are Working (Check App)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
holdpoint |  |  | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | d5bc242e-198a-5fe4-89fd-aa2d862704e9 |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | 65e7e5bf-5179-5b28-89b1-0b98256daecf |  | textbox | Concrete Delivery Docket 1
text | ddb485d9-b658-5895-b8a2-c7ce65ba2b36 |  | textbox | Concrete Delivery Docket 2
text | 629f4247-61b3-5292-92e7-074a48c0a627 |  | textbox | Concrete Delivery Docket 3
text | 09a3b841-f0e5-58b1-af50-05de919ebfbc |  | textbox | Concrete Delivery Docket 4
text | 1f8d1a26-941a-51df-82b4-8e65c1b2c071 |  | textbox | Concrete Delivery Docket 5
text | 68937190-4236-54c8-8ed6-7072e952a1cb |  | textbox | Concrete Delivery Docket 6
text | 32e9f5a8-ebef-541f-ac31-01140b4bff1b |  | textbox | Concrete Delivery Docket 7
text | 691a9416-704e-5968-837f-2d85385773d8 |  | textbox | Concrete Delivery Docket 8
text | 377de638-7a81-55a5-93ee-6c65110a4f5d |  | textbox | Concrete Delivery Docket 9
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 5f884b4f-d4df-535c-a7df-874fbbe13a6f |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified ( WS654TC04 - S65/14/200)
label | bbf79f64-bafd-56de-b60c-09b53bfa0b36 |  | note | Concrete Mix Strength (Mpa)
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | 00c2756c-e7f7-52b7-8376-ed06d275c47e |  | note | 5 - 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | c81d5fc7-1908-54b3-b531-5fd513c02e60 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance
text | d77627c2-1a93-508d-a8f7-66a60991ad9b |  | textbox | Slump 1
text | f621aee8-a0db-501a-bd0f-d90736924785 |  | textbox | Slump 2
label | b8649bc6-16a1-5fc3-9af1-716c304209b7 |  | note | 200 ± 40mm
checkpoint-status |  |  | checkpoint | Truck Tested for strength
text | eaf5ea38-9e36-5b8e-9828-e841190d89a5 |  | textbox | Test Report Reference Number 1
text | f17b016a-c178-5519-b874-596dee6cc6e9 |  | textbox | Test Report Reference Number 2
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks (< 20min)
checkpoint-status |  |  | checkpoint | Concrete Placed within 90min from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour (< 2m)
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 76e496ab-cc01-58cb-b7a8-6fe48d30343f |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Submitted to Client
text | ffe4cd27-3fac-5353-9ac6-adcd7c1af936 |  | textbox | Stripping Strength
label | acbdc093-9fc6-5e09-a7a9-322ed791b373 |  | note | Strength = Reading / 7.851
holdpoint |  |  | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | 598b7281-145b-5cef-928b-da6eee1456b1 |  | note | Length
label | a528a2c1-6f71-5737-949b-627ecda0c70d |  | note | Width
label | cebe45d3-0319-59b4-8e5f-f91f07439a39 |  | note | Height
label | 89df516c-6291-5cbe-8928-91cab3f42587 |  | note | Straightness
label | edd83b4a-d83d-5071-aa61-3f429d8d56f8 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
label | 95009e70-111f-533e-8f19-6dab1c33a033 |  | note | Cast-in Items
label | 441b4cf2-f5bf-506d-b0bd-79e5d4da46c5 |  | note | Fittings
label | f2fff155-ec67-5455-98f4-b4573bab5a49 |  | note | Lifters Position and Type
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Storage/Stacking as per Approved Plan
checkpoint-status |  |  | checkpoint | Curing as per Approved Methodology
checkpoint-status |  |  | checkpoint | Electrical Conductivity verified post Cast
checkpoint-status |  |  | checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlisting Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | 4c8de007-e0fd-5370-94a1-259aa65ff214 |  | textbox | Concrete Test Report Number 1
text | 6812011e-8001-5584-b364-e347458b80e7 |  | textbox | 7 Day Strength (1)
text | 83d550c1-017c-51de-80ef-48626a8fed9d |  | textbox | 7 Day Strength (2)
text | f49a74cf-7835-5696-86da-9256a7335bf0 |  | textbox | 7 Day Strength (3)
text | 7b0b9d48-e6b1-5213-b367-715d105ed1d2 |  | textbox | 7 Day Strength (4)
text | 09871642-037f-5de5-8fda-0aba8e2c0551 |  | textbox | 28 Day Strength (5)
text | c62c9f34-b494-5c15-bf09-d9f741297d64 |  | textbox | 28 Day Strength (6)
text | 67c3dfad-b4e1-51a8-ba83-51aac88e6b04 |  | textbox | 28 Day Strength (7)
text | 9727d4c4-a7e8-569d-bcd9-cf99a1d164f7 |  | textbox | 28 Day Strength (8)
text | 41f8a009-e1df-5fd1-899f-1a137fbcbc92 |  | textbox | 28 Day Strength (9)
text | 5097f656-7700-50d6-8114-6800f4cf107e |  | textbox | 28 Day Strength (10)
checkpoint-group |  |  | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
checkpoint-status |  |  | checkpoint | Completed by
checkpoint-status |  |  | checkpoint | Reviewed by
holdpoint |  |  | signoff | (INTERNAL HOLD POINT)
checkpoint-status |  |  | checkpoint | Client Representative
holdpoint |  |  | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)