## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0031 Installation of Steel Beam Guard Fence | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0031 Installation of Steel Beam Guard Fence
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 1630-SYM-QAC-ITP-0031
label | Rev No. - 00
label | Date of Issue - 15/01/24
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Safety
label | Ensure that the following items have been actioned:
label | – SWMS if applicable
label | – Plant Pre-start Inspection
label | – Service locations identified
label | – Traffic Management Plans (if req’d)
label | – All staff inducted
label | Ref docs - SMP
label | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
label | ○ Plant inspections completed and entered.
label | ○ TSA training completed. Pre-work briefings completed.
label | ○ Service Diagrams available and services located
label | Freq - Once (Pre-Start)
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Service map Attached.
checkpoint | 1.2 - Excavation Permit
label | Ref docs - SMP
label | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
textbox | Permit No
checkpoint | 1.3 - Material Compliance - Steel
label | Ref docs - DoT Clause 708.05 (a) 708.05 (b) 708.04
label | Acceptance criteria - Submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | ○ All testings shall be endorsed in accordance with the NATA registration for that lab.
label | ○ Only safety barrier products listed in RDN 06-04 shall be used
label | Freq - 14 days Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Compliance/test certificates
bool | Action point & linked.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material Compliance - W-beam Base Metal Mechanical Properties
label | Ref docs - DoT Clause 708.05 (a) 708.05 (c) (i)
label | Acceptance criteria - Below information marked on steel W-beams, posts at both ends and all plastic components:
label | ○ Name of the manufacturer; batch number strength grade and base metal thickness of the steel W-Beams
label | ○ W-beams to meets requirements of AS/NZS 1594 Grade HA350.
label | ○ Mechanical Properties of Base Metal:
label | – Min. Yield Strength: 350MPa
label | – Min. Elongation in 80 mm: 16%
label | – Min. Tensile Strength: 430MPa
label | ○ The base metal shall comply with the following tolerances when measured in accordance with the methods of AS/NZS 1365
label | – Base metal thickness 2.7 mm +0.21 mm or -0.10 mm
label | – Mill camber tolerance on 2500 mm length 10 mm max
label | – Mill tolerance on strip width +2.5 mm, -0.0
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compliance/test certificates
checkpoint | 1.5 - Material Compliance - Steel Posts and Blocks
label | Ref docs - DoT Clause 708.05 (c) (ii)
label | Acceptance criteria - Manufactured from steel which meets AS/NZS 1594 Grade HA250
label | ○ Base material thickness shall be 6.0 mm +/-0.27 mm.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compliance/test certificates
checkpoint | 1.6 - Material Compliance - Terminal Sections
label | Ref docs - DoT Clause 708.05 (c) (iii)
label | Acceptance criteria - Manufactured from steel which meets AS/NZS 1594 Grade HA350
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compliance/test certificates
checkpoint | 1.8 - Protective Treatment - Galvanising
label | Ref docs - DoT Clause 708.05 (d)
label | Acceptance criteria - Treatment should be in accordance with AS 1627 Parts 1 and 4 and finished by hot-dipped galvanising in accordance with AS/NZS 4680.
label | ○ Hot-dipped galvanised coating on Bolts, Nuts and Washers shall comply with AS 1214.
label | ○ All galvanised coatings shall be smooth, adherent, and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Appearance is of prime importance and colour shall be uniform.
label | ○ Where curved W-beam of less than 45 m curve radius is specified, the curving operation shall be carried out off site in a manner that will not result in damage to the galvanising.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Galvanisation Compliance/test certificates
checkpoint | 1.9 - Protective Treatment - repair
label | Ref docs - DoT Clause 708.05 (d)
label | Acceptance criteria - Repairs to a damaged galvanised coating to be done with zinc-rich inorganic Paint with a minimum of 2 coats in accordance with AS 3750.9 and one coat of aluminium paint.
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Photo Evidence | Yes,No,N/A
checkpoint | 1.10 - Material Compliance - Breakaway Cable Terminal
label | Ref docs - DoT Clause 708.05 (f)
label | Acceptance criteria - The wire rope shall comply with the requirements of AS3569 and the details shown on Drawings.
label | ○ Wire ropes used in proprietary devices must comply with the manufacturer’s recommendations.
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compliance test certificates
checkpoint | 1.11 - Material Inspection, Handling and Storage
label | Ref docs - DoT Clause 708.06, 708.11, 708.13 IFC Drawings
label | Acceptance criteria - Items are loaded, transported, unloaded, stacked, and handled in such a way to protect items from distortion and that galvanised surfaces are protected from damage.
label | ○ All materials stored to prevent damage and corrosion at least 200 mm above the ground on platforms, slabs, or other supports.
label | ○ Rusted, bent, or damaged steel shall be rejected.
label | ○ If stacks located behind a serviceable road safety barrier system, the clear space must allow for dynamic deflection and proper functioning of the end treatments.
label | ○ Ensure that materials are in compliance with VicRoads specifications and IFC Drawings.
label | ○ Ensure there are no hard objects within the deflection zone of the barrier.
label | Freq - Prior to start of works & Throughout construction process
label | Key - R, I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Incoming Material Checklist
checkpoint | 1.12 - Pre-Construction Planning
label | Ref docs - DoT Clause 708.07 (a), (c) & (d)
label | Acceptance criteria - Plan and execute the work in a manner that prevents damage to underground and above ground facilities. Construct a guard fence to form a smooth line vertically and horizontally, when viewed along the line of the installation, free of humps, sags, or other irregularities, within tolerances.
label | ○ Any component of a guard fence must not be welded, or flame cut in the field under any circumstances. Welding and flame cutting may only be conducted when shown on drawings in accordance with the manufacturer’s recommendations.
label | ○ End treatments and transitions commissioned at the earliest practicable time where the guard fence is being constructed on a road open to traffic. Temporary end treatments to the satisfaction of the Superintendent to be provided until the permanent treatments are complete.
label | ○ Removal of an existing installed safety barrier system includes:
label | ○ Dismantling or demolition of safety barriers, transitions, and end treatments
label | ○ Extracting all posts, anchors and other in-ground components and materials
label | ○ Removing all components and waste materials from the site
label | ○ Cleaning, backfilling and mechanically compacting all excavations and holes in 150 mm layers to not less than the density of the surrounding layers.
label | ○ Stacking or disposing of components and waste materials
label | Freq - Prior to start of works
label | Key - I
label | Resp - SE
checkpoint | 1.13 - Associated Pavement Shoulder widening
label | Ref docs - VR 708.15 VR AGRD 06
label | Acceptance criteria - Where required, widening of the existing shoulder on the median or outer verge applications adjacent to locations where guard fence is to be installed, shall be completed.
label | ○ The edge of shoulder shall be saw-cut to provide a neat straight edge against which the additional pavement can be placed.
label | ○ Pavement layers shall be stepped a minimum 150 mm horizontally to enable new widening to be keyed into the existing pavement.
button | Has the above been completed? | Yes,No,N/A
label | Freq - Prior to start post install
label | Key - H
label | Resp - SE
section | 2.0 Guard Fence Post Installation
checkpoint | 2.1 - Set Out
label | Ref docs - DoT Clause 708.08
label | Acceptance criteria - Prior to installation, the required location and length of all guard fence to be confirmed with the Superintendent.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Posts - Installation
label | Ref docs - DoT Clause 708.08 (a) 708.08 (e) VicRoads AGRD
label | Acceptance criteria - Installed to a depth not less than shown on IFC drawings/manufactures
label | ○ Posts orientated to the direction of traffic as shown on drawings.
label | ○ Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness.
label | ○ If site conditions dictate that the posts cannot be driven, then the posts shall be installed in holes. The bottom of the holes shall be adequately compacted to achieve the same density as the surrounding soil.
label | ○ Posts in rock – 75 mm clearance from back of post to face of the hole.
label | ○ Posts shall be installed such that the back of post is not less than 500 mm from hinge point.
label | ○ Refer to figure 1 at the back of this document for post offsets requirements.
label | Freq - Each lot & Each possession
label | Key - I
label | Resp - SE
checkpoint | 2.3 - Posts - Backfilling
label | Ref docs - DoT Clause 708.08 (a)
label | Acceptance criteria - Posts in rock – Except for anchorage posts, post holes backfilled with a granular material.
label | ○ Other post holes backfilled with selected earth, free of rock.
label | ○ Backfill shall be firmly compacted not exceeding 100 mm compacted layers.
label | ○ Posts in paved areas shall be backfilled 50 mm below underside of such paving and remaining depth filled with paving material.
label | Freq - Each lot & Each possession
label | Key - I
label | Resp - SE
checkpoint | 2.4 - Post - Foundation (Displacement Test)
label | Ref docs - DoT Clause 708.08 (a)
label | Acceptance criteria - Foundation displacement at ground level not to exceed 3 mm when a 1 kN. force is applied 200 mm below the top of the post in any direction.
label | ○ Any failing post shall be rectified and retested plus one similar post within 5 m.
label | ○ Rectification to be completed via re-compaction of material surrounding the post and/or removal and replacement of the post.
label | Freq - Each lot & Each possession
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Records
checkpoint | 2.5 - Non-Standard Post Lengths
label | Ref docs - DoT Clause 708.08 (a)
label | Acceptance criteria - Where non-standard post lengths or other special measures are required (e.g., Shallow Concrete Foundations), details to be provided to the Superintendent.
label | ○ Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SI Key - H
button | Remarks/record (eg. Test frequency reports, certificates, checklist etc) | Yes,No,N/A
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bolted Connection In reinforced concrete beam
label | Ref docs - IFC Drawings VR 670, VR 708
label | Acceptance criteria - Where posts are not required and guard rail is installed directly onto reinforced concrete:
label | ○ Confirm bolt size and grade are as per IFC drawings.
label | ○ After the barrier has been installed and all connections made, the gap between the base plate and the top of concrete footing shall be completely filled with a flowable dual shrinkage compensating proprietary cementitious grout.
label | ○ HP - Railing posts shall not be grouted until the Contractor provides a Survey Certificate verifying compliance with the specified tolerances on lines and levels.
label | ○ Where Welding is required, welds shall be completed in accordance with “RAIL SPLICE DETAIL” as per 1630-P200-SYM-SBR-DRG-0461.
label | ○ Where required, all damaged galvanised coatings to be repaired.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Survey Conformance Check
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Guard Fence Installation
checkpoint | 3.1 - Guard Fence/Rail - Installation
label | Ref docs - PS3060.06 (X) DoT Clause 708.05 (d), 708.08 (b), 708.08 (e)
label | Acceptance criteria - Guard fence shall be installed at the offsets shown on Standard Drawing SD 3502 or as directed as per the IFC drawings
label | ○ Guard Fence/Rail sections lapped so that the exposed ends face away from near sided approaching traffic.
label | ○ Edges of guardrail fixed in contact with post or post blocks.
label | ○ All bolts fully tightened.
label | ○ All bolts on the traffic side of w-beam installations shall be flush with the w-beam.
label | ○ Posts attached to bridges or culverts shall be bolted to supporting members as shown on drawings.
label | ○ Where radius of curvature is 45m or less, guardrail sections shall be curved to shape prior to delivery to site.
label | ○ End treatments constructed in accordance with the drawings.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE, NA
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
checkpoint | 3.2 - End Treatments
label | Ref docs - DoT Clause 708.08 (c)
label | Acceptance criteria - During installation of wire ropes in the end treatments of W-beam, ensure that no twisting of the rope occurs.
label | ○ The anchorage cable shall be tightened sufficiently to remove slack.
label | ○ When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements.
label | Freq - Each lot & Each possession
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
checkpoint | 3.3 - Height of guard fence/rail
label | Ref docs - DoT Clause 708.08 (d), 708.08 (f)
label | Acceptance criteria - Top of Rail shall be within 25 mm of the specified level.
label | ○ Rail shall be within 50 mm of the specified line.
label | ○ Variations in line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | ○ Top of bolt head relative to w-beam -0 mm, +5 mm
label | Notwithstanding the above, the line and level shall be adjusted to provide a smooth and even vertical and horizontal alignment.
label | Guard rail install location:
label | ○ within 0 to 1 m behind the back of kerb:
label | – mounting height (vertical dimension from ground surface to centre of w beam) shall be measured from the lip of kerb.
label | ○ within 1.5 m from edge of carriageway without kerb:
label | – mounting height (vertical dimension from ground surface to centre of w beam) shall be measured from the lip of kerb.
label | ○ Distances beyond 1.5m
label | – the mounting height shall be measured from the nominal ground surface at the guard fence location.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | As-built survey and tabulations verifying compliance (Survey Conformance Report)
checkpoint | 3.4 - Motorcyclist Safety
label | Ref docs - DoT Clause 708.09 IFC Drawing
label | Acceptance criteria - Where specified, steel rub rail or other proprietary under-run systems, as listed in RDN 06 04 to be at attached to Guard Fence on nominated sections of barrier as shown on the drawings only.
label | ○ A 50 mm gap shall be provided between the rub rail and the ground to allow for passage of water.
label | Freq - Each lot & Each possession
label | Key - R, I
label | Resp - SE
checkpoint | 3.5 - Installation of Delineators
label | Ref docs - DoT Clause 708.11
label | Acceptance criteria - Delineators to be as per VicRoads Supplement to AS 1742.2 Clause 4.2.5.4(b).
label | ○ Contractor to supply and fasten flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2.
label | ○ Red delineators on the left side of one-way and two-way roadways.
label | ○ White delineators on the right side of two-way roadways; and
label | ○ Yellow delineators on the right side of one-way roadways
label | ○ Delineators not required where Guard Fence offset is greater than 4 m from the traffic lane.
label | ○ White guideposts with delineators shall be installed in accordance with VicRoads Supplement to AS 1742.2 Clause 4.2.4 – Guideposts.
label | Freq - Each lot & Each possession
label | Key - R, I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
checkpoint | 3.6 - Concrete maintenance strips
label | Ref docs - DoT Clause 708.12
label | Acceptance criteria - Concrete used for guard fence maintenance strips shall comply with AS1379 and VR 703.
label | ○ Concrete maintenance strips beneath all steel beam guard fence railing shall meet the following requirements:
label | ○ 300 mm clear of the rear of the post and 300 mm clear from the face of w beam
label | ○ Bedding to be 75mm thick of class 3 crushed rock
label | ○ Concrete shall be 75mm thick and 20MPa Strength.
label | ○ Edges of infill boarded up prior to pour.
label | ○ Edge board shall be parallel with steel beam guard rail fencing.
label | ○ Surface finished with a wooden float to produce a lightly textured finish.
label | ○ Shall be constructed with a minimum 2% cross fall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
label | – Where maintenance strip is adjacent to kerb or pavement, cork expansion joint or approved alternative shall be placed in between kerb / pavement and infill area.
label | – Where crushed rock is used, provide Incoming material testing requirements for Class 3 material.
label | – Where concrete is to be used, testing of concrete shall be conducted as per 703.11.
label | Frequency of testing:
label | ○ 1 test per lot; or
label | ○ 1 test for every 50m3 of concrete.
label | Freq - Each lot & Each possession
label | Key - R, I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
label | Material Delivery Dockets –
bool | Concrete
bool | Crushed Rock
label | Subcontractor Records
bool | Concrete test results (if required)
bool | Class 3 Crushed Rock Material Certification (if required)
checkpoint | 3.7 - Expansion Joints perpendicular to the line of Guard Fence
label | Ref docs - DoT Clause 708.12 SD 3503 1120-SYM-RFI-0074
label | Acceptance criteria - Full depth expansion joints (cork or approved equivalent) shall be provided, perpendicular to the line of the steel beam guard fence, 200mm each side of every post. alternatively, the following 2 options could also be considered:
label | (i) a 75% depth (56mm) saw cut (200mm each side of every post) for the full width of the maintenance strip;
label | (ii) a leave-out area around the post filled with 75mm thick low strength concrete mix (less than 0.85mpa)
label | Additional option approved as per 1120-SYM-RFI-0074:
label | – Similar to the method used for Kerb, a guillotine cut between 40-70% to be completed during concreting works
label | – Following this a tooled edging to a depth of 20mm to produce a neat groove not less than 5mm wide on the exposed surface as seen on kerb profiles
label | Freq - Each lot & Each possession
label | Key - R, I
label | Resp - SE
checkpoint | 3.8 - Delineators
label | Ref docs - DoT Clause 708.11
label | Acceptance criteria - Delineators to be as per VicRoads Supplement to AS 1742.2 Clause 4.2.5.4(b).
label | ○ Contractor to supply and fasten flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2.
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Delineators Compliance test certificates
section | 4.0 Completion of Steal Beam Guard Fence
checkpoint | 4.1 - Guard Fence Tolerances
label | Ref docs - DoT Clause 708.08 (d)
label | Acceptance criteria - The guard fence shall be installed at the positions so confirmed and shall be constructed true to line and level and to the following tolerances:
label | i. Variation from true plan position of posts ±20 mm
label | ii. Variation of line of w-beams from specified vertical profile ± 10 mm.
label | iii. Variation of w-beams from specified horizontal alignment ± 20 mm.
label | iv. Variation of posts from vertical (measured at top of the post) ± 15 mm.
label | v. Orientation of block and/or post to w-beam +0 mm, -15 mm measured at the point of greatest offset between the block or post to the w-beam)
label | vi. Dimension of holes -0 mm, +50 mm
label | ○ Top of bolt head relative to w-beam -0 mm, +5 mm.
label | Freq - Each lot & Each possession
label | Key - R, I
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Survey Conformance Report
checkpoint | 4.2 - Safety Barrier Compliance Audit
label | Ref docs - DoT Clause 708.10 Table PS3090.021 VR 708.10
label | Acceptance criteria - After Completion, arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract. The audit shall be undertaken, and a report prepared by the Australian Licensed Supplier of the safety barrier system.
label | ○ In addition, complete and submit to the Superintendent, compliance certificates for review.
label | ○ The CoC need to be signed by both Symal representative and the Supplier.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Compliance Audit and Certificate of Compliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Reinstated Works
label | Ref docs - DoT Clause 708.17, 708.18, 708.19, 708.20
label | Acceptance criteria - All existing signs and markings, median crossings and existing vegetation removed due to Guard Fence installation shall be reinstated.
label | ○ Any damage to existing vegetation shall be rectified immediately to the satisfaction of the Superintendent.
label | ○ Reinstatement inspection not applicable for areas where guard rail is installed prior to landscaping works being completed – landscaping to be completed in accordance with the IFC Drawings and inspection to be covered in landscaping ITP.
label | Freq - Each lot & Each possession
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Work Lot Close Out
checkpoint | 5.1 - Test Reports
label | Ref docs - VIC Roads Specifications
label | Acceptance criteria - All Test reports received and Reviewed
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | NATA Endorsed Test Reports
checkpoint | 5.2 - Product Non-Conformance
label | Ref docs - QMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports
checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.