## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0023 General Concrete Paving | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0023 General Concrete Paving
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 1630-SYM-QAC-ITP-0023
label | Rev No. - 00
label | Date of Issue - 08/01/2024
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Concrete mix design approval
label | Ref docs - VR703.01, VR703.05
label | Acceptance criteria - Concrete mix design is approved by the Superintendent.
label | Freq - Prior to start of Works
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
textbox | TeamBinder Ref No.
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Setting Out
checkpoint | 2.1 - Setting Out
label | Ref docs - VR703.15, VR703.17
label | Acceptance criteria - The concrete will be constructed in accordance with the confirmed line, level, grade and cross-sectional profiles as shown on the drawings or as specified in VR703.
label | ○ The Superintendent has reviewed and confirmed the set out.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Subgrade/Subbase
checkpoint | 3.1 - Bedding Preparation
label | Ref docs - IFC Drawings VR703.21
label | Acceptance criteria - Bedding material conforms to the requirements as stated in the design drawings. Immediately before concrete is placed, the bedding is moist with no free water on the surface.
label | Edgings
label | ○ Where edgings are constructed over pavement layers, bedding is provided between the pavement layer and the underside of the edging, or the edging is thickened to match the pavement layer.
label | ○ Where edgings are not constructed over pavement layers, bedding is 100mm thick unless noted otherwise.
label | Footpath and Other Surfaces
label | ○ For footpaths and other surfacing’s, bedding is of 100mm compacted thickness unless noted otherwise.
label | Shared User Path
label | ○ For shared user paths, bedding is 150mm thick and compacted in accordance to Section 304 unless noted otherwise.
label | Jointed reinforced concrete
label | ○ Bedding is to be as per IFC drawings and compacted in accordance with Vicroads Sec304.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 3.2 - Material Testing for Concrete (if applicable)
label | Ref docs - VR304.09
label | Acceptance criteria - For shared user paths, scale B testing is completed in accordance with VR304 with the below requirements:
label | – Moisture Content: >85%
label | – Compaction: ≥97%
label | – Post compaction grading
label | ○ For Jointed reinforced concrete, scale B testing is completed in accordance with VR304 for each material of the subbase.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Material test results
section | 4.0 Installation of General Concrete
checkpoint | 4.1 - Formwork
label | Ref docs - VR703.12
label | Acceptance criteria - Ensure materials, design, construction and stripping of formwork complies with AS 3610. As well as erecting formwork prior to placing concrete so that fresh concrete is not placed directly on the side of the excavation.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
checkpoint | 4.2 - Steel Reinforcement
label | Ref docs - VR703.13
label | Acceptance criteria - Reinforcement complies with AS/NZS 4671, and the minimum cover of reinforcement is 50mm or as per specified in the drawings.
label | ○ Reinforcement is supported using either concrete or plastic chairs.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.3 - Thickness and Steel Reinforcement Requirements
label | Ref docs - VR703.16
label | Acceptance criteria - The concrete paving thickness and reinforcement is as per the drawings.
label | SUP's and Commercial Vehicle Crossings
label | ○ SUP’s and commercial vehicle crossings are reinforced with SL82 mesh and are 150mm and 170mm thick respectively, or as specified in the drawings.
label | Medians
label | ○ Median surfacing within 2m of the edge of the median and bays of footpath, is as per design drawings and reinforced with SL72 steel mesh unless otherwise specified.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.4 - Fibre Reinforced Concrete
label | Ref docs - VR 703.14
label | Acceptance criteria - Where fibre reinforced concrete is proposed to replace up to SL82 steel mesh, the fibres are made from virgin polypropylene or copolymer.
label | ○ The properties meet the requirements of VR 703.14.
label | ○ The worksheet and/or report for determination of fibre content has been reviewed by the Superintendent.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - R
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Worksheet for determination of fibre content
checkpoint | 4.5 - Placing, compacting and finishing concrete
label | Ref docs - VR610.13, VR610.18, VR703.08
label | Acceptance criteria - Immediately before concrete is placed, the bedding is moist but has no free water on the surface as per VR 703.21.
label | ○ Concrete was not mixed when the air temperature is lower than 5°C or greater than 35°C.
label | ○ Discharge Time to be 60 minutes unless mix design is approved for 90 minutes.
label | ○ Concrete was thoroughly compacted by means of continuous tamping and internal vibration.
label | ○ Fresh concrete was not placed against concrete which has taken its initial set, except at properly formed construction joints.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
label | SI Key - H
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Concrete pour record attached.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Provision For Permanent Signs
label | Ref docs - VR703.22
label | Acceptance criteria - Sign post sockets have been supplied and installed to provide for erection of permanent signs in the areas to be paved at locations shown on the drawings.
label | ○ Socket depths, dimensions and installation requirements are in accordance to Section 714.06(d). Any concrete which falls into the sleeve has been removed.
label | Freq - Each Lot
label | Key - H
label | Resp - SE
checkpoint | 4.7 - Conformance Testing
label | Ref docs - VR703.11 Table 703.111
label | Acceptance criteria - The compressive strength of the concrete meets the requirements of table 703.111.
label | ○ The frequency of sampling is once per 50m^3 of each strength grade on each day.
label | ○ The consistency of the concrete is determined by using a slump test of each concrete strength sample in accordance with AS1012.3 and clause 5.2 of AS1379. (Not required for concrete used in kerbs and channels and edgings).
label | ○ Sampling and testing for concrete used in shared use paths is in accordance with Section 610.
label | ○ Compressive strength and slump testing is not required for concrete used in extruded kerbs and channels and other edgings.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Concrete test results attached. | Yes,No,N/A
checkpoint | 4.8 - Surface Finish
label | Ref docs - VR703.25
label | Acceptance criteria - Permanently hidden concrete surfaces including footpaths, edgings and other concrete surfacing have a class 4 surface finish in accordance with AS3610. All other concrete elements have a class 3 surface finish.
label | Edgings
label | ○ Edgings have been rendered with a steel trowel finish. Rendering to be applied within 30 minutes of placing concrete.
label | ○ The mortar used is 2 parts fine aggregate, 1 part cement and mixed with enough water for a suitable consistency.
label | ○ The thickness of the rendering does not exceed 3mm.
label | Footpath, SUP & Other Surfacing's
label | ○ Concrete placed for footpaths, surfacing’s and SUP’s, has been compacted and worked until the coarse aggregate is below the surface and mortar comes to the top. Mortar has been struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.9 - Joints
label | Ref docs - VR703.26 SD2071
label | Acceptance criteria - Expansion Joints
label | ○ Expansion joints are 15mm wide and placed at intervals not exceeding 10m, on either side of vehicle crossings, at junctions with existing footpaths and SUPs. Joints are filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the paving unless noted otherwise in the drawings.
label | Control Joints
label | ○ Control joints are at least 25% of paving thickness and 5mm wide at 2.5m intervals unless stated otherwise.
label | Extruded Edgings
label | ○ Extruded edgings have transverse joints every 2.5m with a width of 5mm and tooled depth of 20mm.
label | Indented bus bay contraction joints
label | ○ Indented bus bays have 15mm transverse contraction joints at 3m intervals, and are filled with neoprene compression seal as per SD2071.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.10 - Curing of Concrete
label | Ref docs - VR703.10
label | Acceptance criteria - The curing process has commenced immediately after finishing operations are completed, when using either water or wet hessian or curing compound.
label | ○ Curing compounds must comply with AS3799.
label | ○ The curing process using a curing compound is completed for a constant period of no less 7 days uninterrupted for general concrete purposes and at least 3 days for concrete edgings.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.11 - Formwork Stripping
label | Ref docs - VR703.12
label | Acceptance criteria - Formwork has not been removed until:
label | ○ 2 days for vertical formwork on external surfaces: and
label | ○ 1 day for vertical forms on permanently hidden surfaces.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.12 - Protection of Concrete
label | Ref docs - VR703.27
label | Acceptance criteria - All concrete is protected from damage from early loading.
label | ○ The contractor has ensured that no vehicles are permitted to cross over private entrance or commercial vehicle crossings a minimum of four days after completion of casting of concrete.
label | ○ Vehicles greater than 1.5t may not be permitted to cross until after 7 days.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.13 - Backfilling
label | Ref docs - VR703.29
label | Acceptance criteria - Concrete is backfilled no earlier than 3 days after placing. Topsoil material is free from perishable matter and then placed and compacted as specified.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
checkpoint | 4.14 - Inspection of Concrete Cracking
label | Ref docs - VR703.03, VR703.30, VR703.25
label | Acceptance criteria - Concrete has no surface cracks of width greater than 0.2mm. Where this occurs, this is identified as a non-conformance and repaired in accordance with section 687.
label | ○ Any concrete repairs have been carried out using a method and materials accepted by the Superintendent.
label | Freq - Each Lot
label | Key - I
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Completion
checkpoint | 5.1 - As Built Survey
label | Ref docs - VR703.15
label | Acceptance criteria - All surfaces satisfy lines, levels, thicknesses, and cross sections as specified on the drawings within the specified tolerances stated in VR703.15.
label | ○ Section dimensions as per the design drawings.
label | Freq - Each Lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Survey Conformance Report Attached | Yes,No,N/A
checkpoint | 5.2 - Test Reports
label | Ref docs - VIC Roads Specifications
label | Acceptance criteria - All Test reports received and reviewed.
button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | Freq - Each lot
label | Key - R
label | Resp - SE
checkpoint | 5.3 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
textbox | NCR No:
button | NCR No | Yes,No
label | NCR reports
checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
label | Freq - Each lot
label | Key - R
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.