## Asphalt - Surfacing
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F - Tongoio Falls Steep Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Asphalt - Surfacing (AC 14) |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Dave Hooker Teams note to Josin 21-Dec-23 | Andrew Harrall on behalf of Trudy Guy 08-Jan-24 | Quality Eng.
Lot No: B1101A - Tongoio Falls Steep Underslip |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 608 RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Installation of Erosion and Sediment Controls | M | Monitor effectiveness of the ESCP Controls throughout the construction process | Prior to commencement | Visual Inspection | Visual Inspection |  | Site Engineer
2 | Survey Setout | H | Set out pegs installed every 20m if required | Prior to commencement | Survey |  | Survey receipt | WSP
3 |  | W | Determine paving run start/stop locations | Prior to commencement | Survey | Mark out on site | Subcontractor QA Records | Higgins
4 | Material Compliance | H | Mix Design approved including peer review | Prior to commencement | Lab Testing | Material is approved by a Notice to Supplier being issued | Mix Design | Higgins | CPS
5 |  | H | Asphalt Material Quality Testing | Prior to commencement | Lab Testing | Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius | Asphalt Plant Results | Higgins | CPS
6 | Asphalt Production Testing | H | Full volumetric and air voids test 1 test - 1 test per day Binder content and grading 1 test per 100t. | Prior to commencement | Lab Testing and measurements | Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature | Asphalt Plant Results | Higgins
7 | Tack Coat | M | A Spray sheet for every day | Prior to placing Surfacing AC | Measure | Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2 | Subcontractor QA Records | Higgins
8 | Construction of Surfacing Asphaltic Concrete | H | Site team QA Checks | During Construction | Site Measurements | Delivery temperature, mat thickness before compaction, mix temperature during compaction | Subcontractor QA Records | Higgins
9 | Surface finish visual inspection | H | Site walk over | Post Construction | Visual Inspection | No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline. | Subcontractor QA Records | Site Engineer | CPS
10 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Higgins
11 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Asbuilts, NCR's and RFI's | Site Engineer
12 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: