## ITP Cover Page
Noise Wall 2-7 - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 008 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | 008
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Noise Wall 2-7 |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STR
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 18.6 - Noise walls
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 20/01/2025 |  | Cordelia Girdler-Brown and Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM |  | Nick Adams
Downer QM |  | Cordelia Girdler-Brown | [5 empty] | Downer QM |  | Cordelia Girdler-Brown
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body_BC
Noise Wall 2-7 - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 008 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-Construction - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL APPROVAL: STRUCTURAL STEEL
3.1.1 | All metalwork to be approved by the engineer after fabrication | Hot dip galvanised to standard hdg 900 | Hot dip galvanised to standard hdg 900 | PS 18.6.3 (a) ii | Supplier data sheet Engineers approval | Prior to Construction | HP | ENG
3.1.2 | Hot rolled steel plates | All hot rolled steel sections shall be grade 300 complying with AS/NZS 3679: part 1 | Grade 300 - AS/NZS 3679 Part 1 | PS 18.6.3 (a) iv | Supplier data sheet/ Mill certs | Prior to Construction | W | SE
3.1.3 | Cold formed steel plates | All cold formed steel sections shall be grade 350lo complying with AS/NZS 1163 | Grade 350 lo - AS/NZS 1163 | PS 18.6.3 (a) v | Supplier data sheet / Mill certs | Prior to Construction | W | SE
3.1.4 | Mild Steel plates | All mild steel plate shall be hot rolled grade 350 complying with AS/NZS3678 (AS/NZS 3678-350) | Grade 350 - AS/NZS 3678 (AS/NZS 3678-350) | PS 18.6.3 (a) vi | Supplier data sheet / Mill certs | Prior to Construction | W | SE
3.1.5 | Round bar/rod | To be grade 300 to AS/NZS 4671 | Grade 300 - AS/NZS 4671 | PS 18.6.3 (a) vii | Supplier data sheet / Mill certs | Prior to Construction | W | SE
3.1.6 | Bolts and treaded rods | All bolts and threaded rods shall be category 4.6/s to AS 1252 | Category 4.6/s to AS 1252 | PS 18.6.3 (a)viii | Supplier data sheet / Mill certs | Prior to Construction | W | SE
3.1.7 | Rough or sharp edges | All rough or sharp edges or protrusions to be buffed smooth | All rough or sharp edges or protrusions to be buffed smooth | PS 18.6.3 (a) x | Visual inspection | Prior to Construction | W | SE
3.1.8 | Epoxy Coating to the Steel column | 250 mm high build epoxy paint all round the UC column concrete interface | all columns must be coted with epoxy at steel and concrete interface | WSP-DR-STR-0306 | Visual inspection | Prior to Construction | I | SE
3.1.9 | Butynol sheeting - membrane | Butynol or any similar approved shall be used between timber and steel | Membrane seal | PS18.6.3 (c)viii | Supplier data sheet Engineers approval | Prior to Construction | W | SE
3.2 | MATERIAL APPROVAL: TIMBER
3.2.1 | Timber | Timber shall be VSG8 grade radiate pine complyng with NZS 3603 and graded to NZS 3631 | VS8 Grade radiate pine with a Timber strength - 11.7MPa | PS 18.6.3 (c) i | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.2 | Timber - in contact with the ground | Round or rough sawn piles in contact with the ground to be H5 | H5 | PS 18.6.3 (c) ii | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.3 | Timber - not in contact wth the ground | Rough sawn timber not in contact with the ground to be H3.2 | H3.2 | PS 18.6.3 (c) iii | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.4 | All timber components of noise wall | Timber treatment shall comply with requirements of the NZ Timber Preservation Council incorporating - MP 3640. All timber shall be branded to NZS3640:2003 and must be treated not less than 2 months prior to use. | MP 3640 NZS3640:2003 | PS 18.6.3 (c) iv & v | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.5 | All timber components of noise wall | Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects. | Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects. | PS 18.6.3 (c)vi | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.6 | All timber components of noise wall | Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602. | Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602. | PS 18.6.3 (c)vii | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.2.7 | Galvanised bolts | All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes | All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes | PS 18.6.3 (c) ix | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.3 | MATERIAL APPROVAL: PRECAST CONCRETE PANELS
3.3.1 | Concrete Grades |  | Concrete grade to be >40 Mpa Exposure classification to be B1 Min.Concrete cover 40 mm | NZS 3109:1997 | Supplier data sheet Delivery dockets | Prior to Construction | W | SE |  |  |  | Verifying document: Add Delivery dockets also
3.3.2 | Concrete Materials and Worksmanship | All worksmanship and materials shall be in accordance with NZS 3109:1997 concrete Construction. | NZS 3109:1997 | NZS 3109:1997 | Supplier data sheet | Prior to Construction | W | SE
3.3.3 | Aggregate & Concrete Mix Design | Aggregate and overall mix design to meet the provisions of 'TR3 Alkali Silica Reaction 2003 (CCANZ)'. | Aggregate used and overall mix design (including additives) shall meet the provisions of 'TR3 Alkali Silica Reaction 2003 (CCANZ)'. | TR3 Alkali Silica Reaction 2003 (CCANZ) | Supplier data sheet concrete mix design approval Delivery dockets | Prior to Construction | W | SE |  |  |  | Verifying document: Add Delivery dockets also
3.3.4 | Concrete | Concrete shall not be spread by vibrating. | Concrete shall not be spread by vibrating. | WSP-DR-STR-0306 | Supplier data sheet | Prior to Construction | W | SE
3.3.5 | Corners and Edges | 20x20 chamfer or fillets | All corners and edges to concrete surfaces shall have a 20x20 chamfer or fillets. | WSP-DR-STR-0306 | Supplier data sheet Visual inpection | Prior to Construction | W | SE |  |  |  | Verifying document: Add Visual inspection also
3.4 | MATERIAL APPROVAL: FOOTING CONCRETE
3.4.1 | Concrete Mix Design | 17.5 MPA Concrete | 28 days concrete strength test of 17.5MPA | WSP-DR-STR-0006 | Delivery dockets and supplier data sheet | Prior to Construction | HP | ENG
3.5 | MATERIAL APPROVAL: FIXINGS
3.5.1 | FH Nails | General structural use 75mm x 3.15mm FH nails . All nails shall be flat headed, unless otherwise shown, hot dip galvanised and fully driven | 75mm x 3.15mm FH Nails | PS 18.6.3 (d) i | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.5.2 | Bolts | Bolts shall be M12 hot dip galvanised engineers bolts fitted with 50x50x5 galvanised square washers both ends. Washers for coach screws shall be provided in accordance with NZS 3604 | M12 hot dipped, 50x50x5 galvanised square washers | PS 18.6.3 (d) iii | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.5.3 | Bolts within 100mm of ground | Bolts within 100mm of ground to be stainless steel. | Stainless steel bolts | PS 18.6.3 (d) v | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
3.5.4 | Coach screws | All screws shall be hot dip galvanised and screw fixings shall be pre-bored. | Hot dip galvanised | PS 18.6.3 (d) vi | Delivery dockets and supplier data sheet | Prior to Construction | W | SE
SECTION 4 – Construction ACTIVITY
4.1 | SITE CLEARANCE - PREPARATION
4.1.1 | Removal of existing timber fences & chainlink fences | Removal of existing timber fences & chainlink fences | Removal of existing timber fences & chainlink fences |  | Visual inspection/photos | After Construction of each Area | I | SE
4.1.2 | Ecology and Environmental Manager Approval | Ecology and Environmental Manager to approve the removal of existing vegetation prior to site clearance. | Ecology & Environmental Manager's Approval | PS 27.3.5 | Visual inspection/photos | Prior to Construction | W | ENG
4.1.3 | Clearing and Disposal of Existing Vegetation | The clearing and disposal of existing vegetation, removal and disposal of existing hardstand surfaces, inorganic debris, site preparation spraying, pruning and minor landscape earthworks, and topsoil re-spreading shall fully comply with Section C of NZTA P39:2013. | NZTA P39:2013 | PS 27.3.5 (a) | Visual inspection/photos | After Construction | I | SE
4.1.4 | Existing Vegetation Mulch | Where possible, existing vegetation, excluding pest plant material, that is removed via site clearance shall be converted to mulch and, if required, stockpiled in an appropriate location. | Existing vegetation converted to mulch and stockpiled if required. | PS 27.3.5 (b) | Visual inspection/photos | After Construction | I | SE
4.2 | NOISE WALL Construction
4.2.1 | Setting out of Noise wall Posts | Setting out to follow design coordinates and levels within tolerance as specified in PS 18.5.7 section (e). | Engineers Approval | PS 18.6.1 | Survey records | Engineers Approval | W | ENG |  |  |  | Verifying document: Survey records also to be addded
4.2.2 | Geo Technical investigation on each post holes | Holes are to be 400mm dia and 2.8m deep Shear vane testing at the base of holes to be completed to a strength of 60kp | Shear vane strength of 60kpa | PS 18.6.2 WSP-DR-STR-(0212-0219) | Shear vane test report | Engineers Approval | HP | ENG
4.2.3 | Noise wall footing concrete | 17.5 MPA Concrete | 28 days concrete strength test of 17.5MPA | WSP-DR-STR-0006 | Concrete Delivery Docket Concrete inspection checklist | After Construction | I | SE |  |  |  | verifying document: Concrete inspection checklist also to be addded
4.2.4 | Installing Wooden Railings | with sufficient embeddment of nails and connecting details as per drawings - WSP-DR-STR-0006 |  | WSP-DR-STR-0006 | Noise wall Checksheet | After Construction | I | SE
SECTION 5 – POST Construction ( HANDOVER)
5.1 | As-builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. | All changes to design need to be captured on the noise wall drawing set | PS 12.2.2 | Redpen Markup | During Construction and After finishing | H | SE
Note on E48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jeremy Martin - please add the drawing number here
Note on E49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jeremy Martin - this should be the drawing number - 232735.02-WSP-DR-STR-0006 as this is not stated in PS18.6.2
Note on C50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jeremy Martin - please add drawing number here
Note on E50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jeremy Martin - please add drawing number here