## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-008 ITP Noisewall 2-7 | itp |  |  |  |  | DN1210-SP2-008 ITP Noisewall 2-7 Rev 0
section | SECTION 3 – PRE-Construction - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - All metalwork to be approved by the engineer after fabrication
label | Detail - Hot dip galvanised to standard hdg 900
label | Acceptance / Conformance Criteria - Hot dip galvanised to standard hdg 900
label | Standard / Specification - PS 18.6.3 (a) ii
label | Verifying Document - Supplier data sheet, Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Hot rolled steel plates
label | Detail - All hot rolled steel sections shall be grade 300 complying with AS/NZS 3679: part 1
label | Acceptance / Conformance Criteria - Grade 300 - AS/NZS 3679 Part 1
label | Standard / Specification - PS 18.6.3 (a) iv
label | Verifying Document - Supplier data sheet/ Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.3 - Cold formed steel plates
label | Detail - All cold formed steel sections shall be grade 350lo complying with AS/NZS 1163
label | Acceptance / Conformance Criteria - Grade 350 lo - AS/NZS 1163
label | Standard / Specification - PS 18.6.3 (a) v
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.4 - Mild Steel plates
label | Detail - All mild steel plate shall be hot rolled grade 350 complying with AS/NZS3678 (AS/NZS 3678-350)
label | Acceptance / Conformance Criteria - Grade 350 - AS/NZS 3678 (AS/NZS 3678-350)
label | Standard / Specification - PS 18.6.3 (a) vi
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.5 - Round bar/rod
label | Detail - To be grade 300 to AS/NZS 4671
label | Acceptance / Conformance Criteria - Grade 300 - AS/NZS 4671
label | Standard / Specification - PS 18.6.3 (a) vii
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.6 - Bolts and treaded rods
label | Detail - All bolts and threaded rods shall be category 4.6/s to AS 1252
label | Acceptance / Conformance Criteria - Category 4.6/s to AS 1252
label | Standard / Specification - PS 18.6.3 (a)viii
label | Verifying Document - Supplier data sheet / Mill certs
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.7 - Rough or sharp edges
label | Detail - All rough or sharp edges or protrusions to be buffed smooth
label | Acceptance / Conformance Criteria - All rough or sharp edges or protrusions to be buffed smooth
label | Standard / Specification - PS 18.6.3 (a) x
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.8 - Epoxy Coating to the Steel column
label | Detail - 250 mm high build epoxy paint all round the UC column concrete interface
label | Acceptance / Conformance Criteria - all columns must be coted with epoxy at steel and concrete interface
label | Standard / Specification - WSP-DR-STR-0306
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.9 - Butynol sheeting - membrane
label | Detail - Butynol or any similar approved shall be used between timber and steel
label | Acceptance / Conformance Criteria - Membrane seal
label | Standard / Specification - PS18.6.3 (c)viii
label | Verifying Document - Supplier data sheet, Engineers approval
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Timber
label | Detail - Timber shall be VSG8 grade radiate pine complyng with NZS 3603 and graded to NZS 3631
label | Acceptance / Conformance Criteria - VS8 Grade radiate pine with a Timber strength - 11.7MPa
label | Standard / Specification - PS 18.6.3 (c) i
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.2 - Timber - in contact with the ground
label | Detail - Round or rough sawn piles in contact with the ground to be H5
label | Acceptance / Conformance Criteria - H5
label | Standard / Specification - PS 18.6.3 (c) ii
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.3 - Timber - not in contact wth the ground
label | Detail - Rough sawn timber not in contact with the ground to be H3.2
label | Acceptance / Conformance Criteria - H3.2
label | Standard / Specification - PS 18.6.3 (c) iii
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.4 - All timber components of noise wall
label | Detail - Timber treatment shall comply with requirements of the NZ Timber Preservation Council incorporating - MP 3640.
label | ○ All timber shall be branded to NZS3640:2003 and must be treated not less than 2 months prior to use.
label | Acceptance / Conformance Criteria - MP 3640 NZS3640:2003
label | Standard / Specification - PS 18.6.3 (c) iv & v
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.5 - All timber components of noise wall
label | Detail - Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects.
label | Acceptance / Conformance Criteria - Timber shall have a moisture content less than 18% at time of installation to avoid excessive shrinkage effects.
label | Standard / Specification - PS 18.6.3 (c)vi
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.6 - All timber components of noise wall
label | Detail - Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602.
label | Acceptance / Conformance Criteria - Treat all cut surfaces with clear zinc naphthenate preservative and in accordance with NZ 3602.
label | Standard / Specification - PS 18.6.3 (c)vii
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.2.7 - Galvanised bolts
label | Detail - All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes
label | Acceptance / Conformance Criteria - All galvanised bolts in contact with H5 treated timber shall be protected using CP grease in pre-greased holes
label | Standard / Specification - PS 18.6.3 (c) ix
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Concrete Grades
label | Detail - CONCRETE (cont.)
label | – – – – – – – – – – – – –
label | C9 CONCRETE GRADES SHALL BE: (UNLESS NOTED ON DRAWINGS)
label | ELEMENT ¦¦ CONCRETE GRADE (MPa) ¦¦ EXPOSURE CLASSIFICATION ¦¦ MIN. CONCRETE COVER
label | – – – – – – – – – – – – –
label | ○ PRECAST METALS ¦¦ 40 MPa ¦¦ B1 ¦¦ 40
label | – – – – – – – – – – – – –
label | Acceptance / Conformance Criteria - Concrete grade to be >40 Mpa
label | ○ Exposure classification to be B1
label | ○ Min.Concrete cover 40 mm
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Supplier data sheet, Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Concrete Materials and Worksmanship
label | Detail - All worksmanship and materials shall be in accordance with NZS 3109:1997 concrete Construction.
label | Acceptance / Conformance Criteria - NZS 3109:1997
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.3 - Aggregate & Concrete Mix Design
label | Detail - Aggregate and overall mix design to meet the provisions of 'TR3 Alkali Silica Reaction 2003 (CCANZ)'.
label | Acceptance / Conformance Criteria - Aggregate used and overall mix design (including additives) shall meet the provisions of 'TR3 Alkali Silica Reaction 2003 (CCANZ)'.
label | Standard / Specification - TR3 Alkali Silica Reaction 2003 (CCANZ)
label | Verifying Document - Supplier data sheet concrete mix design approval, Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.4 - Concrete
label | Detail - Concrete shall not be spread by vibrating.
label | Acceptance / Conformance Criteria - Concrete shall not be spread by vibrating.
label | Standard / Specification - WSP-DR-STR-0306
label | Verifying Document - Supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.3.5 - Corners and Edges
label | Detail - 20x20 chamfer or fillets
label | Acceptance / Conformance Criteria - All corners and edges to concrete surfaces shall have a 20x20 chamfer or fillets.
label | Standard / Specification - WSP-DR-STR-0306
label | Verifying Document - Supplier data sheet, Visual inpection
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Concrete Mix Design
label | Detail - 17.5 MPA Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - WSP-DR-STR-0006
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5.1 - FH Nails
label | Detail - General structural use 75mm x 3.15mm FH nails . All nails shall be flat headed, unless otherwise shown, hot dip galvanised and fully driven
label | Acceptance / Conformance Criteria - 75mm x 3.15mm FH Nails
label | Standard / Specification - PS 18.6.3 (d) i
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.5.2 - Bolts
label | Detail - Bolts shall be M12 hot dip galvanised engineers bolts fitted with 50x50x5 galvanised square washers both ends. Washers for coach screws shall be provided in accordance with NZS 3604
label | Acceptance / Conformance Criteria - M12 hot dipped, 50x50x5 galvanised square washers
label | Standard / Specification - PS 18.6.3 (d) iii
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.5.3 - Bolts within 100mm of ground
label | Detail - Bolts within 100mm of ground to be stainless steel.
label | Acceptance / Conformance Criteria - Stainless steel bolts
label | Standard / Specification - PS 18.6.3 (d) v
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.5.4 - Coach screws
label | Detail - All screws shall be hot dip galvanised and screw fixings shall be pre-bored.
label | Acceptance / Conformance Criteria - Hot dip galvanised
label | Standard / Specification - PS 18.6.3 (d) vi
label | Verifying Document - Delivery dockets and supplier data sheet
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
section | SECTION 4 – Construction ACTIVITY
checkpoint | 4.1.1 - Removal of existing timber fences & chainlink fences
label | Detail - Removal of existing timber fences & chainlink fences
label | Acceptance / Conformance Criteria - Removal of existing timber fences & chainlink fences
label | Standard / Specification -
label | Verifying Document - Visual inspection/photos
label | Testing Quantity Required (based from schedule qtys) - After Construction of each Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Ecology and Environmental Manager Approval
label | Detail - Ecology and Environmental Manager to approve the removal of existing vegetation prior to site clearance.
label | Acceptance / Conformance Criteria - Ecology & Environmental Manager's Approval
label | Standard / Specification - PS 27.3.5
label | Verifying Document - Visual inspection/photos
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 4.1.3 - Clearing and Disposal of Existing Vegetation
label | Detail - The clearing and disposal of existing vegetation, removal and disposal of existing hardstand surfaces, inorganic debris, site preparation spraying, pruning and minor landscape earthworks, and topsoil re-spreading shall fully comply with Section C of NZTA P39:2013.
label | Acceptance / Conformance Criteria - NZTA P39:2013
label | Standard / Specification - PS 27.3.5 (a)
label | Verifying Document - Visual inspection/photos
label | Testing Quantity Required (based from schedule qtys) - After Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Existing Vegetation Mulch
label | Detail - Where possible, existing vegetation, excluding pest plant material, that is removed via site clearance shall be converted to mulch and, if required, stockpiled in an appropriate location.
label | Acceptance / Conformance Criteria - Existing vegetation converted to mulch and stockpiled if required.
label | Standard / Specification - PS 27.3.5 (b)
label | Verifying Document - Visual inspection/photos
label | Testing Quantity Required (based from schedule qtys) - After Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Setting out of Noise wall Posts
label | Detail - Setting out to follow design coordinates and levels within tolerance as specified in PS 18.5.7 section (e).
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 18.6.1
label | Verifying Document - Survey records
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 4.2.2 - Geo Technical investigation on each post holes
label | Detail - Holes are to be 400mm dia and 2.8m deep
label | ○ Shear vane testing at the base of holes to be completed to a strength of 60kp
label | Acceptance / Conformance Criteria - Shear vane strength of 60kpa
label | Standard / Specification - PS 18.6.2, WSP-DR-STR-(0212-0219)
label | Verifying Document - Shear vane test report
label | Testing Quantity Required (based from schedule qtys) - Engineers Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Noise wall footing concrete
label | Detail - 17.5 MPA Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - WSP-DR-STR-0006
label | Verifying Document - Concrete Delivery Docket, Concrete inspection checklist
label | Testing Quantity Required (based from schedule qtys) - After Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.4 - Installing Wooden Railings
label | Detail - with sufficient embeddment of nails and connecting details as per drawings - WSP-DR-STR-0006
label | Acceptance / Conformance Criteria - Skew nails shall be installed as shown.
label | Standard / Specification - WSP-DR-STR-0006
label | Verifying Document - Noise wall Checksheet
label | Testing Quantity Required (based from schedule qtys) - After Construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – POST Construction ( HANDOVER)
checkpoint | 5.1 - As-builts
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - All changes to design need to be captured on the noise wall drawing set
label | Standard / Specification - PS 12.2.2
label | Verifying Document - Redpen Markup
label | Testing Quantity Required (based from schedule qtys) - During Construction and After finishing
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature