## ITP Cover Page
Wetland Maintenance Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 034 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 034
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Wetland Maintenance Access Track |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-PVS
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specifications, TCC IDC
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
1 | Draft | 10/12/204 |  | Cordelia Girdler-Brown |  | Changes made as Per NTC 0402 |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Chris Benson | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler-Brown | [5 empty] | Downer QM

## Wetland Maitenance Acces Track
Wetland Maintenance Access Track Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 034 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | MATERIAL APPROVALS: Imported Material Testing - GAP65-2 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS | [12 empty] | Final
1.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >60% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA,AB,AC,BA,BB,CB or CA | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Percentage Passing 63.0 100% 37.5 68-90% 19 42-76% 9.5 26-58% 4.75 16-44% 2.36 10-33% 1.18 6-24% 0.425 3-14% 0.075 1-6% | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.1.6 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | <8 | NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2 | MATERIAL APPROVALS: Imported Material Testing - AP40-2 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.2.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >130KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >80% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA,AB,AC,BA,BB or CA | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size Percentage Passing 37.5 100% 19.0 66-81% 9.5 43-57% 4.75 28-43% 2.36 19-33 % 1.18 12-25% 0.600 7-19% 0.300 3-14% 0.150 0-10% 0.075 0-7% | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.2.6 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | <8 If SE is <40 | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >40 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | <5 If SE is <40 | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
1.3 | MATERIAL APPROVALS: GAP20 (Class 4)
1.3.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >80KN | M04/4.4.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.2 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA,AB,AC,BA,BB or CA | M04/4.4.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 19.0mm 98-100% passing 9.5mm 50-80% passing 4.75mm 29-61% passing 2.36mm 19-46% passing 1.18mm 11-35% passing 0.600mm 5-26% Passing 0.300mm 3-19%Passing 0.150mm 0-15% passing 0.075mm 0-1% passing | M04/Table 14 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.3.4 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | M4 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.3.5 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | Max 15 | M4/5.4.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
SECTION 2 - CONSTRUCTION - PREP GENERAL
2.1 | GENERAL
2.1.1 | Cut Subgrade Testing - Granular Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 4 blows per 100mm penetration | PS 27.4.2 | Scala Report | 4 test per 400M2 | I | SE
2.1.2 | Proof roll | Visual Inspection of Proof Roll | Visual Inspection of Proof Roll | Appendix XVIII | Visual inspection/ Photos | Across Whole are | I | ENG
SECTION 3 - SUBBASE LAYER - AP65-2
3.1 | Finished Level - Stringline or Equivalent
3.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface. | (-25+5)mm | NZTA B/02 5.1 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.1.2 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 10mm | TNZ B/2 7.7 | Check Sheet | Every 20m Centres 1 each lane | I | SE
3.2 | Compaction - NDM
3.2.1 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | NZTA B/02 7.6 | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
3.2.2 | Clegg Hammer | Clegg Hammer Testing to be Carried out | Min CIV18 Ave CIV 20 | Earthworks Spec | IANZ Accredited Report | 2 set (5 tests) 1000m2 | I | SE
SECTION 4 - BASECOURSE LAYER (AP40-2)
4.1 | Finished Level - Stringline or Equivalent
4.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface. | (-15mm+0mm) | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.1.2 | 3m Straight Edge | Formation check to ensure surface is smooth | +/- 10mm | TNZ B/2 7.7 | Check Sheet | Every 20m Centres 1 each lane | I | SE
4.2 | Compaction - NDM
4.2.1 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >98% of MDD Min >95% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
SECTION 5 - BASECOURSE LAYER ( GAP20)
5.1 | Finished Level - Stringline or Equivalent
5.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface. | As Per Finished Surface | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
5.1.2 | Visual Inspection | Visual Inspecction needs to done With an Engineer for Final Surface | Site Instruction | Standard | Visual Inspection | Across Finish Surface | W | ENG
SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
13.1.2 | As-Builts Red Pen markup | Final inspection of All Work | All works meet project specifications and standards. Record Any Undercuts or change in Design | PS 16.7.6 | Survey Records Red Pen Mark up | During Earthworks | D | SV