## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-023
[11 empty] | Revision : 1 | Date : 12/02/2025
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | St Kilda Light Rail Maintenance |  | Destressing Rail |  | Name: | Leo Watson | Name: | Damon Bromwich |  | Name: | Shaun Kent
Contract No: |  |  |  | Specifications: Yarra Trams Infrastructure - Tram Track Construction Standard, Yarra Trams Technical Specification
|  |  |  | Structure / Component: Tram Tracks in Ballast Sections |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Royal Park, Parkville |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A
1.3 | Stress Free Temperature |  | Each lot | To ensure lateral stability, ensure that the stress free temperature of the rail conforms to the design value (38° C). | NIST-2650 Cl15.1 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A
1.4 | Module Lengths |  | Each lot | The preferred stress adjustment module length is 330 m. The maximum stress adjustment module length is 440 m on timber sleepers and 500 m on concrete sleepers. Shorter modules are permitted if the distance between fixed points is less than 330m | NIST-2650 Cl15.1.3 | Verify | This ITP signed | HP* | Fulton Hogan Engineer YT
1.5 | Closing Weld |  | Each lot | Closing weld is to be located as near as practicable to the centre of the module length (within 13.7m of centre) | NIST-2650 Cl15.1.4 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A
1.6 | Weld Record Sheet |  | Each Lot | Each weld must be recorded on the weld record sheet | NIST-2650 Cl15.1.7 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A
2 | Preparation
2.1 | Set up closing weld |  | Each lot | Mark location of closing weld. Punch mark the field side of the rail head in two places a minimum of 2m clear of each side of the closing weld. Measure the distance between the punch marks and record on the weld record sheet | NIST-2650 Cl15.2 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A
2.2 | Measure pre-existing (initial) gap in rail |  | Each lot | If no gap exists, record zero as initial gap. If there is an initial gap (incluing zero), measure and record the rail temperature at the time of preparation. | NIST-2650 Cl15.2 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A
3 | Stressing Adjustment
3.1 | Creating the module length |  | Each lot | -Measure and record the module length. -Provide anchor blocks as shown in Figure 15 and Table 18 of NIST-2650 -Remove all clips and fastenings over the module length, to ensure free movement of rail -Place a chalk or paint mark through the sleeper at each end of the module length (to monitor for any rail movement extending beyond module) and the quarter points of the module (to monitor for correct rail movement) | NIST-2650 Cl15.3.2 | Verify | This ITP signed |  | Fulton Hogan Engineer | N/A
3.2 | Destressing the rail |  | Each lot | -Ensure module is in a stress free state by using the tensor to close the gap by the distance set out in Table 19 of NIST-2650 -Lightly tap rail on the web at frequent intervals until the gap stops opening -Check that sleepers do not lock up -Check the quarter points to ensure rail is moving freely Check to ensure there is no movement of the rail at the extreme ends of the module | NIST-2650 Cl15.3.3 | Verify | This ITP signed |  | Fulton Hogan Engineer | N/A
3.3 | Punch length |  | Each lot | Upon completion of destressing process, record the distance between the punch marks "Punch Length After Destress" | NIST-2650 Cl15.3.3 | Verify | This ITP signed |  |  | N/A
4 | Closing weld
4.1 | Rail temperature |  | Each lot | Measure the rail temperature and record it on the Weld Record Sheet. If rail temperature exceeds 40° C, provision of stress adjustment gap and tensing of the rail is not required. | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
4.3 | Tense gap to weld gap |  | Each lot | Cut the end of one rail to give the required gap, and tense the rail to provide the weld gap | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
4.4 | Carry out weld |  | Each lot | After completing weld, wait at least 20 minutes before removing the tensor | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
4.5 | Stress distribution |  | Each lot | When the weld has cooled, tap the rail to distribute stresses evenly and reapply clips to the module | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
5 | Completion
5.1 | Punch marks |  | Each lot | Remeasure the distance between punch marks and record on weld record sheet | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
5.2 | Quarter points |  | Each lot | Measure and record the movement of quarter points | NIST-2650 Cl15.3.6 | Verify | This ITP signed | IP | Fulton Hogan | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K18: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on M19: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K20: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on M20: Rodrigo Anchico: Write "N/A" to disable the cell.