## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-008 - Hot Mix Asphalt | itp |  |  |  |  | ITP-008 - Hot Mix Asphalt Rev 0
section | Construction Works
checkpoint | 1.1 Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.3 Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.4 Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 1.5 Longitudinal Joints with existing Pavement
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | ○ Depth of step to be cut to the full depth of each indiviual layer.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c) Project Specs. Section 3040.06 (d)(vii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
textbox | Date Completed:
section | Asphalt Placement works
checkpoint | 2.1 Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Mix Design Confirmation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt mix shall be 10H in accorande with Yarra Trams Track Structure standard drawing.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
label | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Delivery docket, Completed ITP
label | HP*
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.3 Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20 Table 407.111
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.4 Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.5 Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.6 Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
checkpoint | 2.7 Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
label | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-021 - Construction of Track in Ballast Sections | itp |  |  |  |  | ITP-021 - Construction of Track in Ballast Sections Rev 0
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Check Materials
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
label | ○ Check condition of rail sleepers
label | ○ Ensure rail jewellery is of sound condition
label | ○ Ensure ballast is clean, free from clay, dirt and other deleterious matter or weathered pieces of rock and free of dust.
label | ○ Ensure ballast has been tested for conformity by a NATA certified laboratory and the results have been documented and recorded. On-site testing shall be completed for the particle size and shape of the ballast used.
label | REFERENCE DOCUMENTS: AS 1085 & CE-019-ST-0033 cl 4.8.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Client, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Base Course
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Ballast track construction shall not be carried out over any length of formation until the formation has been checked and approved by the superintendent.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 Check Special Works Components
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
label | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Check Curved rail
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent.
label | ○ Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails.
label | ○ This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Welders Qualifications
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
label | ○ TLIW2012 Grind Rails
label | ○ TLIW3015 Weld Rails using Aluminothermic welding process
label | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.6 Ultrasonic Testers Qualifications
label | FREQUENCY: Prior to Commencing Works
label | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Placement and Compaction of Ballast
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Prior to laying sleepers, 50mm Ballast shall be placed, graded and compacted in one or more layers to a total minimum depth of 150mm.
label | ○ Compaction shall be by a smooth wheeled vibrating roller as specified for earthworks.
label | ○ The superintendent shall inspect completed work prior to placement of sleepers.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Installation of Sleeper
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete tramway sleepers shall be installed at 700mm intervals, tolerance of +/- 50mm in placement
label | ○ Concrete tramway sleepers shall also comply with the design offsets at each chainage.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Placement of Rail
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
label | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
label | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
label | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
label | ○ Geometry tolerances as follows:
label | — Centreline location: +/- 3mm
label | — Level: +/- 3mm
label | — Line measured (>10m chord): +/- 3mm
label | — Twist (3.5m chord): +/- 2mm
label | — Cant: +/- 3mm
label | — Gauge (open track): +3mm, -0mm
label | — Gauge,Turnouts (opposite crossings):+2, -0mm
label | — Gauge, Diamonds and ‘H’ Crossings:+2, -0mm
label | ○ Note: Cant shall be applied uniformly over transitions
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completion of track charts
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Fastening of Rail
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to rail with approved jewellery and rail clips.
label | ○ Clips shall be installed with panpuller or equivalent.
label | ○ All fasteners shall be sealed as per agreed method with Yarra Trams.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Tampering of Ballast & Sleepers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: After track construction and prior to tamping, cribs and shoulers are to be filled to top of sleeper with extra ballast.
label | ○ All sleepers shall be lifted, lined and tamped after installation and fastening of rails.
label | ○ The depth of ballast following tamping shall be 200mm from top of sub ballast to bottom of sleepers.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.8
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Rail End Preparation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
label | ○ Minimum closure length from proximity of welds shall be 3m
label | ○ Rail end conditions shall match (i.e flame cut - flame cut)
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.7 Welding of Rail
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: Joints shall be square across the track
label | ○ Maximum skew at square joints shall be 65mm
label | ○ Portions shall match rail type (i.e HHR, Ordinary)
label | ○ Welds shall not be within:
label | — 3m of another weld
label | — 3m of a rail end
label | — 1.5m of a glued insulation joint assembly
label | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
label | ○ Weld Return forms shall be completed by qualified welder
label | ○ Welds shall be grinded after 1 hour
label | ○ Welds shall be free of water
label | ○ Post grinding, welds shall be cleaned for visual inspection
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.8 Grinding & Cleaning Welds
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
label | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer, YT
textbox | Date Completed:
checkpoint | 2.9 Installation of Check Plate
label | FREQUENCY: When required
label | ACCEPTANCE CRITERIA: Where Tee Head Rails are used at special works, crossovers, or on curves up to 325m, check plates shall be fitted in accordance with Table 2 of the Yarra Trams Infrastructure Tram Track Construction Standard.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.7
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.1 Track Adjustment
label | FREQUENCY: When required
label | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress.In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
label | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.9
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.11 Track Bonds
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
label | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
label | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5 Design Drawings
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Testing
checkpoint | 3.1 Track Testing
label | FREQUENCY: Each Weld
label | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator
label | ○ Failed welds shall be cut out and replaced
label | ○ Testing documentation shall be recorded and supplied to the superintendent
label | REFERENCE DOCUMENTS: CE-019-ST-0033 Appendix C
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed Off
label | TP
label | RESPONSIBILITY: Fulton Hogan Engineer/NDT
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | ITP-024 - De-stressing Rail | itp |  |  |  |  | ITP-024 - De-stressing Rail Rev 1
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Stress Free Temperature
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: To ensure lateral stability, ensure that the stress free temperature of the rail conforms to the design value (38° C).
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Module Lengths
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: The preferred stress adjustment module length is 330 m. The maximum stress adjustment module length is 440 m on timber sleepers and 500 m on concrete sleepers.
label | ○ Shorter modules are permitted if the distance between fixed points is less than 330m
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer, YT
textbox | Date Completed:
checkpoint | 1.5 Closing Weld
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Closing weld is to be located as near as practicable to the centre of the module length (within 13.7m of centre)
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.6 Weld Record Sheet
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Each weld must be recorded on the weld record sheet
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.1.7
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Preparation
checkpoint | 2.1 Set up closing weld
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Mark location of closing weld.
label | ○ Punch mark the field side of the rail head in two places a minimum of 2m clear of each side of the closing weld.
label | ○ Measure the distance between the punch marks and record on the weld record sheet
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Measure pre-existing (initial) gap in rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: If no gap exists, record zero as initial gap.
label | ○ If there is an initial gap (incluing zero), measure and record the rail temperature at the time of preparation.
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Stressing Adjustment
checkpoint | 3.1 Creating the module length
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: -Measure and record the module length.
label | — Provide anchor blocks as shown in Figure 15 and Table 18 of NIST-2650
label | — Remove all clips and fastenings over the module length, to ensure free movement of rail
label | — Place a chalk or paint mark through the sleeper at each end of the module length (to monitor for any rail movement extending beyond module) and the quarter points of the module (to monitor for correct rail movement)
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 Destressing the rail
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: -Ensure module is in a stress free state by using the tensor to close the gap by the distance set out in Table 19 of NIST-2650
label | — Lightly tap rail on the web at frequent intervals until the gap stops opening
label | — Check that sleepers do not lock up
label | — Check the quarter points to ensure rail is moving freely
label | ○ Check to ensure there is no movement of the rail at the extreme ends of the module
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.3 Punch length
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Upon completion of destressing process, record the distance between the punch marks "Punch Length After Destress"
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.3
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | RESPONSIBILITY:
textbox | Date Completed:
section | Closing Weld
checkpoint | 4.1 Rail temperature
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Measure the rail temperature and record it on the Weld Record Sheet. If rail temperature exceeds 40° C, provision of stress adjustment gap and tensing of the rail is not required.
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.3 Tense gap to weld gap
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Cut the end of one rail to give the required gap, and tense the rail to provide the weld gap
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.4 Carry out weld
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: After completing weld, wait at least 20 minutes before removing the tensor
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.5 Stress distribution
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: When the weld has cooled, tap the rail to distribute stresses evenly and reapply clips to the module
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
section | Completion
checkpoint | 5.1 Punch marks
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Remeasure the distance between punch marks and record on weld record sheet
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 5.2 Quarter points
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Measure and record the movement of quarter points
label | REFERENCE DOCUMENTS: NIST-2650 Cl15.3.6
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: