## Master List Templates
Id | Type | Name | Values | Prompting Name
719339c2-b674-4139-a24b-dce3581e7913 | checklist | Add Stainless Steel Drainage valve rebuild Checklist |  | Stainless Steel Drainage valve rebuild
10103ae7-a929-46b0-ab3e-da6d7941243d | section | Details
e12fc8ba-94cf-4634-9656-c2f7fb89ae28 | checkpoint | Photo of any pre existing damage to valve or penetration seal
e152c49b-7656-5860-9f81-f0357ee9f632 | textbox | Valve No.
2c7c9829-57d9-41fb-87b5-ffa0197a806c | checkpoint | Photo of valve before
0dcf6e5b-2e30-45f5-933f-17283733875d | checkpoint | Photo of old valve seals
2441ea2f-9c3e-4d9e-8bf3-20f64a774b4b | checkpoint | Photo of inside of the valve
3a220e98-e8a3-4242-81d0-963bbb0baa99 | checkpoint | Photo of new seals installed
e3fa560b-da13-4850-9f07-77751259f360 | checkpoint | Tightend to correct torque list newton meters
6e617f22-f32f-5fb4-b297-f4fe6cbf009b | tickbox | All Bolts Tightend in a cross pattern
f0a5caec-eac5-5cb6-afc3-80bf17f280d0 | number | Newton Meters
c1b21c1f-0d88-424d-a5c8-d3d58ee48d16 | checkpoint-no-value | Installing Plumber
a0b79cff-946a-5f60-8569-18693e782c47 | button | Plumber: | Richard Bell, Brendan Head, Guy Mcelholum

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Prefix | Postfix
1f309b8b-9b9e-412a-afa1-60fafc0a6007 | checklist | Add Fire Penetration Checklist |  | Fire Penetration:
3048d301-4a41-4b66-a3b8-53450f803acb | checkpoint | Treatment Type
8dbff9b8-6e77-5eaa-8951-0a0a3788ba59 | dropdown | Treatment Type: | A1,A2,B,C,D,E,F,G,H1,H2,H3,J,K,M,N1,N2,O,P,Q,R,S,T,V
8607dbf3-ebf5-472c-ba42-0463825d68c9 | checkpoint | Photo of penetration and sticker must be taken
c4af4b95-56a6-5784-a236-d44e5563d78c | textbox | Installed by:
eb26d1a9-f168-515c-b2a9-625f23789267 | textbox | Comments / Reasons why cannot complete:
43b56004-298d-449a-b1ed-b255572bf08e | checklist | Add Project Photos |  | Project Photos
14f60ca8-ca49-47ec-a502-c39afc9d924b | checkpoint | Attach Photos and Comments
de1c1767-4a58-4d3d-adfd-70a644ad14b2 | checklist | Backflow Test Report |  | Backflow Test Report
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b22ecfd6-a0ba-4589-a319-e12e91c45e92 | checkpoint | Description of property or vehicle
11a5b259-83ce-5f4b-8478-f1e255fdfe47 | note | The description must identify all land or vehicles covered in the application
e0144cea-413b-58bb-8b28-195a138e4928 | textbox | Street address (number, street, suburb and postcode)
ca055a16-27a3-59a4-a776-6771b12250f1 | textbox | Water authority property service / installation number
855cb638-80a6-5055-8817-1d8c2ad6dc32 | textbox | Water meter number
86acef16-b089-43e5-806a-74595d773dc4 | checkpoint | Type of test
123f7f21-1b56-5c05-bf75-cea06aa6477d | tickbox | Commissioning of new device
8c491cb5-81f9-5c4b-9c6e-812ee4eb10b9 | tickbox | Replacement
36b160f7-b34f-5791-a908-d1bc4ddead18 | tickbox | Annual
2c0025d3-716c-50f2-ae99-36047f6397f3 | tickbox | Repairs
bb1fe372-484f-56de-979b-daa0cf613e27 | tickbox | Decommission
fc9ec831-9dab-400a-a916-7e818a344456 | checkpoint | Backflow prevention device location
163767ab-00e9-58c9-bb73-1ef877c7fb0c | textbox | Location of device (eg: Northwest side of building @ FHR external)
719561a0-3d07-5a94-acd6-c200cf4fc077 | textbox | Mains pressure (kPa)
72a90940-2996-527c-bdd6-df55646eb53d | textbox | Time and date of test
8c037c4d-c8ea-45ce-ba22-8262a573936a | checkpoint | Main device
e2a32d15-c5f0-574c-97f9-90add341642b | tickbox | RPZD (E)
5ffe70cd-de5a-575b-b22d-e5e9b6e5c7a5 | tickbox | DCV (F)
0a6af0be-d95c-5dd4-a607-ad64ec045b21 | tickbox | SCVT (I)
d5ac9660-3d42-5dc1-ae04-33ee1c9d4c2f | tickbox | Containment
e8d83251-1673-571b-880f-65fcf246a768 | tickbox | Zone
9bebe63e-8c9a-589e-8437-5418f5946408 | tickbox | Individual
3e2c4864-d4de-5e7c-9692-5e62f6e3f402 | textbox | Make
30449c6c-a356-56ed-ad2e-201d4c22c7ba | textbox | Size mm
669c7277-76d8-5b70-8f96-1e0b375d1f45 | textbox | Model
1bdc63c0-ece7-5c2d-ade8-68b7ab953e8e | textbox | Serial number
18a95ec5-a19c-5c1a-945b-88e88195713b | button | Cleaned strainer | Yes,No,N/A
15b09e4e-30f1-56c9-9d9b-42c1874749b0 | button | Upstream IV | Leaked,Tight
09e85b20-7c70-5188-ab25-97b2bfcac56e | button | Downstream IV | Leaked,Tight
da88734a-b25a-54e4-a38a-4445e7fae048 | textbox | Check valve #1 (kPa)
e3ca059a-9ce9-552f-83c1-34f415c5e58a | textbox | Check valve #2 (kPa)
68873d1f-510d-533b-bee5-9f83535fd5fb | textbox | Relief valve opened
87cb07ab-2145-4660-81ae-6d245f6175eb | checkpoint | Device installation notes
4447f5ae-d434-565b-99f2-a2a0c90b3a80 | button | Isolating padlocks installed | Yes,No
e96eb6b1-dbb0-5f3b-b590-0243bd85f181 | button | Installation complies with AS/NZS 3500.1 | Yes,No
202d53c6-764c-4aeb-862a-209c7ccf9918 | checkpoint | Test kit
89453d68-2e4c-5402-9ade-8bd77614b9b0 | textbox | Test kit serial number
282d9378-2cb6-5ed7-adbb-856d1e9c1f30 | date | Date last calibrated
e0c5b6e8-4f1b-41ca-b4e3-5c6870759812 | checkpoint | Authorised testers details
1b87ea16-fa33-5da4-a4d0-402461075cd3 | textbox | Testers name
b00772f9-6991-53c3-a20c-3f367b25bb26 | textbox | Registration licence number
9e02ba64-bd80-5012-a65a-1ca919c6e747 | textbox | Phone number
f9b515eb-824b-4e5f-b546-3c415c1d5adf | checkpoint-no-value | Licence person
ec1dbb23-0023-5822-b0bf-4bc1c2b4721e | note | Full company name - Geschke plumbing
e424e1a1-5ede-56a5-a56a-41a09b4c433f | note | Licensed tester name – David Geschke
48327e51-128e-58ff-9460-125ede61a775 | note | Licence number -50043
55f27e7e-6d7d-4b5e-bdc3-6159fcac3b25 | checkpoint | I hereby state that the information provided in this form is a true and accurate record. I have tested the above device/s in accordance with AS/NZS 2845.3:2020
397a9acf-29f5-530d-bcea-d1b0f90ac189 | note | Note: Failed devices must be repaired and retested within 20 business days as per the Water (Estimation, Supply and Sewerage) Regulation 2014.
02379bc7-961c-5b99-8d0f-be9e5577e43b | textbox | Signature licenced plumber
2f3e89cc-75f1-517b-86da-d7e23cea61f2 | date | Date
cc60320f-7600-5dcf-a06d-b17818640381 | textbox | Signature tester
bf1c10d4-87ad-5a3c-af9b-a30dcd7ee19f | date | Date
21df16d5-aad6-4b38-a8eb-edce1eadacbe | checklist | GPL QA 6 - Quality Control Pressure Test Report (CNRM) |  | QA 6 - Pressure Test #
78e0ef80-990b-4d82-a652-9434e202f1e2 | checkpoint | Quality Control Pressure Test Report:
5457a26c-74a5-5dea-b7a5-eeb2b76f8762 | textbox | Drawing No.:
20f57706-c751-562d-b9b6-24c7a0298f72 | textbox | Rev.:
4ab79727-dd14-5e69-b02f-f33d60bbd260 | button | Test: | Air, Water
3e63fac3-af6c-5f6d-b53d-31d62823d92b | textbox | Section
e7ffecd7-68cb-5c5c-a559-f5ce4117952c | textbox | From
0d31ad42-7b82-50a6-9ed7-8cb68e67e4b4 | textbox | To
ad162884-1fae-575e-8eee-685177f72716 | note | Specified System Working (500 kPa)
1bb69bcf-b27c-4b35-b732-c464fdde1ced | checkpoint | Specified System Test:
de86c30c-93cb-53db-97dd-48c3a1195429 | textbox | Pressure (1500 kPa)
adbbd507-b16b-5e84-b3b4-d0b7afe02291 | textbox | Duration (2 HRS)
91064945-da38-46a8-aea2-ab682367b46e | checkpoint | 1st Reading
f7130a13-b7d5-5136-9b73-3300ba04e54d | textbox | Time
e73db96c-bb10-58d4-83b4-a356a8578cba | textbox | KPA
d29a5d09-8ae0-53c4-85e8-a92a65b664bf | textbox | Ambient Temp
f0ed9edf-7f3a-4324-8326-cfc860d1e47c | checkpoint | 2nd Reading
d05ddd78-dccd-59d7-9688-6b836b501624 | textbox | Time
d7124d87-c3e2-5135-a813-383a21d0c1b9 | textbox | KPA
9eab2f5b-db2b-5ddd-af3a-b17f238c1ca6 | textbox | Ambient Temp
4b37b819-9a07-495b-9484-96e17ee931ba | checkpoint | Test Result - Passed?
1cfea7cf-4c01-5be8-99c0-e856561579fc | textbox | Repeat
209a32a6-ef5c-5c4c-9118-e21f9c7ff436 | note | Company: Geschke Group
4b313b3d-3991-5c3c-934e-dfeb6e8e2da6 | note | Phone: 03 9798 1619
995427f4-ad1d-5e3d-90b5-d477a889d413 | note | Address: 45 Pacific Drive, Keysborough
cade4dba-420f-5d70-9d73-a46860f3f98b | note | Project: Centre for National Resilience Project - Melbourne
0adb1b61-2a5a-5798-a112-6a22156d0440 | note | Principal: Multiplex Constructions
4453bc78-b70c-460e-9eea-ea472cb785dd | checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
d379a38d-2c63-5b18-839c-6ed11361b913 | button | Geschke Group Signature Sign-Off added below | Yes, No
93a4bafa-bfc7-54c8-aee7-7ac24e470ede | button | Principal Contractor Representative Sign-Off added below | Yes, No
a4570e50-7c92-4a8d-affe-159c17a57d38 | checklist | GPL QA 8 - Below Ground Pipework Checklist - Sewer (CNRM) |  | QA 8 - BGS00#
83056da8-4895-4e22-8dca-36bc77baa212 | checkpoint | Principal Contractor Permits Issued
fa8e25b5-23e3-4ce3-9ca0-1ca17feac9bd | checkpoint | Set out pits trench depths and runs.
5ce9e5ef-3018-519b-8ce2-fcd9ce485b89 | textbox | Drawing & Revision # (or Attach photo below)
2ab7e276-cb2b-58c9-8633-439782cb5322 | textbox | Survey setout completed by:
9823e82d-0f32-52fc-acac-6c783a90491b | textbox | Manhole Coordinates - enter Eastings & Northings
1b3ee1dc-4dd7-5bba-a322-f769f2998319 | textbox | Starting IL established - enter IL
8a536be7-a806-5c5f-bc87-7459d6fbffaf | button | Survey confirmed drain started at correct IL | Yes, No
3243e225-0da4-552f-baff-ecfee9e57945 | button | Drawings attached | Yes, No
e281f66a-b791-4238-b5c3-d0209177f743 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
363e8121-0734-50e1-83ce-d8777c7a074a | note | Spec#: AS3500
5f6bb220-22e3-569a-bf35-81995efab50f | textbox | Materials used:
45e018ea-6103-5f17-ab1c-9a0c0c746d22 | button | Approved by Principal | Yes, No
6506582a-31e9-4296-bdd5-cbfa7fe89fe7 | checkpoint | Bedding material, placement and compaction meets specification.
b5709c49-3f7b-5657-8e9f-88d68601111e | note | Spec#: AS3500
40757fa6-8f96-5006-9516-72f23196775b | note | 7mm Q-Minus Bedding
97ca3a62-3e11-4a85-91ed-57bf7443c902 | checkpoint | Laying and jointing of pipes - RL and fall
01bfb074-0fda-59ca-8dda-fe1a69f01b06 | button | PVC pipe with Rubber push fit jointing | Yes, No
e3199da9-ec5e-5053-8cf7-e09be2dfe6cc | button | Fall achieved (1:200 required) | Yes, No
6fd8d5b9-fc33-458e-93b8-a8916ea6babb | checkpoint | Connections to pits and existing services as per spec and Australian Standards
2111ebad-683c-449a-a72c-0abc23385b7f | checkpoint | Hydrostatic tests are carried out as required.
d2d20111-eb88-5035-aa55-3e31777aed31 | button | Air or Water? | Water, Air
b1b2473e-98ec-5001-a6bd-765e8e7b52e3 | note | Inspected and recorded by Independent Certifier or PIC
5b29f5a6-2e83-46e0-8d8a-9054774c798b | checkpoint | Mirror tests completed
bb6d3697-6600-545c-bc36-291aff85b706 | textbox | Independent testing company:
96af207d-dc9d-594c-ba64-07b34bc33909 | button | Inspection report attached | Yes, No
ad71b4b7-86bb-40ab-b027-af92d2b6ed96 | checkpoint | Placement and compaction of backfill and material meets spec - attach applicable reports below
849c74c8-76dc-5b4f-b167-1a99a94a31fb | tickbox | Civil specification 13.4: Trench Backfill Service trenches shall be backfilled with General Fill (Type B Material) compacted to 98% SDDR within 500mm below the Subgrade Level and to 95% SDDR below this depth in pavement areas. The moisture content of the compacted material shall be within 0% and +3% of SOMC.
93ed48a7-6f77-5deb-9a8d-93c24b91b514 | tickbox | 5% Stabilised Sand
da7f6cf3-cb3b-5119-9cd0-0536678fab91 | textbox | Compaction testing completed by:
980af10c-f260-563d-aac0-dfc2fe9407bc | button | Compaction report attached | Yes, No
8aa56ce5-84dd-4578-8860-5459825be202 | checkpoint | Temporary cover provided to open drain.
f8b5e73e-409b-4a2a-9caf-38fe15b8c8af | checkpoint | PVC/ Plastic caps to open ends
916755b6-ea87-4f67-bfb1-112b78edd052 | checkpoint | As built information updated onto drawings
990806e4-ae9e-5233-96b2-2e9c2633005f | button | Drain installed as per nominated drawing | Yes, No
673c6e7f-8e1b-5490-b072-4b1227a7f991 | button | Invert levels checked by independent surveyor | Yes, No
678d7056-962b-5a35-b2ad-8e56b15529c2 | note | As Built drawings to be updated as required
26098e30-a04f-44e0-bbd3-8ab925166209 | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
76b3a383-f92c-55e8-a40c-f1335893435d | note | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
6a089dd6-0f55-5f54-ad0c-6117abe76565 | note | Company: Geschke Group
11b61d9f-049d-5e4a-bae9-7e06192e1725 | note | Phone: 03 9798 1619
83857c1d-4239-599b-bf0c-aeb14f5eeeba | note | Address: 45 Pacific Drive, Keysborough
9ba31341-a0fc-5fa2-bf5b-a5e00399cad0 | note | Project: Centre for National Resilience Project - Melbourne
29a3ed69-6c80-5521-b82e-2f7004c87385 | note | Principal: Multiplex Constructions
abff1d3c-f662-4cac-89a7-b7fd8b086309 | checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
25892185-9580-5dca-a58b-1108b0e5cb97 | button | Geschke Group Signature Sign-Off added below | Yes, No
2e5232e3-e465-5b2b-8fec-041a9e514309 | button | Principal Contractor Representative Sign-Off added below | Yes, No
41221813-f4c4-4357-9b5d-d742c974332d | checklist | GPL QA 8 Below Ground Pipework Checklist - Water, Recycled Water and Fire (CNRM) |  | QA 8 - W/RW/F-00#
748bd702-a1cb-4fb9-8107-dfc3de9a7ff0 | checkpoint | Principal Contractor Permits Issued
a7e180c9-ac3f-4703-a8d5-6b8dd341bc3a | checkpoint | Set out of trench depths and runs
b7bbd840-45d0-5946-82a4-6ef20bf4d7c0 | textbox | Drawing & Revision # (or Attach photo below)
9ac315c3-6125-5afd-8125-e7caa4565c39 | textbox | Survey setout completed by
14e19442-6a73-5f4d-8e50-554f38aa6af3 | button | Drawings attached | Yes, No
f33b66d0-c5af-415e-951a-b23999342b46 | checkpoint | Pipes and fittings comply with relevant Authority and Specification
c96b9c39-8d5a-534e-923a-d68d3b860cd3 | note | Spec#: AS3500
c40df2ec-6728-5ffe-b2ff-538695c26d3f | textbox | Materials used
35f7909c-06f1-570e-aa41-c4140adfb167 | button | Approved by Principal | Yes, No
3e195507-f2b7-4016-9a31-e03fc035e5b5 | checkpoint | Bedding placement and compaction and material meets specification
db31b5b2-8bac-58b0-a989-c4ab0442887e | note | Spec#: AS3500
60fc3c55-6b04-5e3a-bba4-09b50716eb9c | note | Packing sand encased pipe
0b06e226-a6d3-46bf-8fe0-737b521b2063 | checkpoint | Jointing of pipes
f850bfb6-27f9-50e5-b966-76ab01b04878 | note | If either of below are selected, please reference the ITP/Attach below - As applicable
f43721d6-4391-552f-a92f-704eeb3a7e45 | tickbox | Electrofusion GPL QA 16 form
52ab577b-a483-5a04-90bb-5b7b86c93be8 | tickbox | Butt Welds GPL QA 25 form
31077426-5f17-4b97-9b03-e5afdf168838 | checkpoint | Connections to pits and existing services as per spec and Australian Standards
697ba9ee-5d0f-421c-8d63-eac50c47c68e | checkpoint | Testing of pipes are carried out as required
0ff122fb-07df-50be-8b98-bffd5102f37a | note | If below is selected, please reference the ITP/Attach below - As applicable
c4f23f76-7697-50b7-b4fb-7d696e1c67d2 | tickbox | Water system hydrostatic test
62dc1911-4be6-58dc-a7b6-0ae8d7097fe7 | tickbox | Fire system test completed by Independent tester
2834b714-2237-4faa-aedd-20f3fc7479f5 | checkpoint | Additional service within trench
31f1f020-8492-5d5a-92f7-c3c2120f3cac | button | Are there other services to be installed in this trench? | Yes, No
820a0342-c65c-5bb5-b202-87cff63f0643 | button | If Yes have these services been installed prior to backfill of trench? | Yes, No
1667f51a-0f61-4904-ba94-7a3a0d75cf08 | checkpoint | Placement and compaction of backfill and material meets spec - attach applicable reports below
33a1498b-680a-5dc2-bdd5-42997cacedcb | tickbox | Civil specification 13.4: Trench Backfill Service trenches shall be backfilled with General Fill (Type B Material) compacted to 98% SDDR within 500mm below the Subgrade Level and to 95% SDDR below this depth in pavement areas. The moisture content of the compacted material shall be within 0% and +3% of SOMC.
43a02efd-b687-5194-a5c0-88833e674fb9 | tickbox | 5% Stabilised Sand
94d6918d-b0ba-5378-90c3-bbcd0b8ceec5 | note | Detectable marker tape
9181d038-0292-41c6-bafb-8f1e243f9c9e | checkpoint | Temporary cover provided to open drain
bfd114ab-6053-40db-a838-e896572d6d19 | checkpoint | PVC/ Plastic caps to open ends
7407b1aa-757b-4a32-a68d-02daa4c26361 | checkpoint | As built information updated onto drawings
d483ca9c-3ce6-5b67-b717-4f97c668b8b6 | note | Ongoing
feca1634-8a86-5564-a62e-a8d2b55545ae | note | To be provided
1d7638ac-2c4e-41df-b72d-ba46f8bed623 | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
6ef02d5e-1794-59a0-a54b-ba70e45e92c0 | note | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
4e65cdbf-ff8a-5551-b4a2-84883dcaaa96 | note | Company: Geschke Group
4f0737ff-b6a4-5ec2-bb0b-ddbb4865c7d9 | note | Phone: 03 9798 1619
8d58c04b-c5f1-5e11-95c9-495e34026eac | note | Address: 45 Pacific Drive, Keysborough
4b57255c-e4a5-517c-94b0-524108d04dab | note | Project: Centre for National Resilience Project - Melbourne
c2b75d82-ed15-54f2-bf07-a8233484d1a6 | note | Principal: Multiplex Constructions
1f1e1725-53ea-4463-b477-d31e86758c2c | checkpoint | Sign-Offs completed - Click to Attach Signature(s) below
f9f0d780-9930-5d01-bfc0-eee74b7607e8 | button | Geschke Group Supervisor Sign-Off added below | Yes, No
456dff2e-1316-54e6-9ead-3b7980ea9178 | button | Principal Contractor Representative Sign-Off added below | Yes, No
60008bc8-f794-4944-a35f-33b65d13423f | checklist | GPL QA 16 - PE Electrofusion Welding - Field Operational Sheet (CNRM) |  | QA 16 - EF00#
9c8b2128-7815-4a30-a41b-20caabc6f951 | checkpoint | Operator Details
50105370-2477-5bc2-8092-44210283f53e | textbox | Name
5ad0365e-21c8-5eb5-b4fd-c10259390b19 | textbox | ID No.
a5b673f9-ed55-59a5-a03b-af76ae645e2d | textbox | Company
b3545881-e263-51ab-aef9-a208648e100e | textbox | Address
6d27826d-8102-4444-860b-0cbeb926796b | checkpoint | Welding Machine Details
f9cbc115-9843-5b73-b8e7-0dd4d370102b | textbox | Manufacturer
37b47cb6-e84e-5787-8e7c-5e3a6723b03e | textbox | Type/Model
e9920eed-5251-5c45-bc8c-affc7d947916 | textbox | Serial Number
1d28e439-dc6d-5cc7-9996-48dded6a2504 | textbox | Year Built
480d9011-6d45-40d4-9125-1154772a69df | checkpoint | Actual Pipe Size
ef3b8ffc-2702-57f2-864e-f1ab1824e330 | textbox | Type
ef762878-9112-558a-a84b-e71f5801c5ad | textbox | Brand
01444dfa-e8d5-55a2-bade-8f9456e3ea53 | textbox | En
d294d19f-3df8-51c5-a531-01d0c9af58c9 | textbox | OD
479708cc-7cce-5e23-9b63-7736a334c0bf | textbox | Ovality %
a6c741dd-fd2f-4951-b782-7794bb4ba7a6 | checkpoint | Fitting Data
b47e02b6-e1dd-5894-b6f5-74082c0faf9d | textbox | Brand
0b57488f-5d43-5a5f-9a59-49ffd1e5c356 | textbox | Type (Coupling, Tee, Reducer etc.)
7fe86a5a-94ee-4199-b0ad-18d7d121898c | checkpoint | Unit Setting
4def84e5-5df9-50f6-83bc-7d9406596737 | textbox | Manual
fbb60382-82c2-5026-a681-8657a2c26c8d | textbox | Automatic
92ae44a2-3456-4af5-a97c-84dcbe6c77ab | checkpoint | Preparation
3b758a89-1941-5012-9f8a-45918fab20d6 | textbox | Cleaned and Peeled
9fb8669e-df01-5071-b962-427662eac6fb | textbox | Pipe/Fitting Clamped
94f5282b-eb6b-4f7d-80c9-ea3f817f2fb3 | checkpoint | Welding Times
3bfa3def-8c06-5076-9bbd-278323023816 | textbox | Joining Seconds
02f23fab-8e20-55ec-b31a-c3b5734d8f3b | textbox | Cooling Minutes
c1a5de0e-d38f-4eae-97a6-e7d77fcdfc77 | checkpoint | Conditions
3576b119-0cac-53d8-b5f8-9a652ff29fd6 | textbox | Ambient Temp
fff3df04-aa4f-5c09-8491-6f78839ba66e | textbox | Weather
a91e78cc-2268-558f-a7d6-fa59882d9786 | textbox | Preventive Measures
91ed3b4b-c310-48b8-8458-1f32f1c1df3e | checkpoint | Power
f3e8d356-af33-59c8-a3e7-a7b8c0c4164e | textbox | Mains
0e06789a-3863-5272-8c71-9b0451bdbc11 | textbox | Gen Set
41891bf3-0178-4166-b515-f7a2eb718857 | checkpoint | Operator Sign Off
1c6f5d28-c6c6-4db6-83cc-2717b13d2e0e | checklist | GPL QA 25 - Butt Welding Checklist (CNRM) |  | QA 25 - BW00#
e89b88d5-5c65-4875-bd85-56225966b5d9 | checkpoint | Operator Details - Pass once entered
868473d9-ebb9-5ea0-a61e-a7924be2da2d | note | Supervisor sign off at completion of ITP after weld #16
3b0e9d02-2ff1-52af-a4ad-3bb2fef7ca1e | textbox | Name
a7941ee0-ec1f-59af-b224-94b99a84a4c9 | textbox | Certification Number
f640c0aa-434d-4955-80cc-9ada5268131b | checkpoint | Welding Machine Details
69bf3f82-616f-50cd-9f14-2c082fc701fe | textbox | Manufacturer
81f6cdf8-4eb0-5373-8d03-b81c30a61d9c | textbox | Type/Model
087c35fd-2718-5058-ba3e-0784696f24b2 | textbox | Serial Number
91e91cfc-ea84-5568-80a5-4d7f49567842 | textbox | Year Built
d8144425-965b-470a-9760-8947ce894673 | checkpoint | Pipe / Material Details - Pass once entered
b94a4d7d-c381-5f9b-a87e-a61b476db51a | textbox | Dn (OD)
cf05643c-fbab-5c18-af75-057049224bc1 | textbox | SDR
1d16ca26-2a1a-5b4f-bf5d-b01989b51cbc | textbox | En
eec7d8c3-4cf9-51a1-9f37-489b1d2cf9e3 | textbox | Type
63fb66da-7d09-5b65-ab68-bffd9f1d60a2 | textbox | Parameter
23800d42-2e87-5f89-a180-02b251e57bdb | textbox | SLP
c0ccf38f-33bc-5942-a3c4-01c1ab4c3766 | textbox | SHP
1817321c-4c52-4e77-9b38-2e13bcb14a56 | checkpoint | Weld #1
54bab1c5-8a06-5e43-b0e0-36756c558bd0 | textbox | Time
a50d10d7-fb51-5c73-9868-fa3e8a475c45 | textbox | Ambient C
b23128a5-6545-5e62-b0b3-24a8e58587d8 | textbox | Heater Plate °C
9ca04d5d-c426-5ad0-9cf2-00b75218221b | textbox | Drag Pressure
452a2c82-067c-5ee8-8394-773ad10a2d71 | textbox | Bead Up: P1 (Kpa/Bar)
130d7c3e-b148-542d-91cc-47d25da214ad | textbox | Bead Up: t1 (Evidence)
d2d937d8-3dd2-5b33-b065-f9bbb095cb79 | textbox | Heat Soak: P2 (Kpa/Bar)
eb7c04c0-4899-50f4-9eee-fc77fc948089 | textbox | Heat Soak: t2 (Seconds)
915c4529-be51-5647-b2db-195d8ac48ef6 | textbox | Change Over: t3 (Seconds)
7fa3e9f9-b797-5756-8ee1-a168c28d11d7 | textbox | Pressure Up: t4* (Seconds)
662502d5-a221-5fe9-b4a8-469a873e8153 | note | *t4 not applicable for SHP situations
ef64eb3d-cf71-54a5-ac7a-ee729b690d6c | textbox | Weld and Cool: P3 (Kpa/Bar)
f24248bf-c038-5527-946c-51214b7dbabd | textbox | Weld and Cool: t5 (h:m)
238dee11-8b84-5eeb-b2b2-d35058b7846b | textbox | Rough Handling: t6 (h:m)
6abce699-fd53-5810-a6b0-73d167665d9e | textbox | Bead Size: Min
de85a873-9cc8-5fea-a29b-4c9790b60f32 | textbox | Bead Size: Max
5c948bfd-8ca0-5af4-a84a-c293e70b8de4 | textbox | Comments
1d50ca1c-620d-4304-82e6-ffde745a9c41 | checkpoint | Weld #2
c5a2a306-5b77-5f9b-8433-f073c9a3cbc6 | textbox | Time
b294b6a8-6bc9-58b2-87ad-73e7c36b15b3 | textbox | Ambient °C
1833b6b6-d161-569e-a7a8-6d55895f45e1 | textbox | Heater Plate °C
e910b6b4-7dba-5033-bdcf-ec37e2e73668 | textbox | Drag Pressure
24b7548f-fc30-5833-bda6-a8f9a0752abb | textbox | Bead Up: P1 (Kpa/Bar)
70f521e9-311a-5919-97f9-01e819064162 | textbox | Bead Up: t1 (Evidence)
a29239c1-054c-5152-b9b1-3dc234355008 | textbox | Heat Soak: P2 (Kpa/Bar)
0455ccfc-8f06-51d8-a256-96f58ed37328 | textbox | Heat Soak: t2 (Seconds)
a858681a-3523-585f-9855-474d4288d2ae | textbox | Change Over: t3 (Seconds)
23bbcba7-d2fc-5a14-9b7e-87fab85e1d68 | textbox | Pressure Up: t4* (Seconds)
fc501e68-daf9-5a22-b585-94a48217e58f | note | *t4 not applicable for SHP situations
5ba3d9c4-3673-5ecd-bf44-c87a19112a34 | textbox | Weld and Cool: P3 (Kpa/Bar)
ec726010-7321-5413-9bb7-f71d507fe631 | textbox | Weld and Cool: t5 (h:m)
22e3bea8-fbbf-5ecd-bda6-9e539859cbb4 | textbox | Rough Handling: t6 (h:m)
6ec4df14-fb1d-5095-8e8d-aef1b37fffbe | textbox | Bead Size: Min
3b7e7ce6-ffe1-5caa-bb9f-eab955f5a3d0 | textbox | Bead Size: Max
8199315e-15ed-54bc-ba6c-6990030a7505 | textbox | Comments
76d438a5-0a69-482b-81ef-8ccd2c9cff2a | checkpoint | Weld #3
de496c63-0696-5aed-a539-4a8728e164c5 | textbox | Time
c5606f5b-66b9-551a-a69b-b9ddc4fe9094 | textbox | Ambient °C
9189251a-e92f-5085-979c-d344c71eda21 | textbox | Heater Plate °C
4a78511c-963e-5675-bb24-5b8be0c62b09 | textbox | Drag Pressure
80ea9bf2-a22c-58da-a152-2fb793e046d6 | textbox | Bead Up: P1 (Kpa/Bar)
3d48857d-36ad-591c-a16c-f20b20c2aee8 | textbox | Bead Up: t1 (Evidence)
ff0ad25a-1fb3-5113-b9f6-bae26b032f08 | textbox | Heat Soak: P2 (Kpa/Bar)
1523110e-8dd0-56b7-af1e-a040b21038fb | textbox | Heat Soak: t2 (Seconds)
428d6b6d-0f58-5804-8f8f-7e4f4007c0d8 | textbox | Change Over: t3 (Seconds)
4afac44b-ee8f-5f9c-9dcf-b80a0cf20ab1 | textbox | Pressure Up: t4* (Seconds)
9aaf33d9-c47b-5fce-9863-0c56385259c6 | note | *t4 not applicable for SHP situations
665bd811-f3a6-5877-8c7f-ebf601f6c061 | textbox | Weld and Cool: P3 (Kpa/Bar)
148c4f01-ce62-5fc2-a6f9-073147bd3a03 | textbox | Weld and Cool: t5 (h:m)
5ecc47d8-3c76-533f-902f-a54e038e4e6c | textbox | Rough Handling: t6 (h:m)
01e071b0-488f-5d52-a2d8-a871de0393b2 | textbox | Bead Size: Min
02cbf74a-69b6-58fe-8573-a54c52dd14b8 | textbox | Bead Size: Max
6aad925d-12e6-5732-9345-5b86197ec600 | textbox | Comments
e2edb509-42c6-4270-ac2e-b6e3abf89950 | checkpoint | Weld #4
8b3e265e-5b9a-51af-8f23-2154ba81b7ab | textbox | Time
abd3af3f-4ac1-504b-a01a-6fccfe2d242c | textbox | Ambient °C
2182bb64-186a-5b3e-85f2-88ea446cd710 | textbox | Heater Plate °C
c0e30180-805f-5249-8d98-21fdb2850ab8 | textbox | Drag Pressure
2b1e67b2-900d-561b-9155-1cb6588e6937 | textbox | Bead Up: P1 (Kpa/Bar)
35d2dc3c-82cb-5512-a8ff-7a2155aff061 | textbox | Bead Up: t1 (Evidence)
3ed00d3b-a797-529d-aea1-ca5fb0581385 | textbox | Heat Soak: P2 (Kpa/Bar)
e917094a-77f3-5d20-80d1-12bf4d2247d4 | textbox | Heat Soak: t2 (Seconds)
41648483-63b2-5301-bd4a-5a7c626127fe | textbox | Change Over: t3 (Seconds)
d7fb5ac5-f6b6-5bb5-82bc-dbbaf244d68d | textbox | Pressure Up: t4* (Seconds)
6b0cc26e-786b-565d-874e-407cc367f7c3 | note | *t4 not applicable for SHP situations
3f638d8c-6e64-52d0-bf08-d7b7363e47e3 | textbox | Weld and Cool: P3 (Kpa/Bar)
d0ed79c0-b5f7-5cb9-87e6-e54055213c78 | textbox | Weld and Cool: t5 (h:m)
82fc960c-e277-5758-824b-a6f9170032a2 | textbox | Rough Handling: t6 (h:m)
4dadac95-45f8-5c17-ae42-27c6a8935370 | textbox | Bead Size: Min
e46b799c-d4e0-59ac-ac3f-6bdb93ff5adc | textbox | Bead Size: Max
0392e17e-bfb0-533a-9019-ed1b5d456abb | textbox | Comments
364d0471-376e-4387-a487-b25d694a0e6b | checkpoint | Weld #5
c9ba90f7-26dd-53be-8423-c80ec2c22910 | textbox | Time
c201e93f-88c2-5e1e-94d4-610d8a715170 | textbox | Ambient °C
58eb06d8-fd23-5bea-b595-39a80d449893 | textbox | Heater Plate °C
e92e6823-97d0-5177-abe7-8fe2834cab41 | textbox | Drag Pressure
1a99600e-feef-5120-a97f-625556c41a5c | textbox | Bead Up: P1 (Kpa/Bar)
dea228a2-d204-5a7c-8197-5c36ce69fa5d | textbox | Bead Up: t1 (Evidence)
9cf0f39a-589c-5060-9a8b-355ebbcf6def | textbox | Heat Soak: P2 (Kpa/Bar)
9d46a2dc-5cfa-529e-b1fe-8d77a6dd7797 | textbox | Heat Soak: t2 (Seconds)
f6c9a319-f907-5cf2-994a-71ec483d5d0d | textbox | Change Over: t3 (Seconds)
65c3ddf1-0781-5210-9651-0aa3930edb27 | textbox | Pressure Up: t4* (Seconds)
4cb30fd3-878d-5223-801b-35a0e622e698 | note | *t4 not applicable for SHP situations
072020bc-11b2-5fa1-b9ea-e5ccc8b15114 | textbox | Weld and Cool: P3 (Kpa/Bar)
81731702-cf3f-588c-ac49-3a9fcbf764f4 | textbox | Weld and Cool: t5 (h:m)
917c9547-56ae-5f38-a318-f32e6a2a7905 | textbox | Rough Handling: t6 (h:m)
ed0227e2-43e7-5c30-a8b2-bb3f6f3806cf | textbox | Bead Size: Min
0e5a04b3-9d25-5d11-bdaf-39e040a969ff | textbox | Bead Size: Max
1075ddb2-aca6-5655-ac26-d135ea75481f | textbox | Comments
8d7fa738-6f07-4ad9-8ac3-702e4635cd92 | checkpoint | Weld #6
e80182e4-a45c-56d9-97ff-49e63aac9bdd | textbox | Time
ef8526df-cd1d-5335-974a-6a763be1a8ce | textbox | Ambient °C
85ae5909-a8d9-553b-89c4-46421b97b954 | textbox | Heater Plate °C
d07b1478-6ecd-5e19-9b35-eae47e141493 | textbox | Drag Pressure
51b49af1-d3ac-57de-b8be-aeed19c72914 | textbox | Bead Up: P1 (Kpa/Bar)
6240c341-e117-5091-b617-3a847e559f64 | textbox | Bead Up: t1 (Evidence)
f86eceed-1582-5685-945a-1bf9d5bf2621 | textbox | Heat Soak: P2 (Kpa/Bar)
7e098136-c765-518d-aa9b-846191f0dc57 | textbox | Heat Soak: t2 (Seconds)
c1335bbd-a56d-5337-bae6-330f1deb2502 | textbox | Change Over: t3 (Seconds)
9f1f4656-4fea-5f0d-8262-3b4ed41d8496 | textbox | Pressure Up: t4* (Seconds)
fbb23b44-059a-52ed-8648-16fc10b5a790 | note | *t4 not applicable for SHP situations
ba879fd8-0410-52b3-af37-f2332e037aa1 | textbox | Weld and Cool: P3 (Kpa/Bar)
40938317-4f79-51e1-ada9-8fcacaa2a79f | textbox | Weld and Cool: t5 (h:m)
b8321ee0-477b-587b-8fbe-98ee3389960a | textbox | Rough Handling: t6 (h:m)
b49d0ffb-0e6a-5f7f-bbf9-be9dedea8abf | textbox | Bead Size: Min
facfc5d9-b3c2-5d68-8544-dfc32914613d | textbox | Bead Size: Max
188ff98d-1c33-5ba1-ac3e-1b18c44a1f45 | textbox | Comments
dd282bf2-cb9f-49d7-bd1e-b0372f0f495a | checkpoint | Weld #7
d2f10963-1b75-5f6e-a015-bd4690415daa | textbox | Time
b85589f5-f335-5bd0-b464-7167aa770183 | textbox | Ambient °C
73188c74-63b0-55de-a1c4-835eea7e5712 | textbox | Heater Plate °C
c2dad15a-a9ea-5f5f-833f-618723d98820 | textbox | Drag Pressure
d564e2a1-0178-51ce-a1ae-043b19bc11b4 | textbox | Bead Up: P1 (Kpa/Bar)
d0961db0-a0a9-5402-8165-3afca119f53a | textbox | Bead Up: t1 (Evidence)
464068dc-db98-57ae-9a6a-a1b1a0a4d519 | textbox | Heat Soak: P2 (Kpa/Bar)
57f4c18c-bd6c-5576-a6e1-1cceae0aa1f5 | textbox | Heat Soak: t2 (Seconds)
17ec4e43-5b78-5ba9-aa56-212d19bcd367 | textbox | Change Over: t3 (Seconds)
8ac2fb72-662b-5d77-8418-8f69162f3e06 | textbox | Pressure Up: t4* (Seconds)
83cc5339-dba2-52ef-81fe-fca23a746989 | note | *t4 not applicable for SHP situations
30c8dccb-9715-571f-a53e-33bcfa528f8d | textbox | Weld and Cool: P3 (Kpa/Bar)
b9935523-7154-5480-9441-0e838c0a117b | textbox | Weld and Cool: t5 (h:m)
132e6a5c-b926-50e9-b055-f514cc8abc5a | textbox | Rough Handling: t6 (h:m)
f07be6f7-facd-55ce-8a58-d55a74e8d6c7 | textbox | Bead Size: Min
e8e7df7a-5b23-5fff-b204-7666ab1afff3 | textbox | Bead Size: Max
0294de22-d51a-50c4-85fa-6d393c8a21b0 | textbox | Comments
8a600036-a9cd-448e-bdaf-274f7841e3f9 | checkpoint | Weld #8
3f433a48-ebba-59a1-b5d7-755bf55f367c | textbox | Time
68e591d3-6c57-5552-bec1-17905d731881 | textbox | Ambient °C
109674c4-c7f5-5407-88cf-c5ba6b32fba4 | textbox | Heater Plate °C
9d9cfb6e-0e11-5bb6-a64a-e423dde7c4a4 | textbox | Drag Pressure
35e6d7ca-c8d9-5771-8b9a-3b79a3398e74 | textbox | Bead Up: P1 (Kpa/Bar)
d201c972-e722-5d19-a0ea-0d3f94fc71ed | textbox | Bead Up: t1 (Evidence)
4aaa434a-c10d-5503-b5a1-abe9a2b48e8e | textbox | Heat Soak: P2 (Kpa/Bar)
0b7d5cf9-1c0f-54d9-b610-4132d942bfa8 | textbox | Heat Soak: t2 (Seconds)
346977b5-71f3-5c10-9a75-5f2333240767 | textbox | Change Over: t3 (Seconds)
2117ea28-0985-5647-8353-b7b7c8646cc1 | textbox | Pressure Up: t4* (Seconds)
50240e4d-8d4d-5186-b11f-7fedf22ec51e | note | *t4 not applicable for SHP situations
b603d374-cdd2-5871-9f79-f4aa1212e6bd | textbox | Weld and Cool: P3 (Kpa/Bar)
53d472fd-d3fa-5378-9f06-ba943d501700 | textbox | Weld and Cool: t5 (h:m)
1d10d34d-20ba-5072-b47c-2fce7ce88024 | textbox | Rough Handling: t6 (h:m)
691643f0-b71e-5a6e-80ab-4e2c90cfd9ac | textbox | Bead Size: Min
7babdba1-84e0-59ca-84e4-d08e4f8a51a4 | textbox | Bead Size: Max
13e8b951-64f0-595a-8645-ba23e66fea3e | textbox | Comments
15b63699-5313-48a4-ba5f-5b4aba7cf24c | checkpoint | Weld #9
ecad6d8d-92a5-5976-b5fc-e2b18d435839 | textbox | Time
c52fe831-4c2a-5809-baac-583762342ab6 | textbox | Ambient °C
40112dc1-62e3-5f03-8eca-6195baa595a2 | textbox | Heater Plate °C
698835c0-ac58-53ee-afce-6e8476ebfa5c | textbox | Drag Pressure
acc92f10-4a05-52d4-baab-a8c7431cacd0 | textbox | Bead Up: P1 (Kpa/Bar)
18d55494-0589-56da-ba38-007c6b1bf246 | textbox | Bead Up: t1 (Evidence)
6cab7e9a-d1c0-5d42-b764-2076c33f7649 | textbox | Heat Soak: P2 (Kpa/Bar)
49c2dd7d-290e-5b84-994e-0adf71dbeaf8 | textbox | Heat Soak: t2 (Seconds)
8b54709f-9035-5971-b413-98a0ff11a8ae | textbox | Change Over: t3 (Seconds)
9dbc219a-5c41-5e8a-94ab-50efa01c9562 | textbox | Pressure Up: t4* (Seconds)
f1a4afdd-dbb5-599a-a5f6-89e365a48577 | note | *t4 not applicable for SHP situations
2b179b4d-caa3-5860-933a-e63db7198eef | textbox | Weld and Cool: P3 (Kpa/Bar)
b9fa7a91-8962-5323-a512-26b14efaf99b | textbox | Weld and Cool: t5 (h:m)
3a133447-434f-5095-9582-01a27e711a50 | textbox | Rough Handling: t6 (h:m)
92bd7741-6065-526d-866e-0c8a168ffb2d | textbox | Bead Size: Min
2716e22a-b688-53df-b383-2e79afb89b58 | textbox | Bead Size: Max
af6ec192-c209-510a-9329-e951c61f8cfc | textbox | Comments
9c34965d-5e93-4f50-b60c-58be0e071af5 | checkpoint | Weld #10
7d2e6beb-573d-5830-8ec6-75cc5ab41693 | textbox | Time
7e669385-9f94-55e3-ae5d-c76276d3ee35 | textbox | Ambient °C
0260a136-3e3d-5ca1-bb6d-6d582380758c | textbox | Heater Plate °C
24f83136-35b7-5448-97f4-afae1161e145 | textbox | Drag Pressure
caac20c2-e4a3-56c6-bec6-f995af0313c0 | textbox | Bead Up: P1 (Kpa/Bar)
3b6f85be-2ea5-5498-8deb-835cdac9c02d | textbox | Bead Up: t1 (Evidence)
dfa285c6-8f15-55b4-baa9-195b38eacae3 | textbox | Heat Soak: P2 (Kpa/Bar)
9840c107-5dd5-51c2-a32e-96f7c99cb6d0 | textbox | Heat Soak: t2 (Seconds)
89c59cea-7e0c-5a01-9078-11105c201653 | textbox | Change Over: t3 (Seconds)
2acb3ee1-3cc9-5bea-8c6b-5fc59ce30fcc | textbox | Pressure Up: t4* (Seconds)
41854eb0-9094-597c-8146-7c4a807e244c | note | *t4 not applicable for SHP situations
3e908d59-c159-5c0c-813d-f766dff0554d | textbox | Weld and Cool: P3 (Kpa/Bar)
fabd5ebe-c67e-5a03-af2d-d0f248a1c5f2 | textbox | Weld and Cool: t5 (h:m)
18db4482-7d98-54a4-84a5-6ed3dbc0882b | textbox | Rough Handling: t6 (h:m)
368ce56a-5b5f-58e0-8691-a7244f80b048 | textbox | Bead Size: Min
485164d0-feca-537e-a5c7-8a935738eb49 | textbox | Bead Size: Max
9cbac5ef-1eb3-5888-933c-79182ddb4513 | textbox | Comments
bb7fce9e-d5f1-4e31-bb75-6e38810880a6 | checkpoint | Weld #11
98be8b23-037b-5075-a5fb-739d45cb82c3 | textbox | Time
0259fc11-d5bb-5747-a759-92443163b272 | textbox | Ambient °C
ffd958b0-07d0-5fac-992c-1d58717fd95f | textbox | Heater Plate °C
8697b9c0-1f4d-557b-beda-0520e0ff2066 | textbox | Drag Pressure
c4f77b2c-b66e-529b-9e05-6372c9cf2676 | textbox | Bead Up: P1 (Kpa/Bar)
a6b15e5e-c861-5cc0-a159-c0c115db8b27 | textbox | Bead Up: t1 (Evidence)
4b0f8275-8437-5820-86cf-578342ac4d14 | textbox | Heat Soak: P2 (Kpa/Bar)
ec78a648-510b-5093-a4ad-07172b639713 | textbox | Heat Soak: t2 (Seconds)
a1442ed2-d93e-5043-ab27-7800cda7e508 | textbox | Change Over: t3 (Seconds)
812c2e7c-c8fe-5058-a812-e8892d83ec61 | textbox | Pressure Up: t4* (Seconds)
92f3ee21-8d12-5c95-8f56-ce47e90f4b5e | note | *t4 not applicable for SHP situations
55ef00c3-3022-59e4-9bcf-9c54ac3ab2ae | textbox | Weld and Cool: P3 (Kpa/Bar)
f9a56578-08b5-592f-8e6d-987c0da16005 | textbox | Weld and Cool: t5 (h:m)
e9f24562-e0ae-5f56-a313-515f034cb937 | textbox | Rough Handling: t6 (h:m)
9725cb51-1018-5cc0-8dda-aeebb50e5057 | textbox | Bead Size: Min
2a6ba8e6-e9b6-5fc7-b47c-371d28e04973 | textbox | Bead Size: Max
082e67f0-9fea-526b-bafe-fedaa0c4649a | textbox | Comments
21b48318-39ca-4f60-8881-80bdec2fcbb5 | checkpoint | Weld #12
9d121d5b-5bdd-5340-bf70-ddbcad2d2c24 | textbox | Time
de374d64-315b-55e6-b24c-ac5c9f8fa821 | textbox | Ambient °C
99f25dc9-d365-54cf-8684-6d5eecc02c26 | textbox | Heater Plate °C
0938cf96-be8d-5638-907e-e23c2b058d8c | textbox | Drag Pressure
32161794-5c11-5541-b938-7b593ecd0330 | textbox | Bead Up: P1 (Kpa/Bar)
42d75d17-26d4-5b0c-b9c7-8e2117adfe6a | textbox | Bead Up: t1 (Evidence)
dc637c0b-2d7b-5b48-b335-637550049c08 | textbox | Heat Soak: P2 (Kpa/Bar)
0aab5466-1960-598a-8d98-71bca5bccaf0 | textbox | Heat Soak: t2 (Seconds)
70f6fd42-2111-5df3-8f77-fc9993533789 | textbox | Change Over: t3 (Seconds)
73107b4d-0704-531f-8040-ff9bb1a93806 | textbox | Pressure Up: t4* (Seconds)
49ee7f1b-914f-5acc-9fc1-6b1edc132660 | note | *t4 not applicable for SHP situations
12cb4ecd-2ca6-5a1e-baf3-7184e77b3e8b | textbox | Weld and Cool: P3 (Kpa/Bar)
142d2d43-585c-583e-a562-5304afa5187f | textbox | Weld and Cool: t5 (h:m)
15b73c91-ef07-560f-b691-adf571b5897f | textbox | Rough Handling: t6 (h:m)
0ac1e113-4614-5e5b-9abb-f5186bf5d583 | textbox | Bead Size: Min
32da0528-58c7-5341-be14-80b5059a2c94 | textbox | Bead Size: Max
60b8c7a4-d40f-574b-b5f7-1a9fbc80b3ff | textbox | Comments
71160322-f6ac-4933-ac74-6544b8cd002b | checkpoint | Weld #13
cf5baf48-6403-532e-89af-3c57629c7395 | textbox | Time
41702df4-98da-5a9d-b71e-a394e0d1a54d | textbox | Ambient °C
bd8ab6b5-e6e5-5790-8879-50e7d8e02014 | textbox | Heater Plate °C
8986954b-e0bf-57a7-9bb7-6fd095dbfcdf | textbox | Drag Pressure
b63b4caa-e22f-5514-b08b-94656fb6dcc6 | textbox | Bead Up: P1 (Kpa/Bar)
77437e19-3aee-5d59-9fb9-91be4b091620 | textbox | Bead Up: t1 (Evidence)
aeea5e76-a434-56fd-b99b-195db624d116 | textbox | Heat Soak: P2 (Kpa/Bar)
48091125-0cc6-51c0-8b30-3fc8274d082b | textbox | Heat Soak: t2 (Seconds)
9c4c9b1f-976b-51f2-88f8-2a22cdf80567 | textbox | Change Over: t3 (Seconds)
f1f5a972-52c3-57f0-b9bf-63afb01cd044 | textbox | Pressure Up: t4* (Seconds)
c067f551-88ba-5515-ba87-d9b284d1cb06 | note | *t4 not applicable for SHP situations
05164bb9-1a52-5e59-82ff-2cc27ae73d1d | textbox | Weld and Cool: P3 (Kpa/Bar)
e66f57ce-4d56-5520-9f8c-502c2457a860 | textbox | Weld and Cool: t5 (h:m)
0949038c-da99-5cc3-802d-226d758489f4 | textbox | Rough Handling: t6 (h:m)
15a8dc0f-3159-5e2b-a2a0-8322a91f87ab | textbox | Bead Size: Min
fb2bb1ac-dcc5-5a35-9334-b6eeecc451a2 | textbox | Bead Size: Max
90a02f4c-faa1-513c-8b5b-19e7c3cfcfd4 | textbox | Comments
0205da23-f667-4855-9493-179a8bf074a2 | checkpoint | Weld #14
ecc4803d-d751-534a-ad66-c0ccc7f5363d | textbox | Time
69277095-62b9-52bf-ae07-cddb5c3e61d8 | textbox | Ambient °C
a3b7130c-4837-592b-adb0-87eeea7116db | textbox | Heater Plate °C
bbe95e6c-df8e-5c65-84a3-4c0c42165559 | textbox | Drag Pressure
34b39fee-9048-5f51-8067-389b9a89cc10 | textbox | Bead Up: P1 (Kpa/Bar)
0990696f-ad4a-5ed4-805b-a604638ddf69 | textbox | Bead Up: t1 (Evidence)
a893938b-3615-5fe1-b6be-cccf4ee31d5e | textbox | Heat Soak: P2 (Kpa/Bar)
24686fc2-ad6e-5051-b3b5-1a6b4a786ff2 | textbox | Heat Soak: t2 (Seconds)
f9288232-bc13-50a3-af6b-886a4f364cc2 | textbox | Change Over: t3 (Seconds)
54b9c94a-d6c7-5e8b-ae4d-f01e97c0078b | textbox | Pressure Up: t4* (Seconds)
092681c2-cf36-5a48-8388-ece402bf4b92 | note | *t4 not applicable for SHP situations
800cae14-45bc-55f5-bc27-e7928e551c4a | textbox | Weld and Cool: P3 (Kpa/Bar)
a544f829-4b23-5f06-9366-27d9b1c75d8d | textbox | Weld and Cool: t5 (h:m)
b043eae8-dd36-5474-938d-76aae0d48d6c | textbox | Rough Handling: t6 (h:m)
4c980f4c-3c65-508e-8bb4-c9a352e1dc9f | textbox | Bead Size: Min
2e7ec2c1-8e2f-5b80-91f8-8c885dff930c | textbox | Bead Size: Max
07c5a022-b71b-5425-80d0-f0d0198372c9 | textbox | Comments
2cadb5d6-6f90-459d-8110-56b7857eb776 | checkpoint | Weld #15
965467b9-9d8b-56f2-b5dc-fac0d0747c98 | textbox | Time
c2a21cb5-4fcf-5ba3-993a-c813a10f70e5 | textbox | Ambient °C
d8fb08f1-7d77-5ce9-8de1-60475f4fd482 | textbox | Heater Plate °C
0ab23834-3d35-578d-98ad-7522c65fc8b8 | textbox | Drag Pressure
ea83ef63-a62d-5718-9442-0ac98b1c7755 | textbox | Bead Up: P1 (Kpa/Bar)
2ae4e0e0-5f10-5ace-9203-65c3d41178e1 | textbox | Bead Up: t1 (Evidence)
3efc8b82-2b1b-5f41-acd4-fe4204d24653 | textbox | Heat Soak: P2 (Kpa/Bar)
297b0f8a-2cbc-536f-8b23-6ac3829da28d | textbox | Heat Soak: t2 (Seconds)
500e53d8-2b63-55b8-a6b8-fe6c2a3a1cbf | textbox | Change Over: t3 (Seconds)
dfa0a2fc-cb01-53dd-97fd-e5f0aea87792 | textbox | Pressure Up: t4* (Seconds)
5b93ab54-4e43-55d7-8bdf-2b144d12fe1f | note | *t4 not applicable for SHP situations
2ec739d1-d09f-52a7-8ead-d791a20cf5a3 | textbox | Weld and Cool: P3 (Kpa/Bar)
bd98aa67-a962-518d-8837-cf5248765642 | textbox | Weld and Cool: t5 (h:m)
4676f527-03ff-5613-8a93-0479f42d9e77 | textbox | Rough Handling: t6 (h:m)
b5a17053-820a-5303-adc1-1cd122a3d192 | textbox | Bead Size: Min
2da52217-e5ae-576b-8917-0512d17870e2 | textbox | Bead Size: Max
be2509aa-eb95-52af-89fc-08a8d05e3a01 | textbox | Comments
bbada270-9f00-4cea-b89f-994f279d9cc8 | checkpoint | Weld #16
d7492972-c6c4-5326-95b0-836063a7c316 | textbox | Time
2f3bab96-6d28-579d-8c06-2853906fc178 | textbox | Ambient °C
77b6e362-2de5-5b0e-9066-10f1bddf9fa1 | textbox | Heater Plate °C
a638c890-ceaf-5338-b4b1-23283047d436 | textbox | Drag Pressure
27b66de1-6db8-52d5-ba40-5b9ae429bd4a | textbox | Bead Up: P1 (Kpa/Bar)
a436faad-119b-56fe-85f4-73caa04a951a | textbox | Bead Up: t1 (Evidence)
4e0f919c-2ec9-51af-be67-52fd9aba8bcf | textbox | Heat Soak: P2 (Kpa/Bar)
b6f167c0-a026-5337-bb7b-f1e55a32672c | textbox | Heat Soak: t2 (Seconds)
e1b473f0-4654-5355-b34e-c92a44e7bbad | textbox | Change Over: t3 (Seconds)
6dea393a-fda7-5a2d-9d64-9202e8109802 | textbox | Pressure Up: t4* (Seconds)
280e450d-a34d-5297-9c03-1b1f50411b2d | note | *t4 not applicable for SHP situations
3bc31b58-b30b-54ec-8c43-ba2f866649b8 | textbox | Weld and Cool: P3 (Kpa/Bar)
5fcd21cb-5e46-5a22-8a17-3795a584474b | textbox | Weld and Cool: t5 (h:m)
9c84a8a4-457e-5266-a005-a9bc9c87f18a | textbox | Rough Handling: t6 (h:m)
4dacb4a4-71d6-58b8-8f4c-c9d55d3c94b5 | textbox | Bead Size: Min
83455b5a-2cb0-55d7-bd0f-3830f3d52e1e | textbox | Bead Size: Max
175d390f-f5e3-5317-8f17-f994502327ee | textbox | Comments
336f23fb-1f55-4cd4-8d40-2a54fd94d102 | checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
13f99aaf-1289-5df9-9849-00ce3c0b9ab6 | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
a23a27f3-2fa1-5ba5-af32-019e9e91ba2a | note | Company: Geschke Group
d99119a3-57f9-5413-84c0-0109eb7b856f | note | Phone: 03 9798 1619
f04c3a13-8eec-5ed9-a79b-6dab8bbb82f0 | note | Address: 45 Pacific Drive, Keysborough
e1c3175d-2190-5829-b836-cb84644263b1 | note | Project: Centre for National Resilience Project - Melbourne
3afcf1fa-9294-5513-bcf9-45b0d1f06d7b | note | Principal: Multiplex Constructions
a4456394-c872-4e39-ba94-6fb39df211d5 | checkpoint | Foreman Sign-Offs completed - Click to Attach Signature(s) below
afe6fa4c-5df8-5ccb-9d90-b331f353c2d6 | note | Operator Sign-off added to each weld above as required
b83c71e0-3186-5699-b5e3-1f3da2c48419 | button | Geschke Group Signature Sign-Off added below | Yes, No
9f3354af-b20d-5b03-9401-f58055baf38e | button | Principal Contractor Representative Sign-Off added below | Yes, No
f11dfd8f-850e-481c-bbad-53546f3b1148 | checklist | ITP - Fire Sample Excl. Backfill ACOR Review |  | ITP - Fire Sample Excl. Backfill ACOR Review
3cd9a5a3-5efe-4a53-8ade-3d66c94a67d9 | checkpoint | 1. Approve specialist subcontractor
dc523e14-ef55-510f-8606-f0b3f7e0ebfc | note | STAGE / FREQUENCY: Prior to awarding subcontract
e644915b-121f-5d93-9bd4-7c602fd4e035 | note | RECORDS: Refer to Overall Project ITP for Written approval Geschke Quality Management Plans
e7f410f2-84b6-5ab4-8c98-12caa6cba200 | note | ACCEPTANCE CRITERIA: Subcontract is executed and witnessed by authorised representative from associated parties to contract
c3986787-26e4-5720-9594-418f6a1b8367 | note | INSPECTION / TEST PROC: Document
7918d1d6-45ae-5e43-8f6e-f41777bf7b9f | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
33189d52-1540-5ee1-900e-3bfdd0a70305 | note | HOLD OR WITNESS POINT: Hold Point
be41d16c-f142-444d-ab12-c26170740949 | signoff | hold point
da947173-17bb-4eb0-a32d-4f265c2b770f | checkpoint | 2. Approve Samples
99bc775b-8f6e-55e2-995b-eaaf0ae0a4d1 | note | STAGE / FREQUENCY: Prior to ordering materials
f8178d8c-2995-5bd2-8130-731ecc155e96 | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
1d0fcff4-60b8-5f14-ab29-13bb350269b4 | note | ACCEPTANCE CRITERIA: Samples is marked with Approved For Construction
dff86934-445a-5029-b50c-7f17b796962c | note | INSPECTION / TEST PROC: Document and Review
24673bd7-30c4-598b-b324-585c59b40961 | note | INSPECTOR / APPROVER: Engineer. Geschke
959d08b4-15b4-55d3-8bd9-f81aead36343 | note | HOLD OR WITNESS POINT: Witness Point
cca8bd33-a05b-4349-bad8-8437957e03a7 | checkpoint | 3. Approve technical details
c475480b-8139-5510-a32a-8fb62d0a24bd | note | STAGE / FREQUENCY: Prior to ordering equipment
721bff54-0e83-5047-b42e-3404ac57bd58 | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
e9f00d93-d0ea-5b03-aa4a-04c79bfaca4a | note | ACCEPTANCE CRITERIA: Technical Data is marked with Approved For Construction
52489b4c-18c6-516b-b4b7-5fd928d03d5d | note | INSPECTION / TEST PROC: Document and Review
1d3b9390-4f70-5e48-8063-9aecfdad6e39 | note | INSPECTOR / APPROVER: Engineer. Geschke
54698364-625d-5bfc-9748-561497a347ab | note | HOLD OR WITNESS POINT: Witness Point
ebffe12f-9e84-4408-9b57-17dc452f2768 | checkpoint | 4. Approve shop drawings
fec1c958-ef34-5853-a3f2-2150deed6384 | note | STAGE / FREQUENCY: Prior to commencement
4d304ed8-02ec-5ba9-9f92-99b8faf1fc1c | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
6f27304f-6777-5f22-99cd-98b6d28de995 | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
592614cd-7416-58c4-afec-83cd73449366 | note | INSPECTION / TEST PROC: Document and Review
1ef6b93f-6c4a-5371-9acf-65593587ab2b | note | INSPECTOR / APPROVER: Engineer. Geschke
c81f88fb-e726-549a-b35e-a742b24932b6 | note | HOLD OR WITNESS POINT: Witness Point
14b42376-79b8-4680-a435-a8f442031e1e | checkpoint | 5.01. Check set out of excavations
d68430f0-c853-55f0-8456-c82aa28eb2a1 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
78664af2-ca89-51ca-bada-0dd30034d297 | note | RECORDS: 'Before' Photographs
c6ad23a5-b988-5b97-87b4-9ce0fdeff511 | note | ACCEPTANCE CRITERIA: Set-out is marked with pegs and alignment matches design layout
775d6147-72d8-5aff-abb6-62af0aaa6d9a | note | Minimum falls
d4b47644-1f59-5d97-bc52-233597982dee | note | All 'known' existing services have been potholed, marked using a riser 1m above ground and backfilled with sand.
37dae68d-78e7-5de6-9149-42d288227698 | note | Excavation alignment is outside of minimum clearances from above ground assets, below ground assets and boundaries or plan for excavation works or temporary works meets requirements within exclusion zone.
f65e55d7-815a-5d65-b85d-5ff317b58008 | note | INSPECTION / TEST PROC: Visual Inspection and Document
2b76408b-27d0-5767-9f08-7e2d0ad57276 | note | INSPECTOR / APPROVER: Foreman. LLB
e07b7c58-1e7a-5bb3-af58-4198296bbfa5 | note | HOLD OR WITNESS POINT: Witness Point
ecaae01c-29aa-4a45-b778-65905094722b | checkpoint | 5.02. Approve Temporary Traffic Management Plan if trench crosses existing road, road reserve or footway
39b99aa0-9596-5ba8-9722-2cbd720ab0c8 | note | STAGE / FREQUENCY: Each delivery
7c61a581-e0c7-52f0-9e4a-e6b66449b87c | note | RECORDS: Delivery dockets name, signed and dated by Geschke
28900078-91fd-5738-b866-2522ad29c018 | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
831832a4-8398-54b6-ab43-3c3c2cfb30aa | note | Grade or class matches design
da1ded88-edfa-5793-9a00-837ab91dd61b | note | Size and thickness matches design
f79ad6e1-6e97-5b1f-803f-50c1131063ee | note | Supplied items are free of defect
efd647ca-a941-56dc-b566-13a7a777ddd9 | note | Marking, packaging and preservation is fit for storage / construction. i.e pits covers marked with SS.
e9da029a-85af-5915-8880-70e162cf638d | note | INSPECTION / TEST PROC: Visual Inspection and Document
760bbe01-5b7c-5113-be39-f97960b8de64 | note | INSPECTOR / APPROVER: Foreman. Geschke
fe4c391b-55e3-5069-a541-0d2bedcb92ea | note | HOLD OR WITNESS POINT: Witness Point
99ffd385-fcf1-40a2-a771-ca6830f38a2c | checkpoint | 6. Check deliveries of materials
e89e96d8-94e4-5b81-b31f-b61bfcd3f532 | note | STAGE / FREQUENCY: Each delivery
47dfe151-d278-5483-824e-48942f5c6e79 | note | RECORDS: Delivery dockets name, signed and dated by Geschke
226be74c-d2e2-56d6-8515-ab410b2ec2ae | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
882c4b4b-672e-5b1a-a684-5556660551f2 | note | Grade or class matches design
050e6e4a-0223-5e79-8007-48e11ed0fa12 | note | Size and thickness matches design
8225b5cc-7757-5600-905b-39da31976aca | note | Supplied items are free of defect
ccce2296-4aab-5a7a-8a98-45be3521ac6c | note | Marking, packaging and preservation is fit for storage / construction. i.e pits covers marked with SS.
21222ea8-54e6-509e-9188-780b94c293b3 | note | INSPECTION / TEST PROC: Visual Inspection and Document
fe0b28a2-abcc-5395-9841-38d00267169c | note | INSPECTOR / APPROVER: Foreman. Geschke
a173b87c-24d2-5d17-900b-34536714c793 | note | HOLD OR WITNESS POINT: Witness Point
28b6e2ae-c6ec-43c1-b158-509e81d650cd | checkpoint | 7.01. Check below ground pipework - pipe joints - HDPE-HDPE welds, DICL- DICL/Other Material Flange, GMS-GMS Rolled Grove Gasket. If HDPE- HDPE welds:
c4216462-9e1f-51b5-bc54-7c453508073c | tickbox | Standard Bead Profile Test
7ea71799-3ff7-56fa-9c35-ea866f978976 | tickbox | Standard Destructive Tensile Test
26017bb3-c9d8-5b6f-96d2-8e120056f089 | tickbox | Standard Ovality Test If DICL- DICL/Other Material Flange
45e159a7-17cd-5c2a-906a-a9dc146bfb8b | tickbox | Gasketing Record GMS-GMS Rolled Grove Gasket
5a2571b4-419c-5583-8adc-7a85f88a4cb9 | tickbox | Gasketing Record
cb323036-3d22-502d-a43a-4d123d9d63b7 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling/ 1 test per 50 pipeline welds approx.1000 l.m
f3fb5125-e465-51f2-8a7a-0ff70117c832 | note | RECORDS: ElectroFusion Welding Record QA16 Butt Welding Record QA 25 Gasketing Record QA 18 Standard Bead Profile Test Certificate Standard Destructive Tensile Test Certificate Standard Ovality Certificate
723c58ef-ec2e-558f-a95a-80a4ea6f1aaa | note | SPECIFICATION / STANDARD: ISO 13953 , ASTM F2620- 20 & ASTM F2928 AS4087 AS1110 & AS 1112 ACOR Consultants Civil Specification Section 6.15.1 AS 2566.1
df31a190-a3ea-5763-b8cf-f403b96a0117 | note | ACCEPTANCE CRITERIA: Meet or exceed tensile pipe strength
d66e2601-c73d-523d-a91f-fa1982080958 | note | Bead size to be uniform, symmetrical and free of contamination and air.
998ece51-5dcc-5df8-a0c1-97a6d2dbf316 | note | Bolt tightening to be completed using the correct sequence
d4e1292f-f57b-5b98-9f4e-7d1d894fbcc4 | note | Final torque on bolts shall not exceed manufacture specification.
1d327233-6234-57a7-91b4-d1725accda74 | note | Standard Pipe Ovality Test shall be meet and be no greater than 2% for cast iron pipes or 5% for all other pipes
8ef7ce63-03b3-528c-b88f-9b3a7a084cf1 | note | INSPECTION / TEST PROC: Document and Review
8ad33e0a-6f19-5bf2-a74f-5a310a51dea0 | note | INSPECTOR / APPROVER: Engineer. Geschke
aa101a40-cf91-51e3-8669-42968bd67006 | note | HOLD OR WITNESS POINT: Witness Point
d04f5fd6-e777-4c96-ba49-b09b8877da3f | checkpoint | 7.02. Check below ground pipework - pipes and fittings
536585b0-e531-5078-9983-60846d892271 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per Grid
3acc421b-46ae-590d-a128-8a8931398083 | note | RECORDS: 'During' Photographs & As-built Survey
d6df78bd-c2ca-51de-abbb-47b05b745d0d | note | SPECIFICATION / STANDARD: AS 2566, AS 3500, AS 4130 and AS 5065
18194696-1090-5075-8969-b466e7872ab0 | note | ACCEPTANCE CRITERIA: Service type clearly labelled with dimension & colour stripe
fe48ccff-905e-5803-8d02-1d1039ce22c2 | note | Joints, fittings and connections match design
6df2f8a4-640d-55ea-896d-dc9be20067b2 | note | Alignment and position are as drawn
48e50cf1-19f9-5dff-a490-e27498bbd68a | note | INSPECTION / TEST PROC: Visual Inspection & Document and Review
a05b72a6-ea5b-5af7-b3be-50379c759cfa | note | INSPECTOR / APPROVER: Foreman. Geschke
9158ae86-cea6-5c1a-a959-455db3ca4fc3 | note | HOLD OR WITNESS POINT: Hold Point
cefd2584-0a91-4cb1-a55e-3f318a8b7a4c | signoff | hold point
a0c49bfe-0434-48a3-9ce9-32c38519c029 | checkpoint | 7.03. Check below ground pipework - Hydrostatic pressure testing. Standard Hydrostatic Pressure Test
7b43706b-9f14-545d-806a-46e7292a4fd2 | note | STAGE / FREQUENCY: Upon completion but prior to covering and backfilling.
83744ee8-6682-5205-a077-529b5d064ce3 | note | RECORDS: Standard Pressure Test Certificate QA.6
c539ac66-a22e-5074-8b11-e59bb7a8bdfd | note | SPECIFICATION / STANDARD: Clause 2.3 of WSA 03 1999 & Clause 18.3 of WSA 03 1999
60d7a01f-d9ba-5851-9b63-62dd34ab9687 | note | ACCEPTANCE CRITERIA: Pipeline and joints are watertight up to 1,700kPa pressure for two hours
cd88f1cd-9bae-550f-a212-d5e08a9ca4ac | note | Pipeline is flushed free of all debris
3da71ae3-304e-5099-8d21-721773d984da | note | Test Passes MRWA Water Supply Pressure Test for PE Pipe
715674cb-c445-507d-b921-8e214b13c4bc | note | INSPECTION / TEST PROC: Document and Review
3b88cba1-aa69-51da-a22f-e5ccddfd9134 | note | INSPECTOR / APPROVER: Engineer. Geschke
f66420ad-e080-5f49-9537-18bc88ad2c10 | note | HOLD OR WITNESS POINT: Witness Point
1f2e645d-724f-46cb-ac4e-81da3b45c911 | checkpoint | 7.04. Check below ground pipework - bedding, haunching, surrounding and encasing
dfdb8ce2-ea4a-56c9-a0e2-444cae82eb4d | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per Grid
5bb92b4d-cfb1-582f-a55e-4346927694b1 | note | RECORDS: Photograph
85d6a98f-46a7-59cc-933c-18d3b937d03c | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.6
a387fd1b-debd-508c-9738-32cb22d55ba7 | note | ACCEPTANCE CRITERIA: Constructed using approved WASA material
86513410-06f5-552c-92d7-38e090cc4249 | note | Thickness of surrounding aggregate shall meet or exceed specified depth
a1240c29-dbb8-590e-91f4-79f3facaab4c | note | Detector wire/traceable foil backed tape laid 300mm above the pipe alignment
f7d248bd-ed81-5e9b-b678-2acb901a8076 | note | INSPECTION / TEST PROC: Visual Inspection
2ca7b540-1bdb-5fce-889e-0a5697600e5a | note | INSPECTOR / APPROVER: Foreman. Geschke
ef833776-6d17-535a-9cfd-9452a521dc8e | note | HOLD OR WITNESS POINT: Witness Point
7b7f6035-9bde-412e-b349-dc5abfdec883 | checkpoint | 9. Check Completed Surface - Make Good
b62e9cb6-c0da-54be-bd95-b0c0680996bb | note | STAGE / FREQUENCY: Prior to practical completion
b86c98d1-0ea1-54a9-8e0f-02391fbc8c91 | note | RECORDS: 'Upon completion' Photographs
763e70c6-968a-5f35-aa6c-8f7212317f52 | note | ACCEPTANCE CRITERIA: Completed surface is free of obstruction/debris and matches finished levels for pipework
97f6c90f-de4a-56d2-a64b-a9dc3c589b62 | note | INSPECTION / TEST PROC: Visual Inspection and Document
c4d7da46-ae2f-5386-a68d-fb7ac956e87e | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
2f4038a0-4bf1-523b-b38f-0fe0520dbc95 | note | HOLD OR WITNESS POINT: Hold Point
a4b9d9b9-b75b-46fa-a0e6-1a0eb813b92b | signoff | hold point
6e5095a8-0143-47d5-9d2b-912d68078d85 | checkpoint | 10. Obtain as built documents
d8c73f8c-5f3d-577e-bb57-f76f15776a8d | note | STAGE / FREQUENCY: Prior to practical completion
320c10ff-72d3-5d58-ae30-cb96f64cbd8c | note | RECORDS: As built documents
d0ff0aff-77d2-5993-9b97-4aea1563c1c6 | note | ACCEPTANCE CRITERIA: Drawings are marked with As-Built
795e1edc-7bc7-5eef-bf27-b771b92cc6c4 | note | INSPECTION / TEST PROC: Document and Review
8f5f56b9-a1c3-51e5-8b38-57b1836135ff | note | INSPECTOR / APPROVER: Engineer. Geschke
afe94cc9-3ab7-5777-9a61-c141c79f732a | note | HOLD OR WITNESS POINT: Witness Point
4333809b-3938-4c39-a171-d60f380ddae9 | checkpoint | 11. Obtain operating and maintenance manuals
e9c28399-9d42-5cd3-a9bb-220ff9ad3928 | note | STAGE / FREQUENCY: Prior to practical completion
01c1400b-1c0c-5587-b428-79395c4970a0 | note | RECORDS: Manuals
c52c5768-9ea3-5f2b-837f-ac31652b5b79 | note | ACCEPTANCE CRITERIA: A copy of the certificate for compliance shall be approved by the independent authority.
ab1a5463-db03-5961-b84f-890783ea321b | note | INSPECTION / TEST PROC: Document and Review
f62c2949-b3d9-5326-935a-6ed4ee80566c | note | INSPECTOR / APPROVER: Engineer. Geschke
d1d96bbe-1696-56d9-88c4-2c48b41f0f71 | note | HOLD OR WITNESS POINT: Witness Point
d20463b5-8900-4424-954f-8cf53ca8024b | checkpoint | 12. Obtain guarantees
c23e964a-2d02-5202-95da-853bf42523b9 | note | STAGE / FREQUENCY: Prior to practical completion
40adab2b-3679-5674-b338-09264787542d | note | RECORDS: Final commissioning checklist
510bb39f-9edf-5330-8633-2b8a2f497976 | note | INSPECTION / TEST PROC: Document and Review
1757ac8c-1899-5cab-b3fb-f70edfa2a048 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
b9d0f6cc-0b71-5da5-a30e-338c08c63b47 | note | HOLD OR WITNESS POINT: Witness Point
88b965e5-36ce-4b85-99ff-04e6729554d8 | checkpoint | 13.01. Check above ground Hydrants - Signal and Flow Test. Standard Flow Test
1cfaa637-c7f8-5fac-be45-d0426486df34 | note | STAGE / FREQUENCY: Upon installation / one test per hydrant
0a73a45c-321f-5ef6-a1f8-b5907552ceee | note | RECORDS: Standard Flow Test Certificate QA 6E
edee860c-8e4d-5dd1-a4e5-ad4fc39aaef4 | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.6
37766967-2e9f-5efa-acf2-a871e45b9d8e | note | ACCEPTANCE CRITERIA: Hydrant flows up to 30l/s
b6038c7d-899b-5c65-83b8-2c2b918aeb01 | note | Hydrant tagged and signed
8f41133c-17c7-5ce7-9f43-25ef4d49a908 | note | Bollards installed
2e328a26-aa73-5b74-8868-e3393b80866e | note | Signal sent to Building Sub FIP
ede815fc-6c74-52db-a15d-74a4ba513d73 | note | INSPECTION / TEST PROC: Visual Inspection and Document
41193414-1287-5d43-bba7-8e28137e96d0 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
4d486439-9baa-5bd4-9bbe-ecc2c0f2ef22 | note | HOLD OR WITNESS POINT: Hold Point
9dbb2bc5-06b9-4a5f-9344-a79e8bd472b2 | checkpoint | 13.02. Final commissioning & inspection & independent report
1f6cff2e-acff-5cbd-8dda-84f54ea3f049 | note | STAGE / FREQUENCY: Prior to practical completion
fc5ed97f-22ad-58ef-ac60-46f0d44647eb | note | RECORDS: Final commissioning checklist Independent Report
0203246a-3da8-51a2-aace-45cff19310fb | note | INSPECTION / TEST PROC: Document and Review
a10e7644-8443-5dc0-a24c-fc1111e20cb3 | note | INSPECTOR / APPROVER: Independent Engineer. Geschke
557010b0-453a-5643-8f69-c5f7ef04d679 | note | HOLD OR WITNESS POINT: Witness Point
d7c3d39b-3e0c-44e7-a9d5-d09cf33f9c4e | checklist | ITP - Gas Sample Excl. Backfill ACOR Review |  | ITP - Gas Sample Excl. Backfill ACOR Review
dabc1973-fc07-4ecd-91a7-56a41dee5689 | checkpoint | 1. Approve specialist subcontractor
8e98feaa-8f94-51da-a4c5-6cb9604f4413 | note | STAGE / FREQUENCY: Prior to awarding subcontract
775daa3c-c35e-5bf4-b0d9-aa8728b89c2d | note | RECORDS: Refer to Overall Project ITP for Written approval Geschke Quality Management Plans
3e66b696-4a84-5c3c-9caf-f551b4cf4dbd | note | ACCEPTANCE CRITERIA: Subcontract is executed and witnessed by authorised representative from associated parties to contract
b3b9089b-3779-56b1-a48b-79f1a0e23d9d | note | INSPECTION / TEST PROC: Document
b5362a5c-d6a0-5f7d-8098-b37ecb178fec | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
58d8bf03-8bab-5d07-baa0-648ff526abbf | note | HOLD OR WITNESS POINT: Hold Point
2b068e8b-86e9-4bb9-8da0-ba5f84b8da66 | signoff | hold point
eb706d72-a543-46e8-84bc-8177b93b950d | checkpoint | 2. Approve Samples
a032d4a8-01c2-5782-bcf6-0c69b74f4286 | note | STAGE / FREQUENCY: Prior to ordering materials
25a297b7-d3bf-5c0b-ae64-167efb6fe1dd | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
6a72b33c-d4e0-5341-9693-0f6ed20643a8 | note | ACCEPTANCE CRITERIA: Samples is marked with Approved For Construction
71e14af3-953b-5640-80ca-e7fed171ebcc | note | INSPECTION / TEST PROC: Document and Review
c17cd636-8118-588d-b9cd-f3d07ece4691 | note | INSPECTOR / APPROVER: Engineer. Geschke
339e10b1-8b6b-5d8d-a247-2ea54de8d736 | note | HOLD OR WITNESS POINT: Witness Point
fa806941-c02d-4d27-80c9-a58bf108b8e3 | checkpoint | 3. Approve technical details
ba3dd578-8d92-533a-89f7-630a52415184 | note | STAGE / FREQUENCY: Prior to ordering equipment
4072cfd4-c7ca-54e9-b2a2-d40b86cfabb7 | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
cb086b64-3b4a-5f31-8587-4cc9391fdbb9 | note | ACCEPTANCE CRITERIA: Technical Data is marked with Approved For Construction
626bf9e8-43c9-5b05-9326-0af409c8fd19 | note | INSPECTION / TEST PROC: Document and Review
992bafba-f05f-50c9-85dd-321e56e9763f | note | INSPECTOR / APPROVER: Engineer. Geschke
4e94744f-9689-5ee6-b2e1-94a5d4f46ee7 | note | HOLD OR WITNESS POINT: Witness Point
4e31d6d6-09ac-4858-932f-cbcdf876356e | checkpoint | 4. Approve shop drawings
fa26deae-dd0d-5fe3-bcef-8a246e97db9c | note | STAGE / FREQUENCY: Prior to commencement
b528a5b9-47b8-5532-8830-0f80d6b85e4d | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
2b577499-143a-5cad-b160-92c6e5095bdf | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
2eabf42e-4b3f-5c53-a34d-96e9c0ec9139 | note | INSPECTION / TEST PROC: Document and Review
b3446539-7a93-5e9f-b8b6-998792a7ba58 | note | INSPECTOR / APPROVER: Engineer. Geschke
d78f1626-3464-57e8-b98b-2a8dffb26b51 | note | HOLD OR WITNESS POINT: Witness Point
60bc164b-a2dc-42e0-ab06-a1518070681c | checkpoint | 4.01. Approve shop drawings
fd09096a-b5a5-5ccb-ac6a-f55083645a45 | note | STAGE / FREQUENCY: Prior to commencement
da9d8ea4-ea6b-5c66-9fa5-ec087da1012b | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
a42e4234-9e25-5ed9-bdda-8f827caf0d2a | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
8a2c08cf-0ec6-542f-aa72-77cf4d852d74 | note | INSPECTION / TEST PROC: Document and Review
9556b72c-ea04-50d6-af86-b04ee2763b30 | note | INSPECTOR / APPROVER: Engineer. Geschke
fe13fc0a-11e1-5d0a-9e6f-5669121f375c | note | HOLD OR WITNESS POINT: Witness Point
eb4d8770-cc7f-4356-bbeb-7d371a241f1a | checkpoint | 4.02. Approve Method of Work Plan
fdaaedae-d4de-5357-b4d4-bd066ca617c5 | note | STAGE / FREQUENCY: Prior to commencement
58b7911f-4984-54e8-8d83-3632fe2851e9 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.26.10
396cbe10-8166-5f23-98de-4c76e4e859d6 | note | ACCEPTANCE CRITERIA: Construction staging plan to execute the works
cde2d9c4-d871-5302-af42-553abee58f88 | note | Pipeline construction schedule
fcae433e-e099-593e-855f-fc66fd526261 | note | Nominate temporary supply
ae77f8e1-1ffc-56fd-8c62-a9aa4d687209 | note | Nominate safe work measures
68de276d-fd36-544c-ac4f-01c3a5dc3e57 | note | Nominate notification procedures
3c2a3d52-2190-5239-835a-6e24aac846bb | note | INSPECTION / TEST PROC: Document and Review
77d4e5cd-f1d6-5d99-b2b5-bd9ac14c760e | note | INSPECTOR / APPROVER: Engineer. Geschke
28c60a0d-6151-5586-acfd-12b9ee2cd16b | note | HOLD OR WITNESS POINT: Witness Point
eab35252-511b-481c-8966-aa69a79c4349 | checkpoint | 5.01. Check set out of excavations
666e44d9-1aba-5aa1-9470-a04a08363307 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
bd7fc441-44f7-5fbe-a552-65fc244338c5 | note | RECORDS: 'Before' Photographs
b2dbc0ee-0830-5d9c-a21e-def57ce4722c | note | ACCEPTANCE CRITERIA: Set-out is marked with pegs and alignment matches design layout
e3e7b180-0333-55b1-9cc2-ed66cd6b950d | note | All 'known' existing services have been potholed, marked using a riser 1m above ground and backfilled with sand.
196da0b5-01d5-5121-922c-a582d6005318 | note | Excavation alignment is outside of minimum clearances from above ground assets, below ground assets and boundaries or plan for excavation works or temporary works meets requirements within exclusion zone.
10b69c19-00de-5a21-afd6-65c6d920cc66 | note | INSPECTION / TEST PROC: Visual Inspection and Document
1176953e-bd21-5469-b33a-4bdece56bc3e | note | INSPECTOR / APPROVER: Foreman. LLB
9d05233f-2d67-541d-9e28-2837b2e0adf7 | note | HOLD OR WITNESS POINT: Witness Point
e91f1bce-0777-4a28-b00c-32d87f290466 | checkpoint | 5.02. Approve Temporary Traffic Management Plan if trench crosses existing road, road reserve or footway
0086df3b-6935-5d03-a7cb-44a38ad4afa0 | note | STAGE / FREQUENCY: Prior to commencement / each TMP
c9c0146c-1f87-5f32-a97c-a7d78b239183 | note | RECORDS: Copy of Consent and Traffic Management Plan
8cc3e5fd-476e-5861-90fd-7019b79b9435 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.2.4
74caad10-8e61-5e65-a353-d836a61676a7 | note | ACCEPTANCE CRITERIA: A copy of the consent for working in the Road Reserve and Temporary Traffic Management Plans approved by the relevant Statutory Officer
1936df8e-b18c-55e3-9641-4604cf34fb05 | note | INSPECTION / TEST PROC: Document and Review
3b3043c7-004b-5f21-84e2-7b731134fec0 | note | INSPECTOR / APPROVER: Contractors Authorised Representative. LLB
14d7a0eb-353a-5e22-bb5b-b9dac4de0ecb | note | HOLD OR WITNESS POINT: Hold Point
376b3a43-831e-49a0-bbb7-944316f42415 | signoff | hold point
f4368d0a-2792-4f2f-bdb9-442f259323e6 | checkpoint | 6. Check deliveries of materials
cd6f13f3-9d2c-52bb-996d-42aafc24592a | note | STAGE / FREQUENCY: Each delivery
d661622d-2345-5771-a070-e13c769f2b7d | note | RECORDS: Delivery dockets name, signed and dated by Geschke
15e359f3-a285-59d1-919f-ac5531cca2b5 | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
796e679f-0abb-54fc-ba25-9af0a6b78398 | note | Grade or class matches design
10707bea-8a13-5e2c-84a4-be6d21baad1a | note | Size and thickness matches design
a85f751c-7906-57ee-a2f7-878fbcafe897 | note | Supplied items are free of defect
66c73256-2904-53e9-ad9f-874a9969b871 | note | Marking, packaging and preservation is fit for storage / construction. i.e pits covers marked with SS.
cd834f1b-478d-5b61-8cef-1a9ddc187773 | note | INSPECTION / TEST PROC: Visual Inspection and Document
bc1e2889-1975-5899-a7ca-71b5e9f45175 | note | INSPECTOR / APPROVER: Foreman. Geschke
946a13ad-d7d1-5559-9cac-ca3ad52f8594 | note | HOLD OR WITNESS POINT: Witness Point
14be79ac-81e7-4c16-a463-abcdf2ffac1a | checkpoint | 7.01. Check below ground pipework - pipe joints - HDPE-HDPE welds, DICL- DICL/Other Material Flange, GMS-GMS Rolled Grove Gasket. If HDPE- HDPE welds:
f70763c0-f3a2-55fe-a233-4127cf1503ce | tickbox | Standard Bead Profile Test
06edb9c6-dc44-5c2e-ac96-b5500534208d | tickbox | Standard Destructive Tensile Test
c1ac92f5-9826-5b83-86b6-1713a479c689 | tickbox | Standard Ovality Test If DICL- DICL/Other Material Flange
b32ce6a3-dc94-5239-a99d-50b2934a9e15 | tickbox | Gasketing Record GMS-GMS Rolled Grove Gasket
2c17e1e4-f353-56be-8937-413bd66ba848 | tickbox | Gasketing Record
189c1cf9-2f2b-5d97-957b-89f859d7e992 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling/ 1 test per 50 pipeline welds approx.1000 l.m
0b2ab383-46d4-5dec-94d5-8defcb5f161c | note | RECORDS: ElectroFusion Welding Record QA16 Butt Welding Record QA 25 Gasketing Record QA 18 Standard Bead Profile Test Certificate Standard Destructive Tensile Test Certificate Standard Ovality Certificate
b19dac05-caf5-54a3-bd3a-e1f3c312f2e8 | note | SPECIFICATION / STANDARD: ISO 13953 , ASTM F2620- 20 & ASTM F2928 AS4087 AS1110 & AS 1112 ACOR Consultants Civil Specification Section 6.15.1 AS 2566.1
9069c0ea-c41f-5af1-bc16-3ea96511fcee | note | ACCEPTANCE CRITERIA: Meet or exceed tensile pipe strength
992686de-5f11-5bd7-be32-ecb9f7104d98 | note | Bead size to be uniform, symmetrical and free of contamination and air.
552562ef-4ba6-50e3-b59d-5a982a0a068c | note | Bolt tightening to be completed using the correct sequence
bff01896-cb68-5233-acbe-412d08d6b09f | note | Final torque on bolts shall not exceed manufacture specification.
9d0511d1-9a85-5ed0-8cf5-5374b08922df | note | Standard Pipe Ovality Test shall be meet and be no greater than 2% for cast iron pipes or 5% for all other pipes
816c4bf9-98e8-5dab-9b80-fe85b24e44f4 | note | INSPECTION / TEST PROC: Document and Review
61e87d83-8428-5872-a963-c7ae27359f70 | note | INSPECTOR / APPROVER: Engineer. Geschke
9715498c-d711-584c-9e05-c16c8df30269 | note | HOLD OR WITNESS POINT: Witness Point
924188ec-7ccf-44ea-8e47-e3075f70caf4 | checkpoint | 7.02. Check below ground pipework - pipes and fittings
6506145a-4717-5a60-85f3-ea723c270f69 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per Grid
031a86e6-e8af-533e-8a3e-57eaf4120bf5 | note | RECORDS: 'During' Photographs & As-built Survey
12a111b7-0177-5d87-9438-e38f421df7b5 | note | SPECIFICATION / STANDARD: AS 2566, AS 3500, AS 4130 and AS 5065
181e210f-d178-569d-9e03-f5f39c3992ad | note | ACCEPTANCE CRITERIA: Service type clearly labelled with dimension & colour stripe
b835d4ae-0a87-58b4-b1ac-0949792bbc44 | note | Joints, fittings and connections match design
6a470fc2-8995-5c6c-9723-fbea73581dd9 | note | Alignment and position are as drawn
7f954646-cb1a-50fe-a57d-6ed020f5e611 | note | INSPECTION / TEST PROC: Visual Inspection & Document and Review
fc9bb897-d12d-5531-8d20-cd96e5181c25 | note | INSPECTOR / APPROVER: Foreman. Geschke
9ba0a4d8-fba8-535c-9981-51d2f78685ba | note | HOLD OR WITNESS POINT: Hold Point
befa92af-34c1-462d-bef3-76a78e0684b4 | signoff | hold point
c7d37547-45a9-44d4-9841-8f7b5bbd76da | checkpoint | 7.03. Check below ground pipework - Air pressure testing & swabbing. Standard Air Pressure Test
48130a7a-7d92-5799-81d2-a0408be8331b | note | STAGE / FREQUENCY: Upon completion but prior to covering and backfilling / one test every 750 lm each pipeline
a6e9004b-5603-5235-a516-9764ac393ed8 | note | RECORDS: Standard Pressure Test Certificate QA.6
e10166b6-dbec-5cbd-b23d-2e0b0a503f84 | note | SPECIFICATION / STANDARD: AS 5601 ACOR Consultants Civil Specification Section 6.26.8
e3063862-8dad-5c47-acfb-671d53473582 | note | ACCEPTANCE CRITERIA: Pipeline and joints are airtight under the greater of 7 kPa pressure or 1.5 times the working pressure for 5 mins
458b1f99-797f-55aa-ab3e-a1941ba9039f | note | Pipeline is flushed free of all debris
06c9eae0-6b23-52d4-97b9-7b4593c014c2 | note | INSPECTION / TEST PROC: Document and Review
4a2aae93-79eb-5f7a-8cb6-ccc0477f814b | note | INSPECTOR / APPROVER: Engineer. Geschke
e189ebef-7ea3-5104-a2cd-1ecdb36248ac | note | HOLD OR WITNESS POINT: Witness Point
3d6e66ef-aca0-4332-b0fe-af8f1e97c8d3 | checkpoint | 7.04. Check below ground pipework - bedding, haunching, surrounding and encasing
609d7b63-d53e-545d-8de1-9fbcf511e5e3 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per Grid
cbd82b23-c7af-58bf-968d-42f6bc725509 | note | RECORDS: Photograph
aa0c194d-4859-5eb4-bef3-1300b5298212 | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.6
1e6d7e65-e15f-522f-8e59-ef31821a4b56 | note | ACCEPTANCE CRITERIA: Constructed using approved WASA material
b914466a-70ff-5b75-a08c-682e226951ca | note | Thickness of surrounding aggregate shall meet or exceed specified depth
2190e9ca-c96c-5904-aa07-524ad2e46b86 | note | Detector wire/traceable foil backed tape laid 300mm above the pipe alignment
b7eae5f1-29a6-508e-b95e-0384d44caae9 | note | INSPECTION / TEST PROC: Visual Inspection
79b64eae-8227-5f14-b2a2-1d0cf65e06e7 | note | INSPECTOR / APPROVER: Foreman. Geschke
60628964-8250-5246-8814-64327a0efa25 | note | HOLD OR WITNESS POINT: Witness Point
6a766b4c-d069-4ee2-95a0-7dccb45727e8 | checkpoint | 9. Check Completed Surface - Make Good
c135f6f9-7933-52a0-a186-644b38c16a8c | note | STAGE / FREQUENCY: Prior to practical completion
310eaece-fbf5-5652-b526-15f2c5977ce0 | note | RECORDS: 'Upon completion' Photographs
5fd4599a-ea56-580c-bfc5-12ab264ccf29 | note | ACCEPTANCE CRITERIA: Completed surface is free of obstruction/debris and matches finished levels for pipework
0e4f7c66-57c5-500e-ac94-b0469732d1a4 | note | INSPECTION / TEST PROC: Visual Inspection and Document
3c0debb2-3568-5fa5-969a-e2bf49020764 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
b29c83c9-b2e0-5fcf-91bb-f40f74ddfd06 | note | HOLD OR WITNESS POINT: Hold Point
ce054210-6c0f-40c2-9588-4ed27a18848f | signoff | hold point
79992496-78ce-4bbb-a221-4b3eaf761039 | checkpoint | 10. Obtain as built documents
94dc814b-cee6-5297-890f-a5c219a091c7 | note | STAGE / FREQUENCY: Prior to practical completion
a1d2192e-43f5-56c6-8da1-8b6fb3712a94 | note | RECORDS: As built documents
4fbb1513-0916-5614-bd58-5298b58dc4fc | note | ACCEPTANCE CRITERIA: Drawings are marked with As-Built
f8eaed7d-8603-57c0-a45d-bae59d0903d8 | note | INSPECTION / TEST PROC: Document and Review
3bbe1c30-3653-5735-9312-31e9f0276a99 | note | INSPECTOR / APPROVER: Engineer. Geschke
2483a9ea-adcc-5a83-8616-6d2532c42c54 | note | HOLD OR WITNESS POINT: Witness Point
8173df98-a99e-4318-af34-b9eec6e8740e | checkpoint | 11. Obtain Regulatory Authorities certificates and approvals
45b32009-613a-535e-9ffe-fd4455531bd1 | note | STAGE / FREQUENCY: Prior to practical completion
c3783366-eafa-55c9-b3d0-9916103cd581 | note | RECORDS: Certificates; Written approvals
f20fe307-a9c5-52b9-bf94-dd06ac3452be | note | ACCEPTANCE CRITERIA: A copy of the certificate for compliance shall be approved by the independent authority.
1c1f2585-43e4-52a2-abd5-4c40db0fb065 | note | INSPECTION / TEST PROC: Document and Review
7ce2d428-8fe9-5786-9b26-2bed61a7c70c | note | INSPECTOR / APPROVER: Independent Authority. LLB
de6e143b-dad4-5243-ad2e-bf9fd81bf622 | note | HOLD OR WITNESS POINT: Hold Point
f4366bab-d06f-40ff-b68c-309a1dfa3d48 | signoff | hold point
72f0cbef-c9dd-4a6a-b2cc-a085d450cc5c | checkpoint | 12. Obtain operating and maintenance manuals
e09b8f7e-c861-5603-bea7-a97a6f1d47e8 | note | STAGE / FREQUENCY: Prior to practical completion
f31eed10-b298-506f-8935-b4fa20c84f4d | note | RECORDS: Manuals
bfa9da76-3b15-5148-9976-e25f3958cc6a | note | INSPECTION / TEST PROC: Document and Review
5f5c34c1-4f8a-5bbe-b308-af7faa45068f | note | INSPECTOR / APPROVER: Engineer. Geschke
31e3d6d0-701c-58cd-a3ad-6889501cc3de | note | HOLD OR WITNESS POINT: Witness Point
953f01da-3460-4171-9c62-b4ed006ba089 | checkpoint | 13. Obtain guarantees
002a4df3-0cef-5bfe-98e5-ab9e795497ae | note | STAGE / FREQUENCY: Prior to practical completion
81d06bf4-e678-5f9a-8f57-6f2ddac60a10 | note | RECORDS: Final commissioning checklist
79dc1889-9259-5394-b412-383d3768e7c0 | note | INSPECTION / TEST PROC: Document and Review
f4725f12-6091-58ac-bdcc-55e0e349e48f | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
3f047b94-1bc3-57dc-a6bc-b39ee195c919 | note | HOLD OR WITNESS POINT: Witness Point
475bb0c5-716d-4c6a-aa17-9b478f2332bb | checkpoint | 14. Final commissioning & inspection
e2dccb04-781f-5513-816e-dcb33c47b360 | note | STAGE / FREQUENCY: Prior to practical completion
adde1f32-c8d4-5142-9b77-d21d30cd6b3c | note | RECORDS: Final commissioning checklist
1d1baaa2-0baa-556a-9798-a7567e3c3b08 | note | INSPECTION / TEST PROC: Document and Review
6a249861-f46e-5883-9301-80c085057213 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
3924fb89-05e2-500c-a1d6-5e130ca67941 | note | HOLD OR WITNESS POINT: Witness Point
5c89c765-bdc0-4796-9e3c-2d955ffaf4d8 | checklist | ITP - Sewer Rising Main Sample Excl. Backfill ACOR Review |  | ITP - Sewer Rising Main Sample Excl. Backfill ACOR Review
a4826ab2-63fd-4418-be12-fef75d7cb29f | checkpoint | 1. Approve specialist subcontractor
9b1a56dd-a7ce-563f-86d1-27d96761f35f | note | STAGE / FREQUENCY: Prior to awarding subcontract
1e98bae4-8922-58dc-b3d3-2c215db3cd7b | note | RECORDS: Refer to Overall Project ITP for Written approval Geschke Quality Management Plans
32270505-96e5-532b-b8d0-dd698c7b9c65 | note | ACCEPTANCE CRITERIA: Subcontract is executed and witnessed by authorised representative from associated parties to contract
e9631e99-d5b8-567e-a4bd-3bd512bac2d1 | note | INSPECTION / TEST PROC: Document
0abbec92-250a-5e92-b519-c607b0a147ec | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
eff87b2c-e08c-5e22-9877-45bd1d00c58c | note | HOLD OR WITNESS POINT: Hold Point
b8302469-acad-4299-8cc2-7278ef830a3f | signoff | hold point
dc66fa82-1b35-42f7-961f-528e329f06c0 | checkpoint | 2. Approve Samples
16fde646-9426-5933-8dbd-f4cf0a706b66 | note | STAGE / FREQUENCY: Prior to ordering materials
379f9518-7475-55eb-8783-cebce963b571 | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
58f2ec1b-9221-584b-811e-d76299a308e8 | note | ACCEPTANCE CRITERIA: Samples is marked with Approved For Construction
6c93e7f7-4778-590d-8d92-ccd0a4c2e5a6 | note | INSPECTION / TEST PROC: Document and Review
aff1c699-bac2-500e-ae74-1b0b7ec810e0 | note | INSPECTOR / APPROVER: Engineer. Geschke
c030b78c-9a5f-5f59-b309-7cc109e1fab2 | note | HOLD OR WITNESS POINT: Witness Point
b3451ca7-465c-4197-89ec-289a5fe66da7 | checkpoint | 3. Approve technical details
3a941d6e-6a46-53cd-87fd-8997720c2d3f | note | STAGE / FREQUENCY: Prior to ordering equipment
58dda1e4-cab3-5f83-9d09-83d7e7a0cb45 | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
0e8ae2b8-0ec1-5b2f-9b75-d8aa6d257950 | note | ACCEPTANCE CRITERIA: Technical Data is marked with Approved For Construction
79406de8-1707-579d-bf87-af39b7edcf21 | note | INSPECTION / TEST PROC: Document and Review
b2c1978c-eb8b-5c4e-8e05-7112574286e6 | note | INSPECTOR / APPROVER: Engineer. Geschke
37abf84e-2a9c-5887-bf8d-f30d76aab7c5 | note | HOLD OR WITNESS POINT: Witness Point
1107a8c3-5715-4b63-acb7-268c5c8d3145 | checkpoint | 4. Approve shop drawings
17fd9d47-3f6a-5cc8-b82c-3823cb250468 | note | STAGE / FREQUENCY: Prior to commencement
14af391e-8526-509a-bf44-4c0fc5af63e5 | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
54f64fec-715c-5ccd-a20e-c3fd2f5c74e9 | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
9ee787a6-c122-56c2-8d72-05ca78e97eab | note | INSPECTION / TEST PROC: Document and Review
c2acaba6-de72-578f-ba57-c79518fdd135 | note | INSPECTOR / APPROVER: Engineer. Geschke
ed7882c9-92d4-5d9d-8d7a-c0b9b56790e2 | note | HOLD OR WITNESS POINT: Witness Point
ce22128b-674c-4746-a372-1278020e8ce7 | checkpoint | 5.01. Check set out of excavations
a0abeb24-03a7-5b86-924e-1df745c008e1 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
9fe6a4b8-7fde-5523-b7b4-f2581a350ee3 | note | RECORDS: 'Before' Photographs
39362a40-a9be-5c7d-8acf-bd3b65eba2ee | note | ACCEPTANCE CRITERIA: Set-out is marked with pegs and alignment matches design layout
a4719d0a-982d-50da-b895-1b08d836bed2 | note | Minimum falls
29ca89d0-5fa2-596a-8a3d-d56965bbc19f | note | All 'known' existing services have been potholed, marked using a riser 1m above ground and backfilled with sand.
c692ac3a-f69b-590c-8dc1-21ccbb8aaa27 | note | Excavation alignment is outside of minimum clearances from above ground assets, below ground assets and boundaries or plan for excavation works or temporary works meets requirements within exclusion zone.
267c6bc3-6a34-518e-8448-40f677a65a29 | note | INSPECTION / TEST PROC: Visual Inspection and Document
d6eeae5e-be10-5a05-854e-7f3e21fa3b81 | note | INSPECTOR / APPROVER: Foreman. LLB
1e159756-1096-506c-abff-badbf6ee6adc | note | HOLD OR WITNESS POINT: Witness Point
2813285b-3c1b-47c7-9054-ca5e8aebb231 | checkpoint | 5.02. Approve Temporary Traffic Management Plan if trench crosses existing road, road reserve or footway
a13f465f-1d4f-5f2d-89f0-2de3a0c56079 | note | STAGE / FREQUENCY: Prior to commencement / each TMP
44a6981b-2b41-56aa-bb3f-581858f15e60 | note | RECORDS: Copy of Consent and Traffic Management Plan
3735673a-d2b7-5150-a9a3-ffb28d854f59 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.2.4
9323224e-afb3-5c5d-be56-2a6687c5012f | note | ACCEPTANCE CRITERIA: A copy of the consent for working in the Road Reserve and Temporary Traffic Management Plans approved by the relevant Statutory Officer
bf51f723-583f-56d2-8256-a2cfcf419cda | note | INSPECTION / TEST PROC: Document and Review
1c9d958c-c288-5e4a-a830-c28882882d7d | note | INSPECTOR / APPROVER: Contractors Authorised Representative. LLB
481cdce1-67be-5d77-b141-340e4813c044 | note | HOLD OR WITNESS POINT: Hold Point
ea90c142-cfc9-48a3-a267-36a9ea0f1b5d | signoff | hold point
7d24cbfd-1a9f-4ff7-a373-b12ceec3aaa6 | checkpoint | 6. Check deliveries of materials
6abacc85-5856-5fc8-8325-16a3c13d2892 | note | STAGE / FREQUENCY: Each delivery
1f220e67-cde6-5911-a8b4-5d694b6d1262 | note | RECORDS: Delivery dockets name, signed and dated by Geschke
806ac390-e39b-5396-8ffa-3838c0d4bf17 | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
46ef0600-a342-55ef-9a2a-bd4f53b89c45 | note | Grade or class matches design
516a857d-d132-5f79-9635-5eb776c0839f | note | Size and thickness matches design
96bfd4c9-1e0c-57d9-8060-9c823eec6cd7 | note | Supplied items are free of defect
d6a64810-4efe-5069-ab88-ce2cc14f3f3a | note | Marking, packaging and preservation is fit for storage / construction. i.e pits covers marked with SS.
219ae022-9490-5f56-8fb9-982d533a5a58 | note | INSPECTION / TEST PROC: Visual Inspection and Document
dcba30b1-1053-53f6-96d0-a2c9f0ac5fa2 | note | INSPECTOR / APPROVER: Foreman. Geschke
e69485cf-aa6b-56b4-ac67-036d6020ca1f | note | HOLD OR WITNESS POINT: Witness Point
7a0e2f19-655c-4764-b950-fbf1472d0a9d | checkpoint | 7.01. Check below ground pipework - pipe welds. Standard Bead Profile Test Standard Destructive Tensile Test Standard Ovality Test
59fcdc2e-9e77-5a4b-bd07-c510d4fdbfcd | note | STAGE / FREQUENCY: Upon installation but prior to backfilling 1 test per 50 pipeline welds approx.1000 l.m
d44a3d93-ea6d-5a4b-bb68-63c82c901268 | note | RECORDS: ElectroFusion Welding Record QA16 Butt Welding Record QA 25 Standard Ovality Certificate Standard Bead Profile Test Certificate Standard Destructive Tensile Test Certificate
2d022da8-f03c-5d5a-b186-fc8a2c984427 | note | SPECIFICATION / STANDARD: ISO 13953 ASTM F2620- 20 ASTM F2928 ACOR Consultants Civil Specification Section 6.15.1 AS 2566.1
28c6bc5d-b20a-5f0f-8c90-00b19b79df4f | note | ACCEPTANCE CRITERIA: Meet or exceed tensile pipe strength
c0a8f0f4-2203-509b-a1ec-2994c81f8a68 | note | Bead size to be uniform, symmetrical and free of contamination and air.
d826fe89-64ae-50b0-abff-50df9e1deb20 | note | Standard Pipe Ovality Test shall be meet and be no greater than 2% for cast iron pipes or 5% for all other pipes
e6e91c60-fbd8-591b-88ef-12822c4d37ca | note | INSPECTION / TEST PROC: Document and Review
26dbea3a-43a1-54e3-93ae-cbec99fcbce5 | note | INSPECTOR / APPROVER: Engineer. Geschke
b55c5a10-36c1-54a6-89b3-705414aa98fb | note | HOLD OR WITNESS POINT: Witness Point
c6d52a9b-562c-4529-9b6f-fa90ef022192 | checkpoint | 7.02. Check below ground pipework - pipes and fittings
e8a6b7ae-881f-5654-9978-230eba3d9f58 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
ef616c44-0699-51fc-aa26-1c1ea9de2d65 | note | RECORDS: 'During' Photographs & As-built Survey
f8ffead5-a4bf-54f4-81ea-4620d19614b4 | note | SPECIFICATION / STANDARD: AS 2566, AS 3500, AS 4130 and AS 5065
f0b706e7-8325-5272-a2ef-ade51e242fc5 | note | ACCEPTANCE CRITERIA: Service type clearly labelled with dimension & colour stripe
c8587cf4-b764-569b-bddf-6401c3091bc8 | note | Joints, fittings and connections match design
27a78cd1-4f6a-52ea-b135-da6d119a8866 | note | Alignment and position are as drawn
aa92908f-450c-5eba-9f0e-212ca093ba6b | note | INSPECTION / TEST PROC: Visual Inspection & Document and Review
76927fea-4ff4-58e5-b3fe-09d9905fe492 | note | INSPECTOR / APPROVER: Foreman. Geschke
12a5f896-de56-5156-951c-71ed71a1455e | note | HOLD OR WITNESS POINT: Hold Point
e094d63b-5ecd-418c-8cf8-2e9d3e43029b | signoff | hold point
e0001c0b-d718-4d8c-9db1-00bbb0f3666f | checkpoint | 7.03. Check below ground pipework - Hydrostatic pressure testing. Standard Hydrostatic Pressure Test
25bda725-3fc2-576a-90a9-ca25bd2e2547 | note | STAGE / FREQUENCY: Upon completion but prior to covering and backfilling
14d0cff4-afca-564a-a2ad-2f318f29655b | note | RECORDS: Standard Pressure Test Certificate QA.6
ae62b391-6792-5107-8fc4-1a64bc2e7757 | note | ACCEPTANCE CRITERIA: Pipeline and joints are watertight up to 1,500kPa pressure for two hours
560963b7-1f96-578c-af36-9de50b3adb56 | note | Pipeline is flushed free of all debris
2b7b7d10-2ee6-54b6-9b8e-9cf545513a1e | note | Test Passes MRWA Water Supply Pressure Test for PE Pipe
1b917aed-c169-522b-aeaf-5ed0e823b2f5 | note | INSPECTION / TEST PROC: Document and Review
2cffae0a-3d90-5d9a-941b-30102f83c1f0 | note | INSPECTOR / APPROVER: Engineer. Geschke
c477492c-04e1-56c6-a98b-f4fd644ee207 | note | HOLD OR WITNESS POINT: Witness Point
3cdaee18-49bc-41c3-9442-95b2b11ddae2 | checkpoint | 7.04. Check below ground pipework - bedding, haunching, surrounding and encasing
67f85c9b-c26b-5abe-aa59-721076ab7684 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
1f529678-0cb9-599e-ab0c-05fb1b49b5d2 | note | RECORDS: Photograph
8ba4ff9f-9c0a-5262-baab-b19296305467 | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.6
a26b7a7f-72d3-523b-891c-62ab24010227 | note | ACCEPTANCE CRITERIA: Constructed using approved WASA material
23407055-9424-542a-8762-b9f43f676f0d | note | Thickness of surrounding aggregate shall meet or exceed specified depth
d7b11f4f-18da-5790-b645-03e55c46b830 | note | Detector wire/traceable foil backed tape laid 300mm above the pipe alignment
5f08ed74-d9b7-5262-b89a-c1d19da18cbb | note | INSPECTION / TEST PROC: Visual Inspection
6e569a9e-07e6-5c29-909b-a4661f3b023e | note | INSPECTOR / APPROVER: Foreman. Geschke
079313d2-aaf4-5d52-9dff-117afaae3c42 | note | HOLD OR WITNESS POINT: Witness Point
1a0bd640-9435-4e77-a0fe-14a1989211d4 | checkpoint | 9. Check Completed Surface - Make Good
aba0280f-413d-5b10-b02e-6b9928ec9177 | note | STAGE / FREQUENCY: Prior to practical completion
be1e2b8c-53ab-5bf2-aecc-db0b8d99ae11 | note | RECORDS: 'Upon completion' Photographs
6a280e70-3441-5f1e-a0db-40882a638870 | note | ACCEPTANCE CRITERIA: Completed surface is free of obstruction/debris and matches finished levels for pipework
a57f7152-5e63-5a35-bba3-f975535f94fc | note | INSPECTION / TEST PROC: Visual Inspection and Document
66a64042-23f5-512c-8e8e-b5b57fce3bab | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
b3ad91f4-8c1a-591e-932f-1cda946377fc | note | HOLD OR WITNESS POINT: Hold Point
358a15c2-236f-49d2-be6a-fac445eacec2 | signoff | hold point
5a2bd53c-99df-4bad-9b72-616737be34e6 | checkpoint | 10. Obtain as built documents
15424ba2-ecc4-517d-b146-02aaafae86db | note | STAGE / FREQUENCY: Prior to practical completion
0cd63827-c5f5-5273-9ea3-83973cd00d16 | note | RECORDS: As built documents
b003b32c-8141-5490-a267-1b05361a7a50 | note | ACCEPTANCE CRITERIA: Drawings are marked with As-Built
271a2ca9-512b-5007-910e-f53c808a2b7c | note | INSPECTION / TEST PROC: Document and Review
b6602c4e-995a-50b2-9767-974fa6e12c12 | note | INSPECTOR / APPROVER: Engineer. Geschke
85470ec2-b1ae-54bb-82bd-c83fcd58e655 | note | HOLD OR WITNESS POINT: Witness Point
f325c159-d464-4793-bdcb-8fe2c329d38d | checkpoint | 11. Obtain Regulatory Authorities certificates and approvals
314411e5-af6f-5305-b677-69feafa904f5 | note | STAGE / FREQUENCY: Prior to practical completion
3724ecb2-08be-58c6-aeff-7c1153b5b258 | note | RECORDS: Certificates; Written approvals
03e3d848-a540-5328-9fd7-630d64dc8fcb | note | ACCEPTANCE CRITERIA: A copy of the certificate for compliance shall be approved by the independent authority.
6d23a117-826b-5f4b-a2b4-3d2acc636013 | note | INSPECTION / TEST PROC: Document and Review
eee34bcc-08e7-564a-9a33-35eed6b31cc0 | note | INSPECTOR / APPROVER: Independent Authority. LLB
f5c9b3aa-a751-5180-a07d-7f9da647d4e9 | note | HOLD OR WITNESS POINT: Hold Point
f85fcebd-b759-4f7e-b041-22e537216e7b | signoff | hold point
f52acfb8-0e1a-4c58-8286-edc65a10d2b9 | checkpoint | 12. Obtain operating and maintenance manuals
001c615e-86ba-5b5e-a289-e04878d5b2a1 | note | STAGE / FREQUENCY: Prior to practical completion
0c346b97-d01c-59c6-8ff8-94836c77ba60 | note | RECORDS: Manuals
42c5e34a-bd9a-550f-ac1f-1f45ec47d772 | note | INSPECTION / TEST PROC: Document and Review
a502c3b5-b3b8-5abc-9158-23819fd5fc5a | note | INSPECTOR / APPROVER: Engineer. Geschke
0945f469-ceff-5816-9afb-df76887891b9 | note | HOLD OR WITNESS POINT: Witness Point
33d4e75a-dee4-4c2e-b3da-5797bc8155d1 | checkpoint | 13. Obtain guarantees
ca7e4f73-c732-53d3-80b9-6354bf1ea869 | note | STAGE / FREQUENCY: Prior to practical completion
15999e9e-54ff-5b5a-b60d-944ccbcab6ba | note | RECORDS: Final commissioning checklist
90ccaf34-cb71-51f3-b4d9-a290e560f78f | note | INSPECTION / TEST PROC: Document and Review
4716fa78-5126-5487-a6be-4cef3ac88405 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
f3838718-2ef2-5d66-80d4-e9ab1a6c240a | note | HOLD OR WITNESS POINT: Witness Point
ed6c4a54-571c-4cf1-9209-f6250d83b50e | checkpoint | 14. Final commissioning & inspection
e37d24ff-4332-5d0c-b7ce-559a6152cd70 | note | STAGE / FREQUENCY: Prior to practical completion
adf8ce7c-a965-523e-8116-b76092afe62c | note | RECORDS: Final commissioning checklist
f0d4d09b-66ed-5d07-9bdc-c102be218ce9 | note | INSPECTION / TEST PROC: Document and Review
84e37ace-bd3c-5704-a211-3a723d8e6857 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
8f841f59-ea3a-596b-89aa-5c3686c11f07 | note | HOLD OR WITNESS POINT: Witness Point
7a911f75-98a2-4435-b58a-576d98016566 | checklist | ITP - Storm Water Sample Excl. Backfill |  | ITP - Storm Water Sample Excl. Backfill
c01ead93-8199-4aa3-b4f6-f5e54036b77d | checkpoint | 1. Approve specialist subcontractor
272c9fe5-f385-5a4f-b798-7d060fdbf188 | note | STAGE / FREQUENCY: Prior to awarding subcontract
b6b2c4aa-9dae-5b74-861d-44a89f9ec796 | note | RECORDS: Refer to Overall Project ITP for Written approval Geschke Quality Management Plans
b0d57164-8eed-55d5-9702-cf314ba6f570 | note | ACCEPTANCE CRITERIA: Subcontract is executed and witnessed by authorised representative from associated parties to contract
3ad992d5-aae8-5c47-9604-37fceca81c94 | note | INSPECTION / TEST PROC: Document
45209602-84b8-5701-8a6f-ed5cedbb708a | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
646f2d1b-fdc1-5030-b95a-bf84c147fcd2 | note | HOLD OR WITNESS POINT: Hold Point
b0ef61d9-4839-4055-be12-900f26f1e64a | signoff | hold point
08083411-083a-4ead-8f34-a3e04e4569b5 | checkpoint | 2. Approve Samples
b5558fdd-78d3-5f5e-b51c-f695fc090817 | note | STAGE / FREQUENCY: Prior to ordering materials
44b3d618-bf38-52d0-8df8-cbcb90bab62c | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
f4dc8da7-93e1-55a8-a609-9c7bad45f11e | note | ACCEPTANCE CRITERIA: Samples is marked with Approved For Construction
1474dff1-d719-5a1c-936b-aa01a414c7dc | note | INSPECTION / TEST PROC: Document and Review
ed02156e-0631-563a-8ca4-88f4958cdd8e | note | INSPECTOR / APPROVER: Engineer. Geschke
a9190c3c-d325-5cbf-bde4-ed4d8d60bcc0 | note | HOLD OR WITNESS POINT: Witness Point
813d40a7-5eab-4b44-9729-38738ecffa9b | checkpoint | 3. Approve technical details
97ed5eaf-e6a8-511f-aaab-4a130202aea1 | note | STAGE / FREQUENCY: Prior to ordering equipment
9d40b3d5-1906-5be1-b999-8d0b4d71929b | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
5d7f9fcd-b618-5bee-b9c6-713383e89c81 | note | ACCEPTANCE CRITERIA: Technical Data is marked with Approved For Construction
6ca1a21b-f267-579f-8794-2447f989673c | note | INSPECTION / TEST PROC: Document and Review
a1cccf5a-c55a-5c5e-a92b-4023aa2e7056 | note | INSPECTOR / APPROVER: Engineer. Geschke
18ab9a10-ee5f-5a7a-8825-fcbb7a764ff8 | note | HOLD OR WITNESS POINT: Witness Point
153839bd-a9f9-4830-9d20-9eda3fe4516a | checkpoint | 4. Approve shop drawings
25a826fa-6ec0-5a1d-9ef5-70d5307435a6 | note | STAGE / FREQUENCY: Prior to commencement
4bd5961e-5a75-57e1-9782-1cededde86c4 | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
32d2f220-a03e-54f0-9fe9-fb3c07d158a1 | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
fc957cb3-99ae-533d-bea6-763a451f33e4 | note | INSPECTION / TEST PROC: Document and Review
467d0f13-7e63-5fcc-9dad-2e421510f069 | note | INSPECTOR / APPROVER: Engineer. Geschke
4a3816d3-1ea6-541c-b2ef-979a4c1217a0 | note | HOLD OR WITNESS POINT: Witness Point
5288e974-fa47-4dc6-9611-8a032220eb5c | checkpoint | 5.01 . Check set out. By Delta
4e802dfd-56f6-55ef-a758-a2d73a0ed3c9 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
b5890be6-4d7e-501b-87cb-e2c81b163ea9 | note | ACCEPTANCE CRITERIA: Set-out of pits is marked with pegs and alignment matches design layout
003bfe98-c964-5055-860f-56fc4db2ea7c | note | Height control point is marked within 40m of works area.
4018c6a6-5703-540e-b261-865eca0acc1f | note | All 'known' existing services have been potholed, marked using a riser 1m above ground and backfilled with sand.
d514bf83-187b-5c1e-abd7-58bf0f693a1e | note | INSPECTION / TEST PROC: Visual Inspection and Document
d9cfb342-678d-51b1-92bf-37bb72381038 | note | INSPECTOR / APPROVER: Foreman. Delta
07ae8020-0179-538f-8f10-7ad35d9b7f17 | note | HOLD OR WITNESS POINT: Witness Point
c89ec58c-d8bc-40aa-8e9e-097a23e3dcc1 | checkpoint | 5.02. Check excavations
8c854a68-4160-5f62-8601-cce861cea528 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
6eda77dd-7c41-5dac-a335-ba9eed7f69b4 | note | RECORDS: 'Before' Photographs
5fc4e74e-c4c4-55fb-99fe-97dc1e3ba735 | note | ACCEPTANCE CRITERIA: Alignment commences at outlet and proceeds upstream
bd5e2c49-a8ac-5b95-b2d0-d574804bc6fc | note | Minimum falls
152406fa-c55b-5cf1-9b6e-781b3af1833d | note | Excavation alignment is outside of minimum clearances from above ground assets, below ground assets and boundaries or plan for excavation works or temporary works meets requirements within exclusion zone.
eed9803b-fbb6-5437-a202-b60e816b7110 | note | INSPECTION / TEST PROC: Visual Inspection and Document
f0b127b4-f5f3-53f1-b619-ea0d1722e230 | note | INSPECTOR / APPROVER: Foreman. LLB
d02f093d-2a58-55b0-b303-db6c16d92a38 | note | HOLD OR WITNESS POINT: Witness Point
8e3b0dc0-b8dc-4f35-a4c4-55db857e09c1 | checkpoint | 5.03. Approve Temporary Traffic Management Plan if trench crosses existing road, road reserve or footway
a377be9a-20bb-5b8d-89e7-0990a692551a | note | STAGE / FREQUENCY: Prior to commencement / each TMP
d22676a9-0b66-58e7-b586-40ab365ab722 | note | RECORDS: Copy of Consent and Traffic Management Plan
a07c1a48-abb1-52af-97d9-cbfa42e53d23 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.2.4
14ea55ea-317e-5b57-8ebd-882697de4c19 | note | ACCEPTANCE CRITERIA: A copy of the consent for working in the Road Reserve and Temporary Traffic Management Plans approved by the relevant Statutory Officer
e5c5a920-8611-5bc4-8fdf-b6ae1c5835e1 | note | INSPECTION / TEST PROC: Document and Review
bf385c45-b5d9-595c-91b8-d644149c6d0c | note | INSPECTOR / APPROVER: Contractors Authorised Representative. LLB
c9d81593-3255-5fe1-a7d7-7ed3d2782aa9 | note | HOLD OR WITNESS POINT: Hold Point
c270bd45-8d70-4b38-b5a0-c771feafbf04 | signoff | hold point
1ad7939e-d2d5-42ff-99ce-f64f99260de6 | checkpoint | 6. Check deliveries of materials
d07cc913-5d82-5d49-9709-549ac43d602e | note | STAGE / FREQUENCY: Each delivery
9595e291-6119-517c-9550-ed234dadd98f | note | RECORDS: Delivery dockets name, signed and dated by Geschke
bb1efc22-864e-5841-a82d-1552903c0082 | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
4dc7bce7-cf71-5a7f-aacd-1f89a7b0c31d | note | Grade or class matches design
38d1632e-e46b-54ad-afd6-13161a1afdbb | note | Size and thickness matches design
1727aa94-8b5c-51fb-a7c6-8d761f520808 | note | Supplied items are free of defect
74e8b62f-5805-57aa-a5dc-7216c99e1d0d | note | Marking, packaging and preservation is fit for storage / construction
7654f954-5401-5af8-8b9d-7097eda52155 | note | INSPECTION / TEST PROC: Visual Inspection and Document
34eabd68-1530-55d6-b4d7-451ed858c74e | note | INSPECTOR / APPROVER: Foreman. Geschke
93a3daca-6014-509c-b895-5c755ae87915 | note | HOLD OR WITNESS POINT: Witness Point
299eab87-8bdd-4333-8fab-87e247a345f2 | checkpoint | 7.01. Check below ground pipework - rubber ring joints
21e78a7a-6661-5a16-a421-723af4e1ce01 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / one test each grid
e3a198eb-c3b0-5bcc-a44c-418891f451bf | note | ACCEPTANCE CRITERIA: Joints are secure and flexible
865e85d3-d65b-5664-ac7c-e463df6739b6 | note | INSPECTION / TEST PROC: Visual Inspection
ae321497-d185-5f05-9832-f8d5654b8641 | note | INSPECTOR / APPROVER: Foreman. Geschke
f4d92b25-7a16-584a-b75d-2535412b9cdb | note | HOLD OR WITNESS POINT: Witness Point
50f21f94-f505-4dce-b0d6-0f820cbf30a6 | checkpoint | 7.02. Check below ground pipework - pipes and fittings. By Delta
fd678bb8-590a-5d93-abdd-a025c84f8997 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / once per grid
855e39a8-f035-5794-84ba-2df39fc62042 | note | RECORDS: 'During' Photographs by Delta & As- built Survey by Delta
b103ec03-2766-5179-98a1-054719c850c4 | note | SPECIFICATION / STANDARD: AS 2566, AS 3500, AS 4130 and AS 5065
d8083de4-16d6-528a-911c-9f0a61ead369 | note | ACCEPTANCE CRITERIA: Service type clearly labelled with dimension & colour stripe
bf8d4aaf-7768-5101-b949-985e48705e0b | note | Joints, fittings and connections match design
49927e54-b51a-5638-ab19-abc1b911018f | note | Alignment and position are as drawn
fe20ba53-22f9-5455-9de3-8189c0c7da25 | note | INSPECTION / TEST PROC: Visual Inspection & Document and Review
fef5aefd-2d86-5e9a-8f47-256b8a01a10c | note | INSPECTOR / APPROVER: Foreman. Delta
058046b5-a6f6-5736-b22b-c26aa86178ac | note | HOLD OR WITNESS POINT: Hold Point
dac13059-874d-43ec-a867-66e550570bd7 | signoff | Hold Point
f8a6a360-2e7a-4b06-b0d2-7353ab42b928 | checkpoint | 7.03. Check below ground pipework - bedding, haunching, surrounding and encasing
6343733b-9639-5456-b7b7-52294a80e018 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
a213a366-0f34-534b-a1eb-ff520c0350d9 | note | RECORDS: Photograph
e3b1a3e1-75ed-58e1-b070-fd4bb89e824f | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.6
9d3b38ea-8db4-54b2-800f-07df38c50c20 | note | ACCEPTANCE CRITERIA: Constructed using approved material
b14a6285-2db1-5ccb-9c87-4afe8fa74f76 | note | Thickness of surrounding aggregate shall meet or exceed specified depth
6f109bf8-8581-5872-bcd3-8702237c18b3 | note | Detector wire/traceable foil backed tape laid 300mm above the pipe alignment
e1cce678-c97e-5ed9-85ce-a27dac430354 | note | INSPECTION / TEST PROC: Visual Inspection
cd2fffd2-dc57-5777-99ac-983b3708f153 | note | INSPECTOR / APPROVER: Foreman. Geschke
401bca0e-85a2-5ddc-9c32-c4203b5639a2 | note | HOLD OR WITNESS POINT: Witness Point
376d276a-6737-444b-beda-9285ad9d6c6c | checkpoint | 9. Check Finished Surface - Make Good. By Delta
41d3f62d-df17-5feb-b3e5-b78acf6d7d5d | note | STAGE / FREQUENCY: Prior to practical completion
3fafb118-eecc-5bba-90e2-9f0eea4216ce | note | RECORDS: 'Upon completion' Photographs by Delta
0c28ff16-3de8-5b9c-9edb-f2d3ee531f78 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.18.5.12
f3f2dff7-bfe9-54a5-9b46-04a72349c6e7 | note | ACCEPTANCE CRITERIA: If works are in existing roadways, paving or asphalt has been replaced.
a619a378-5ff9-584c-a682-c81092c9af05 | note | Finished surface is free of obstruction/debris and matches finis
dcc885e7-6186-58e9-9960-1aa4f5dce53f | note | INSPECTION / TEST PROC: Visual Inspection and Document
de22c492-4c17-5069-a0ff-0025f048cd24 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Delta
26399e6e-00e7-56ef-a139-8b41adb29bec | note | HOLD OR WITNESS POINT: Hold Point
8e05a70f-e138-42b1-bcff-926aa4e03b7b | signoff | hold point
a69f0749-9b3e-4fae-ad4c-2f2e8132c1b2 | checkpoint | 10. Obtain as built documents. By Delta
92cf91e1-2eda-5b22-bbfc-c66565fec6a5 | note | STAGE / FREQUENCY: Prior to practical completion
fd5af1d9-53b8-51f9-88e3-dbac10eb98dc | note | RECORDS: As built documents by Delta
3c134a85-378f-5d65-a3b8-51c55b2eb9f5 | note | ACCEPTANCE CRITERIA: Drawings are marked with As-Built
2eb800db-3d1b-589e-aaa1-c926f0920bba | note | INSPECTION / TEST PROC: Document and Review
d3653e1f-cdf3-55ac-b032-7dc33fe5891e | note | INSPECTOR / APPROVER: Engineer. Delta
cc3a25ad-a2ee-516b-8160-07d822382679 | note | HOLD OR WITNESS POINT: Witness Point
8c7a6196-b4cc-42e6-b4d4-e228bc0a2033 | checkpoint | 11. Obtain operating and maintenance manuals
22d774de-e7fe-5aee-ae58-3f660b34139c | note | STAGE / FREQUENCY: Prior to practical completion
69ae8ef5-0a0e-5418-8a76-f15ee8acaee9 | note | RECORDS: Manuals
ce1da72d-79f1-598c-a3aa-6ab2bae56875 | note | INSPECTION / TEST PROC: Document and Review
2abd8a01-d420-53dd-8200-5bb16e90ccfc | note | INSPECTOR / APPROVER: Engineer. Geschke
831794a1-8d07-5246-9ee4-39dd3b82b5c7 | note | HOLD OR WITNESS POINT: Witness Point
49c4a93c-6e39-4d23-88d3-8d24e63c120d | checkpoint | 12. Obtain Guarantees
568a482f-a827-5aaa-b72b-f9f4f3b7b5db | note | STAGE / FREQUENCY: Prior to practical completion
18ab3648-d3d6-55ab-82d7-b3c93fb852f2 | note | RECORDS: Written guarantees
91e85bcf-3d41-591d-bbc0-0a7cd297684b | note | INSPECTION / TEST PROC: Document and Review
f42b4c23-f909-5fdd-b935-c27dd25c0fbc | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
b2fc1fb6-c00f-5e82-a78a-9376218b8587 | note | HOLD OR WITNESS POINT: Witness Point
b62083ba-ad30-4203-a2d8-a3aecbd6721c | checkpoint | 13. Final commissioning & inspection
42a4fd7d-ef96-59a2-be4d-d9442f46be7d | note | STAGE / FREQUENCY: Prior to practical completion
67627053-98a7-59b8-8204-4df78d8abf6b | note | RECORDS: Final commissioning checklist
60596913-a04e-500a-9df2-b49511b7ab9c | note | INSPECTION / TEST PROC: Document and Review
1237a8c3-8a40-55bf-8b1c-650dccd9c018 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
b62a2243-38eb-5698-b05e-aa034d39a549 | note | HOLD OR WITNESS POINT: Witness Point
707e3fb6-1463-4145-a1fc-c2fbc42fb71c | checklist | ITP - Subsoil Sample |  | ITP - Subsoil Sample
4ed6ba3d-07e2-43b9-ac27-686e5c55ed56 | checkpoint | 1. Approve specialist subcontractor
66c64a1b-266f-58ce-b7f7-c53ce69129bc | note | STAGE / FREQUENCY: Prior to awarding subcontract
71424ad9-27cc-55e6-a0bf-f49a17128ef5 | note | RECORDS: Refer to Overall Project ITP for Written approval Geschke Quality Management Plans
1ef2f8a4-566f-5b68-abbe-c4ec8ebcc58b | note | ACCEPTANCE CRITERIA: Subcontract is executed and witnessed by authorised representative from associated parties to contract
0d5bb9fc-a75f-5197-b910-98f259363ac0 | note | INSPECTION / TEST PROC: Document
154da85b-3765-54c0-8320-43bcea7b5f1a | note | INSPECTOR / APPROVER:Subcontractors Authorised Representative. Geschke
4475be6b-aef1-5e53-bd93-547a03ed7ac5 | note | HOLD OR WITNESS POINT: Hold Point
94ca92aa-5d6c-4cd8-915e-f11d06ce631b | signoff | hold point
98fd8d2c-33d2-4b23-8718-44d3b1a9da5d | checkpoint | 2. Approve Samples
c8919b1d-3829-5c21-ab45-57d4580a247c | note | STAGE / FREQUENCY: Prior to ordering materials
2f51bf28-a693-5e06-a9c7-e4c1918d65fd | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
d9d9bb5b-b90b-51f1-a83c-d55c5929a1f1 | note | ACCEPTANCE CRITERIA: Samples is marked with Approved For Construction
bb0b154d-7507-54a6-ac71-fee5acfd4ed7 | note | INSPECTION / TEST PROC: Document and Review
8d34606f-aee5-59b5-ac8b-f8259d42cf16 | note | INSPECTOR / APPROVER: Engineer. Geschke
4f2a3075-559a-5fd6-a3d8-fa9e396025df | note | HOLD OR WITNESS POINT: Witness Point
f8240c1c-bbde-443b-a3f1-bb019a636696 | checkpoint | 3. Approve technical details
2e9df509-e671-520e-99a6-8435ff16e4b6 | note | STAGE / FREQUENCY: Prior to ordering equipment
b12437ce-a7bf-5da6-9d98-f3183d52b6fc | note | RECORDS: Refer to Overall Project ITP for Written approvals QA.1 Geschke Quality Submission Register
aa69d209-017b-5f93-9bb1-1b33d73b0ca1 | note | ACCEPTANCE CRITERIA: Technical Data is marked with Approved For Construction
9c13e9d0-bcdb-5a90-84db-456a62e16074 | note | INSPECTION / TEST PROC: Document and Review
5bd2cf87-97e8-5464-81bc-f41ca9e01ed2 | note | INSPECTOR / APPROVER: Engineer. Geschke
1e1ac5ff-65f5-5599-b199-2784e0a16a50 | note | HOLD OR WITNESS POINT: Witness Point
ce2e386b-a491-443a-941d-a4a988139953 | checkpoint | 4. Approve shop drawings
04e6c10f-0ba1-5114-8a3a-07a5e0ed8a59 | note | STAGE / FREQUENCY: Prior to commencement
903ccd32-b86d-590c-acc2-a5f56e3f8ce1 | note | RECORDS: Approved Geschke Shop Drawings & QA.2 Geschke Drawing Register
2e2622e5-4b69-5f90-82b5-27aea3b358be | note | ACCEPTANCE CRITERIA: Drawings are marked with Approved For Construction
9319c94f-8f8f-585d-bd0a-e106f0fabf6b | note | INSPECTION / TEST PROC: Document and Review
ce245f92-c3cd-5a07-b888-d32fd644e6a7 | note | INSPECTOR / APPROVER: Engineer. Geschke
a1a4edd8-8574-5dc7-9c12-ff945d76e367 | note | HOLD OR WITNESS POINT: Witness Point
fcaedd18-56b3-46c6-a7b4-2642edd42847 | checkpoint | 5.01. Check set out - Works by Delta
07386669-0e84-5f0f-8c60-f91e81a6c1f2 | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
b34ba4f7-69d8-5a8e-b13a-f944b89358be | note | ACCEPTANCE CRITERIA: Set-out of pits is marked with pegs and alignment matches design layout
e6353a83-ae61-51e7-b8fd-672919b7ec24 | note | Height control point is marked within 40m of works area.
33afac11-9b12-5f5d-8bfd-2e37a885ada7 | note | All 'known' existing services have been potholed, marked using a riser 1m above ground and backfilled with sand.
5a1af02a-7da5-5551-bf32-6601ae0cae3b | note | INSPECTION / TEST PROC: Visual Inspection and Document
3c3d8b7f-2546-5305-843f-bdd05ce3c37e | note | INSPECTOR / APPROVER: Foreman. Delta
2e455527-8541-5ca9-8470-8533842ad26b | note | HOLD OR WITNESS POINT: Witness Point
b0578238-e5d1-426b-8b3a-6bc9d0363c8d | checkpoint | 5.02. Check excavations
2fa66e26-baa7-50e3-8d5a-ff5f0fb932df | note | STAGE / FREQUENCY: Prior to commencement / Once per grid
37cef734-2872-5d1c-822e-c050d2a5be5c | note | RECORDS: 'Before' Photographs
816a81a9-d437-56be-aed6-855e7f0e7e65 | note | ACCEPTANCE CRITERIA: Alignment commences at outlet and proceeds upstream
cc818ef2-b0cd-5fd2-a5e8-6c7ff9033555 | note | Minimum falls
61539ebe-852e-5913-93f5-258a4105e31c | note | Excavation alignment is outside of minimum clearances from above ground assets, below ground assets and boundaries or plan for excavation works or temporary works meets requirements within exclusion zone.
302afdb4-4238-54a6-8afc-f6defb9ede3f | note | INSPECTION / TEST PROC: Visual Inspection
decaeff5-d359-5bb2-be9c-938bf3cea074 | note | INSPECTOR / APPROVER: Foreman. LLB
7c50b054-00f2-5745-a4d5-58112fbf877d | note | HOLD OR WITNESS POINT: Witness Point
b34d1f6f-82ab-462f-82d8-5152e8d11c06 | checkpoint | 5.03. Approve Temporary Traffic Management Plan if trench crosses existing road, road reserve or footway
76456617-7de5-5396-8470-3942120fe706 | note | STAGE / FREQUENCY: Prior to commencement / Each TMP
635b03df-90fa-5af0-ace6-0b7775834ba0 | note | RECORDS: Copy of Consent and Traffic Management Plan
a1c10c1e-a51c-55a3-9952-e7383a3af8b1 | note | SPECIFICATION / STANDARD: ACOR Consultants Civil Specification Section 6.2.4
f26921f5-7b9f-5a4e-9658-e6d42f763996 | note | ACCEPTANCE CRITERIA: A copy of the consent for working in the Road Reserve and Temporary Traffic Management Plans approved by the relevant Statutory Officer
c27f28f0-a96a-5a25-9004-0b6794e1a7ae | note | INSPECTION / TEST PROC: Document and Review
09aa9777-2d50-52f7-9bc6-b937cd5aae54 | note | INSPECTOR / APPROVER: Contractors Authorised Representative. LLB
f03aa9ce-b5a4-5b37-8864-7ebcc4d09cf0 | note | HOLD OR WITNESS POINT: Hold Point
739df03c-557d-4edd-95af-d6c925d6ef5a | signoff | hold point
92e1d7a3-caf0-44e7-b6dd-4164f829e66c | checkpoint | 6. Check deliveries of materials
3d0b189f-ffd4-5353-b80f-fce5c4ba44c6 | note | STAGE / FREQUENCY: Each delivery
cefa0723-72d6-54d9-a3ed-83b1e34d307f | note | RECORDS: Delivery dockets name, signed and dated by Geschke
5c617623-d2a5-5767-a778-93034981aaff | note | ACCEPTANCE CRITERIA: Type and material supplied matches design
0f0d2e25-a3bc-5046-9523-650a0885ac3d | note | Grade or class matches design
ef5f3bb3-78d4-51eb-a898-7a6d5641e9c7 | note | Size and thickness matches design
d9c6d2e4-54ae-57f4-afda-05cdb6087752 | note | Supplied items are free of defect
1b505c11-49e2-5a4f-b582-52dfcc946fb8 | note | Marking, packaging and preservation is fit for storage / construction.
72d8b3b8-6b9b-57b4-b18e-5189cd82367f | note | INSPECTION / TEST PROC: Visual Inspection and Document
03205799-01b2-542c-8c22-0cde067bbff1 | note | INSPECTOR / APPROVER: Foreman. Geschke
1d7bcbb1-9daf-5faf-8a7e-20f417731377 | note | HOLD OR WITNESS POINT: Witness Point
a8809823-ac64-487c-904d-38c504bb15bf | checkpoint | 7.01. Check below ground pipework - pipes and fittings
e64a5c33-d5aa-5507-a38d-42a2c4360a6c | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
25432159-d1c7-5913-b640-e68df178d06e | note | RECORDS: 'During' Photographs & As-built Survey by Delta
9887345f-71cf-53db-996a-6e8ea31f3b69 | note | SPECIFICATION / STANDARD: AS 2566, AS 3500, AS 4130 and AS 5065
d6a05427-0a3d-565d-97bc-ab2185e1d247 | note | ACCEPTANCE CRITERIA: Joints, fittings and connections match design
cc4bf531-0df9-5986-b9ad-0095d9f67897 | note | Alignment and position are as drawn
4e94e25e-4e6b-5103-b0d9-a91f65e7c05a | note | INSPECTION / TEST PROC: Visual Inspection & Document and Review
8c73e0a5-e4ec-5317-8c23-1c90d0124070 | note | INSPECTOR / APPROVER: Foreman. Geschke
273109f9-30b7-52b0-a30e-e5cf5fb974a1 | note | HOLD OR WITNESS POINT: Hold Point
155ae6ea-c419-4c3f-92e0-2a9e8634815a | signoff | hold point
9a9bdd2e-f1bc-40bb-ac87-fd4079ced6db | checkpoint | 7.02. Check below ground pipework - high ends and flushing points
b07080c4-209e-5bcc-8813-bdb0eee31443 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
c4aa45f7-7ef5-5ee7-a2fe-e5765f104412 | note | ACCEPTANCE CRITERIA: Capped at surface level with hinged lid, cast iron box in concrete surround 300 x 300 x 150mm
c9551a4b-e62d-5fda-abcd-c343d570bd21 | note | INSPECTION / TEST PROC: Visual Inspection
c9862e6c-059d-58c1-bf82-0522527d7d0a | note | INSPECTOR / APPROVER: Foreman. Geschke
44021ef3-c21c-57da-9c29-ef5342d57852 | note | HOLD OR WITNESS POINT: Hold Point
7236e760-d73f-4587-84dd-6304c1172b88 | signoff | hold point
558b7c6f-79ae-4362-96ba-772a1ae2e0a9 | checkpoint | 7.03. Check below ground pipework - haunching, surrounding and encasing
e1411e0a-d955-5325-a424-a1f924980a26 | note | STAGE / FREQUENCY: Upon installation but prior to backfilling / Once per grid
70ccc299-07c9-539b-9928-772cab2812ab | note | RECORDS: Photograph
07c7deda-5d33-5c0e-ad95-863b305dcf6f | note | SPECIFICATION / STANDARD: AS 1289 3.6.1 ACOR Consultants Civil Specification Section 6.19.3
1f88779f-46b6-5458-a836-e65dedabb639 | note | ACCEPTANCE CRITERIA: Free draining granular material
a8b5b18c-f3e0-5cdc-9566-40aee4ac27dd | note | All faces of filter material in contact with topsoil or similar shall be covered in geotextile
980cf106-c8a8-55c9-87a0-5c34ebe1ef4a | note | Material used is as specified and approved.
d14372f4-2c16-5627-8788-becf4689c5af | note | INSPECTION / TEST PROC: Visual Inspection
6b504564-d36d-5cce-9847-b9ca923d8fea | note | INSPECTOR / APPROVER: Foreman. Geschke
1ef367a2-ce54-587b-b2d0-5adb6b84d0f3 | note | HOLD OR WITNESS POINT: Witness Point
a4cad869-4647-48f4-90ba-0bc57da002ac | checkpoint | 8. Check Completed Surface - Make Good
ebf34a87-1f60-537f-99a8-0709ae960a0e | note | STAGE / FREQUENCY: Prior to practical completion
0a736d4b-99c1-57d9-ae48-f39ea8414556 | note | RECORDS: 'Upon completion' Photographs
9a658535-f39d-58bb-8327-e9746583fb5b | note | ACCEPTANCE CRITERIA: Completed surface is free of obstruction/debris and matches finished levels for pipework less depth of works by others
7ee24ec9-9696-5819-8564-90e5c321bfdf | note | INSPECTION / TEST PROC: Visual Inspection and Document
e1c02c06-4860-5539-b8be-a195f07a83d3 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
5e0c4ab4-1df9-5f3e-9e15-3b7cedce3bd6 | note | HOLD OR WITNESS POINT:
55489d4b-cef4-5368-bd5f-2b8724f45b75 | note | HOLD OR WITNESS POINT: Hold Point
60973056-88d7-463e-a2e8-9524d79a90bb | signoff | hold point
a1dba6d6-d140-46ff-b3f1-1cbc2d86f2a6 | checkpoint | 9. Obtain 'as built' documents - Works by Delta
8ebf3cce-1959-589e-becf-d7310f5786c7 | note | STAGE / FREQUENCY: Prior to practical completion
d8dc0953-1e74-5c21-bf53-df7747e2ae46 | note | RECORDS: As built documents by Delta
3e655d90-736a-582f-aa8c-6c6bf3a0c3fe | note | ACCEPTANCE CRITERIA: Drawings are marked with As-Built
b82eabe1-0981-59e2-9bb1-2bd269373535 | note | INSPECTION / TEST PROC: Document and Review
521a970d-3fe6-56a1-a07a-f437ddad15a7 | note | INSPECTOR / APPROVER: Engineer. Delta
2c6132af-dd14-5209-acaf-0766d7fd5039 | note | HOLD OR WITNESS POINT: Witness Point
4f750be7-bca0-4ae7-b488-cc557f0b0bfb | checkpoint | 10. Obtain operating and maintenance manuals
7ef99b21-fc21-5107-a2dc-496d8b6c68d9 | note | STAGE / FREQUENCY: Prior to practical completion
4c99b825-39f9-5dd3-8ca7-3ca5489ef51c | note | RECORDS: Manuals
c7765700-27af-5a4f-b080-f7dad995cf94 | note | INSPECTION / TEST PROC: Document and Review
fb973eb6-f0ce-528a-814d-54cce15b209d | note | INSPECTOR / APPROVER: Engineer. Geschke
9ee74849-cb09-5d0e-8a9f-6909e0a91ae5 | note | HOLD OR WITNESS POINT: Witness Point
edd703ab-6972-4c59-a843-7e6c89972393 | checkpoint | 11. Obtain Guarantees
241eeae2-11a5-5894-938c-daf66e001963 | note | STAGE / FREQUENCY: Prior to practical completion
d4309055-72df-5c14-9b4c-94350d491a67 | note | RECORDS: Written guarantees
4199e4c0-268e-59b5-9175-188a85d0b047 | note | INSPECTION / TEST PROC: Document and Review
bb4bdca0-315c-5a4d-b1aa-d8c10c7be970 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
59c26532-81e5-5040-af48-9d298d085cd3 | note | HOLD OR WITNESS POINT: Witness Point
57faa3de-9e56-4d8e-8836-2f97ce854c2d | checkpoint | 12. Final commissioning & inspection
1e9d11c9-ea16-520e-b5b0-fbeef1b016e3 | note | STAGE / FREQUENCY: Prior to practical completion
dddeff82-73ca-5ae4-8291-5e34989fd565 | note | RECORDS: Final commissioning checklist
b8d14593-4b36-5e8a-92b6-2b96f9d6dc33 | note | INSPECTION / TEST PROC: Document and Review
89f64c3a-74ef-598d-8b94-6adc23f99a09 | note | INSPECTOR / APPROVER: Subcontractors Authorised Representative. Geschke
ae57d0c3-e3b7-5e62-b53d-3453743702f5 | note | HOLD OR WITNESS POINT: Witness Point
37e9f460-4493-403b-8890-614efacc9d83 | checklist | ITP - Trench Compaction - Various Services |  | ITP Trench Compaction - Various Services
34ef1dec-c6ef-44cb-ab17-3aff4fccef6e | checkpoint | 8.01 - To assist with the requirements of not only test results but ensure supervision to assess the competency of the construction methods a Level 1 GITA tester will be on hand to express an opinion on the compliance of the work practices. Geschke Plumbing are to compact in 150mm layers with Trench Pad Foot Roller.
9d30dc5c-8845-599b-9237-9d98ef008745 | note | STAGE / FREQUENCY: During compaction
606ff724-373c-5c72-ada4-5191ea10d556 | note | RECORDS: Written document by Level 1 GITA tester. Geschke mark-up of backfill type, test & observation location by grid
96d7214e-b330-5f63-a6a0-10f59d0accbc | note | SPECIFICATION / STANDARD: AS 3798-2007
46211d24-65be-53d0-8f07-6686a8c61f03 | note | ACCEPTANCE CRITERIA: Geschke are to compact in 150mm layers with Trench Pad Foot Roller
63d107f9-ea34-5a9c-866e-f901bed4d3b8 | note | INSPECTION / TEST PROC: Audit Activity
f5a630b2-3b1c-5985-beb2-bfd3bc12c9d7 | note | INSPECTOR / APPROVER: Geotechnical Testing Authority. Geschke
2a730bf0-a83b-5182-ae5f-c73bdf3f6da6 | note | HOLD OR WITNESS POINT: Witness Point
7b186ce5-143e-4881-a052-4f7c44ae3e64 | checkpoint | 8.02 - If Stab Sand is required for back fill this will be delivered 5% stab sand as per approved material. 5% stab sand on 100 slump poured straight from the shoot
e3bc2af5-612f-553d-a2e3-7b0116c60aa6 | note | STAGE / FREQUENCY: Prior to installation / Each pour.
94c5fc27-759f-5d52-b7f9-a46d56f63d99 | note | RECORDS: Geschke mark-up of backfill type, test & observation location by grid
0f736b4f-020a-5b83-b4dd-011201c0e1f4 | note | ACCEPTANCE CRITERIA: Stabilised sand mix meets 100 slump direct from concrete truck shoot
8b0513f4-d40c-5ab0-bba7-8d00fece066a | note | INSPECTION / TEST PROC: Document and Review
623283f8-c96c-5aff-b209-b2d720cf0434 | note | INSPECTOR / APPROVER: Foreman. Geschke.
87b3051a-3f37-55c6-ba36-aba24b4135d6 | note | HOLD OR WITNESS POINT: Witness Point
ee186a4b-a307-4179-972b-c85eb06f14db | checkpoint | 8.03 - Testing to be completed in backfilled zones with 1 test through 2 layers every 40 linear meters. We will test our trenching through 2 layers at finished height less topsoil depth. This test will be completed approx. every 40 linear meters.
5eeda234-09bd-59ac-9484-5f5cabf9d3bf | note | STAGE / FREQUENCY: Prior to completion / one test every 40 linear meters
8775b491-f6c3-5503-a9c0-010af70491c4 | note | RECORDS: Geschke mark-up of backfill type, test & observation location by grid
07114a8b-60ae-5573-a60d-460abeb22062 | note | SPECIFICATION / STANDARD: AS 1289.5.7.1 ACOR Consultants Civil Specification Section 6.12 & Table 8.1
61933593-b71a-5443-a7d1-119e775091e4 | note | ACCEPTANCE CRITERIA: Rapid HILF Compaction Testing shall meet or exceed 90% or an equivalent density of existing ground found adjacent to the trench alignment. This shall include one field nuclear density test through 2 layers or between 150 - 750mm below finished level every 40 linear meters.
a90d7312-d6e2-551c-9e33-01b24c66bcfd | note | INSPECTION / TEST PROC: Test Activity
e969ac16-4c2a-5783-a3a1-871f0eba4698 | note | INSPECTOR / APPROVER: Foreman. Geschke
9eb9ac85-4ce8-5471-9c5a-d8b84799c55a | note | HOLD OR WITNESS POINT: Witness Point
bed8fdaf-b754-4130-ad84-96b60bad9879 | checkpoint | 8.04 - Testing to be completed adjacent to work zone as required by digging back top soil layer and testing in ground. One test in existing ground adjacent to work zone through 2 layers at finished height less topsoil depth.
1df5bd95-da27-5f5c-b58c-20eb89121e0e | note | STAGE / FREQUENCY: Prior to completion / one test as required
381a2cb4-afc5-500d-a26c-739cf20fdfe5 | note | RECORDS: Geschke mark-up of backfill type, test & observation location by grid
3e2d1c1a-86c9-5ffb-b180-dd9153daf7a2 | note | SPECIFICATION / STANDARD: AS 1289.5.7.1 ACOR Consultants Civil Specification Section 6.12 & Table 8.1
139d9832-89f6-50ea-8c41-fb424835541d | note | INSPECTION / TEST PROC: Test Activity
b047034b-9135-5aa1-8482-7ea5bff672a9 | note | INSPECTOR / APPROVER: Foreman. Geschke
8b42a669-7559-5f35-a5eb-60426e240988 | note | HOLD OR WITNESS POINT: Witness Point
e636f31d-206d-434e-82b4-466b4f30e72f | checkpoint | 8.05 - Compaction Test Results. Test Results as per above test plan.
d35ddd64-2c9e-5fa2-9ee9-f67fdc496fcd | note | STAGE / FREQUENCY: Testing as per above
c1a8300c-ee1d-55ae-bc0b-3c2f640c9fc6 | note | RECORDS: Standard HILF Test Certificate
b942cb8c-3188-534f-86d0-8aaeed4f5cff | note | SPECIFICATION / STANDARD: AS 1289.5.7.1 ACOR Consultants Civil Specification Section 6.12 & Table 8.1
1bbc548c-7d87-5b2b-bbdd-feb1d6c26fc3 | note | ACCEPTANCE CRITERIA: Rapid HILF Compaction Testing shall meet or exceed 90% or an equivariant density of existing ground found in the trench alignment. This shall include one field nuclear density test through 2 layers or between 150 - 750mm below finished level every 40 linear meters.
d7cb6dc0-df05-5b09-8b9d-4ec0a01369ab | note | INSPECTION / TEST PROC: Document and Review
b8470bde-a1e9-51e1-824a-ecc3967e3328 | note | INSPECTOR / APPROVER: Foreman. Geschke.
a581c9d1-8c7d-5006-b743-cd8129042e8e | note | HOLD OR WITNESS POINT: Witness Point
6d25da24-94be-440a-9ffc-344d7ec4fbfb | checklist | Maintenance Inspection Report (Dec 2021) |  | Maintenance Inspection Report -
bca4ca5f-770d-407a-84a0-d1e717daadcf | section | Details
37015876-30c9-4c6a-a5ca-9445e05eb373 | checkpoint | Inspection Details - Pass once entered
173facdc-5be2-592c-9dca-311f47c6dc95 | textbox | Site Name
40901af8-a638-51ee-9df2-af2d3532c395 | textbox | Date
29fef049-c923-544c-9695-d318814cce6c | textbox | Site Address
affb2989-fcee-5343-860b-63abd716c219 | textbox | Contact
78b1558e-fdf1-5cf1-8d87-f87fd612724f | textbox | Contact Phone #
05cb14ea-140c-5710-80f2-80251b499281 | textbox | Inspection Task Location
c68a1683-13d4-5bc8-8b45-012ccf5a695e | textbox | Item/Equipment to be Inspected
575785df-065b-4c1b-9e3a-7762abb62ea9 | section | Inspection
b654b67d-d665-4d57-8049-d5fb73240a86 | checkpoint | Does installation comply with manufacturer's instructions
48fd428a-b7cc-41ca-bd65-742de18e0bf0 | checkpoint | Does the item function as it was designed to
a4bb0291-f3a7-46dc-95f4-3229b823c025 | checkpoint | Is there any reports from the customer of the item not working or any issues
8715ef90-2a7d-46a6-a73d-a0dec77f1c52 | checkpoint | Is the item free from damage or future damage
fe25b839-ebfd-4b4c-9f5f-4d395a755ee5 | checkpoint | Has all parts i.e strainers, sumps and pits been cleaned
fb1d6f53-19d6-45d5-a2be-77314eeee41f | checkpoint | Is there further maintenance or parts required to complete inspection
76058714-fdb9-49f3-8542-05561f8f34db | checkpoint | Photo taken and uploaded to report
1eb09e08-5f79-4fb5-af5f-0e64046d6ca4 | checkpoint | Item left in safe working order
2315ddef-4443-458f-b02e-55eee287a2cd | checkpoint | Inspection Completed
5346401c-be07-5e55-802e-5090670d0aea | textbox | Additional Comments
1ae8df5f-7d61-4c5d-8085-94aabd94dd4c | signoff | Click to Add Inspector's Signature
df1175e0-943d-4b9e-9924-9908f1257fcc | checklist | QA 4 - Installation Test Sheet (Waste, Vent, Downpipes etc.) |  | Installation Test Sheet (Waste, Vent, Downpipes etc)
d61eabd9-453b-4a8c-9990-44dcb6132c18 | checkpoint | Installation Test Sheet:
865002af-9860-5362-9d6b-38b8caddfe60 | textbox | Drawing No.:
acacc423-1213-52a2-970e-3d1726d30dc6 | textbox | Rev.:
ce9627b4-e916-477e-ac6b-465ac5f31364 | checkpoint | PIPE CLIP HANGERS
90114581-fb78-5d84-bbf8-30b21d6422ac | textbox | Details:
b0dd64c7-da11-5cca-9bc1-31080e76669a | textbox | Tester:
e2d14497-9223-513b-9821-f7a96a5988e3 | textbox | Date:
184e01b6-5c93-55ba-af16-154448289c0d | textbox | Notes:
d6d4c591-4615-486a-8030-f20a7b26838f | checkpoint | MATERIAL AND SIZE
7bc25c43-67e8-55db-9a6d-b43d87646cea | textbox | Details:
fef81cb1-f7eb-5b4c-bae9-2eafef9fb15d | textbox | Tester:
5c650540-710c-5ca1-b8a1-7b6c13e74aa0 | textbox | Date:
4f8368c6-91c2-5387-8f92-f8bd75e62cbc | textbox | Notes:
a2fd230e-8b15-4edf-ab42-df22605740b3 | checkpoint | ALIGNMENT
1a71d3f3-a7e0-5596-86f6-719f011221e9 | textbox | Details:
deb9a368-f303-5e14-a591-537f0d648f50 | textbox | Tester:
f36ce674-c811-55be-b610-c2662302e59f | textbox | Date:
e8f7e6a0-a4b3-5673-8bdd-bb5837d1f447 | textbox | Notes:
b798a096-30f0-4b3a-8b4e-71d66684ea77 | checkpoint | LABELLING AND IDENTIFICATION
a83e5c70-5ed7-5e22-bf93-92cb186e13ad | textbox | Details:
2e0d15a3-b329-56ed-8c7a-306ef1a16e21 | textbox | Tester:
469deb27-134b-57a0-aca2-80ebcb569b8f | textbox | Date:
08bee49c-54cd-5d88-9ebd-cf4bb16a7cfd | textbox | Notes:
9fe6537d-6a18-4617-b52a-c870abf9390a | checkpoint | JOINTING
d055a8b2-16cf-590d-bc01-3732c1d0b891 | textbox | Details:
fd7e4d23-bb83-549a-b4ac-bbed02409f77 | textbox | Tester:
3d0e76d1-d81b-5ba4-a5be-47db3e79d9bc | textbox | Date:
8121ded3-ee9c-55c9-b56b-8ed5c2864348 | textbox | Notes:
869bbfa9-8a55-41fc-a8fb-ae193d8786ed | checkpoint | PENETRATION SEALING
1e466e8b-56e2-56d7-873d-46bd2effe87c | textbox | Details:
f78ecc4c-ad94-5c09-aa27-644845e3f65e | textbox | Tester:
25966cb1-5a4d-5f5e-8859-449c048d2391 | textbox | Date:
a0208de0-7a50-5cbf-a649-e6832ee841c6 | textbox | Notes:
2492b675-3c47-4101-9340-b015d0d02fac | checkpoint | FIRE STOP COLLARS
f1697486-02a2-54e8-842b-87ceebcbf888 | textbox | Details:
545c2857-7062-5902-82ae-c562a1fcb50c | textbox | Tester:
e2e5e2e9-c81d-59ed-8b59-48e3df246717 | textbox | Date:
96c1b56b-7a63-5790-985b-334c3af240b0 | textbox | Notes:
ff9ef9b5-de1a-4cee-b153-a10af211142e | checkpoint | TESTING
0477ebe8-65b9-5373-855f-a7cafd7d4828 | textbox | Details:
961c7a09-0a98-53f4-a9c2-9fe68654ee0d | textbox | Tester:
89dc101e-f591-5564-a4f2-0c4ff59823fa | textbox | Date:
33e537ef-b0b1-563b-a4d7-5cf4f5d79c93 | textbox | Notes:
51b27625-c467-4115-88d4-e728948b9f13 | checkpoint | AUTHORITY INSPECTION (if applicable)
70559272-b336-57cd-9722-c6a5f99233f8 | textbox | Details:
7de6bd66-4993-5b2f-b300-36da446573bd | textbox | Tester:
34055e4c-449f-54a7-bae6-db7ccc4bc5d5 | textbox | Date:
664e3649-88c3-5c3c-bd05-53eec0a13f2f | textbox | Notes:
720b8a8a-b7b8-46bf-a305-37e962c7794d | checkpoint | AS BUILT INFORMATION UPDATED ONTO DRAWINGS
73344cee-7a33-5237-b505-2e20f80b5b4d | textbox | Details:
34b93872-4e37-5672-9fde-2b88c3cdc664 | textbox | Tester:
b1e37c52-2097-52ae-abdb-28527f31a4b2 | textbox | Date:
25c32bb1-a5ab-58fd-beae-177135eece3d | textbox | Notes:
b7b977a1-f7e9-43c4-a574-aa70a4dccf96 | checklist | QA 5 - Installation Test Sheet (Cold Water, Hot Water & Flusher Line) |  | Installation Test Sheet (Cold Water, Hot Water & Flusher Line)
b1a47ba6-d4a9-424b-a63c-069aca12bb94 | checkpoint | Installation Test Sheet:
6f331396-beda-5e0a-9e19-d3ebb950d6f4 | textbox | Drawing No.:
e951db47-ffa4-51f0-9fa2-e713659c6229 | textbox | Rev.:
8e83bedd-47b0-42b3-a11d-fc9e52cf3fa9 | checkpoint | PIPE CLIP HANGERS
ea29039e-6d80-575c-ae48-7e25ac694726 | textbox | Details:
87717eb5-5d6f-5190-8c95-9e1971edc4b5 | textbox | Tester:
8ee67267-7ad8-5b45-a08b-da85899ee548 | textbox | Date:
5c106275-034e-5cb5-bd0d-af217ea9ee65 | textbox | Notes:
e11c7348-6de1-4ee4-bbda-0c9e9416031c | checkpoint | MATERIAL AND SIZE
57ba1b18-5826-5b6a-9b6e-fd7f241b54a3 | textbox | Details:
4a5e2cdb-f879-5818-b4a6-37819fe517cc | textbox | Tester:
4a61ee21-327c-55a1-a438-d14afbebbeb3 | textbox | Date:
279dfeb9-5b55-5f58-bfa4-ec8985ae598f | textbox | Notes:
810aba50-326d-46f2-aa1c-8e2f72954f37 | checkpoint | ALIGNMENT
6b1ed9d6-61d3-559c-81bd-a194a6dc091e | textbox | Details:
521f9dd1-e004-5cba-9964-648614c42aec | textbox | Tester:
7bdcf999-524e-574a-9d42-34560dcc3658 | textbox | Date:
5c0605f3-043d-5869-bbb9-05688a1d4901 | textbox | Notes:
234ada13-ee8f-49be-9dd8-8034cc17d092 | checkpoint | LABELLING AND IDENTIFICATION
9d7d38f1-2c63-584a-afbf-401b6109fbc8 | textbox | Details:
f797c120-662b-58bc-a1b4-55ec59b77ca1 | textbox | Tester:
4e4596cd-6a16-50aa-a038-31bfa5e96eea | textbox | Date:
e5940198-3fb9-5bc2-b9a7-bb4022b1714f | textbox | Notes:
e6a16bb6-1346-4c09-a50f-d18020d608b5 | checkpoint | JOINTING
6c163469-68b9-5801-8936-c041ed040c1f | textbox | Details:
82f928a7-b23d-5bea-8b8a-9a2192c47e1a | textbox | Tester:
9de60ac4-c169-5b5b-9f29-8633ba371746 | textbox | Date:
64d7f69b-1827-5895-a0f6-43c2d993cbc4 | textbox | Notes:
1f097b79-471a-457e-9a81-aefbda99dff8 | checkpoint | PENETRATION SEALING
a8ac1159-25fb-563a-bcf1-936f76184795 | textbox | Details:
e610cb0a-74cd-55fd-9228-57d2ae723a05 | textbox | Tester:
e30e8c4c-b44b-5bc5-aaac-02754d9673b5 | textbox | Date:
ec48209e-bfc5-5339-9146-f98fa334a2e3 | textbox | Notes:
573e85db-e9f1-44bb-a56d-803e838cb449 | checkpoint | FIRE STOP COLLARS
b754b20f-5d85-5ebe-b521-fc6cdca55d7b | textbox | Details:
6fe7d69f-58e4-5851-825b-626c9ef2f7bf | textbox | Tester:
f3a6cd4c-8b40-5c2a-906d-69318231c54d | textbox | Date:
f5efc67c-23c5-5eab-a2f5-0ae27876257c | textbox | Notes:
010de0e2-e37a-4af4-accf-074b9dd92ffc | checkpoint | PRESSURE TESTING COMPLETED (QA6)
bab60c70-15da-50d1-b60b-c9dc33da82eb | textbox | Details:
0e943e78-5f01-5704-a3c5-ed407067193a | textbox | Tester:
e03a456b-de0b-573c-a1b3-71517e94da82 | textbox | Date:
68f2e5ca-15cd-5b9f-a98d-04ec0204a39e | textbox | Notes:
45a5dce1-bd81-4e9d-a9c2-d6179dce847a | checkpoint | AUTHORITY INSPECTION (if applicable)
20678877-92f9-5169-82dc-b6782c9dd1e6 | textbox | Details:
63437ab3-da4a-50c5-8aca-eac6c84bd173 | textbox | Tester:
a6ced86d-1ba9-59e5-aab8-b156724c042b | textbox | Date:
c3e35415-345f-56cc-a3ba-6b58f6a6fbac | textbox | Notes:
f7bf0e4b-fe3c-4021-ad41-9ab6e54884de | checkpoint | AS BUILT INFORMATION UPDATED ONTO DRAWINGS
d89f0364-9c94-5a93-a943-5f3076f67a12 | textbox | Details:
f147c560-df08-540d-893a-34450b7f725f | textbox | Tester:
23c0b22c-da18-5974-9978-15ab57970d68 | textbox | Date:
34654f08-ac5c-5f34-9623-6ee964aa78a9 | textbox | Notes:
5af7309c-8195-4e71-a2dd-f123252bfb17 | checklist | QA 6 - Quality Control Pressure Test Report |  | Quality Control Pressure Test Report
b6e5fcc8-a24f-4d60-b520-d6ee05cde3df | checkpoint | Quality Control Pressure Test Report:
93f18759-a806-57d3-bff0-694626d323f0 | textbox | Drawing No.:
c86540b6-3b82-5da3-857a-b0a71649c115 | textbox | Rev.:
67477a7a-75b7-5c83-8fa9-1407c523123d | button | Test: | Air,Water
a141cf9a-0ba8-5fae-86d7-1d5cedd2ed7f | textbox | Section
3c4989ed-a9ca-57a8-b8cd-7d2249592ea8 | textbox | From
84815884-8de1-5489-9265-98782147bcee | textbox | To
1bdb1070-9771-5f92-8c67-4d3df28277d0 | note | Specified System Working
f50addbd-3eeb-5175-bc39-07df27b75e11 | textbox | Pressure (KPA)
588ac93d-9cf8-5388-96c3-e5656b556a88 | textbox | Duration (HRS)
10c6b757-055b-5061-bcf9-94249b1d2438 | note | Specified System Test
04d5856e-02be-5fd5-afcf-b87949918712 | textbox | Pressure (KPA)
5d0797b2-557c-5c7a-b860-0cfe4601ed50 | textbox | Duration (HRS)
e9e1a39f-f929-4651-b265-aa2b67882a36 | checkpoint | 1st Reading
593de185-14d8-5bd7-b5d6-ae03385b3684 | textbox | Time
b162c9d2-e75f-5f2a-a6ba-1f035264a0bc | textbox | KPA
6ac6f08b-cdd7-5139-bebb-2eb5883863de | textbox | Ambient Temp
6fcfd78e-6157-4e1a-b671-f213d714b008 | checkpoint | 2nd Reading
7b448093-6638-54a9-aa3e-75b5e41c541f | textbox | Time
a25ccab4-f932-597a-be06-0d6e7ab8ad86 | textbox | KPA
fc025def-4427-5dcd-aa86-5cc301170147 | textbox | Ambient Temp
5bc0f09d-083a-4f8e-ab61-736e38aa1ed9 | checkpoint | Test Result - Passed?
8dde9df7-e8ed-5b07-8d2d-8f635a5c0426 | textbox | Repeat
0d68e8a6-6611-49f5-94d4-882f8756b766 | checkpoint | Sign Off
cedf0c99-ec01-5a89-85c2-4f9f6b9b95ec | textbox | Geschke Pty Ltd. Representative
7b20c8aa-10f1-5e64-bc28-59e40fe5c5c5 | textbox | Others Present
b5679c65-1f08-52be-8865-73d8868e11e9 | textbox | Date of Satisfactory Completion
a7eb4ba2-508d-4712-a0e1-ee49720b3525 | checklist | QA 6D - Quality Control Gas Regulation Test Report |  | QA 6D - Quality Control Gas Regulation Test Report
af117be9-e20a-4f24-8155-71fb48a189dd | checkpoint | Quality Control Gas Regulation Test Report:
85995cc7-88ee-5b77-9e18-66dd807efcb4 | textbox | Drawing No.
969133b6-2538-51e0-8f7a-12dc00ae655b | textbox | Rev:
f16e13ae-4711-4fa7-824a-7cc17472e004 | checkpoint | Test - Flowing inlet pressure to project
2969a14b-6634-5a0d-bbfd-ffefb38cc0f5 | textbox | Inlet Pipe and Size:
ee3dedef-0c64-5f98-a744-68bc84d0c954 | textbox | Spring range:
9089ea89-61d2-50dc-bef2-0deecc632bca | textbox | Orifice Size:
9b4885ce-16f4-5c4d-9ee2-0e5d0a9a77aa | textbox | Model:
e49b0afa-1ed9-471b-8fcb-24b65bd1f2e8 | checkpoint | Section
a444a5eb-f5f6-59b8-9d1d-9b491ecf7c81 | textbox | Section:
88641c21-d9cf-5cff-88b2-3b1831cadc03 | textbox | Pressure (KPA)
0527c65b-838a-4b7f-98c9-613bae92d2ab | checkpoint | Test upstream inlet pressure to regulation
89392d4f-34db-5023-a18f-201e11798c9a | textbox | Pressure (KPA)
c16f4d6f-ee30-47b4-923c-21bacd280472 | checkpoint | Test downstream out pressure to regulation
322f7cdb-7b1a-5f66-aa73-8802bc4a3325 | textbox | Pressure (KPA)
c9201a6c-6bc8-5702-af31-cea479771c5c | textbox | Duration (hrs)
9d57eccf-33d3-410b-9e26-ee726cb9bffc | checkpoint | Adjust out pressure KPA as stated on GPL shop drawings
65f7ffe3-9d70-565f-88a5-8a147cafa293 | textbox | Reading (KPA)
3ec5972b-6dd0-472d-9746-a32730753be4 | checkpoint | Confirm outlet KPA does not fluctuate more than 0.8KPA
79d9f55e-3100-5f5d-8197-c5688ed4417a | textbox | Repeat:
bf3e4448-c6b6-4fef-9a4b-8b8cf9e0ee4e | checkpoint | Sign Off
61e33637-a3ab-5980-a972-5998402ab0ef | textbox | Geschke Pty Ltd. Representative:
62d36b55-c337-5800-835b-560711d55445 | textbox | Others Present:
411f7ad2-ef3d-513f-897d-efec52b97133 | textbox | Date of Satisfactory Completion:
ae3261d4-088e-4d6c-b4ea-07edb4d1f131 | checklist | QA 7 - Commissioning Test Report |  | Commissioning Test Report
3480aa2c-84af-4344-8a57-011d4161fdd8 | checkpoint | Commissioning Test Report:
079a8bce-6b34-5b42-a051-b05dac576503 | textbox | Zone/Grid:
d2389e6f-6e8f-508c-893a-d1b0fad1e084 | textbox | Drawing No.:
25da6b86-5ef0-5dfd-849b-2661e3acf45a | textbox | Rev.:
ca0eef96-0f48-49e9-b582-535674ee6e5a | checkpoint | Item: FIXTURE OPERATION - Pans, Basins, Sinks, Other
88c06588-3046-5291-a55e-0ee355588e56 | note | Test:
246cedf0-7df4-567a-ae07-53af960d867e | note | Performance Test CL 2.20
ab33bc8a-637c-5b5c-9313-34e70e268a32 | note | Fill fixture with water remove plug
df9b1cbb-d394-5bd7-817c-2c01f138e6e5 | note | Test for:
83aec071-fbca-543b-a108-7611ac67f53d | note | Leaks
484111cb-3f7b-56d1-a5c8-fc6eb77864f5 | note | Loss of water
a87c34d6-4e30-50b8-8b6b-8ce5be1e1b83 | note | Seal in Trap
7746bfda-c826-5fd4-bfb4-e3880dc10ef1 | note | Induce siphonage in trap of adjacent fixture
789d924e-869e-5f38-b17b-2dba7b835238 | note | Complete draining of fixture
e0d1c951-c9e4-5ccc-b972-0ee1bb0d8625 | textbox | OK:
74e5720c-66f8-59ef-ac6f-6254a647a597 | textbox | Not OK:
8898e941-b059-42dc-ac2a-4c0089f6ffec | checkpoint | Item: Water Supply
edaf65db-fee6-56ec-91fa-f67df4ced910 | note | Test:
10f2e14c-93bb-5a6f-9a41-6c4e6f06db3b | note | Performance Test CL 2.20
270ddcbb-7962-5ab3-82bc-3e0a91b630f1 | note | Check for adequate water volume.
2c509e16-b210-5638-8aff-70ec957a8639 | note | Flush out pipework
e57ba660-c07d-5d8a-9da0-495f0cb56930 | note | Clean aerator
91413705-2d84-5cdc-b884-bc2e15cca717 | note | Water hammer
7defb458-48f6-575d-a696-f3c07194f157 | textbox | OK:
092100e8-8116-5623-ad0a-f4168e6fe10e | textbox | Not OK:
ecab8b24-c7f6-483d-a338-7e3781225b15 | checkpoint | Item: Flush Performance
0c2adc94-2ba9-56dd-ac41-812eee50284a | note | Test:
76de1069-004b-53fa-9245-75ec650fc9b2 | note | Performance Test
84a418f6-b97e-5050-9066-75fdb801becf | note | Check for:
45f38a8e-e8a7-549c-9a67-8a0fafda8d2b | note | Water Volume
b3aed500-0918-57de-84cd-a6a3db8e64d5 | note | Duration of flush
6c3595df-cf48-5803-8bc0-6aaa718abe21 | note | Flush out pipework
860bebb5-3f8f-5754-b867-687dc919aeb3 | note | Water hammer
951157ae-ca7f-5641-a37d-399f7bfc850a | textbox | OK:
cacda3b1-f456-5cf5-bd27-df4c3cb84db2 | textbox | Not OK:
55c0e1ea-8117-4807-9fe9-8e9a4ab458c2 | checkpoint | Other
756bf183-06e4-4509-a564-f0533a203803 | checklist | QA 8 - Below Ground Pipework Checklist - Fire |  | Below Ground Pipework Checklist - Fire
37e6c060-a374-43a6-a416-b8a37ec62534 | checkpoint | Principal Contractor Permits Issued
7c43304c-64d3-4619-9247-3f811c27b05c | checkpoint | Set out pits depths and trench runs.
a6cf7285-5217-58d1-be03-3b3cbf9cbeca | note | As per DRG#
11073322-0959-47d4-a3bd-14fd2c05a034 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
3c3037f2-320b-53ba-874b-0587c78a1eb7 | note | Spec#: AS3500
de1416e5-2e76-579a-b1fa-6b790b762c96 | note | MDPE SDR11 PE100 PN16
9941329b-2f6a-4225-aa4a-3ad9aa713490 | checkpoint | Bedding placement and compaction and material meets specification.
7fa5f524-8b9a-515f-ac34-2e4c5d6ade01 | note | Spec#: AS3500
70850a09-cd08-50e2-a0df-c252686f99d0 | note | Packing sand encased pipe
383e318b-4b29-4079-8a39-d636da9e72b7 | checkpoint | Jointing of pipes
28f0a228-c7de-5b83-afae-d8766f0189e9 | note | Electrofusion and/or Butt Welds
18d64471-fe2a-522a-8b26-b26c67695d34 | note | GPLQA16 form
0c555e18-570a-4a95-adbd-66f93dcc6eae | checkpoint | Connections to pits and existing services as per spec and Australian Standards
43f03d2e-c9a8-4e44-aa47-5dcd87ab91b3 | checkpoint | Hydrostatic tests are carried out as required.
77120e0e-2b8e-5b35-8b4e-2059e303aeb4 | note | GPL QA6 form completed
668cdf7f-a92e-5a7c-901e-1edce6ec2764 | note | Fire system tested to 1700 kpa regularly prior to finished surfaces installed. Independent fire test at completion.
351f1b8d-1e7a-40e7-a1b2-511a665c458d | checkpoint | Placement and compaction of backfill and material meets spec.
a4fbd417-cf16-594d-b252-872ec9db5c7b | note | Compacted crushed rock backfill 80% to 100% compaction
f2c021a2-31b4-55a9-b438-8ce1f9a05253 | note | Detectable marker tape
e763e870-a1d3-40f8-bc80-d59382d78149 | checkpoint | Temporary cover provided to open drain.
94107c4c-944e-4d43-8ccc-a17a0fd40079 | checkpoint | PVC/ Plastic caps to open ends
d4527b69-b75d-483a-b661-409d82bf4ede | checkpoint | As built information updated onto drawings
9facc06e-3249-5436-98e6-d607a305eea9 | note | Ongoing
825976e9-47d8-5bc3-b4b6-1034e06411b7 | note | To be provided
567593a6-dc13-44d7-811a-1bceb9818877 | checklist | QA 8 - Below Ground Pipework Checklist - Sewer |  | Below Ground Pipework Checklist - Sewer
b4465f27-0e63-441b-a28c-4a2dbcbc0477 | checkpoint | Principal Contractor Permits Issued
d0e6a7c5-2edf-4f9b-acd6-9e01c037426f | checkpoint | Set out pits depths and trench runs.
84a5dc5b-8134-5a78-bf33-32d141091e8e | note | As per DRG#
b30e0cda-e16a-482f-be40-4c7c1b4e86e1 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
dfed3bd9-04c4-59a0-adb3-bea67fe4cf85 | note | Spec#: AS3500
f1649ccf-43a8-5d48-8948-1462efa954ee | note | UPVC BEP Type ISO 14001
5c53bc53-e5e6-4b8d-b218-d563ed20cbe0 | checkpoint | Bedding placement and compaction and material meets specification.
ca560de6-2550-5690-9ce2-ad8ce5087ba4 | note | Spec#: AS3500
213e9e6e-527b-539d-8a5d-102301c2455d | note | 75mm Q-Minus Bedding and Encasement to top of pipe
f90a56ce-dc26-4301-abf1-37378c824fa8 | checkpoint | Laying and jointing of pipes R.Ls and falls
bff3222a-468d-5434-8feb-5364bbbbbc7d | note | PVC solvent welded
0d570978-d7f7-5f30-b197-f0bfcc5789ca | note | 1:60 fall
65b79130-80b7-5439-83b9-2efa4577a5c7 | note | AS3500
d1eb2dd9-ba27-5cde-a176-f9ff0aead355 | note | RLs as per hyd drgs
a86edb41-61f3-4164-9d5a-0365e55d429e | checkpoint | Connections to pits and existing services
98e7fb93-a512-4250-8991-d386d44bea25 | checkpoint | Hydrostatic tests are carried out as required.
8ce51020-efce-5c94-81ca-f7b8f65bc73e | button | Air or Water? | Water,Air
caaccab3-c27d-5dad-8390-7943baf540a0 | note | Inspected and recorded by Independent Certifier or PIC
3887eb38-5faa-4777-a570-164d178360b0 | checkpoint | Mirror tests are completed if required.
e6d60fd3-77ac-4c03-9bcf-62aee966db47 | checkpoint | Placement and compaction of backfill and material meets spec.
b1152238-c688-5105-bc9d-86d36e22bc37 | note | Compacted crushed rock backfill 80% to 100% compaction
28f8f7e9-245d-4b57-a5a2-a10cf3475af2 | checkpoint | Temporary cover provided to open drain.
d855105b-25d3-4985-bc31-63304ff71366 | checkpoint | PVC/ Plastic caps to open ends
854f53ca-520d-4982-aff1-a009a9986465 | checkpoint | As built information updated onto drawings
7e63fc08-0a35-5534-8386-bf3f76d9cab7 | note | Ongoing
55d9d7de-81ea-5f97-80c7-a7f19c145584 | note | To be provided
7f696d3b-f740-45a0-861a-6ccef9f44d23 | checklist | QA 8 - Below Ground Pipework Checklist - Water |  | Below Ground Pipework Checklist - Water
badda441-cd60-4a46-a30f-189bc42c75b0 | checkpoint | Principal Contractor Permits Issued
8849b50e-dfdb-4763-9f86-0e1d4fa9ac8c | checkpoint | Set out pits depths and trench runs.
6ba65634-2b39-5bd6-8946-8b42071015db | note | As per DRG#
a4631077-1e95-4b32-8436-9df58d70c789 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
d3f7dcb9-e05b-5bdf-9ddf-ad6e76fdf377 | note | Spec#: AS3500
57d1135c-7f60-51ba-bcc7-1c2e19728108 | note | MDPE SDR11 PE100 PN16
bd22c8d5-5856-42de-8c5f-a1e7229495ad | checkpoint | Bedding placement and compaction and material meets specification.
b5bf630a-f40f-54d1-afe8-5dad94038022 | note | Spec#: AS3500
c1442e7b-02e3-534f-9652-9ecd01944d5d | note | Packing sand encased pipe
dd1d346f-d05d-4cf3-8e7a-2cffd80ce61a | checkpoint | Jointing of pipes
e11efbfe-872b-55a0-ba76-672c4f269cb1 | note | Electrofusion and/or Butt Welds
67fb1fdb-3142-597c-87df-65f15aea06d0 | note | GPLQA16 form
25a6ad15-ecf3-42df-9ef0-3ccb8affedea | checkpoint | Connections to pits and existing services as per spec and Australian Standards
055e42df-a1ea-406b-8f54-937542819db0 | checkpoint | Hydrostatic tests are carried out as required.
3d907dbc-5fb2-5300-bd07-1c6de71c6921 | note | GPL QA6 form completed
9423463c-5a55-5251-9a23-d44fd2b06a82 | note | Water system tested to 1400 kpa regularly prior to finished surfaces are completed.
7a219ea4-d36d-4e32-a8ae-cce336876a3d | checkpoint | Placement and compaction of backfill and material meets spec.
ecd75ae1-c455-5b82-91a1-75d4e4221185 | note | Compacted crushed rock backfill 80% to 100% compaction
2db41911-7702-5da6-8a05-7a78293458fd | note | Detectable marker tape
22907b34-50a7-475e-8388-06d1104cc23b | checkpoint | Temporary cover provided to open drain.
3e5e756f-3b09-4710-82b0-eb39b40c256d | checkpoint | PVC/ Plastic caps to open ends
64bcf8fa-8350-474b-8585-dd5ea57ef7fd | checkpoint | As built information updated onto drawings
d35549b2-dc99-55ec-a0b8-18b4ae2e6c3f | note | Ongoing
9df1ecac-ca63-58f3-b52e-d771df092242 | note | To be provided
f55a1393-1b74-4180-9bcc-6ed79db05a89 | checklist | QA 8A - Grease Trap Checklist |  | Grease Trap Checklist
2507209e-fb3d-4d67-9480-0897c9d7f878 | checkpoint | Set out of pits.
d5ff3995-e8be-4d2f-9768-7fb5dfa12730 | checkpoint | Pipes and fittings comply with relevant Authority and Specification.
68ebc6d8-1b83-439c-a315-f111296780bf | checkpoint | Bedding placement and compaction and material meets specification.
076440f8-5936-440d-9f40-41746413d560 | checkpoint | Laying and jointing of pipes R.Ls and falls
a458e8ac-68c5-4c46-9f1d-44768906c94f | checkpoint | Connections to pits.
b4f57cc6-6544-4aff-ba27-88a06a1d77d5 | checkpoint | Baffle is in place.
07a4b5f8-4262-4662-9c18-09d7e5abcbe4 | checkpoint | Penetrations are patched and made watertight.
6166c1f3-9833-434f-8c70-eda7dbed10b3 | checkpoint | Suction line is installed as per spec.
ac5865ed-78ac-4e9b-8f99-976a65609a6f | checkpoint | Outlet pipework is installed as per spec.
8ed75a00-3e10-42b4-a929-19b8034cc1b6 | checkpoint | Vents are connected and terminated to comply with Authority and Specification.
8e40f722-014e-4f5d-ad5f-d9a27cd81d0d | checkpoint | As built information updated onto drawings
88ed8501-fa5c-46b7-8a4e-e4877f4aeb36 | checklist | QA 8B - Stormwater Drainage Inspection Report |  | Stormwater Drainage Inspection Report
cd5c6f6b-b403-42ec-a977-254c44e2b187 | checkpoint | Stormwater Drainage Inspection Report Details:
b2edab19-eec6-5769-93df-b0fdf4fadb8c | textbox | Spec No.:
89c1857a-7260-5507-b6d4-a3e17dac4489 | textbox | Drawing no.:
82bd6680-b6a7-5490-8210-dfebd3818708 | textbox | Zone:
4a6ff950-0344-48c5-ac0b-5f95044d966a | checkpoint | Pipe Lines
52746675-cc5b-5189-954b-48f612bc88f9 | textbox | Date started:
1fe587f6-99bf-5ea1-848f-aee38f956b0e | textbox | Drainage Line Number:
be30ead2-7921-5d4c-92fe-53237447d76f | button | Pipe Damaged? | No,Yes
310e832d-b404-55b5-8019-22833155682c | textbox | Size and Class
96fed7e8-d27a-51ac-bbed-206fe8fca394 | textbox | Jointing Required
ab8367fb-de63-56b4-bd2f-653211355f7a | note | Bedding and Haunching
4db992b9-fda7-5439-bde9-05098b5da2c8 | textbox | GPL - Initial/Date
cf99209a-d31d-5708-bcf4-7c71087bea59 | textbox | Builder - Initial/Date
5ab15e9d-4b74-5f9e-a8bc-cf27834aac9c | note | Backfill
d0f427fc-514f-5d44-b4ba-51b84bc6c3dc | textbox | GPL - Initial/Date
22fa0696-07a1-5203-a25f-636730c0cf21 | textbox | Builder - Initial/Date
0c6d3f7a-b512-588c-9261-c04a5f126b33 | textbox | Comments
6b42dbb3-d71d-5cb6-b2b5-27c2733bc57c | note | Final Sign Off (Initial & Date)
da734233-753f-5956-b6fb-9011bd4d72fc | textbox | GPL
cf3e8128-2b46-5dcd-a373-d30dc76f91f1 | textbox | Builder - Initial/Date
662abbc2-e6e2-58fc-b556-8e65dbc205e6 | textbox | HCC/CARDNO
ae332d74-68e9-4c27-a706-e32d55f5550b | checkpoint | Drainage Pits
e08b8f41-6985-506f-b5c7-879bec36342a | textbox | Date Installed:
e1657a52-8222-50ad-823d-365dbccf7a42 | textbox | Pit Number:
5609a519-4258-56ce-909d-16da29601e1f | textbox | Pit Base:
25f4f1c7-a28c-5845-8af9-ac9f14716974 | textbox | Step Irons - GPL Initial/Date
3f2c8db8-880a-5cf9-9e50-1ac2565a4a31 | textbox | Bedding - GPL Initial/Date
b977c42a-ce20-5bcc-913c-90806f026faf | note | Benching, Grouting and Patching
9aa0ef34-4b46-5ec1-8901-2d683d4040d3 | textbox | GPL - Initial/Date
ad04e10f-f1b9-5ade-a2ef-8eebb7dcd95c | textbox | Builder - Initial/Date
6ea074d7-16e7-5d44-9d75-ea41f9179ee0 | note | Placement of cover
5e9daa6b-cb30-5c72-840f-68fdf13cc0ab | textbox | GPL - Initial/Date
f538ed1d-b29f-5bfe-85be-65ebac6a23bb | textbox | Builder - Initial/Date
5b2fe081-6824-5a33-b778-799103dd4c2d | textbox | Comments
4cb97f6e-e085-53cd-9ef5-bc60d2a231ab | note | Final Sign Off (Initial & Date)
985f7af3-7f28-5d65-900f-bfe8edf07b6f | textbox | GPL
2807683a-bafa-5135-93be-9609c09b5d5b | textbox | Builder - Initial/Date
71392e2e-4065-54ab-833f-c7638b924811 | textbox | HCC/CARDNO
ac57d077-9950-4485-9b85-334c8c0d13b5 | checkpoint | Compaction Test Report No.
16e3239c-5a94-56fd-832a-e2c01b2f3fa6 | textbox | Compaction Test Report No.:
058ca05b-ac50-4d31-8da8-6d156b4e6d75 | checklist | QA 9 - Non-Conformance and Rectification Report |  | Non-Conformance and Rectification Report
28905a3a-82ab-4ff9-8938-6201f8dafd5f | checkpoint | Non-Conformance and Rectification Report Details:
076f25e6-897e-53ca-a01e-3aa3a32e9341 | textbox | Drawing No./Rev:
f8c837f3-920b-5123-b29a-3f1b66cb7316 | textbox | Zone or Grid:
bb22edce-b0da-5492-b28a-48e56e2634a7 | textbox | Issued To:
83a8350b-963a-5798-9fe4-b8dbab002b98 | textbox | Item Not Conforming
5242587e-b147-52d8-aaf7-184f26893d56 | textbox | Reason For Non-Conformance
5ba80e8f-ce1b-5019-8f30-63c1dabfc7cc | textbox | Consequences: Impact On Time, Cost Coordination Etc
e60424b6-0189-5d2e-81ad-6a6d4fe9e116 | textbox | Action Required:
0bd36f90-02ce-5bf8-8b19-f0a48afcf2c2 | textbox | Date:
717460af-a5de-5e08-899c-e70bb66b2787 | textbox | Rectification:
1501a6ac-1e60-5ffa-8b38-8040394fc77c | textbox | Date:
25fa2c9d-1936-5274-9191-a05b8ad6d1f5 | note | Note: Non-conformance register to be updated
c4a16092-5e9a-4755-b736-29677a17f424 | checklist | QA 11 - Equipment Calibration Register |  | Equipment Calibration Register
16dfcc29-2400-48e8-8993-a73c87edbce7 | checkpoint | 1
3abdc284-ee3a-56f9-876b-a3ab63ed4dbb | textbox | Equipment Type:
9047e86d-4eb1-5868-8f00-b7256b9aad11 | textbox | Manufacturer:
8cd93a7a-3db5-5045-be71-08196ee1ee6e | textbox | Model and Type:
172b5773-b8cb-545a-a7fd-6440ccb42719 | textbox | Serial No.:
476805ea-7d6d-5598-ac0f-b559bdc31111 | textbox | Next Service Due:
2b694811-2618-4e70-b1f9-d93ab02049c6 | checkpoint | 2
821d9165-e62c-5b93-9ca3-4938ba9f3bbb | textbox | Equipment Type:
538940d8-b279-5abb-82a6-66663892b688 | textbox | Manufacturer:
1f84b5c6-b94b-5d8b-b9cf-c7ab08de5988 | textbox | Model and Type:
b776f94e-b665-5ad9-bb0b-2088be79ac98 | textbox | Serial No.:
ffe9719f-0596-5e1b-978f-882d556a929f | textbox | Next Service Due:
e159f171-2e24-4685-b398-af241ef0c36f | checkpoint | 3
8a56bb03-8b02-5ae2-9e86-da8479067aca | textbox | Equipment Type:
16d3e595-9b0e-5e85-a66c-910248d2eea0 | textbox | Manufacturer:
5e743a6e-4241-5701-9204-9a7212f923f9 | textbox | Model and Type:
d7e29e40-368d-5320-8684-89e99f05d804 | textbox | Serial No.:
c12aa48f-065f-5c9d-be4d-8440956ef34d | textbox | Next Service Due:
8a16fbec-35ce-4dd0-8356-2029aff21b7c | checkpoint | 4
0ede1325-d450-55b9-bd6f-ce0b1b94e778 | textbox | Equipment Type:
968c2d13-9aba-5e3f-9276-8b1cd29209a1 | textbox | Manufacturer:
c3aa9db6-1da1-5d49-af8e-4b5ab6feca53 | textbox | Model and Type:
835a4956-5c19-5fa4-9b1b-daa458b290cb | textbox | Serial No.:
a5e6a497-71e7-5b69-b962-d389e14cce39 | textbox | Next Service Due:
e9ed66d0-0518-454f-99f3-2e168d474187 | checkpoint | 5
601574bd-e5d7-5795-a8ed-bcf4808fc562 | textbox | Equipment Type:
9b4b7fbd-fd1b-5583-8239-288f7d83f517 | textbox | Manufacturer:
1502b231-9e59-5246-ad15-25c587344eaa | textbox | Model and Type:
c9943076-fe95-5a02-9dfb-5bf62423632e | textbox | Serial No.:
f7a52ce5-0fb6-5479-a21a-cda7b3788e46 | textbox | Next Service Due:
66af078f-eff6-464f-925e-1de62bb14b11 | checkpoint | 6
6cde2e03-431d-5c58-ae00-a43e097542d5 | textbox | Equipment Type:
1c104ed3-d434-5443-b4f7-428eb3f4a5d5 | textbox | Manufacturer:
69520c67-32dd-5a2d-8902-b76773ec0160 | textbox | Model and Type:
03a2dd5c-6a5a-5f4a-be3b-03125cef2980 | textbox | Serial No.:
87823f58-c997-5cdd-b997-95f161c74717 | textbox | Next Service Due:
db92014d-d87e-4d78-88e3-a6a6f501b7c5 | checkpoint | 7
1ac5021d-a160-5dcd-b14f-0d415dbc6967 | textbox | Equipment Type:
0bb2c153-1663-5c1a-abd4-c53199c1b9e2 | textbox | Manufacturer:
099c9ffa-a334-51c4-95e3-28c29ce0758a | textbox | Model and Type:
71a6c865-7453-51d2-a437-1ad2f087e34e | textbox | Serial No.:
de96b63b-4297-54f8-b0e6-e1d2cdd7766b | textbox | Next Service Due:
e7886cfc-10ce-44ba-a573-335dda096144 | checkpoint | 8
c55c262e-9200-5967-b9d4-f0cc4e944d30 | textbox | Equipment Type:
7c1d9e4f-9332-52fa-87eb-722e764d2a5a | textbox | Manufacturer:
131c4144-a0e4-54b8-b113-196354c44d08 | textbox | Model and Type:
c04df94a-1f4c-5dd9-b415-136d2c51003d | textbox | Serial No.:
4ca322aa-a07d-58d7-8410-7bb68b544467 | textbox | Next Service Due:
591738e9-6e68-4e0e-b701-0e8fc6354063 | checkpoint | 9
184807b0-e596-50f5-9210-5ab01c8823cb | textbox | Equipment Type:
cb938d78-4f3e-5a9d-9b8f-af752aee248b | textbox | Manufacturer:
d466fcd1-a963-5a63-8b94-78a239279022 | textbox | Model and Type:
f523bfbd-30ab-534d-b81e-d4c7f8783715 | textbox | Serial No.:
207576ee-8f04-5fe0-ad2e-3639d6e1d266 | textbox | Next Service Due:
962f6eef-f45b-4124-ada9-6a6a99d8e1f3 | checkpoint | 10
335c5ef2-71cd-55a9-8178-b6b60c065dc1 | textbox | Equipment Type:
bbdd2519-b99d-5067-87b4-d3a93a01bd27 | textbox | Manufacturer:
b875d342-d485-545a-b731-f97da9cfdbc1 | textbox | Model and Type:
a1c4c4c6-7983-5d67-ad58-af962b9598be | textbox | Serial No.:
388877d3-9410-5153-bb67-6d648dec9d77 | textbox | Next Service Due:
dbfca4d4-2fe0-4dfc-9b58-ab4838c90877 | checklist | QA 15 - Pre Cast Slab Penetration Placement Checklist |  | Pre Cast Slab Penetration Placement Checklist
1dda8a95-ac4e-42be-8cbe-7462bf2a8dd0 | checkpoint | Pre Cast Slab Penetration Placement Details:
85d7458e-b722-5112-a8f5-5bb7c9cd8810 | textbox | Drawing No. / Rev:
6d2f206b-f8bc-53dc-aede-0504c26567c9 | textbox | Slab No.
b4c8be4b-6dc2-55a1-851e-25af0d269b39 | textbox | Total: Sewer - waste penetrations
50a28ec4-8451-5d62-b6d2-98570a667ae4 | textbox | Total: Stormwater penetrations
852fbf58-4c95-513c-aafb-a2ca2b89ac20 | textbox | Total: Water
9c6cc596-4e9a-563f-aa08-3aa5bf04f26a | textbox | Other:
fd2caaae-d5f2-4dca-8df9-c8943ec683cc | checkpoint | Geschke Representative Sign Off
fa4f9484-f195-4bf6-81d9-9020a9d84b49 | signoff | Request Sign Off
8ee917a6-5576-4427-b1e2-30b0f8168b46 | checkpoint | Construction Company Representative Sign Off
359ef188-5e2d-490f-ba52-e1145431a3da | signoff | Request Sign Off
37255df6-4878-4a78-9bbd-6319ae3bae59 | checklist | QA 16 - PE Electrofusion Welding - Field Operational Sheet |  | QA 16 - PE Electrofusion Welding - Field Operational Sheet
188308ca-c45f-4aa1-a844-aac5d264d74d | checkpoint | Operator Details
d8cae2d2-e13e-5f03-8382-6671628f0a14 | textbox | Name
58961c6f-d0cc-5b99-a336-26f08a1dc5ca | textbox | ID No.
119d65be-ab30-56ab-bcf0-d1ee6d64275d | textbox | Company
63474602-563a-547a-a98e-6792c7dfa054 | textbox | Address
0c5b236f-cb77-4d96-aca6-5f5be281173f | checkpoint | Welding Machine Details
550e3e70-0c63-502a-8ffe-061498aae6e9 | textbox | Manufacturer
b61e8599-1ae4-5526-8e36-e3dd782fbdfc | textbox | Type/Model
d1f9601d-7e3d-51b9-8cd9-31a4dca5909d | textbox | Serial Number
0d974315-6848-5eb3-a017-c0a509b47900 | textbox | Year Built
744454fb-c618-4148-84e0-f24f4f12c0a8 | checkpoint | Actual Pipe Size
e2e75a5a-dd30-542c-809e-4a3200d706aa | textbox | Type
df9d9b5b-8fc9-57e7-92b8-e5f7a341658c | textbox | Brand
c20072f4-191f-5341-83fc-29949f217d12 | textbox | En
2fcba489-7283-5f42-9bb2-fd377b9d1e6e | textbox | OD
3a9a0978-ec44-5acd-82ef-39f6443855f2 | textbox | Ovality %
d39a0bb6-0ad6-4190-8ad5-100d3c1b5c27 | checkpoint | Fitting Data
0dac2f5e-63c4-5082-91cb-3d2b8d4b2ece | textbox | Brand
97c997a4-e8ff-5f41-b6e2-d9de2a44eff7 | textbox | Type (Coupling, Tee, Reducer etc.)
f4cc372c-79f9-473f-b0bb-61da7f9cff86 | checkpoint | Unit Setting
4e88ab79-fd1e-58da-b929-efa734ac7032 | textbox | Manual
3a9ce9ca-8e34-5abf-9908-980d48291449 | textbox | Automatic
be00b0d8-211c-4074-86e0-5ee337a1c93e | checkpoint | Preparation
17b7dff0-9798-51a3-addc-0a41f1014882 | textbox | Cleaned and Peeled
80a665cc-a914-5791-87fa-e40090e8a93e | textbox | Pipe/Fitting Clamped
736b1dca-0d4a-4a62-a396-86f9853ffe06 | checkpoint | Welding Times
ef5e37b3-10f6-5391-a603-6a95f9703d26 | textbox | Joining Seconds
ed7efd5f-1217-53bf-b967-f0c3a6b0f169 | textbox | Cooling Minutes
7ff17f4f-b491-4611-a86b-6603947c581f | checkpoint | Conditions
18f621e4-09ac-5fa5-ab94-0543282e2acd | textbox | Ambient Temp
77327db9-54e1-512f-8bef-6fec519d9079 | textbox | Weather
680f706d-cb79-5f89-8e40-c5069955762f | textbox | Preventive Measures
4787a8c4-386e-4491-aac9-6bc91d0143e6 | checkpoint | Power
2a8a5de2-2d03-5de6-b8f1-5b2bc4801734 | textbox | Mains
b22b45e0-71d6-568d-8750-eb7f44da0651 | textbox | Gen Set
edc827c8-4b1a-418d-b792-ed7dfed405e7 | checkpoint | Operator Sign Off
4aa57c15-9c2a-439a-8745-7fe5a7f12dcb | checklist | QA 17 - Water Meter Accuracy Test |  | Water Meter Accuracy Test
9523f5dd-a89e-45a3-b5d8-11b6c4aae213 | checkpoint | Water Meter Accuracy Test Details:
17d4521c-5617-5442-9f61-063337927931 | textbox | Date:
9566afd9-8857-55ce-8bd6-565edb40f222 | textbox | Project:
51f20310-0b39-597e-9efa-695add12309a | textbox | Location of Water Meter:
7aa6de4b-c34f-5a8f-a3cf-de33cb61c75d | textbox | ID Number of Water Meter:
65de26e2-2f81-5b0e-8521-d9ef3a6a77bd | textbox | Model & Manufacturer:
d6fcd7fb-e268-5736-839c-b90f678bd0ff | textbox | Current Counter Reading:
40172f9c-c617-5c81-89af-0c397adb38ec | textbox | Zone/Appliances to be Metered:
bb0d0586-43eb-5e6b-9e50-213a984e1cc5 | textbox | Pulse Rate:
51d05efc-c6ee-40e8-a20e-73f9e6a98871 | checkpoint | Measurement Apparatus
20447cf9-0f2a-5f79-ae83-1a220b7d4d64 | tickbox | Bucket
64a87d70-01b7-5d14-92b0-e7d2fe4025a8 | textbox | Bucket Size
1512ae7a-2fae-5e58-8a7f-f4c213470f5b | tickbox | Water Meter
5faec01b-dc5a-57f0-9683-06bd55ccb106 | textbox | Calibrated Date:
fe7b0cd0-f6a0-5608-a4bd-93691d800a7c | textbox | Other
6ce2fd7d-ca51-459f-b0d6-2ee9ab318c04 | checkpoint | Measurement Method
f75831ac-cd95-5b89-8e65-78aafd0ec51b | note | Isolate all fixings
1143504c-04f5-5a71-948d-0204897e7ea7 | note | Place bucket at outlet of fixture and fill
708f5541-b02a-5e8b-8e50-b78678f8e8f0 | note | Fill in completed counter reading and minus "current reading" to measure accuracy
3df2ce1d-56ed-55f6-80eb-a49a631a4a01 | textbox | Completed Counter Reading:
37e2b36e-4c8b-5b16-b093-37a7977d1af7 | note | Accuracy
5a37c326-1fd6-5e4e-9f66-fa38cd14d64c | textbox | OK
94e33a47-4e9e-535a-a627-217084bf5098 | textbox | FAILED
4021003d-094f-5c03-a0d4-fbc6561ab88a | note | Replace Counter and Re-Test
30d8ee2b-0bb8-53d5-aff2-e29ed4acf743 | textbox | OK
1e9e8082-9b90-5eb7-83d0-ac0fe4bcb145 | textbox | FAILED
d5aa29a9-f6ac-49c2-84c7-dbc78a972855 | checkpoint | Pulse Check
56882a99-8e4c-5dca-8615-0d8adde0fbe5 | note | Method:
15b9f849-3a91-5465-969d-ec613b02a918 | note | Connect multimeter to the 2x wire connection points on pulse kit and set multimeter OHMS
fe70a518-6c44-508e-bb65-dae0f17b83dd | note | Turn a fixture on and wait for pulse reading on multimeter, then stop flow immediately
5b9bf237-301c-5394-9818-65ca836e4be9 | note | Measure bucket contents:
2d62a02e-5216-5770-906b-6a4dae9085fd | textbox | Pulse Registered:
0fc2a96c-90fb-554f-97ac-2cae2d77b207 | note | No Pulse - Install new pulse kit and repeat process
a49a9471-67e4-5dbf-a1db-550be4dd0acf | note | If Pulse registered OK
96830e81-0fed-5eab-98d3-3382bfceaac2 | textbox | Pulse Accuracy:
569b3d3b-6269-542a-a296-9fff41f5d284 | note | (Bucket contents match spec at top of page)
a05c0113-0af7-5ca1-adb1-752b58297a74 | note | Failed - Install new pulse kit and repeat process
19a58da7-5452-4d54-b1c3-477226acb7a0 | checkpoint | Sign Off
f930794e-b356-5012-8495-3b0083e9bac1 | textbox | Name - Geschke Representative
82c3a546-451b-431a-8e86-93e87ed2da15 | signoff | Signature - Geschke Representative
305e5800-59e5-4441-8147-70165640d06d | checklist | QA 18 - Gasket Installation |  | QA 18 - Gasket Installation
f6eed089-81cd-45ff-bd6c-c9082f2f196f | checkpoint | Gasket Installation:
de28023e-f296-5234-811b-65996862153c | textbox | Location/Identification:
1b169728-3da9-5de6-a659-b6f60e68fb6d | textbox | Nominal Bolt Size:
346bdd67-fdc5-57e3-9bbc-38bcd11a191d | textbox | Gasket Contact Surface Finish on Flange:
9dbe5284-1ffa-5c46-aa04-44be846df39c | textbox | Lubricant used:
26e8f390-5bf8-515d-992f-3391c1808833 | note | 1. Galvanised nuts and bolts must use good quality lubricating oil on threads
d6906c1c-4181-5233-b5d3-67dac3c699a0 | note | 2. Below Ground Galvanised nuts and bolts must denzo and plastic wrap full flange and cover bolts
31227d5f-47b4-5369-bdc4-790c525e0d4c | note | 3. Stainless steel nuts and bolts must use anti seize / molybond on threads must return 24 hrs later to tighten in sequence and required torque
9c2f7f77-fd6b-5c5e-b83c-26769eb29559 | note | 4. Galvanised nuts and bolts on stainless steel flanges / backing rings - Thinsulators (insulating top hats) or insulating washer with thin PE sleeve must be used, and complete flange must be denzo wrapped with plastic protection
190778cc-96b0-52e6-9f4d-21545b21033d | note | 5. Stainless Steel nuts and bolts on galvanised steel flanges / backing rings - Thinsulators (insulating top hats) or insulating washer with thin PE sleeve must be used, and complete flange must be denzo wrapped with plastic protection
a7231c64-2b60-5c90-b9a0-7203fd364181 | note | 6. Zinc bolts, nuts and washers rust when used externally use galvanised
6e5b27a5-9c5d-451f-97b4-20f6d5df2b38 | checkpoint | Visually examine and clean flanges, bolts, nuts and washers. Replace components if necessary. Alignment of flange faces is very important and maintain support of the flange, pipework and valve at all times
922ec6a7-3437-453b-86ab-7b432b56b371 | checkpoint | Lubricate bolts, nuts AND flange surface AROUND BOLT HOLES, not on flange/gasket surface, or use hardened steel washers. Use anti-seize on stainless steel threads and nuts or on galvanised bolts and nuts lightly oil with good quality lubricating oil. Insert bolts in locations 1 to 4 as indicated in the below diagrams.
a51b6cdb-0544-4222-b838-7b82be134fe3 | checkpoint | Install new gasket. DO NOT REUSE OLD GASKET, OR USE MULTIPLE GASKETS. Gaskets for water applications must be EPDM potable water gasket PN16 type. Gaskets for gas need to be AGA and GPL approved
82023ce8-e2f6-409b-a1fb-4753f472e097 | checkpoint | Number bolts in cross-pattern sequence according to the appropriate sketch below with a marker pen, black or white
5593961d-a4a4-42d3-94e6-9062e926335f | checkpoint | IMPORTANT! HAND TIGHTEN; then PRE-TIGHTEN BOLTS to 7Nm torque, but DO NOT EXCEED 20% of Target Torque. Target torque is required to be supplied by Gasket manufacturer / supplier seek from GPL foreman
002ff6c2-b5df-4fa0-b16a-b4c237067fa5 | checkpoint | Check gap for uniformity.
1cc91cb7-ac9c-4f40-8472-10707b713bdc | checkpoint | Use the appropriate cross-pattern tightening sequence in the sketch below for Rounds 1,2 and 3 and/or Round 4 (each sequence constitutes a Round)
57196e94-77e3-4bf6-8b46-92b6511f34d4 | checkpoint | Final Torque
b07652d1-118f-52d7-8205-04cecf710424 | textbox | Final torque*: |  |  | (Nm)
49aad949-843a-5496-9bd9-a4e9f0bd3ab2 | note | * Refer to gasket manufacturer spec with torque chart on next page and GPL advice
d881fa75-8a29-55e6-90be-2367878e9764 | note | Lubricate, Hand Tighten, Pre-Tighten bolts (5% of final torque) (as mentioned in item 5 above)
abeba1a6-805e-5929-b339-be6c50e2dd03 | textbox | Round 1 Tighten to: |  |  | (Nm)
32021e4c-b9b4-561d-b7b5-eea004288985 | textbox | Round 2 Tighten to: |  |  | (Nm)
0d384c9e-6587-580f-b80e-a3e144a5d9ba | textbox | Round 3 Tighten to: |  |  | (Nm)
5a5e925e-cdb6-5ee0-b349-107b6363f0c3 | note | Check gap around the circumference between each of these rounds, measured at every other bolt. If the gap is not reasonably uniform around the circumference, make the appropriate adjustments be selective bolt tightening before proceeding.
8a1f1d1e-47c1-5977-8efb-93ec65a81ae3 | note | Final Rotational Round 100% of Final Torque (same as Round 3 or 4 above). Use ROTATIONAL, clockwise tightening sequence starting with Bolt No.1, for one complete round and continue by selective bolt tightening before proceeding.
87454ad3-ab43-5db2-86ab-d6dd9bb89fc1 | note | Short-term bolt preload loss can occur between four to twenty-four hours after initial tightening due to bolt relaxation. Consider retightening to help recover this loss.
0378cf3b-47cc-50a9-a553-55a65f792e70 | dropdown | Tightening Method Used: | Hydraulic Torque Wrench, Impact Wrench, Manual Torque Wrench, Other,Hand Wrench
97dd0e06-22d3-5da5-ab75-182b9c4fbe26 | textbox | Other:
72c3de42-f702-5d7a-b9f9-66aca63c1885 | textbox | Where was torque information provided from:
7868f9f9-dae3-530c-bb29-ac85ac4b1cd7 | textbox | Joint Assembler Name:
59a573b6-49ea-419e-b65e-40b0dfc60df3 | signoff | Joint Assembler Signature
7320b64f-7f9d-4be2-b3c8-8fc4762a9ab8 | checklist | QA 19 - Service Cross Connection Check List Report |  | Service Cross Connection Check List Report
249ea096-ba85-415f-aca1-026d8f36d0f4 | checkpoint | Service Cross Connection Check List Report Details:
54f1a585-917a-5138-8a2a-297ad596b466 | textbox | Zone/Grid:
8da098b0-a81a-5fff-bcce-e2a68142eab1 | textbox | Drawing No.:
6b9717a9-3cd7-51e0-8ce5-6368ccaf4aa6 | textbox | Rev:
056ac593-081e-47fa-8f0f-379c0341c407 | checkpoint | Service to be tested
df98d547-9241-5c92-9c12-1606b910001f | note | Isolation of potable supply in general.
e9e9793a-64d8-4780-9d2e-d964067f11c0 | checkpoint | Potable Water Supply
050c0f4a-116e-5918-be18-058fd7259241 | note | Confirmation of service isolation at all fixtures.
09ce6b2f-be88-5006-94d8-8df574b8509a | note | Keep potable water turned off.
b2a91258-7478-4fcc-8cdc-bc0c1f7e20e4 | checkpoint | Non Potable Supply
6a03d777-41ef-5c26-b184-7a4b28ac700c | note | Confirmation of water flow for non potable water supply at each non potable fixture while potable is still isolated.
b802b8c8-9c95-48b3-be1a-9d13263a615f | checkpoint | Turn potable back on
826eb87b-d25d-535f-9333-7106ecadc82c | note | Potable back on
8bb04af1-41c9-4b5e-9749-dc11214b76fe | checkpoint | Non potable supply
6737e08e-76f8-55fd-9870-5c222fccc30e | note | Isolate non potable water flow and prove that each non potable fixture has no water flow.
e6b8b4ea-7c39-40ed-a8ae-7da945beeb06 | checkpoint | Potable Supply
c7ab190c-14a3-517e-860c-e53e8092af52 | note | Check all fixtures that receive potable water are still getting potable water.
0a80610f-9b40-4a0c-866f-3e7dc30a7683 | checkpoint | Pipe Identification
74eca2e2-a352-564f-a89d-4b39ee359134 | note | Confirm recycled water piping is identified by colour and labelling.
91e67532-1398-4931-8ab0-6d69c06967bd | checkpoint | Other
9c09f732-eba1-49be-92cb-7304808f305b | checklist | QA 20 - Fire Hose Reel (FHR) Test Report |  | Fire Hose Reel (FHR) Test Report
0cc18b20-8615-4472-a50b-d8356fdc9dac | checkpoint | Fire Hose Reel (FHR) Test Report:
1582ef4c-cf45-557d-b1b6-d5e427ef8545 | textbox | Location of FHR:
dfab6619-ef28-51a8-a58a-156a8b2e834e | textbox | ID Number of FHR (If applicable):
f0d878b8-1a75-5dbd-9f0c-3800d2496a75 | textbox | Manufacturer:
5062ec38-60a3-544f-bff6-8dc5db5a7d58 | textbox | Model:
eca17d0d-8cf8-50d6-a661-4c8c3bdcf2ab | textbox | Size:
c78f3a58-2faf-5330-96e5-4024ef40ee69 | note | Aust. Standard Flow Rate: 0.33 LPS @ 210-230 KPA
a663fa3b-f3db-5152-ade3-c30dd440135f | button | Measurement Apparatus: | Bucket
4887d9e3-c558-5ca7-8c8c-259f14e45a85 | textbox | Bucket Size:
d0a6210c-4cc7-5c73-9804-f342a889e1c8 | note | Measurement Method:
a4efe093-984a-54d6-9f43-390b956b33fa | note | 1. Connect pressure gauge and outlet to end of hose
93ad9e5f-2b1a-504c-842a-8c81438f7651 | note | 2. Note static pressure reading on gauge
22006bc9-45e3-5791-b45c-e4257bf3389e | note | 3. Place bucket at outlet of FHR and fill
14672a4a-b3dd-4c06-b9d8-6714ae895df7 | checkpoint | Reading
a69ef4b7-fd9e-59b8-a398-2f7534dcc91c | note | 3.3L
a77a8d77-b5d0-52b6-afc8-411a851147ca | textbox | TIME (sec)
7637b132-0687-514f-9893-620240055c62 | textbox | Flow Pressure:
5b414ab3-7f5f-54f2-9203-756382640d38 | note | 6.6L
2b24968a-ed82-5ecb-b8be-a594d942ffb9 | textbox | TIME (sec)
aee76d79-cccc-5c10-aa30-1680dd7ba7c8 | textbox | Flow Pressure:
f641ed8b-f58b-560f-bc9d-fb27b277573a | note | 9.9L
26706552-a79b-5dfe-b2c3-163d939973b2 | textbox | TIME (sec)
1a3a1552-22c7-582e-915d-7bc26fdae61b | textbox | Flow Pressure:
bc302b5c-0a3b-45b7-8e08-eeb8e981c5e0 | checkpoint | Completion
99337701-5264-5612-ace4-c3fbafce8be6 | textbox | Geschke Pty Ltd. Representative:
d3bfc6c3-5e03-5e04-8b45-e77b4c69a4ec | textbox | Others Present:
765c17f9-c347-567e-b2f6-14bc1505e0e9 | textbox | Date of Completion of Satisfactory Test:
2101619c-78f9-44c7-b5af-84e645340530 | checklist | QA 22 - Hot Water Service Maintenance Log |  | Hot Water Service Maintenance Log
9ea81300-a10b-4269-9958-5b2eaea11daf | checkpoint | Hot Water Service Unit Details
2994575f-3bf3-5bbf-9bb4-4d08b47ebfd2 | textbox | Purchased from:
c2ae6bbb-a39e-59a9-ad93-38fce8ef9eb0 | textbox | Make:
ce1a27e6-cce5-5153-9113-755b7f86644f | textbox | Model No.:
5d3084e2-76d7-53fb-8dff-bd84bab10aef | textbox | Location:
b1324d40-f433-50ea-9ee8-905ca6757424 | textbox | Room Designation:
a18a71d1-0494-5f41-b0a5-9fc6b1c59759 | textbox | Installed by:
e4c13f46-13ef-5126-8d29-96e94781027c | textbox | Installation Date:
9de630f3-716b-5584-86d8-0f3737cc4d29 | textbox | Number of units in series:
6f1e5cfe-4dae-56ef-8bed-9e749c3703e6 | textbox | Prescribed temperature set on unit or combined package:
3a648562-2c35-4e7c-ae08-ff8032e34400 | checkpoint | Does installation comply with manufacturers instructions
69f9f263-5c22-4a89-a578-6e625dd75865 | checkpoint | Does installation comply with current requirements of the local water supply authority
721c4616-f054-4be2-9cbf-4c060de5dace | checkpoint | Clean Pump Strainers
62c2eeba-0dc2-45a5-a033-3c9582e2fdf1 | checkpoint | Clean Hot Water inlet Strainer
df55d3e0-015e-4ae1-9e03-9d7e175c6bff | checkpoint | Clean Hot Water Return Strainer
4645c18b-6555-4cd8-8167-b3b3ede993fc | checkpoint | Confirm all Valve Isolation reinstatement
f15a25eb-e72b-4207-9e35-7451ae1037d7 | checkpoint | Confirm Unit is Operational
ce0441e8-1937-4e97-8f73-d5e538663abe | checkpoint | Confirm Unit is Back to Operational Temp with no leaks on Strainer seals
35bf6a93-d09e-4cfc-bdb4-bc0e2bcc803e | checkpoint | Commissioned By:
9e0d204b-f0b2-5693-b740-5cf96563baef | textbox | Name:
abbb49b9-a212-5965-b54c-e7c54c569295 | textbox | Date:
8de486d3-3be8-4821-8fd8-7d0304ee8839 | checklist | QA 23 - Boiling Water Service Maintenance Log |  | Boiling Water Service Maintenance Log
c725d8f9-02b7-40c1-96d6-d11f5d699793 | checkpoint | Boiling Water Unit Service Details
7c44d8cb-4b7f-550e-8e3b-51401192cd52 | textbox | Purchased from:
b278d574-e8f4-5342-abb2-75e71684b137 | textbox | Make:
7321685a-47b2-56d6-9395-051ad1d95845 | textbox | Model No.:
8bc605bc-7cef-5323-b92b-0312438e11cb | textbox | Location:
f3d1ff6d-3b36-58f0-bf8f-be2c75ba8da4 | textbox | Room Designation:
fb0768b9-3a92-591d-b496-bb21196849d7 | textbox | Installed by:
be7d5416-b371-507b-8fd8-67128d3ea142 | textbox | Installation Date:
906b8c5a-6822-41d9-89c1-fa4984222c2b | checkpoint | Does installation comply with manufacturers instructions
36eee675-405a-46a1-a050-2d02f9edec2f | checkpoint | Does the installation appear in good working order.
c26bb4c3-6ff0-4f12-bfd2-142d2113dc77 | checkpoint | Confirm all warning lights working correctly
ea451467-d664-4542-89d1-b3987a9b60ee | checkpoint | Confirm filter is clean
b58bf2be-b5a3-47e0-900c-6cdf9de25656 | checkpoint | Confirm Unit is Fully Operational
0dd015a7-84e3-41a2-b82f-b17c2c480880 | checkpoint | Commissioned By:
cf5cdec1-a45b-5a71-8412-7aa768b8883e | textbox | Name:
c23bbe17-91ea-5323-a7e1-08d041efc8b2 | textbox | Date:
2396793b-acd7-4221-aaa5-58e9456cc4f0 | checklist | QA 24 - Hose Reel Register |  | QA 24 - Hose Reel Register
ccb995ef-0b6d-4524-a86f-fe6db35f6ce1 | checkpoint | Hose Reel Register
48791e67-151d-54ba-aeed-56ee88bc6ab3 | textbox | Ref No:
56c7158f-62f9-500b-85ce-2822c23df4bf | textbox | Building:
ac969ed7-aa80-56fb-a011-204aadf3a5ce | textbox | Zone:
a790a91f-5e9e-5761-9f89-05f8afbfa33e | textbox | Level:
3461901b-4456-5687-b5e4-9af033fa5cb8 | textbox | Adjacent to:
ed350bde-af42-5491-92a8-341095f9f1e0 | textbox | Length:
272f8499-3996-53c9-b664-37c90724ba1c | textbox | Date Tested:
2b855fb6-2533-5f41-afbb-f1bc365acd23 | textbox | Flow Rate:
272c8006-70b0-5718-860b-39faab88b0d0 | button | Obstructed Access | No,Yes
f2456b36-17d7-5550-bf91-d6d5da1c4a43 | button | Operating instruction visible and legible | No,Yes
e4be757d-e526-5217-af8c-9ec07e87d262 | button | No leaks throughout hose reel mechanism | No,Yes
016f63fd-190a-5681-93a5-2c60ddae6d3e | button | Hose runs freely through guides | No,Yes
ab7ed424-f147-5ce1-a549-0b551366ffb5 | button | No signs of corrosion | No,Yes
1b4595ee-679b-4764-8429-f73ae4d48f46 | checkpoint | Result (Pass / Fail)
5d90fe0b-f1b4-44ce-9fde-7df0f78b91a4 | checklist | QA 25 - Butt Welding Checklist |  | Butt Welding
2f928484-70cf-4e12-ae17-0c81ab9bb18b | checkpoint | Operator Details:
c5fbfb9a-85a9-5acf-8696-20e26bf1ab07 | textbox | Name:
1607fdf9-80cd-5509-8c2d-b66657e6516c | textbox | Company:
85d2f18d-e939-54d0-ae1b-570675a426f6 | textbox | Phone:
57a583fc-7ce9-50ee-b9bb-86095aca456f | textbox | Address:
c5581c33-7eba-4a2c-8109-7465d4ced386 | checkpoint | Welding Machine Details:
cefea694-2e4a-5c26-838c-594cf061bfb7 | textbox | Manufacturer:
c0eab02a-28d1-5b18-b7d8-ee0380cb2f2e | textbox | Type/Model:
ca8dfd59-389c-53a4-ab0f-9d03e0663c5e | textbox | Serial Number:
c9857b87-0058-513b-a378-0f2c355b244c | textbox | Year Built:
76da8b46-8964-4375-bb7d-52d58a87cf57 | checkpoint | Pipe / Material Details:
0ade1bc9-8408-5121-8b39-9e487e6d400c | textbox | Dn (OD)
2d83e2a9-079b-5ba6-9963-236563904155 | textbox | SDR
6061948b-250a-5e07-b6dd-52918471e9e9 | textbox | En
72dd8e96-20c2-533f-8722-04226f5bc205 | textbox | Type
d79bd2f2-652a-5ff1-acac-fa48e54447e8 | textbox | Parameter
00dfe434-518b-5f8f-8008-df3940e44305 | textbox | SLP
272ab6fb-8ac0-5744-8a44-edfddafe7db0 | textbox | SHP
7eb2d36b-4c8c-4bdd-bed5-001ff3d874a6 | checkpoint | 1
5f7deb02-1aa1-5b95-a35f-adb9b7bf6a77 | textbox | Time
8bc208ed-bb3c-5139-9c73-1244c1cae62f | textbox | Ambient °C
9140e586-ae20-5639-8803-db35d507deca | textbox | Heater Plate °C
6ffafeb8-d7be-5c51-bcb5-d7e59d54356b | textbox | Drag Pressure
2da7badc-4627-5cf2-9aa3-9886ef007d20 | textbox | Bead Up: P1 (Kpa/Bar)
01d0cc0b-8783-5f4d-90cd-2959f8b6d48b | textbox | Bead Up: t1 (Evidence)
2f563c7d-acce-5713-9e52-8d7a08f818e1 | textbox | Heat Soak: P2 (Kpa/Bar)
357994d9-4a60-5d35-bb45-760c2ede1270 | textbox | Heat Soak: t2 (Seconds)
575d039b-f07a-50ae-87d7-fe031e8f2c96 | textbox | Change Over: t3 (Seconds)
8a711b27-989d-5e58-b16c-2e7f2609a351 | textbox | Pressure Up: t4* (Seconds)
38610547-5a86-5821-bdba-f64bce927dc8 | note | *t4 not applicable for SHP situations
33e6322a-8bf2-5bc5-ae78-99330cbad75c | textbox | Weld and Cool: P3 (Kpa/Bar)
9ca6a5df-2053-5f67-8523-8c70ea474306 | textbox | Weld and Cool: t5 (h:m)
fa5421ba-9b0a-5723-ace4-6db6828e26ba | textbox | Rough Handling: t6 (h:m)
1b2da10d-6473-583d-993e-7df964137e7d | textbox | Bead Size: Min
16c372d1-5fd6-51a2-947a-80b1028f454b | textbox | Bead Size: Max
b07ad621-cbab-5733-ab83-1e5373de51c6 | textbox | Comments
73e11f1a-f050-4087-a673-6c22464344fc | signoff | Add Operator Signature
dbba146f-cfdc-44d5-b7a9-a3cbf3e660ea | checkpoint | 2
10cc99ed-028f-5093-8923-31a4388515d6 | textbox | Time
72db1f38-c8e9-523e-b4f2-096de1f3914f | textbox | Ambient °C
4161078b-49ba-5a91-a96c-927d659fc636 | textbox | Heater Plate °C
d8bb0aba-a3c5-579f-bdc8-9a3be542de97 | textbox | Drag Pressure
519cb00a-e53b-5315-9971-ca59c47f318f | textbox | Bead Up: P1 (Kpa/Bar)
05866bb9-2d1f-56a4-a671-9df4ee4f066a | textbox | Bead Up: t1 (Evidence)
8bb23ca8-23be-5d11-8c95-8826c623572e | textbox | Heat Soak: P2 (Kpa/Bar)
fb2656ec-2a59-5a59-9b40-c536c0ee5146 | textbox | Heat Soak: t2 (Seconds)
f77d9125-13f0-57d6-a4e2-cf5f05f84c53 | textbox | Change Over: t3 (Seconds)
9011a5b2-fe30-539a-b6f4-ef04fbedb39e | textbox | Pressure Up: t4* (Seconds)
3863c930-dd64-5773-b7c4-82186d29b63c | note | *t4 not applicable for SHP situations
42be56db-ebed-5b07-aac5-7aad40a365a2 | textbox | Weld and Cool: P3 (Kpa/Bar)
7972b58d-cdf7-58ec-ab3d-dcc83b23c40b | textbox | Weld and Cool: t5 (h:m)
56b06e56-a886-535f-aa7f-adad3b6a3ec5 | textbox | Rough Handling: t6 (h:m)
77e5c3ab-2819-5445-b430-b55ff0f59a59 | textbox | Bead Size: Min
df7501fe-0691-52ee-81fa-a7b623c9a780 | textbox | Bead Size: Max
9554a7b0-44f3-5eaa-a7ef-63c9d0f9714a | textbox | Comments
4080ffaf-a3f4-4f66-ba74-89a4df99edaa | signoff | Add Operator Signature
f0020007-a05f-4270-b0e8-81a8d81d5241 | checkpoint | 3
b6c8244b-db09-5488-a968-0002d814e204 | textbox | Time
aa1500f8-c529-55fe-b27b-86a05b0139a6 | textbox | Ambient °C
843c7282-982a-5ed8-a013-7da712b8b9b0 | textbox | Heater Plate °C
8cd86c56-ccef-5837-b299-04d5b1d4a337 | textbox | Drag Pressure
83ca8544-f438-5f77-a24e-538160b5e4b4 | textbox | Bead Up: P1 (Kpa/Bar)
f3b54d0e-65e7-5309-a90b-3ae9be881f75 | textbox | Bead Up: t1 (Evidence)
aab253ee-aeef-5393-944b-cf3a5ae4bf76 | textbox | Heat Soak: P2 (Kpa/Bar)
b602b7bb-36df-516b-b8ff-c4133ee2ab14 | textbox | Heat Soak: t2 (Seconds)
34b695b1-88f0-5fb0-ad13-d1d8180887e0 | textbox | Change Over: t3 (Seconds)
3e3ccc49-8a77-5ae7-90bb-0763724655fc | textbox | Pressure Up: t4* (Seconds)
6dcf1426-6a23-567b-bc5d-ff2cad6aadd1 | note | *t4 not applicable for SHP situations
a4f10bd9-5e4c-5374-bf9c-aaf2b1cf01e3 | textbox | Weld and Cool: P3 (Kpa/Bar)
8eb932ed-b701-569a-a561-f7c6033126a0 | textbox | Weld and Cool: t5 (h:m)
43031907-9ca1-5f00-bbb2-c067ac05fb30 | textbox | Rough Handling: t6 (h:m)
f42680f8-26f8-5389-b564-98c9b7f81443 | textbox | Bead Size: Min
5875698c-b2e2-5c40-9644-27e4675261bb | textbox | Bead Size: Max
0fb15f55-b5c0-5ba1-9d89-8b7b3cb7f102 | textbox | Comments
145c652f-4363-48fe-9fc9-182134784486 | signoff | Add Operator Signature
6e197300-dffd-4e49-8da4-1409fa9e097f | checkpoint | 4
bdca8c6a-a9c0-52f3-b496-e9108dbaa906 | textbox | Time
58b468db-2bef-57e3-a518-f5e52cb5534b | textbox | Ambient °C
0ad40836-d1e1-5c23-86c6-f3287568d2c2 | textbox | Heater Plate °C
22262623-b3a2-5ba4-8601-3f2b0ec49c94 | textbox | Drag Pressure
a5ae380b-9006-561f-acee-a4466f7cf53a | textbox | Bead Up: P1 (Kpa/Bar)
212bb57b-891a-5984-be27-39bd124a71ba | textbox | Bead Up: t1 (Evidence)
0039850b-30d5-50b5-9153-d016ddb9e75e | textbox | Heat Soak: P2 (Kpa/Bar)
76c59e31-a859-5944-beeb-3c6533b58cd9 | textbox | Heat Soak: t2 (Seconds)
26cd8663-9ea2-571e-9d50-61a1398d399b | textbox | Change Over: t3 (Seconds)
d7e4831c-f427-536a-9595-b1840bf54bdd | textbox | Pressure Up: t4* (Seconds)
1ae0ce49-2c07-5381-b4f4-7ca8ba8db502 | note | *t4 not applicable for SHP situations
e66b8b7d-19a3-5fcf-816a-eeef2460bd16 | textbox | Weld and Cool: P3 (Kpa/Bar)
0eccac6e-73ba-5479-bec3-18245f30196a | textbox | Weld and Cool: t5 (h:m)
9321e388-c948-5a39-bf67-3540fcef82a2 | textbox | Rough Handling: t6 (h:m)
6a8f9264-e984-5883-bcff-06fbbe080e39 | textbox | Bead Size: Min
d4e99397-e3fa-5853-926d-17f602742070 | textbox | Bead Size: Max
25046f58-828f-5da7-944a-f7ab9844e5ba | textbox | Comments
29376b3a-7c12-4586-97c8-6f07507332af | signoff | Add Operator Signature
a511372c-d10d-44ee-9f50-aec7936a8d38 | checkpoint | 5
f4ce74f9-5ee1-583e-a121-6ad5d2858a9c | textbox | Time
a3940be2-d942-5108-af58-8ff020137709 | textbox | Ambient °C
14c316b8-7332-5fd6-911e-885b3edf86b3 | textbox | Heater Plate °C
afdc6182-2a41-5e35-8f6d-7966adc9d66f | textbox | Drag Pressure
f98a343b-4db6-54ce-87e3-2fd62dc3a96d | textbox | Bead Up: P1 (Kpa/Bar)
6ad047f2-ec09-5772-93a2-792bc734dbb3 | textbox | Bead Up: t1 (Evidence)
e030adc3-8de2-503f-a73f-4d666f967415 | textbox | Heat Soak: P2 (Kpa/Bar)
8535f51a-9baa-5525-b8e8-da98c3bc4e3f | textbox | Heat Soak: t2 (Seconds)
484fc7de-e152-56ac-82f7-206d7471d459 | textbox | Change Over: t3 (Seconds)
c599cd4b-0609-5f73-b3b5-d105b49e1b5a | textbox | Pressure Up: t4* (Seconds)
d5f2ee5d-a0f3-5474-8870-775e07eaa1a0 | note | *t4 not applicable for SHP situations
53574eaf-66fd-50d3-9033-db7adecdda79 | textbox | Weld and Cool: P3 (Kpa/Bar)
f0cc56b3-5dc6-534e-9baa-3e45afe65760 | textbox | Weld and Cool: t5 (h:m)
f6514a9b-ed5e-5c8c-9b67-7a18e3e516d6 | textbox | Rough Handling: t6 (h:m)
b0991ce8-27de-5408-b561-6199c15af575 | textbox | Bead Size: Min
aa63fafb-b109-5a14-86fb-b8161dc22ddc | textbox | Bead Size: Max
76d41958-a768-5627-9b93-26adbe305fc8 | textbox | Comments
53771825-29d0-4962-af76-cd31918fde35 | signoff | Add Operator Signature
5d49eb3d-8263-4a44-a917-6e2bc3779f67 | checkpoint | 6
60306e0c-f83f-5534-a435-e6fb50e83a43 | textbox | Time
d4f5f4b1-67d1-5c77-98a5-a16f39b84985 | textbox | Ambient °C
292d516f-0417-5f55-83f0-3d28f95b5368 | textbox | Heater Plate °C
b47e8dbd-60c3-5517-ad3e-907f8d4da710 | textbox | Drag Pressure
c5ffbe8e-2abb-50f9-86b1-b80211bc495b | textbox | Bead Up: P1 (Kpa/Bar)
16a76ca3-0a8b-5709-bff4-00689db7b606 | textbox | Bead Up: t1 (Evidence)
699ea13c-0aef-582e-b7ec-86ba348ce8eb | textbox | Heat Soak: P2 (Kpa/Bar)
2ef088d0-7d51-57cc-84e7-9d6c7c784fbb | textbox | Heat Soak: t2 (Seconds)
d3d9fa6c-8819-5239-a9fe-77936b857154 | textbox | Change Over: t3 (Seconds)
16c8085d-cf61-569a-bbf4-60564ee0a8a2 | textbox | Pressure Up: t4* (Seconds)
eeaa0060-06ba-534c-92f7-da0275c237d5 | note | *t4 not applicable for SHP situations
a1fc04b1-16c8-540d-b441-eaa229767535 | textbox | Weld and Cool: P3 (Kpa/Bar)
d6fa83ff-7f02-5723-a55b-493f8e5e896d | textbox | Weld and Cool: t5 (h:m)
4e3808aa-8920-54d6-9459-8847bb48bb2e | textbox | Rough Handling: t6 (h:m)
192b9dfd-4ef1-5e10-9a4d-70cdae6eaf30 | textbox | Bead Size: Min
aaf35c86-3dd2-5374-9765-499251fbccbd | textbox | Bead Size: Max
fac0a395-a380-5d52-972e-ec077576b3c4 | textbox | Comments
d0cab266-99da-42b2-b767-8c4a63283ce9 | signoff | Add Operator Signature
b13bb755-f1a3-4121-b5a0-3976b88c98a4 | checkpoint | 7
0980f412-a28b-5564-9618-cd81488cea99 | textbox | Time
9d48400f-031e-57d7-a80e-097c625be518 | textbox | Ambient °C
80f394f7-e2fd-51ae-a90d-1813e519c02d | textbox | Heater Plate °C
4b52713d-7e6f-55e1-b892-53a6f7275de2 | textbox | Drag Pressure
ca7c8627-e7d5-54fa-b328-7a96346c6ad8 | textbox | Bead Up: P1 (Kpa/Bar)
4cd5bd93-7c5f-5172-aa6a-9619d6ffabbc | textbox | Bead Up: t1 (Evidence)
37cfaf04-69d2-5289-9a86-445dc721ba28 | textbox | Heat Soak: P2 (Kpa/Bar)
73b9d823-2f78-5e6a-a195-bd20ad3d3db9 | textbox | Heat Soak: t2 (Seconds)
0a20ee48-8136-54db-8feb-1cceac7fb256 | textbox | Change Over: t3 (Seconds)
25dbdf99-568d-5b19-881c-cad0ba2898ad | textbox | Pressure Up: t4* (Seconds)
30024fa5-4916-5b6e-8edd-bed4e1b414f4 | note | *t4 not applicable for SHP situations
bf01294f-f43c-5d7c-af85-2dd3c5c82906 | textbox | Weld and Cool: P3 (Kpa/Bar)
9bb65bb8-978a-562b-8f80-ae44d2251c61 | textbox | Weld and Cool: t5 (h:m)
e2604abe-1ed2-5fc1-a343-50a5aa0f9bfe | textbox | Rough Handling: t6 (h:m)
2340bf82-9a6f-5c14-8050-e47aa52c085d | textbox | Bead Size: Min
98c4da4c-1faf-51c6-84b4-96f20f1a33b8 | textbox | Bead Size: Max
4763f60b-dd70-54f5-8a0c-be15f09177a8 | textbox | Comments
3a5faf9f-bfef-4f65-96d6-54d66be4f694 | signoff | Add Operator Signature
009b57f5-358d-457d-bcf5-869be9e0a8ea | checkpoint | 8
f63cf0b7-892f-51ce-88f5-7ffed5669996 | textbox | Time
b62f00f3-ad8c-5e95-bbc3-6d77cdad2cf3 | textbox | Ambient °C
11df5477-7252-5be4-8c27-e75c8fff2e6f | textbox | Heater Plate °C
69e5ab58-8aa3-5bd7-a8eb-e45f0462fb6d | textbox | Drag Pressure
c0230cbf-82cb-5bb8-b1e8-36b4b6655170 | textbox | Bead Up: P1 (Kpa/Bar)
5e79e7c7-db62-52e1-8e99-fee545e74e8d | textbox | Bead Up: t1 (Evidence)
223bce61-c802-5881-9b2d-c8844be21dc9 | textbox | Heat Soak: P2 (Kpa/Bar)
dc1c2864-cf00-5ce5-a555-10860dfb6c6b | textbox | Heat Soak: t2 (Seconds)
7a13f9b9-b5c1-587a-a863-eee81b017236 | textbox | Change Over: t3 (Seconds)
6547a070-7dbe-5607-893a-4200b63f3481 | textbox | Pressure Up: t4* (Seconds)
819ad55e-596e-5f70-9ce0-2e3c3965752c | note | *t4 not applicable for SHP situations
10c86548-07e5-5e52-bf36-87927c53e805 | textbox | Weld and Cool: P3 (Kpa/Bar)
bf83d8fe-e10b-5e78-85bd-948b0d0e25b6 | textbox | Weld and Cool: t5 (h:m)
30098575-1e3d-5ce2-ac7e-f211a88e3275 | textbox | Rough Handling: t6 (h:m)
9e269860-90f7-509f-b09d-37084457659e | textbox | Bead Size: Min
985de7bf-c63c-5393-8bcc-719f04ff1da8 | textbox | Bead Size: Max
8619a62e-785b-5966-9512-1693549364a5 | textbox | Comments
3ea7fa12-b797-42bc-a0a9-43423ff4dd85 | signoff | Add Operator Signature
e7649665-85da-4748-91ad-6ad4cc70c2fc | checkpoint | 9
bc64d748-2a64-5fdb-b0b3-de908ea3421f | textbox | Time
10ca9cc4-b9fa-5089-a83b-3a559649eaab | textbox | Ambient °C
fd973952-4d59-5a49-a27b-fa5da0f28f1e | textbox | Heater Plate °C
86f233b1-2cee-58de-b0bd-8790b54c4fe9 | textbox | Drag Pressure
4a9e1d2e-0ab2-5852-9f4c-bb75e7eb72e1 | textbox | Bead Up: P1 (Kpa/Bar)
39103451-9f85-524c-b55c-ba7f4d3323a1 | textbox | Bead Up: t1 (Evidence)
6be7ecba-34b5-50a4-827e-c0fc5ec104c5 | textbox | Heat Soak: P2 (Kpa/Bar)
17c3d009-bfa0-5ade-8f2f-1245b92aa312 | textbox | Heat Soak: t2 (Seconds)
15d29ab9-2501-5703-845f-00dae31ef3dc | textbox | Change Over: t3 (Seconds)
3fa0cf64-45df-56b1-be01-39c3a8588520 | textbox | Pressure Up: t4* (Seconds)
0e282ccb-ef6e-5e05-b406-98bb8be81425 | note | *t4 not applicable for SHP situations
18a41e43-c6c8-5225-a7d2-1212ec8fe96b | textbox | Weld and Cool: P3 (Kpa/Bar)
4ad7a126-5386-536c-8462-7480869881cd | textbox | Weld and Cool: t5 (h:m)
7e936da2-9091-5d57-ae2f-c36762ee4424 | textbox | Rough Handling: t6 (h:m)
f1b0be69-b0ca-56c0-8c78-08bd96b2d719 | textbox | Bead Size: Min
27f6ce60-b922-52d5-a741-20befaea9dd7 | textbox | Bead Size: Max
feac72d8-2c9c-5e61-b693-0362e2c89084 | textbox | Comments
787294f0-ad4d-45f5-8e49-ea6c8448a7e9 | signoff | Add Operator Signature
2dfd1885-9ad3-4286-94da-43efb1ba7080 | checkpoint | 10
489ae8d7-2dc2-5580-b3bf-e1a167811a9c | textbox | Time
f7bec650-6649-56e3-8a68-613e11da2911 | textbox | Ambient °C
c275f511-2264-54ec-80a4-57ea7d47a36b | textbox | Heater Plate °C
3d605ecf-2bd1-5590-b732-a4dd68532797 | textbox | Drag Pressure
21bb56d9-ed3b-5269-8f45-b653b7aaf2a7 | textbox | Bead Up: P1 (Kpa/Bar)
eee9d420-85b2-591e-b98e-059450d8fb83 | textbox | Bead Up: t1 (Evidence)
83b9b67f-3e1d-5586-ba28-47c02721281d | textbox | Heat Soak: P2 (Kpa/Bar)
78e5637b-2c21-5f41-9377-f6c63454e397 | textbox | Heat Soak: t2 (Seconds)
f67a751e-098d-506e-89ce-00878b215037 | textbox | Change Over: t3 (Seconds)
96584e04-0e1f-5fce-a3c3-5c070ab8bc61 | textbox | Pressure Up: t4* (Seconds)
741ffe13-ffa8-5050-8164-abe0010e9c26 | note | *t4 not applicable for SHP situations
de99bcae-22e2-5c0a-a9df-00261c62a6f1 | textbox | Weld and Cool: P3 (Kpa/Bar)
0d692281-dc17-5dca-94a4-c68fd1c77391 | textbox | Weld and Cool: t5 (h:m)
dee75392-714f-57dd-869e-97abc2e4f8c4 | textbox | Rough Handling: t6 (h:m)
29675291-23b8-59cb-ae68-5a6098438cc5 | textbox | Bead Size: Min
6c328f54-3d03-5932-b129-1ab3d0738147 | textbox | Bead Size: Max
8578d927-0979-5c3e-9d7d-ae9c0d22b639 | textbox | Comments
39ac2268-7f34-4dcb-af98-33df095b5d69 | signoff | Add Operator Signature
bf836aaf-e0d3-417e-8632-9a0af3004220 | checkpoint | 11
4826eff0-22c2-5d36-99dc-da3012c9a0f6 | textbox | Time
ee9fc40a-e923-597d-ac5e-c5e5f5d6a0fb | textbox | Ambient °C
34075d0d-c89e-5475-a87c-2d8d9cdcae21 | textbox | Heater Plate °C
9d077a82-a064-599d-8c5b-c03650d0b2a7 | textbox | Drag Pressure
2700e4d7-85b5-5f55-83fe-e27f65ea99d0 | textbox | Bead Up: P1 (Kpa/Bar)
e847bb12-c1d5-5d62-b226-96d45d3491b2 | textbox | Bead Up: t1 (Evidence)
f740eec0-1328-5dc2-ac47-7139b4ac8d96 | textbox | Heat Soak: P2 (Kpa/Bar)
51d0b483-f9cb-586d-bb0b-cd3c855412be | textbox | Heat Soak: t2 (Seconds)
845d4ab2-f50c-5d97-b073-428bbfeafb72 | textbox | Change Over: t3 (Seconds)
ec836469-6045-5349-bad9-361c101e325d | textbox | Pressure Up: t4* (Seconds)
d507b92e-726e-5817-aec2-f0e9be2e73fb | note | *t4 not applicable for SHP situations
a421c94b-6e11-51a5-ba86-f5f4437c5884 | textbox | Weld and Cool: P3 (Kpa/Bar)
4defe1fb-7065-56fc-8b50-dd77639d9c10 | textbox | Weld and Cool: t5 (h:m)
b7195b6b-90f6-52e7-ac93-9a69079f4880 | textbox | Rough Handling: t6 (h:m)
dfae2a65-e294-5ba7-9869-3d96f07af44f | textbox | Bead Size: Min
01d3bb4e-bb1c-5a5e-a90f-1894a5e03f1a | textbox | Bead Size: Max
61ec193b-e670-5ba3-8e4e-fc2748746b71 | textbox | Comments
b681f156-a69f-4d3c-a414-4655af32f9d8 | signoff | Add Operator Signature
192b2332-19b6-40ff-9c1c-c4d3f0b6370d | checkpoint | 12
f5367dac-b137-5a45-9313-30e9ec612705 | textbox | Time
7ef8c6b5-f697-513d-8fbe-9be4307594c5 | textbox | Ambient °C
c6101647-7d47-5942-9827-cb824ddcf6c1 | textbox | Heater Plate °C
2fbd8db0-281e-51d4-bd08-bca71f0e1b76 | textbox | Drag Pressure
20b8bfa1-5117-5643-b27c-4ee5d6b7026a | textbox | Bead Up: P1 (Kpa/Bar)
d71ddf52-6790-5aba-bc27-4abeca0e904b | textbox | Bead Up: t1 (Evidence)
35261288-d77d-53bd-8f9d-62ef8c446f95 | textbox | Heat Soak: P2 (Kpa/Bar)
205b988f-2fd6-574c-8cca-12056a043acd | textbox | Heat Soak: t2 (Seconds)
2c8f1efa-4252-576a-ac03-c53a4eac3075 | textbox | Change Over: t3 (Seconds)
1958695d-b9f5-5651-b0b8-93940c55d97c | textbox | Pressure Up: t4* (Seconds)
614843c9-ecbc-5653-a6d3-f40e813c99af | note | *t4 not applicable for SHP situations
e03e0de7-115d-5ca5-8613-4f0fccb44223 | textbox | Weld and Cool: P3 (Kpa/Bar)
8c0448d1-2811-5a2d-8a40-986ecfee3482 | textbox | Weld and Cool: t5 (h:m)
4eee98b0-a1eb-5956-a6e7-2a2bc5d04a98 | textbox | Rough Handling: t6 (h:m)
55f3ab69-bf6e-56ad-bbb0-549cc0d677f9 | textbox | Bead Size: Min
e5e9a1f6-7558-5839-8a93-423841440004 | textbox | Bead Size: Max
86e6ce83-b16f-5d09-9017-45c18f45f79c | textbox | Comments
17bbb46a-283d-47fc-87aa-9822cea36fde | signoff | Add Operator Signature
675933af-7250-4b3b-aea9-7c69e22857d0 | checkpoint | 13
44a6bab9-480c-547a-9508-978d440f67dc | textbox | Time
53316c51-92cb-56c4-97e3-341e909d8354 | textbox | Ambient °C
f336d865-f4d2-596c-87a7-81ae8362976c | textbox | Heater Plate °C
069c771d-4537-5fd9-8f84-83029cf61d1d | textbox | Drag Pressure
4e4515ab-3e69-571a-bdef-bd396816b007 | textbox | Bead Up: P1 (Kpa/Bar)
0828bd4b-b4a0-5be7-82ce-5c1b6842df9f | textbox | Bead Up: t1 (Evidence)
b08333b2-5bf2-56d0-95a3-505f3cc66447 | textbox | Heat Soak: P2 (Kpa/Bar)
2673f2d8-9831-522a-9f8b-e12868e70d08 | textbox | Heat Soak: t2 (Seconds)
e6f4851d-75c6-5f80-91c9-f08f2e43ab75 | textbox | Change Over: t3 (Seconds)
e65f2fc1-594c-5bc7-b5ae-f30f849efc96 | textbox | Pressure Up: t4* (Seconds)
3698669d-f3c8-50d3-aa57-4ede31715a3f | note | *t4 not applicable for SHP situations
699ff415-6413-5df3-acdd-055b14424e67 | textbox | Weld and Cool: P3 (Kpa/Bar)
5942a348-82bc-5d6e-b6a0-5cf5dafd7b4b | textbox | Weld and Cool: t5 (h:m)
b6ba5a1b-5d2f-55be-9993-41f88bf0939e | textbox | Rough Handling: t6 (h:m)
77847778-f72d-5e72-a981-110277bb96c7 | textbox | Bead Size: Min
35a5c8d2-b116-58df-af3b-504603eaf9e2 | textbox | Bead Size: Max
7a4ad26d-e9c3-55c6-9e41-3f729fe94be5 | textbox | Comments
918c9194-e774-4c8e-b562-bf5284e68186 | signoff | Add Operator Signature
e9a3a7f4-241f-4592-86f4-772886b364ea | checkpoint | 14
d7fc1f91-9fc2-5dad-aa1f-7cb66b5b583d | textbox | Time
37b6926d-0d5b-58e8-9462-01850bd0969c | textbox | Ambient °C
f2b13aa7-f44a-5888-8213-a1954f5e4f38 | textbox | Heater Plate °C
3c1700d4-c2cf-5d52-87c7-d7ba3ad0fdc4 | textbox | Drag Pressure
090c8cee-c37b-515b-ad65-5b5aec351b35 | textbox | Bead Up: P1 (Kpa/Bar)
421386b0-d443-5dfc-a5e2-b322ba69244b | textbox | Bead Up: t1 (Evidence)
e0460b02-b46f-5836-94f1-10eb753dc00c | textbox | Heat Soak: P2 (Kpa/Bar)
ef24839a-56c0-55bf-88af-482378f6d45f | textbox | Heat Soak: t2 (Seconds)
816fee3f-8892-5c4c-b3ec-933e26a07c99 | textbox | Change Over: t3 (Seconds)
6932b4f2-86c7-5113-a890-137401f11262 | textbox | Pressure Up: t4* (Seconds)
d66c085a-9ae8-521e-9881-7c738637c8e9 | note | *t4 not applicable for SHP situations
ca91c1b7-5d9f-576f-b3ca-0210d21c579f | textbox | Weld and Cool: P3 (Kpa/Bar)
ad9c7ff6-91c1-52a4-a2c9-038555328660 | textbox | Weld and Cool: t5 (h:m)
a5c4d832-2615-5574-859f-66d4f10afe62 | textbox | Rough Handling: t6 (h:m)
a1ed48ae-f89b-505d-9153-f4a3a2201ad9 | textbox | Bead Size: Min
26f99a9d-d4c3-53b0-ab19-d4678dc2786a | textbox | Bead Size: Max
5c7bb4bd-5a23-518f-943c-446de8aafe86 | textbox | Comments
61909e96-369b-4a90-bb43-e543e2c1c593 | signoff | Add Operator Signature
a5e5873e-54ea-4d95-9d81-084289609c8a | checkpoint | 15
30371167-8795-566c-9524-302606cef576 | textbox | Time
adc81c44-b79d-5584-bb6e-80a4fdede818 | textbox | Ambient °C
e6d8c9a6-1fc1-55f9-ba52-2f4db426e1e2 | textbox | Heater Plate °C
c4ae151c-c68c-572e-aeb1-e4e68d456f57 | textbox | Drag Pressure
bb360a6a-b261-5bb2-bee6-aa34a4718f37 | textbox | Bead Up: P1 (Kpa/Bar)
8d299b25-096e-5498-a96b-968b127a9b96 | textbox | Bead Up: t1 (Evidence)
7c97333b-a2fe-53ad-826f-0b6e99533cb3 | textbox | Heat Soak: P2 (Kpa/Bar)
952f311a-f719-51e9-826e-6259db4f65c1 | textbox | Heat Soak: t2 (Seconds)
4ca1a43a-2c95-5656-bd9d-b283f2917ec5 | textbox | Change Over: t3 (Seconds)
27ea7860-269c-5d57-83b3-1a77960d2fb3 | textbox | Pressure Up: t4* (Seconds)
2d3d4041-3e7e-5296-add3-e8a55e6a6f24 | note | *t4 not applicable for SHP situations
84dabab0-506b-54bd-8811-293267251005 | textbox | Weld and Cool: P3 (Kpa/Bar)
73e75bd9-c2ca-57b6-807f-42e57d3db061 | textbox | Weld and Cool: t5 (h:m)
c91024f1-1e94-5247-94ba-8a436d9dbe72 | textbox | Rough Handling: t6 (h:m)
8ea7450a-ffdd-53fc-aecd-81a7fb932078 | textbox | Bead Size: Min
8e43def3-aa84-50fb-ba7d-6dec55144bb6 | textbox | Bead Size: Max
de1ad4be-cbe5-58e7-9f29-9f2155cc68b6 | textbox | Comments
cbae4aeb-638e-4021-bd67-342f774ff530 | signoff | Add Operator Signature
7d7db5cc-5189-4e28-8361-338bb24faa7d | checkpoint | 16
e99eec53-4feb-5ca2-a638-e869192c4ac7 | textbox | Time
e301af37-57ec-53f1-8d74-80c1550f9bf3 | textbox | Ambient °C
0a1c3d64-e3ce-5e92-8413-a91718dcdb9c | textbox | Heater Plate °C
82e6f141-1338-5aa6-9964-8a8bc694cd35 | textbox | Drag Pressure
63b9af12-3b32-5a4c-a76e-f57db7f32815 | textbox | Bead Up: P1 (Kpa/Bar)
3cebece7-2430-5c20-a1f0-9409b4923a6e | textbox | Bead Up: t1 (Evidence)
665e1ac7-3d53-5716-9d63-e385307166da | textbox | Heat Soak: P2 (Kpa/Bar)
05aabeb3-bd15-57d0-b332-845857a51508 | textbox | Heat Soak: t2 (Seconds)
5bd847ac-82a0-5c5f-a1b2-80ded156a049 | textbox | Change Over: t3 (Seconds)
769f8cab-792b-52cc-9238-f3829b2dcdb4 | textbox | Pressure Up: t4* (Seconds)
9427a0b0-11e1-5060-b6db-4760ba04ae42 | note | *t4 not applicable for SHP situations
b832107f-e9c0-5399-9e18-d6a76a622ddd | textbox | Weld and Cool: P3 (Kpa/Bar)
20c4f2b6-86b2-5e7b-a068-afe0ff0ebdf4 | textbox | Weld and Cool: t5 (h:m)
854f3a2c-774e-5a25-9bf4-0a28ca1ac332 | textbox | Rough Handling: t6 (h:m)
cbd09c11-b20a-558f-add6-6a1afd466282 | textbox | Bead Size: Min
14aebeca-e309-577a-a9b3-ac7638dede5a | textbox | Bead Size: Max
66d25fb4-ed09-5d95-be99-d397f15acf44 | textbox | Comments
2fd7393b-9d57-4acc-9760-f99eee6f5fc5 | signoff | Add Operator Signature
832142a6-f7a5-4465-a2b8-a05cd4b75d76 | checklist | QA 29 Periodic Flushing / Copper Protection Test Sheet |  | QA 29 Periodic Flushing / Copper Protection Test Sheet
9bcea4c3-e87f-416a-bdf9-3d8f8e4ce9c2 | checkpoint | ITP QA 29 Periodic Flushing / Copper Protection Test Sheet
f6a914b4-07d6-56cd-b28c-02d8b3c51095 | note | Copper systems are failing in the construction industry due to stagnant water being left in both hot and cold copper pipelines. Copper needs to form a protective layer of copper oxide on the internal surface which is formed by the contact with fresh aerated and oxygenated water. Periodic flushing of the systems is the only way to ensure this occurs.
c37ab051-294b-5c4f-ae86-6ca6490d6b70 | note | The purpose of this ITP is to help you create the strategy to get this water out and replaced with fresh water every four weeks.
d59548c3-e22e-473b-ad0a-50bf614d7618 | checkpoint | Flushing Details:
b2ac589f-283f-5018-9cd0-682b71cf7374 | textbox | Level / building being flushed:
47e03b91-60b1-54ee-a657-4c61454eaf69 | button | Time and Type of flushing: | Ring main Single point for flushing; the entire loop can be achieved in a maximum 10-minute flush., Non ring mains Any copper sub-branch from the main feed requires individual flush time of 5 minutes (an example of this would be a corridor feed)., Short branches of copper that feed rehau do not need individual flushing., Multi storey projects will require flushing on each level. Starting from the top and working your way down
6ece6db2-d9c6-5f0e-aa73-7a954554a614 | textbox | Which fixtures are being used to flush the system (Point of connection and point of discharge):
ff9e723c-2b42-5c09-b47d-20e9f75c2360 | textbox | Start time of flushing:
db1d1c4d-9367-583d-8829-a412d2d0eadb | textbox | Zone/branch to be flushed:
44755842-a3e3-5c70-9f80-57f089ca833e | textbox | Finish time of flushing:
2f91ff37-9d4c-5aa7-b5be-216365796d92 | textbox | Zone/branch to be flushed:
55a16626-868d-4c13-a96d-27fe100ad575 | checkpoint | Has the schematic / layout of the flushed zone been highlighted, attached and flush points nominated.
fcdea052-3f12-4102-8294-cd733d4d57fb | checkpoint | Is the flushed water clear with no visible debris or dirt. If NO, discuss with project foreman and or head office on why this might be the case.
6bb9b8ac-f95f-4419-b855-78306bbe202b | checkpoint | Have you set a reminder for the next flushing of this pipework?
ddcdbd8f-a714-494c-9280-f23f2654eae6 | checkpoint | Have the hot and cold been interconnected for flushing purposes?
7d836adf-d162-411a-b503-f284bdd8fb06 | checkpoint | Date for next flushing (Flushing to be performed every 4 weeks):
257eb460-9064-5f98-897a-1050db2fe611 | textbox | Date for next flushing:
339761a5-53bd-5899-aa1f-300207d152a0 | textbox | Test completed by:
1aa91e5d-3ca0-5a57-bafb-1c75fce011ea | textbox | Builder Representative:
a1a58449-e7db-4407-ae5d-36069a5f4069 | checklist | QA 30 - Fixture/Hydraulic Installation |  | Fixture/Hydraulic Installation
bc50833b-f0c1-4574-b112-12da6556371f | checkpoint | What is being installed?
d4372281-51d7-41d4-bd4d-e27e4520e972 | checkpoint | Where is this fixture being installed?
828cf6f3-9428-4a46-a393-675d74538b6e | checkpoint | Have all parts been connected/completed and tested? If no, please detail why?
c6bd0e2b-9903-458c-9bd8-69dc37a7578a | checkpoint | Has photos of installation been taken and uploaded?
56131d50-d36e-4378-a66a-db8d186c00dc | checklist | QA 31 - Hot Water Service Maintenance Log |  | Hot Water Service Maintenance Log
81dbd060-db29-4fd1-8843-acae262ea53d | checkpoint | Hot Water Service Unit Details
d2ed7f00-c0a8-5a67-91e4-427a7843fe72 | textbox | Purchased from:
dafa1771-4792-5a64-addc-74998e601bdc | textbox | Make:
4fa0eb70-30b2-5480-a028-7a1fc6dca40c | textbox | Model No.:
50310867-559b-58e8-b918-acd5b910af4c | textbox | Location:
47b891b0-9fbb-5293-94a8-04fdd52d57cd | textbox | Room Designation:
e224e22b-9691-5ca9-9b0f-a9f3709a2e17 | textbox | Installed by:
4f29790e-c344-5861-ac59-ef75ec25bf65 | textbox | Installation Date:
0c36f8df-7c3e-5d5c-9a24-3c15a6fb9378 | textbox | Number of units in series:
551c9aef-429d-5b94-9eae-1f5ba6e2a477 | textbox | Prescribed temperature set on unit or combined package:
146c2c00-528d-4319-8b65-e77098d6c6af | checkpoint | Does installation comply with manufacturers instructions
983881a6-e621-4bf7-aa57-87a99aa149b2 | checkpoint | Does installation comply with current requirements of the local water supply authority
49c7bf5d-90cc-48e6-b133-099e93caf4e9 | checkpoint | Clean Pump Strainers
03f0241c-9adc-418b-af7a-76370e53ec0e | checkpoint | Clean Hot Water inlet Strainer
c32f5830-6cf2-4af9-8897-1e377d245756 | checkpoint | Clean Hot Water Return Strainer
e8bb702b-3e04-44c3-82a8-7fcc1d9d1fa3 | checkpoint | Confirm all Valve Isolation reinstatement
fe3b06e4-e8c7-4845-848f-71bbc94b5d1c | checkpoint | Confirm Unit is Operational
533f187d-a794-4ef1-8fb2-0d8376efa3ef | checkpoint | Confirm Unit is Back to Operational Temp with no leaks on Strainer seals
2b728bac-e745-4de5-82f4-357e9e59a706 | checkpoint | Commissioned By:
dd27a4d3-4325-5c69-b40e-8fc93e131c2d | textbox | Name:
2e721997-2816-594e-988f-9d746405a79f | textbox | Date:
8714f120-4842-4f61-8640-54881a1f0f81 | checklist | Safety Shower Functionality Audit |  | Safety Shower Functionality Audit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
eb0ae755-6282-40f8-a6fa-ef1a974e8734 | checkpoint | Accessibility
ae9755bb-157b-51e2-bc6e-bbf5897a6838 | note | Is the location of the product in an accessible area, eg, no more than 10 seconds away from the hazard and has a clear path leading from the hazard to the safety product.
500e2ea7-b8bb-4f6e-a3f6-17b08360dabc | checkpoint | Identification
589f75f4-8638-5964-9c25-1a2659ad6d65 | note | Is the safety product clearly identified with appropriate signage visible from the hazardous area
ce577773-0874-4e57-931d-157b1824fec6 | checkpoint | Support Brackets
fa722e3a-7c31-51c3-8093-679f8117f528 | note | Is the safety product securely fixed with corrosion resistant anchors and brackets
2a5e91d2-1005-4676-bb69-f3642592d1a3 | checkpoint | Installation details
7932d1f9-d133-55b3-8cf6-b936d6c25524 | note | Is the safety product installed at the appropriate height
4fa2d64b-b9f1-4725-a429-a214dcc10d9f | checkpoint | Exterior and operating instructions
c887039d-3c00-5980-9cac-15eeacc3ffe4 | note | Is the safety product fitted with operational instructions and a test tag
f0deded8-6e64-4c0b-ac2e-3eba810bd3c3 | checkpoint | External Damage
017a3110-c162-5efb-8b39-268e7f0a1eb8 | note | Is the safety product free from visible damage
b0e3cd7a-d3e5-453f-a65f-f198b3028d57 | checkpoint | External Corrosion
4dafde56-7954-59a9-8e84-a3f6c187c7bd | note | Is the safety product free from external corrosion
35108e62-8bb2-47fb-8e43-d68f3f5a0877 | checkpoint | Activation Points
60d5bc96-097f-5889-a54a-8f8ce1c78ea7 | note | Are all activation points secure and in good working order
f913190a-1e2d-41b0-b8c4-e9c7bfff4aef | checkpoint | Leak Test
b0965ceb-79aa-57a3-932c-e08973a5ab80 | button | Check that shower/eye/face wash has no leaks - shower rose. | Pass, Fail, N/A
7363be4d-1893-5461-8940-0436862a52d6 | button | eye/face outlets | Pass, Fail, N/A
c2573847-c42c-5ad2-b406-702ae76a5710 | button | ball valves - shower 1" | Pass, Fail, N/A
f8e613d1-c6e2-5718-9b21-552748f0ee5e | button | ball valves - eyewash 1/2" | Pass, Fail, N/A
642ce250-64f1-46e3-bc78-ec4d5c74dda1 | checkpoint | Dust Caps
5f707d18-e9cd-5fbf-9140-6ae2c81ac7eb | note | Are the dust caps correctly fitted and in good working order
d24f9f99-31f6-4e64-bce2-10a7ba5d3e3e | checkpoint-no-value | Flow details
a9d2a869-1ab0-53cd-85b3-6ffc74ecf169 | note | What are the flow details from the safety eye wash outlet
d62994b2-4240-511a-aa6e-f7f1afcba19f | button | Does the flow meet in the middle | Pass, Fail, N/A
1b14598e-4c16-5258-aa76-9b7cb5a261bd | note | what are the flow details from the safety product with all outlets flowing
4ac9bd97-9404-53f5-a924-ef27db236ee4 | button | Litres per second | Pass, Fail, N/A
f9c8b658-fa19-525d-977f-91455f2b64ee | textbox | LPS
496e03b1-b66e-49d7-adc8-3483e2f26d1c | checkpoint | Temperature Test
a217c12f-ce9d-51df-84c5-1788df20b34a | note | Turn on shower, test temperature
653ccc68-7592-5ba8-b0e9-d633cd262612 | textbox | Temperature
1c038f87-8603-4ad8-9252-48db7f1f37ec | checklist | TMV 12 Month Service Log V.040221 |  | TMV 12 Month Service Log (use a separate checklist for each valve)
116e6e74-b7d2-49d6-9a60-1896965ff6d2 | checkpoint | TMV 12 Month Service Log
6f50691a-1052-508d-8942-49e4f9fee3e3 | textbox | Building name:
4b152a5c-c292-5f2b-b65c-9bd875e1b6b0 | textbox | Contact person:
9009d3d3-e172-5e90-98c6-2424962fd352 | textbox | Address:
fe012bfe-2595-5101-b131-a979e02183bb | textbox | Phone number:
2474ad68-5cf5-5eb5-bfbd-2aa6b41ee866 | textbox | Make of valve:
b58ba77d-9724-59e0-b632-a2c01965168a | textbox | Model number:
cec86261-f94b-5a41-ac58-08fa2f04f68d | textbox | Valve location:
e0416798-48a1-5701-87e1-805195bb6fda | textbox | Room name:
07f0cc2d-796d-535f-ad26-3220c5fe212e | textbox | Date of service:
74dc33f9-1bd1-5c78-a8ca-969583863bd7 | textbox | Temperature: |  |  |  | °C
34c78806-8271-5c24-911f-9d7ebdc7ae05 | button | Element: | Ok, Faulty
7b702738-5414-58fe-a150-2d29a9bfc558 | button | O' rings: | Ok, U, S
42b01cf6-fa34-54d8-8d06-354262c6949c | button | Strainers: | Ok, Dirty
5b9b3278-8c97-5b0f-849a-0a296e4355c0 | button | Non-return Valves | Ok, Faulty
3364de9b-9acd-5733-b0fa-6204cd3ed21b | button | Fail-safe test | Ok, Faulty
71c93ee4-c284-55ce-99e2-9bd18f206e34 | textbox | Serviced by:
4fd502bb-1d32-589f-b31f-cc82df6a231d | note | Note: It is recommended that a new thermostatic element should be fitted at least every 5 years
69d4fea7-b3d5-4b8c-aa75-cc798157c646 | checkpoint | Completion
bb196e3b-d980-5044-b91f-ae492fc70d5c | textbox | Plumber Name:
5b82eaf8-fadb-4804-b04c-6501d5a93493 | signoff | Add Signature
70ce1a85-16ab-401c-94fa-79f6e2412133 | checklist | TMV Commissioning Log Sheet V.040221 |  | TMV Commissioning Log Sheet
e8182b0b-fa9f-406a-ad2c-47c729f95d41 | checkpoint | TMV Commissioning Log Sheet:
9f0bf24e-39f2-5c6b-bf33-a8edc85cdfa6 | textbox | Building Name:
29103dd6-d8cb-577f-b7d9-f449b1906eb5 | textbox | Contact Person:
6d18ba29-682e-5da1-9104-efa93435de13 | textbox | Address:
2ec58e74-ef3c-5cf4-a190-4406ec66736a | textbox | Lic:
f69e5aae-4468-521a-b6eb-7de2694381c1 | textbox | Registration number:
b36d29ed-7c34-5bc5-9a76-7448e2f9cef1 | textbox | Phone number:
bc92ad01-037c-50cc-bb5c-9a6821b1bd73 | textbox | Make of valve:
d9afaa02-7648-55fb-9afb-0d42915b4c0a | textbox | Model number:
8f6a3bd0-0920-5abe-80fc-3685b016a626 | textbox | Valve location:
049b3d11-a66d-5604-bed7-38652f36bb1f | textbox | Room name:
5f200e7e-b76a-5779-86df-fba8bad1e9ae | textbox | Valve purchased from:
abb00ae4-f52c-5d13-bd19-acd7dcb35da9 | textbox | Installation date:
6cd468bc-b997-5aab-b67d-8931c75acd2e | textbox | Valve installed by:
e1a76320-3439-5f3e-8234-7f213e776ad6 | textbox | Number of outlets served - Baths:
69d73907-49ac-5288-bb0b-e81b9b96bcca | textbox | Number of outlets served - Basins:
0fd663e9-ba0b-5369-a6eb-109331e61414 | textbox | Number of outlets served - Showers:
f679e83a-7610-5a8b-94c9-3a4cb399183a | textbox | Total number of mixing valves on site:
a0af0018-51be-5c98-ac24-9fc4ba2d24a6 | button | Does the installation comply with the manufacturer's/supplier's published installation instructions? | No,Yes
2c3519de-b6eb-5748-9912-adc5862bd855 | button | Does the installation comply with the current requirements of the local water supply authority? | No,Yes
c1afa83c-8620-53a2-bbc6-30195bd5eb29 | textbox | Temperature of hot water supply?
5469c0f1-a87c-5dec-b8af-ffaa2cb89ef7 | textbox | Temperature of cold water supply?
a9e8aaba-a2a8-5e15-ae04-f3c600f21166 | textbox | Temperature of warm water delivery at outlet fitting?
58c94c55-a085-5bf4-a63a-6f8686c68d4a | textbox | Dynamic pressure of hot water:
4882deed-a398-50a7-a596-cfe28dfab5a8 | textbox | Dynamic pressure of cold water:
2c52f738-3bf6-4f1e-abbe-0a47fc298b94 | checkpoint | Check fail safe operation (hot water at least 20c above warm water)
d889f445-2b68-4ab3-9cfd-0798a5649a13 | checkpoint | Commissioned by
9fc0a3ea-3d08-5e60-93a3-b41dca7ac4a0 | textbox | Commissioned by:
3799a94d-b1a7-50bc-ab5a-ad18b6dc72ba | textbox | Company name:
6d1a0fb8-2733-4b30-9a42-07b65369dc74 | checklist | TMV Routine Service Log Sheet V.040221 |  | TMV Routine Service Log Sheet
3aa489bf-906e-41b1-9625-a0b7d0762ddc | checkpoint | TMV Routine Service Log Sheet:
de108ca9-045b-51ec-ac90-9aaaf30a0f57 | textbox | Building name:
2d5406bd-1297-5966-bcaa-412d36893369 | textbox | Contact Person:
76669310-3155-5f84-a1e4-32321c8f99e3 | textbox | Address:
4d2da354-be7f-5050-a853-c621e26885c4 | textbox | Phone number:
6aff2f47-152c-55e2-8760-e73b51aca6a8 | textbox | Make of valve:
6dff3c39-83bf-593b-ba74-5be35611d6ff | textbox | Model number:
3e3939fd-3737-521c-9078-297762e602ad | textbox | Valve location:
76cfd843-4753-5fc7-b3ad-28fb16d3e130 | textbox | Room name:
2d02dafb-8985-57a1-a6c1-83fa530649ff | textbox | Date of service:
1bbea2b5-feae-5eb0-acef-198adfecc344 | textbox | Outlet water temperature:
051a6086-0156-5ebe-acec-4f674dc705d8 | button | Outlets flushed for 15 seconds | Yes, No
ae7bd563-d881-58c3-bc72-fb0bc49c83b2 | button | Shower heads disinfected | Yes, No
3534533e-e201-524c-84e0-40a5fe48fbc9 | textbox | Serviced By:
a8e4d684-68da-4f67-95af-099937d7e72c | checkpoint | Recommended Service Periods
c8115d3a-fb00-5228-a6d4-d30cf1c9d60d | note | Outlet water temperature = Fortnightly
2f59439a-ed9f-590a-9968-f743e6bb7300 | note | Flushing of outlets = Weekly
0b250475-3026-57ce-b49d-01315bb3266a | note | Disinfect shower heads = Monthly
efadc1dd-2ac8-437c-9c22-7b6636f0693f | checkpoint | Completed by:
f067c984-d2fe-562a-b041-22f787cf4c8d | textbox | Plumber Name:
62c47805-03c4-4e19-9d2f-3a6a721b4aa1 | signoff | Add Signature
8eec95fa-497c-4040-8c9e-d7a3102bfd42 | checklist | VHH - Water Protection ITP (V.090421) |  | VHH - Water Protection -
1106b99f-fc56-4cfe-83ab-3d7e20e6002d | section | Part 1 - VHH Periodic Flushing / Copper Protection Test Sheet
a3131085-a926-48c7-b062-e15c8981a087 | checkpoint | ITP details
fcfab434-52ef-5781-8af5-7bf05365c406 | note | Copper systems are failing in the construction industry due to issues relating to design, water quality, the management of water during construction, long term maintenance of buildings with issues arising from building management team not following protocols outlined at hand over. Stagnant water being left in both hot and cold copper pipelines have been deemed to have been a contributing factor to recent copper failures. Copper needs to form a protective layer of copper oxide on the internal surface which is formed by the contact with fresh aerated and oxygenated water
4233a24e-5a14-5b7f-9fbf-9c6a2f675485 | note | Geschke Plumbing in consultation with John Holland & AECOM have put forward a proposal of periodic flushing of the systems during construction to mitigate the stagnant water issues that have arisen in the construction industry. The purpose of this ITP is to help create a strategy to ensure water is flowing through the piping system and flushed at nominated locations
f5fe9278-8bae-50a9-895f-e840313293c4 | note | Plans to flush to be submitted to John Holland prior to any flushing occurring on site
e475c560-1525-4383-b0e3-83a1586cd7de | checkpoint | Flushing Details (Flushing to be Completed with Water ONLY)
74024900-81bc-5f94-8315-cb6e454ced1a | textbox | Level being flushed
ab5e1661-4f72-5eaf-8cd4-69cc40985f8f | note | Stage of Flushing During the Project
77da9493-50b8-5488-a816-ef7e305961b1 | tickbox | 1. Initial flush after installation of pipework and prior to Quality Control Pressure Test Report (Geschke QA 6)
93b5a8e4-acdf-53c9-bfeb-fd76c1a0261c | tickbox | 2. Final flush post disinfection
42883cbb-6f5f-5393-8d9c-cca7cb1c7265 | tickbox | 3. Periodic flushing during construction (to be completed every 4 weeks in line with AS 4809 clause 6.2.9)
ac3e2040-0dc0-5241-9f0a-77bd8d3a3c0a | tickbox | 4. Periodic flushing from final flush until PC (to be completed every 4 weeks in line with AS 4809 clause 6.2.9)
8daff784-653f-445d-9a9f-3867f580ff25 | checkpoint | Time & Type of Flushing (As per reference table below)
a8bda40b-d021-548c-a4af-8f71e96dd0bc | tickbox | 5. Ring main Single point for flushing; the entire loop can be achieved in a maximum 10-minute flush
efe7688e-9f0a-595b-83c8-11b3f5590481 | tickbox | 6. Non ring mains Any copper sub-branch from the main feed requires individual flush time of 5 minutes (an example of this would be a corridor feed)
161d9c49-2ce9-53e9-b131-db0465d29e13 | tickbox | 7. Short branches of copper that feed rehau do not need individual flushing
2501e3e8-db1c-40a1-8d11-b3530f756570 | checkpoint | Which fixtures are being used to flush the system (Point of Connection & Point of Discharge)
4646e70f-770b-5133-ab99-6cd711d81e64 | note | Fixture 1
206a4a04-c25f-53c8-8883-6881b16882ff | textbox | Start time of flushing
adef5a3d-1b20-525c-bbac-90a5ac9b80fb | textbox | Zone/branch to be flushed
53cc672d-2296-57de-abb1-354040a8e5fe | textbox | Finish time of flushing
6d30accf-e002-5b3e-948b-57a96307c83e | textbox | Zone/branch to be flushed
8589a259-eb52-57ed-ab7b-0b7c1949cf2b | note | .. ..
54ca1775-0dbe-5351-a3d4-bc035786ca9f | note | Fixture 2
ceb686f2-dfe9-5f7a-9fa2-8158c3870e1f | textbox | Start time of flushing
30682b25-ad5f-58f3-b795-5703d572d605 | textbox | Zone/branch to be flushed
dbd02dff-f361-5eb9-9873-c09e6f68d91c | textbox | Finish time of flushing
e7ce8746-1938-58ce-948e-8dbe40d3ec5c | textbox | Zone/branch to be flushed
4614c0dc-7d2e-5222-991e-97bfce035efe | note | .. ..
5e0885a1-fe9b-5322-9505-3f66db2f2950 | note | Fixture 3
96a1bcef-6c54-5f16-8d10-8e1b241a253a | textbox | Start time of flushing
228bb253-8118-56f8-a3c8-28f8955d21ac | textbox | Zone/branch to be flushed
e9710f36-e9b3-5467-95ca-c12aef7e2f78 | textbox | Finish time of flushing
ec683d79-6d8e-5617-ab04-31b1fcca6c60 | textbox | Zone/branch to be flushed
44154805-9979-52a4-98a9-b6614ae0d9f4 | note | .. ..
d8c3352a-c17e-5131-9b6f-b61a337746e2 | note | Fixture 4
98a53cc5-bc1f-588f-970f-5da64e9683a0 | textbox | Start time of flushing
844a5e19-f798-59e6-b750-de6dd61293a9 | textbox | Zone/branch to be flushed
00017df9-98f7-57ef-840c-cc5b36e8bf43 | textbox | Finish time of flushing
1be4723e-9810-575f-b72f-6ddd31fc52f7 | textbox | Zone/branch to be flushed
640715f2-b842-56f3-b335-b5cbaf49b903 | note | .. ..
f862734a-75ea-5582-9be6-2d5cd4ecc47a | note | Fixture 5
c1c7c272-948e-563f-9dcc-81bf2c50e9e5 | textbox | Start time of flushing
b5f2317a-c511-5307-b8da-c39d8d10f1d4 | textbox | Zone/branch to be flushed
a1d1352f-27c8-569d-8ce6-747a928e261c | textbox | Finish time of flushing
9ade41be-ebb8-52f9-a9da-6d2c78ede42d | textbox | Zone/branch to be flushed
282b4793-1ca1-540d-8e5a-0487fa39cac0 | note | .. ..
4a2c7ca6-f142-4e0f-acbf-348afc5e3251 | checkpoint | Sign-Off - Pass once entered
91281d5c-40c7-5ba2-a255-9657d74cc550 | note | Add comments/photos below as applicable
561e7093-533a-540c-adb7-e831497d560b | button | a. Has the schematic / layout of the flushed zone been highlighted, attached and flush points nominated | Yes, No
560cbbcd-2da2-5572-8e97-3480349ab156 | button | b. Is the flushed water clear with no visible debris or dirt. If NO, discuss with project foreman and or head office on why this might be the case | Yes, No
1accc7a6-8853-5d7d-9878-66d10c015132 | button | c. Have you set a reminder for the next flushing of this pipework | Yes, No
84e71b54-5c93-5f05-bb43-c3c97e9f1a35 | textbox | Test completed by
892166ea-023b-5edf-bb50-dad20e4fb319 | textbox | Date for next flushing (Flushing to be performed every 4 weeks at a minimum)
130d86d3-d830-4ec3-aaab-a294fb7a0932 | signoff | Click to add Builders Signature(s)
5b2cba2d-abbb-43f0-881d-20658af58566 | checkpoint | Reference Table
bd3a1249-5a68-5596-9b2e-f0ab71778bda | note | 25mm Pipe / 0.49 (L/m) / Flush for 0.15 (Mins)
b7f4ac3b-ba99-540d-979b-b28b757933cc | note | 32mm Pipe / 0.80 (L/m) / Flush for 0.25 (Mins)
f8d184c0-8edc-5470-a243-1a424a9d46cb | note | 40mm Pipe / 1.26 (L/m) / Flush for 0.39 (Mins)
277a0a6f-ad75-5305-a8a0-c2bb167e63f6 | note | 50mm Pipe / 1.96 (L/m) / Flush for 0.61 (Mins)
c8dfbc04-76ce-5e62-ad29-4be64b7fd7b7 | note | 65mm Pipe / 3.32 (L/m) / Flush for 1.04 (Mins)
68ad44be-fee7-5576-985e-cbddb68ac7bf | note | 80mm Pipe / 5.02 (L/m) / Flush for 1.57 (Mins)
15e2733f-adda-573d-8662-07ce9326fce8 | note | 100mm Pipe / 7.85 (L/m) / Flush for 2.46 (Mins)
9587bba6-14d7-543c-b2e3-502a3024c135 | note | 150mm Pipe / 17.66 (L/m) / Flush for 5.53 (Mins)
deae1bc4-ed6c-5779-8451-cc18cea8e4db | note | NOTE: The table flushing time is based on 100 metres of pipework discharging through 16mm nozzle at 350KPa
439c27fa-0b08-4ef0-bb92-5f7c3be27bae | section | Part 2 - Water Quality Testing Frequency
0d759abe-6f6e-4d9f-b771-6b678955a6fe | checkpoint | Water Quality Testing Details
438896da-08aa-5879-829c-790aa69d45d1 | note | Stage of water quality testing during the project
07cdd341-5c1d-5ad7-8b40-a0f63b433925 | tickbox | 1. Periodic water quality testing during construction (to be completed every 3 months)
4815eebc-9e85-5f0e-8387-e3f0da53b5c3 | tickbox | 2. Water quality testing post final flush
a09c6076-9c53-4ea5-9643-4cf08ec6af09 | checkpoint | Sign-Off - Pass once entered
7bf2cffe-acaf-5cbc-8272-61c59b6bcfe5 | note | Add comments/photos below as applicable
81f60b49-cab4-574c-81a8-773e6fe21a4f | button | a. Geschke and John Holland management informed of sample / testing | Yes, No
dacf1719-7f8c-508f-9821-6f6e2c5d2ccd | button | b. Has the schematic / location of the sample collection been highlighted, attached, and nominated | Yes, No
940cea3d-137d-5fb0-a3a1-6d52a7936d42 | button | c. Sample captured as per laboratory requirements | Yes, No
a6e500d9-aa50-5d91-ba0e-f119f65ca94b | button | d. Time and date of sample recorded | Yes, No
cda5dd94-3661-5564-9807-60aeb465778b | textbox | Time of Sample
5acbbee5-3e62-5b25-abd1-656118b1c0c3 | textbox | Date of Sample
b3e41faf-6503-516d-a257-cb069ce0c55b | textbox | Location of Sample
58a7cc12-323b-593d-a532-8ed1e0bf2bf5 | note | .. ..
8246125b-b1aa-55d6-a5fe-9099135e1c6a | textbox | Sample collected by
7c94540d-960d-5ace-b608-209008bbe8f9 | textbox | Date for next Water Quality Sample (Water quality testing to be performed every 3 months at a minimum during construction)
1adfbf83-3b45-4895-b2de-c05b04bbf20d | signoff | Click to add Builders Signature(s)
647d68c7-474c-4392-8887-e864b753e51d | section | Part 3 - Disinfection of Pipework & Tank
593ae028-a8b2-48b5-8a20-92b24b8a53f5 | checkpoint | Disinfection Checks - Pass once below completed
59a92363-f60b-51c3-b588-62aa2200246f | note | Add comments/photos below as applicable
82d5dbc8-4537-5ab6-a7fa-88d4b7387557 | button | a. Geschke and John Holland management informed of disinfection with plan provided | Yes, No
818cbf4b-bd4a-5581-86f9-4965a506f07f | button | b. Has disinfection occurred for 6 hours as per AS/NZS 3500.1 appendix I | Yes, No
7d9bdc8f-70ca-52af-8e45-94941949b8c2 | button | c. Time and date of disinfection | Yes, No
156ceef9-0a8f-56d5-9ff2-d98664cc0295 | button | d. Flush all levels and branches until chlorination levels have reached safe chlorine levels as per Australian drinking water guidelines. | Yes, No
51793f46-81c3-57f8-a745-00d9e6ddd788 | textbox | Time of Disinfection
c740c100-bab7-5902-a74b-d69b32a7b84a | textbox | Date of Disinfection
a6167667-d0d0-5f78-91d1-b7e3d67ee610 | note | .. ..
0c40b44d-41d9-5d0e-aa84-c2b43807c05d | textbox | Disinfection Completed by
f592805c-b46f-4f19-a356-f75cf0c45e98 | signoff | Click to add Builders Signature(s)
7d31e301-6832-4706-8e67-671cd649b63a | checklist | zSYS - TMV 12 Month Service Log V.040221 (old version) |  | TMV 12 Month Service Log (use a separate checklist for each valve)
e5fbe876-8a3e-40a8-aad1-468ca2f4f906 | checkpoint | TMV 12 Month Service Log
3fbe4c28-6ad5-543f-8833-c2dd0be9f62f | textbox | Building name:
2d656847-717d-58fb-8aa8-25f0a93824e2 | textbox | Contact person:
f5d9b259-1878-5cbf-bf8a-660cb4ab25de | textbox | Address:
1107afbb-2821-54da-b547-350c969bbf6e | textbox | Phone number:
c398eeeb-f5b3-5466-bfbd-532c69266cf9 | textbox | Make of valve:
0c12b722-d46a-5dad-814e-f065d6923229 | textbox | Model number:
26a5dad7-14a5-55b3-9f9a-5dc2f35a6d12 | textbox | Valve location:
13ab5eb0-8fc3-5757-b5df-b9bddaff4c16 | textbox | Room name:
8df9c017-58e2-5f5a-9436-6e153a1637f5 | textbox | Date of service:
ce1154d6-94ab-5963-ad29-a1a60660d06a | button | Element: | Ok, Faulty
8f914401-3813-5f18-82d1-5a41c09f054f | button | O' rings: | Ok, U, S
59fe50a5-b450-5136-be5a-7971ff4d4c88 | button | Strainers: | Ok, Dirty
96589ee1-910e-5f6f-a274-856a72d3191f | button | Non-return Valves | Ok, Faulty
77bf64e8-b9a0-5ee0-9f13-282a86b83ced | button | Fail-safe test | Ok, Faulty
0ab7082a-a0ed-515d-95cd-8f78563aa49e | textbox | Serviced by:
bb341c9a-53eb-5138-8cab-8064aabc2355 | note | Note: It is recommended that a new thermostatic element should be fitted at least every 5 years
df050261-04ec-49e8-9569-1c1d3092a704 | checkpoint | Completion
a7eacff3-34c9-5395-ab9c-5f82dfb2fa1f | textbox | Plumber Name:
f5343cc6-510c-4ee7-bf69-8575b82172e4 | signoff | Add Signature