## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-244-STR-HOP-Bored Piling sense 600 | itp |  |  |  |  | ITP-244-STR-HOP-Bored Piling sense 600 Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-244-STR-HOP-Bored Piling Sense 600
label | ITP Description: Bored Piling Sense 600
label | Discipline (e.g. CIV/STR/RAIL): 244-STR-HOP
label | Revision Number: 0
label | Revision Date: 3/03/2025
label | ITP created by: Manwel Kalyana
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 606 - July 2017
label | ○ VicRoads Section 610 - Feb 2020
label | ○ VicRoads Section 611 - November 2018
label | ○ AS2159-2009
label | ○ AS3810.1 2018
label | ○ AS5100.3-2017
label | ○ AS/NZS 4671 - 2019
label | ○ AS/NZS 1554.3 - 2017
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix
label | Reference - 610.07 Table 610.071
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | Reference - 611.05 (a)
label | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days of award of contract
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
label | Reference - 610.26 (a)
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Working Platform certification
label | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement. As per seperate ITP.
label | Method - Document Review
label | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | Category - HP
label | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Piling Operations Work Procedure
label | Reference - 606.03 (a)
label | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to the commencement of piling
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Temporary Steel Casings
label | Reference - 606.03 (b)
label | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, prior to use
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Casting Under Water Procedure
label | Reference - 606.06 (a)
label | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | Method - Document Review
label | Frequency - Where applicable, once, prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
label | Reference - 606.03 ( c)
label | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | Method - Document Review
label | Frequency - Where applicable, once, prior to commencement of boring
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Dynamic Pile Testing Procedure
label | Reference - 606.07 (c)
label | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, prior to testing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
label | Reference - 606.07
label | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | ○ Details of the consultant to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, two weeks prior to testing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, AS/NZA4671 - 2019, 611.14 (b)
label | Acceptance Criteria - All welding procedures shall be provided to the engineer and proof engineer for review for compliance with the design requirements.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Reinforcement Welding Specifications & Qualifications
label | Reference - 611.13 (a) & (b), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b), AS/NZA4671 - 2019
label | ○ IFC Drawings
label | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
label | Acceptance Criteria - All quality documentation and test results to support the prequalification of the welding procedures shall be provided to the engineer and proof engineer to demonstrate compliance with the design requirements.
label | ○ This documentation, along with the engineer's and proof engineer's endorsement, shall be submitted to dtp for review, prior to commencement of welding reinforcement to be used in the structure.
label | i. all welded splices for sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017 and the requirements of section 611.14(b). welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
label | ii. engineer and qualified welding personnel shall be engaged to develop welding procedures for the welded joints of 600N reinforcement bars for hopkins road bridge, and to propose testing programs for the welded joints;
label | iii. testing of welds shall be performed;
label | iv. the testing results shall be reviewed by engineer and demonstrate the testing results meet the design requirements for the welded joints;
label | v. the satisfactory weld testing evidence together with the engineer’s assessment shall be submitted to dtp for review (not endorsement)
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Survey Set-out
label | Reference - IFC Drawings 606.08 (a - c)
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Surveyor, SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Protection of Adjacent Piles
label | Reference - 606.04
label | Acceptance Criteria - Pile construction shall not:
label | i. result in damage to adjacent newly cast piles due to ground vibration.
label | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - HP*
label | Responsibility - SPE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Boring Operations
label | Reference - IFC Drawings 606.03 (a)
label | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | ○ Excavation clean and de-watered (where applicable) for inspection.
label | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Formwork Extension
label | Reference - IFC Drawings
label | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | Method - Measure, Visual
label | Frequency - Where applicable, each pile
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Inspection of Pile Excavation
label | Reference - 606.05
label | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | ○ Attach: Geotechnical Field Sheet or Report
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - HP
label | Responsibility - Geotechnical Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Reinforcement - Placement
label | Reference - IFC Drawings
label | ○ 611.06
label | ○ 611.09
label | ○ 611.10
label | ○ 611.11
label | ○ 611.12
label | ○ 606.06 (a)
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Reinforcement - Electrical Continuity
label | Reference - IFC Drawings 610.29 (d), 610.43, AS/NZS 1554.3-2017
label | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2, 611.13 (a)
label | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
label | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | ○ Welding of sense 600 reinforcement shall comply with the requirements of dtp specification 611 and as/nzs 1554.3-2017 with the following modifications:
label | i. tack welding of sense 600 reinforcement is also permitted, provided welding is not within 50mm of the tangent point of a bend in the steel.
label | ii. all tack welding of sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017. welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
label | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | Method - Measure, Visual
label | Frequency - Where applicable, each pile
label | Category - IP
label | Responsibility - Earthing Engineer, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Cast-in Items
label | Reference - IFC Drawings 610.46 (a) Table 610.462, 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
label | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | Method - Measure, Visual
label | Frequency - Where applicable, each pile
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Pre-pour Inspection
label | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the excavation.
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Weather Conditions & Evaporation Limits
label | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Measure, Visual
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.9 - Concrete Testing - Sampling Frequency
label | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | — 0m³ to 10m³ = 1 sample
label | — 10m³ to 25m³ = 2 samples
label | — 25m³ to 50m³ = 3 samples
label | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken. where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
label | Reference - 610.13 (b)
label | Acceptance Criteria - Spread range = 550mm to 750mm
label | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | ○ Passability = ≤10mm (aggregate height differential)
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample of Self-compacting Concrete
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
label | Reference - Site Sampling & Testing Procedure 610.16
label | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
label | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
label | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | ○ All concrete batches are traceable.
label | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged. The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | ○ Record: Required information on the Concrete Pour Record.
label | ○ Attach: Concrete Pour Record
label | ○ Attach: Concrete Dockets
label | Method - Visual
label | Frequency - Each load
label | Category - SP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents -
date | Date Completed:
checkpoint | 5.13 - Surface Finishes
label | Reference - IFC Drawings 610.31, 610.20
label | Acceptance Criteria - Surface finish as per IFC drawings.
label | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | Method - Visual
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Pile Trimming
label | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
label | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | ○ Any weak or damaged concrete shall be removed back to sound concrete.
label | Method - Measure, Visual
label | Frequency - Where applicable, each pile
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.2 - Compressive Strength Test Results
label | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cylinder
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Pile Integrity Testing
label | Reference - 606.07 (a, d & e), AS2159 Clause 8.8
label | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | ○ Cross-sectional area = ≥95%
label | ○ If any test fails, all piles shall be tested.
label | ○ Attach: Pile Integrity Test Report
label | Method - Document Review
label | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | Category - IP
label | Responsibility - Testing Consultant, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.4 - Static Load Testing
label | Reference - IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
label | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | ii. Creep rate = <2mm / log cycle of time at the test load
label | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | ○ Attach: Static Load Test Report
label | Method - Document Review
label | Frequency - Where applicable, as shown on the IFC Drawings
label | Category - IP
label | Responsibility - Testing Consultant, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.5 - Dynamic Pile Testing
label | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
label | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | ○ Measured Ultimate capacity = ≥ values on IFC drawings
label | ○ Attach: Dynamic Pile Test Report
label | Method - Document Review
label | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | ○ At least 1 test per 10 piles
label | Category - IP
label | Responsibility - Testing Consultant, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.6 - As-built Survey
label | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
label | Acceptance Criteria - The following tolerances apply to piles:
label | i. Pile head plan location = ±75mm
label | ii. Variance from vertical or rake = 1:100
label | iii. Irregularities in straightness = 1:100
label | iv. RL = ±25mm
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each pile
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.7 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-245-STR-HOP-Structural concrete sense 600 | itp |  |  |  |  | ITP-245-STR-HOP-Structural concrete sense 600 Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-245-STR-HOP-Structural Concrete Sense 600
label | ITP Description: Structural Concrete Sense 600
label | Discipline (e.g. CIV/STR/RAIL): 245-STR-HOP
label | Revision Number: 0
label | Revision Date: 3/03/2025
label | ITP created by: Manwel Kalyana
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 606 - July 2017
label | ○ VicRoads Section 610 - Feb 2020
label | ○ VicRoads Section 611 - November 2018
label | ○ AS2159-2009
label | ○ AS3810.1 2018
label | ○ AS5100.3-2017
label | ○ AS/NZS 4671 - 2019
label | ○ AS/NZS 1554.3 - 2017
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix
label | Reference - 610.07 Table 610.071 IFC Drawings
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | Reference - 611.05 (a)
label | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days of award of contract
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | Reference - 610.26 (a)
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Evaporative Retardant
label | Reference - 610.17 (f)
label | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Curing Compound
label | Reference - 610.23 (d)
label | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
label | Reference - 610.18 (a) (i)
label | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Concrete Sampling and Testing Procedure
label | Reference - 610.18 (a) (v)
label | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
label | Reference - 610.18 (a) (iv)
label | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | ○ Minutes of this meeting to be submitted to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
label | Reference - 610.17 (a)
label | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 2 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
label | Reference - 610.23 (a)
label | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Concrete Drilling Procedure
label | Reference - 610.46
label | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, 2 days prior to drilling
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Temprature difference measuring-Calibration
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Calibration records are valid and up to date.
label | ○ Attach: Calibration certificate
label | Method - Document review
label | Frequency - Where applicable
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - This ITP, Attached calibration certificate
date | Date Completed:
checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
label | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, AS/NZA4671 - 2019, 611.14 (b)
label | Acceptance Criteria - All welding procedures shall be provided to the engineer and proof engineer for review for compliance with the design requirements.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Reinforcement Welding Specifications & Qualifications
label | Reference - 611.13 (a) & (b), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b), AS/NZA4671 - 2019
label | ○ IFC Drawings
label | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
label | Acceptance Criteria - All quality documentation and test results to support the prequalification of the welding procedures shall be provided to the engineer and proof engineer to demonstrate compliance with the design requirements.
label | ○ This documentation, along with the engineer's and proof engineer's endorsement, shall be submitted to dtp for review, prior to commencement of welding reinforcement to be used in the structure.
label | i. all welded splices for sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017 and the requirements of section 611.14(b). welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
label | ii. engineer and qualified welding personnel shall be engaged to develop welding procedures for the welded joints of 600N reinforcement bars for hopkins road bridge, and to propose testing programs for the welded joints;
label | iii. testing of welds shall be performed;
label | iv. the testing results shall be reviewed by engineer and demonstrate the testing results meet the design requirements for the welded joints;
label | v. the satisfactory weld testing evidence together with the engineer’s assessment shall be submitted to dtp for review (not endorsement)
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Survey Set-out
label | Reference - IFC Drawings 610.47 (a) Table 610.472
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Excavation support
label | Reference - 602.02
label | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Where applicable, not less than 10 business days prior to excavation
label | Category - WP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.4 - Excavation Inspection
label | Reference - 602.03
label | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | Method - Visual
label | Frequency - Where applicable, prior to placing blinding concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction Activities
checkpoint | 5.1 - Formwork Design and Construction
label | Reference - IFC Drawings 614.04, 614.05, 614.06
label | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | Method - Document Review, Visual, Measure
label | Frequency - Each type of element
label | Category - IP
label | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | Reference - 614.08
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | ○ Walls with heights greater than 2.0 metres
label | ○ Any member for which self-compacting concrete is proposed.
label | ○ Attach: Attachment A
label | ○ Attach: Attachment B
label | Method - Document Review, Visual, Measure
label | Frequency - Each element (where greater than 2m)
label | Category - HP
label | Responsibility - Temporary Works Designer, Proof Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | Reference - 614.08
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | ○ Walls with heights less than 2.0 metres
label | ○ Attach: Attachment C
label | Method - Document Review, Visual, Measure
label | Frequency - Each element (where 2m or less)
label | Category - HP
label | Responsibility - Temporary Works Designer, Proof Engineer
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Pre-pour Survey
label | Reference - 610.47 (a) Table 610.472
label | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
label | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP*
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Reinforcement Placement
label | Reference - IFC Drawings
label | ○ 611.06
label | ○ 611.09
label | ○ 611.10
label | ○ 611.11
label | ○ 611.12
label | ○ AS5100.5-2017
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Cast-in Items
label | Reference - IFC Drawings 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
label | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
label | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | ii. Running dimensions of a group of the above = ±6mm
label | iii. Ducts and conduit location = ±12mm
label | iv. Diameter of ducts and conduits = ±3mm
label | Method - Measure, Visual
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Thermal Differential Monitoring
label | Reference - 610.22
label | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
label | ○ Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | Method - Measure
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.8 - Pre-pour Inspection
label | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
label | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ○ All foreign material has been completely removed from the forms.
label | ○ ATTACH: Pre-Pour Checklist
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - Weather Conditions & Evaporation Limits
label | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
label | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.10 - Concrete Testing - Sampling Frequency
label | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | — 0m³ to 10m³ = 1 sample
label | — 10m³ to 25m³ = 2 samples
label | — 25m³ to 50m³ = 3 samples
label | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | ○ For each additional 50m³ and additional sample shall be taken.
label | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each element
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.11 - Concrete Testing - Slump
label | Reference - 610.16 (c)
label | Acceptance Criteria - Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | — Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample of Standard or Superplasticised Concrete
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
label | Reference - 610.13 (b)
label | Acceptance Criteria - Spread range = 550mm to 750mm
label | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | ○ Passability = ≤10mm (aggregate height differential)
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample of Self-compacting Concrete
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
label | Reference - Site Sampling & Testing Procedure
label | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Test
label | Frequency - Each sample
label | Category - IP
label | Responsibility - Concrete Tester
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.14 - Supply & Discharge Rates
label | Reference - 610.13 (a) & (f)
label | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | ○ No water is to be added once discharge commences.
label | ○ Maximum time between batching trucks is 25 minutes.
label | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
label | ○ Record: Required information on the Concrete Pour Record.
label | Method - Measure, Visual
label | Frequency - Each load
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.15 - Placement & Compaction
label | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
label | Acceptance Criteria - All concrete batches are traceable.
label | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ○ Concrete is not dropped freely from a height exceeding 2m.
label | ○ Concrete is not moved horizontally by use of vibrators.
label | ○ Adequate compaction is ensured
label | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | ○ Concrete layers are not more than 350mm
label | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | ○ Record: Required information on the Concrete Pour Record.
label | ○ Attach: Concrete Pour Record
label | ○ Attach: Concrete Dockets
label | Method - Visual
label | Frequency - Each load
label | Category - SP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP, Concrete Pour Record
date | Date Completed:
checkpoint | 5.16 - Surface Finishes
label | Reference - IFC Drawings 610.31, 610.20
label | Acceptance Criteria - Surface finish as per IFC drawings.
label | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.17 - Curing-Top Surface
label | Reference - IFC Drawings
label | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.18 - Curing after formwork removal
label | Reference - IFC Drawings
label | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Thermal Differential Monitoring
label | Reference - 610.22
label | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | ○ Only applicable if the element has:
label | i. the smallest sectional dimension exceeding 500mm
label | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | ○ Attach: Thermal Monitoring Report
label | Method - Document Review
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
label | Reference - IFC Drawings Table 610.251
label | Acceptance Criteria - Minimum Period before Removal of Formwork and Formwork Supports is 7 days or until such time as the concrete has reached the specified 7 day compressive strength, whichever is the greater.
label | ○ Attach: 7 days Concrete Test Results Result
label | Method - Document Review
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Surface Inspection - Cracks
label | Reference - 610.24
label | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | Method - Visual, Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.4 - Surface Inspection - Surface Finish
label | Reference - IFC Drawings 610.31 (a) - (n), 610.32
label | Acceptance Criteria - Comply with the IFC drawings and specifications.
label | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.5 - Measurement of Concrete Cover
label | Reference - 610.34
label | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | ○ Minimum 10 no. measurements recorded in each area.
label | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | ○ Attach: Covermeter Check Record
label | Method - Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
label | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
label | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | ○ Attach: Concrete Test Results or Maturity Test Results
label | Method - Document Review
label | Frequency - Where applicable, each substructure element
label | Category - SP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.7 - Compressive Strength Test Results
label | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cylinder
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.8 - As-built Survey
label | Reference - IFC Drawings 610.47 Table 610.472
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.9 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP