## Table 1
Abbreviations
Third Party |  |  | TP |  | RSA Contractors | RSA | Nominated Project Personnel |  |  |  | NPP | Principle Contractor |  |  | PC
Surveyor |  |  | SUR |  | RPEQ | RPEQ | Supervisor |  |  |  | SUP | Inspect |  |  | INS
Test |  |  | TST |  | Project Engineer | PE | Witness Point |  |  |  | WP | Hold Point |  |  | HP
Visual |  |  | VIS |  | Check | CHK | Written |  |  |  | WRI | Monitor |  |  | M
Milestone |  |  | MST |  | Review | R
Inspection and Test Plan Details | [11 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By |  | Standard / Spec | Criteria |  |  | Frequency |  | Record | Resp | Type | Signoff | Resp | Type | Signoff
1 | Lot Identification |  | Contractor |  | Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Location of Works identified in accordance with project technical specification |  |  | 1/Lot |  | ITP Verification Checklist/Lot Map | RSA | Check |  | Senex | Check
2 | Lot Identification – Lot Plan |  | Contractor |  | Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required) |  |  | Prior to commencement |  | ITP Verification Checklist / Lot Plan | RSA | Hold Point |  | Senex | Hold Point
3 | Underlying Lot Conforms |  | Contractor |  | Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification. |  |  | 1/Lot |  | ITP Verification Checklist/Lot Map | RSA | Hold Point |  | Senex | Hold Point
4 | Placement of General Fill – Outer Zone and Inner Zone |  | Contractor |  | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology. Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination. Overfill to outer edges of embankment to allow for trim back to design surface Completed under Level 2 Testing |  |  | Each Lot |  | ITP Verification Checklist/Lot Map | RSA | Check |  | Senex | Witness Point
Inspection and Test Plan Details | [11 empty] | Contractor |  |  | Client
Item | Inspection Activity |  | Work By |  | Standard / Spec | Criteria |  |  | Frequency |  | Record | Resp | Type | Signoff | Resp | Type | Signoff
5 | Placement of Select Fill (if required) |  | Contractor |  | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0 Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness. The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material Finished surface to be free of all stones or other objects with potential to puncture liner. Completed under Level 2 Testing |  |  | 1 / Lot |  | ITP Verification Checklist/Lot Map | RSA | Check |  | Senex | Witness Point
6 | Testing – Outler Layer Density and Moisture |  | Contractor |  | Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 & 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) |  |  | 1 / 500m3 |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
7 | Testing – Outler Layer Material Quality |  | Contractor |  | Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below) |  |  | See Criteria |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
8 | Testing – Inner Layer Density and Moisture |  | Contractor |  | Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 & 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) |  |  | 1 / 500m3 |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
9 | Testing – Inner Layer Material Quality |  | Contractor |  | Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below) |  |  | See Criteria |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
10 | Testing – Select Fill Density and Moisture |  | Contractor |  | Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 & 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) |  |  | 1 / 500m3 |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
11 | Testing – Select Fill Material Quality |  | Contractor |  | Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below) |  |  | See Criteria |  | ITP Verification Checklist / Report | RSA | Check |  | Senex | Witness Point
12 | Rework / Repairs to fill (if required) |  | Contractor |  | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.  If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.  If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.  If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.  If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification. Retesting (if required) in line with requirements of the Zone being repaired. |  |  | As required |  | ITP Verification Checklist/Lot Map | RSA | Hold Point |  | Senex | Hold Point
13 | Survey – Progress |  | Contractor |  | Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement. |  |  | 25%, 50%, 75% |  | Survey | RSA | Check |  | Senex | Hold Point
13 | As-constructed Survey |  | Contractor |  | Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0 | After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance. Tolerances  Embankment Crest o -0 / +200mm  Liner Subgrade o -20 / +50mm  Final Liner Subgrade Grader o Within 1/20th specified grade  Emergency Spillway (invert) o -20 / +20mm  Extraction Pipework o ±50mm |  |  | 1/Lot |  | Survey | RSA | Hold Point |  | Senex | Hold Point
Notes: 1. HILF test method (AS 1289.5.7.1) may replace Standard Compaction test method specified provided conditions of Section 9.5 OPS-TETW-CS-SPE-001 IFC Rev 0 are satisfied.
Test Details | [5 empty] | Normal Testing Level | [5 empty] | Required Result(s)
General Fill Outer Zone
Item | Test |  |  | Description |  | Max Lot Size |  | Min Test Frequency |  | Min No of tests |  | Criteria
1 | AS 1289 2.1.1 AS 1289 5.1.1 AS 1289 5.4.1 AS 1289 5.8.1 |  |  | Standard Moisture Content and Dry density ratio |  |  |  | 1/500 m3 |  | 1 Test per Every Layer per Lot |  | -2% dry to +2% wet OMC MDD 98% Refer Note 1
2 | AS 1289 3.6.1 |  |  | Particle size |  |  |  | 1/1000m3 |  | 1 Test per Every Layer per Lot |  | Passing 75mm 100% Passing 19mm 80% - 100% Passing 2.36mm 30% - 100% Passing 0.075mm 15%-80%
3 | AS 1289 3.3.1 |  |  | Plasticity Index |  |  |  | 1/1000m3 |  | 1 Test per Every Second Layer per Lot |  | 10 to 40
4 | AS 1289 3.2.2 |  |  | Liquid Limit |  |  |  | 1/1000m3 |  | 1 Test per Every Second Layer per Lot |  | 20 to 60
5 | AS 1289 3.8.1 |  |  | Emerson class | [5 empty] | 5 Test evenly distributed around the Dam |  | 2
6 | AS 1289 4.1.1 |  |  | Organic content | [5 empty] | As per Superintendent recommendation
Test Details | [5 empty] | Normal Testing Level | [5 empty] | Required Result(s)
General Fill Inner Zone
Item | Test |  |  | Description |  | Max Lot Size |  | Min Test Frequency |  | Min No of tests |  | Criteria
1 | AS 1289 2.1.1 AS 1289 5.1.1 AS 1289 5.4.1 AS 1289 5.8.1 |  |  | Standard Moisture Content and Dry density ratio |  |  |  | 1/500 m3 |  | 1 Test per Every Layer per Lot |  | -1% dry to +2% wet OMC MDD 98% Refer Note 1
2 | AS 1289 3.6.1 |  |  | Particle size |  |  |  | 1/3000m3 |  |  |  | Passing 75mm 100% Passing 19mm 80% - 100% Passing 2.36mm 30% - 100% Passing 0.075mm 15%-100%
3 | AS 1289 3.3.1 |  |  | Plasticity Index |  |  |  | 1/3000m3 |  |  |  | 10 to 50
4 | AS 1289 3.2.2 |  |  | Liquid Limit |  |  |  | 1/3000m3 |  |  |  | 20 to 70
5 | AS 1289 3.8.1 |  |  | Emerson class | [5 empty] | 5 Test evenly distributed around the Dam |  | 2
6 | AS 1289 4.1.1 |  |  | Organic content | [5 empty] | As per Superintendent recommendation
Test Details | [5 empty] | Normal Testing Level | [5 empty] | Required Result(s)
Select Fill
Item | Test |  |  | Description |  | Max Lot Size |  | Min Test Frequency |  | Min No of tests |  | Criteria
1 | AS 1289 2.1.1 AS 1289 5.1.1 AS 1289 5.4.1 AS 1289 5.8.1 |  |  | Standard Moisture Content and Dry density ratio |  |  |  | 1/500 m3 |  | 1 Test per Every Layer per Lot |  | -1% dry to +2% wet OMC MDD 98% Refer Note 1
2 | AS 1289 3.6.1 |  |  | Particle size |  |  |  | 1/1000m3 |  |  |  | Passing 2.36mm 100% Passing 0.075mm 35%-100%
3 | AS 1289 3.3.1 |  |  | Plasticity Index |  |  |  | 1/1000m3 |  |  |  | 10 to 50
4 | AS 1289 3.2.2 |  |  | Liquid Limit |  |  |  | 1/1000m3 |  |  |  | 20 to 70
5 | AS 1289 3.8.1 |  |  | Emerson class
6 | AS 1289 4.1.1 |  |  | Organic content | [5 empty] | As per Superintendent recommendation
Built in accordance with this document: | [5 empty] | Signed Position | [5 empty] | Date
Test results received. Lot conforms to Specification: | [5 empty] | Signed Position | [5 empty] | Date
Document Status
Revision Status |  | Responsible Person |  |  | Signed | Dated | Revision
Draft By: |  | Sean Parsons |  |  |  | 2024-06-28 | Draft Rev A
Reviewed By: |  | Sean Parsons |  |  |  | 2024-06-28 | Rev 0
Submitted By: |  | Sean Parsons |  |  |  | 2024-06-28 | Rev 0
Approved By: |  | Sean Parsons |  |  |  | 2024-06-28 | Rev 0