## Sheet1
01 | Lot Identification | Contractor | Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Location of Works identified in accordance with project technical specification | 1/Lot | ITP Verification Checklist/Lot Map | RSA | Check | Senex | Check | 01 - Lot Identification | Work By - Contractor | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - Location of Works identified in accordance with project technical specification | Frequency - 1/Lot | Record - ITP Verification Checklist/Lot Map | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Check | 01 - Lot Identification
02 | Lot Identification – Lot Plan | Contractor | Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required) | Prior to commencement | ITP Verification Checklist / Lot Plan | RSA | Hold Point | Senex | Hold Point | 02 - Lot Identification – Lot Plan | Work By - Contractor | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required) | Frequency - Prior to commencement | Record - ITP Verification Checklist / Lot Plan | Contractor: Resp - RSA | Contractor: Type - Hold Point | Client: Resp - Senex | Client: Type - Hold Point | Work By - Contractor
03 | Underlying Lot Conforms | Contractor | Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification. | 1/Lot | ITP Verification Checklist/Lot Map | RSA | Hold Point | Senex | Hold Point | 03 - Underlying Lot Conforms | Work By - Contractor | Standard / Spec - Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification. | Frequency - 1/Lot | Record - ITP Verification Checklist/Lot Map | Contractor: Resp - RSA | Contractor: Type - Hold Point | Client: Resp - Senex | Client: Type - Hold Point | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
04 | Placement of General Fill – Outer Zone and Inner Zone | Contractor | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology. Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination. Overfill to outer edges of embankment to allow for trim back to design surface Completed under Level 2 Testing | Each Lot | ITP Verification Checklist/Lot Map | RSA | Check | Senex | Witness Point | 04 - Placement of General Fill – Outer Zone and Inner Zone | Work By - Contractor | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology. Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination. Overfill to outer edges of embankment to allow for trim back to design surface Completed under Level 2 Testing | Frequency - Each Lot | Record - ITP Verification Checklist/Lot Map | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Criteria - Location of Works identified in accordance with project technical specification
05 | Placement of Select Fill (if required) | Contractor | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0 Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness. The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material Finished surface to be free of all stones or other objects with potential to puncture liner. Completed under Level 2 Testing | 1 / Lot | ITP Verification Checklist/Lot Map | RSA | Check | Senex | Witness Point | 05 - Placement of Select Fill (if required) | Work By - Contractor | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0 Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness. The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material Finished surface to be free of all stones or other objects with potential to puncture liner. Completed under Level 2 Testing | Frequency - 1 / Lot | Record - ITP Verification Checklist/Lot Map | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Frequency - 1/Lot
06 | Testing – Outler Layer Density and Moisture | Contractor | Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | 1 / 500m3 | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 06 - Testing – Outler Layer Density and Moisture | Work By - Contractor | Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | Frequency - 1 / 500m3 | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Record - ITP Verification Checklist/Lot Map
07 | Testing – Outler Layer Material Quality | Contractor | Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below) | See Criteria | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 07 - Testing – Outler Layer Material Quality | Work By - Contractor | Standard / Spec - Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below) | Frequency - See Criteria | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Contractor: Resp - RSA
08 | Testing – Inner Layer Density and Moisture | Contractor | Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | 1 / 500m3 | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 08 - Testing – Inner Layer Density and Moisture | Work By - Contractor | Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | Frequency - 1 / 500m3 | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Contractor: Type - Check
09 | Testing – Inner Layer Material Quality | Contractor | Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below) | See Criteria | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 09 - Testing – Inner Layer Material Quality | Work By - Contractor | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below) | Frequency - See Criteria | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Client: Resp - Senex
10 | Testing – Select Fill Density and Moisture | Contractor | Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | 1 / 500m3 | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 10 - Testing – Select Fill Density and Moisture | Work By - Contractor | Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below) | Frequency - 1 / 500m3 | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | Client: Type - Check
11 | Testing – Select Fill Material Quality | Contractor | Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below) | See Criteria | ITP Verification Checklist / Report | RSA | Check | Senex | Witness Point | 11 - Testing – Select Fill Material Quality | Work By - Contractor | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below) | Frequency - See Criteria | Record - ITP Verification Checklist / Report | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Witness Point | 02 - Lot Identification – Lot Plan
12 | Rework / Repairs to fill (if required) | Contractor | Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.  If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.  If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.  If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.  If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification. Retesting (if required) in line with requirements of the Zone being repaired. | As required | ITP Verification Checklist/Lot Map | RSA | Hold Point | Senex | Hold Point | 12 - Rework / Repairs to fill (if required) | Work By - Contractor | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.  If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.  If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.  If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.  If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification. Retesting (if required) in line with requirements of the Zone being repaired. | Frequency - As required | Record - ITP Verification Checklist/Lot Map | Contractor: Resp - RSA | Contractor: Type - Hold Point | Client: Resp - Senex | Client: Type - Hold Point | Work By - Contractor
13 | Survey – Progress | Contractor | Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement. | 25%, 50%, 75% | Survey | RSA | Check | Senex | Hold Point | 13 - Survey – Progress | Work By - Contractor | Standard / Spec - Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0 | Criteria - The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement. | Frequency - 25%, 50%, 75% | Record - Survey | Contractor: Resp - RSA | Contractor: Type - Check | Client: Resp - Senex | Client: Type - Hold Point | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
13 | As-constructed Survey | Contractor | Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0 | After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance. Tolerances  Embankment Crest o -0 / +200mm  Liner Subgrade o -20 / +50mm  Final Liner Subgrade Grader o Within 1/20th specified grade  Emergency Spillway (invert) o -20 / +20mm  Extraction Pipework o ±50mm | 1/Lot | Survey | RSA | Hold Point | Senex | Hold Point | 13 - As-constructed Survey | Work By - Contractor | Standard / Spec - Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0 | Criteria - After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance. Tolerances  Embankment Crest o -0 / +200mm  Liner Subgrade o -20 / +50mm  Final Liner Subgrade Grader o Within 1/20th specified grade  Emergency Spillway (invert) o -20 / +20mm  Extraction Pipework o ±50mm | Frequency - 1/Lot | Record - Survey | Contractor: Resp - RSA | Contractor: Type - Hold Point | Client: Resp - Senex | Client: Type - Hold Point | Criteria - Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required)
Frequency - Prior to commencement
Record - ITP Verification Checklist / Lot Plan
Contractor: Resp - RSA
Contractor: Type - Hold Point
Client: Resp - Senex
Client: Type - Hold Point
03 - Underlying Lot Conforms
Work By - Contractor
Standard / Spec - Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
Criteria - The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification.
Frequency - 1/Lot
Record - ITP Verification Checklist/Lot Map
Contractor: Resp - RSA
Contractor: Type - Hold Point
Client: Resp - Senex
Client: Type - Hold Point
04 - Placement of General Fill – Outer Zone and Inner Zone
Work By - Contractor
Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
Criteria - Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology. Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination. Overfill to outer edges of embankment to allow for trim back to design surface Completed under Level 2 Testing
Frequency - Each Lot
Record - ITP Verification Checklist/Lot Map
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
05 - Placement of Select Fill (if required)
Work By - Contractor
Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
Criteria - Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0 Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness. The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material Finished surface to be free of all stones or other objects with potential to puncture liner. Completed under Level 2 Testing
Frequency - 1 / Lot
Record - ITP Verification Checklist/Lot Map
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
06 - Testing – Outler Layer Density and Moisture
Work By - Contractor
Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below)
Frequency - 1 / 500m3
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
07 - Testing – Outler Layer Material Quality
Work By - Contractor
Standard / Spec - Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below)
Frequency - See Criteria
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
08 - Testing – Inner Layer Density and Moisture
Work By - Contractor
Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below)
Frequency - 1 / 500m3
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
09 - Testing – Inner Layer Material Quality
Work By - Contractor
Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below)
Frequency - See Criteria
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
10 - Testing – Select Fill Density and Moisture
Work By - Contractor
Standard / Spec - Table 10 CHAR(AMP) 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 10 CHAR(AMP) 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 (See below)
Frequency - 1 / 500m3
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
11 - Testing – Select Fill Material Quality
Work By - Contractor
Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below)
Frequency - See Criteria
Record - ITP Verification Checklist / Report
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Witness Point
12 - Rework / Repairs to fill (if required)
Work By - Contractor
Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0
Criteria - The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.  If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.  If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.  If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.  If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification. Retesting (if required) in line with requirements of the Zone being repaired.
Frequency - As required
Record - ITP Verification Checklist/Lot Map
Contractor: Resp - RSA
Contractor: Type - Hold Point
Client: Resp - Senex
Client: Type - Hold Point
13 - Survey – Progress
Work By - Contractor
Standard / Spec - Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
Criteria - The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement.
Frequency - 25%, 50%, 75%
Record - Survey
Contractor: Resp - RSA
Contractor: Type - Check
Client: Resp - Senex
Client: Type - Hold Point
13 - As-constructed Survey
Work By - Contractor
Standard / Spec - Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0 Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0
Criteria - After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance. Tolerances  Embankment Crest o -0 / +200mm  Liner Subgrade o -20 / +50mm  Final Liner Subgrade Grader o Within 1/20th specified grade  Emergency Spillway (invert) o -20 / +20mm  Extraction Pipework o ±50mm
Frequency - 1/Lot
Record - Survey
Contractor: Resp - RSA
Contractor: Type - Hold Point
Client: Resp - Senex
Client: Type - Hold Point