## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP006 - EC - Embankment Construction | itp |  |  |  |  | ITP006 - EC - Embankment Construction - Rev0
section | Inspection and Test Plan Details
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist / Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Check
checkpoint | 02 - Lot Identification – Lot Plan
label | Work By - Contractor
label | Standard / Spec - Clause 3.5 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - Lot Plan submitted to the Superintendent 5 days prior to the commencement of the Work (if required)
label | Frequency - Prior to commencement
label | Record - ITP Verification Checklist / Lot Plan
label | Contractor: Resp - RSA
label | Contractor: Type - Hold Point
label | Client: Resp - Senex
label | Client: Type - Hold Point
holdpoint | HOLD POINT
checkpoint | 03 - Underlying Lot Conforms
label | Work By - Contractor
label | Standard / Spec - Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - The Superintendent shall inspect the results of the testing of each layer in each lot of material for conformance with the Specification.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist / Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - Hold Point
label | Client: Resp - Senex
label | Client: Type - Hold Point
holdpoint | HOLD POINT
checkpoint | 04 - Placement of General Fill – Outer Zone and Inner Zone
label | Work By - Contractor
label | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - Outer Zone and Inner zone earth fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness in line with RSA construction methodology.
label | ○ Any existing surfaces to be lightly scarified and moisture conditioned prior to placement of subsequent layer to provide sufficient bond and prevent lamination.
label | ○ Overfill to outer edges of embankment to allow for trim back to design surface
label | ○ Completed under Level 2 Testing
label | Frequency - Each Lot
label | Record - ITP Verification Checklist / Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 05 - Placement of Select Fill (if required)
label | Work By - Contractor
label | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 9.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - Select Fill shall comprise clay-rich soils sourced from the excavation of the dam and onsite borrow areas that conform to the geotechnical properties specified in Table 8 of OPS-TETW-CS-SPE-001 IFC Rev 0
label | ○ Select fill to be placed, moisture conditioned and compacted generally in layers not exceeding 300mm thickness.
label | ○ The final surface shall be prepared with a smooth drum roller to create a smooth surface immediately prior to the deployment of the geomembrane material
label | ○ Finished surface to be free of all stones or other objects with potential to puncture liner.
label | ○ Completed under Level 2 Testing
label | Frequency - 1 / Lot
label | Record - ITP Verification Checklist / Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 06 - Testing – Outler Layer Density and Moisture
label | Work By - Contractor
label | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
label | Frequency - 1 / 500m3
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 07 - Testing – Outler Layer Material Quality
label | Work By - Contractor
label | Standard / Spec - Table 6 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Outer Zone Conforming to properties provided in Table 6 (See below)
label | Frequency - See Criteria
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 08 - Testing – Inner Layer Density and Moisture
label | Work By - Contractor
label | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
label | Frequency - 1 / 500m3
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 09 - Testing – Inner Layer Material Quality
label | Work By - Contractor
label | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 7 (See below)
label | Frequency - See Criteria
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 10 - Testing – Select Fill Density and Moisture
label | Work By - Contractor
label | Standard / Spec - Table 10 & 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 10 & 11 of OPS-TETW-CS-SPE-001 IFC Rev 0 (See below)
label | Frequency - 1 / 500m3
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 11 - Testing – Select Fill Material Quality
label | Work By - Contractor
label | Standard / Spec - Table 7 and 11 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - Testing in line with Table 11 of OPS- TETW-CS-SPE-001 IFC Rev 0 material for Inner Zone Conforming to properties provided in Table 8 (See below)
label | Frequency - See Criteria
label | Record - ITP Verification Checklist / Report
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Witness Point
checkpoint | 12 - Rework / Repairs to fill (if required)
label | Work By - Contractor
label | Standard / Spec - Clause 9.4 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - The Superintendent shall approve the extent of all repairs to damage, eroded, cracked or otherwise non-conforming materials and also the finish product of the repairs.
label | ○ If the moisture content is within plus or minus 1% of the range, the Contractor may scarify that layer or area and add moisture, or work the clay to dry out as appropriate, re-compact, and present for retesting.
label | ○ If the moisture content is drier than 1% of the specified range, the layer shall be removed and reworked to a satisfactory condition before it is reused.
label | ○ If the dry density ratio is within 3% of the specified requirement additional compaction using a roller may be performed to increase the density and the layer, then presented for re-testing.
label | ○ If the dry density ratio is more than 3% below the specified requirement, the layer shall be removed and be replaced to achieve specification.
label | ○ Retesting (if required) in line with requirements of the Zone being repaired.
label | Frequency - As required
label | Record - ITP Verification Checklist / Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - Hold Point
label | Client: Resp - Senex
label | Client: Type - Hold Point
holdpoint | HOLD POINT
checkpoint | 13 - Survey – Progress
label | Work By - Contractor
label | Standard / Spec - Clause 3.6 of OPS- TETW-CS-SPE-001 IFC Rev 0
label | Criteria - The Contractor shall submit to the Superintendent 25%, 50% and 75% embankment fill placement completion surveys within 48 hours days of each milestone achievement.
label | Frequency - 25%, 50%, 75%
label | Record - Survey
label | Contractor: Resp - RSA
label | Contractor: Type - Check
label | Client: Resp - Senex
label | Client: Type - Hold Point
holdpoint | HOLD POINT
checkpoint | 13 - As-constructed Survey
label | Work By - Contractor
label | Standard / Spec - Clause 3.4 of OPS- TETW-CS-SPE-001 IFC Rev 0, Clause 20.2.4 of OPS-TETW-CS- SPE-001 IFC Rev 0
label | Criteria - After all work, or parts of work requiring survey acceptance has been completed, a final survey of all elements of the work shall be performed and submitted to the CQA Engineer for review and acceptance.
label | Tolerances:
label | — Embankment Crest
label | ○ -0 / +200mm
label | — Liner Subgrade
label | ○ -20 / +50mm
label | — Final Liner Subgrade Grader
label | ○ Within 1/20th specified grade
label | — Emergency Spillway (invert)
label | ○ -20 / +20mm
label | — Extraction Pipework
label | ○ ±50mm
label | Frequency - 1/Lot
label | Record - Survey
label | Contractor: Resp - RSA
label | Contractor: Type - Hold Point
label | Client: Resp - Senex
label | Client: Type - Hold Point
holdpoint | HOLD POINT
checkpoint | Built in accordance with this document:
date | Date
holdpoint | Signed
checkpoint | Test results received. Lot conforms to Specification:
date | Date
holdpoint | Signed