## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [8 empty] | Document # FHC-8B4000-ITP-051
[12 empty] | Revision : 01 | Date : 06/06/2023
Client: |  | Yarra Trams - ZALEP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  |  | Approved by :
Project: |  | New Preston Depot - Maintenance Shed |  | Rigid Insulation Installation |  | Name: | Jack Wood | Name: | Charles Bate |  |  | Name: | Damon Bromwich
Contract No: |  |  |  | Specifications: AS 3600-2018, Contract Drawing Specifications, Manufacturer Guidelines
Project No: |  | 8B4000 |  | Structure / Component: |  | Signed : |  | Signed : |  |  |  | Signed :
Mix Design Code:
|  |  |  | Location (Include Map): |  | Date : | 2022-06-06 | Date : |  |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Building Surveyor | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A | N/A |  | N/A
1.3 | Approval of material |  | Prior to works commencing | At least one week prior to works commencing, submit details of materials and material approval to client. | Contract Drawings | Verify | This ITP signed | HP | Fulton Hogan/ Superintendent |  | N/A |  | N/A
2 | Installation
2.1 | Correct Material |  | Prior to works commencing | Rigid Installation Material aligns with Yarra Trams Material Approval and associated Installation Guides | Material Approval | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A |  | N/A
2.2 | Correct Fastners and complimentry equipment |  | Prior to works commencing | Fastners and Aluminum Tape are aligned with Yarra Trams Material Approval | Material Approval | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A |  | N/A
2.3 | Aluminum Tape |  | Prior to Works Continuing | All Rigid Insulation Boards have adequate aluminum tape coverage. - 25mm overlap on each exposed edge - Even tape lining on adjoining edges | Manufacturers Installation Guide | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A |  | N/A
2.4 | Fastner Frequency |  | Prior to Works Continuing | Fastners adhere to frequency outlined in manufacturers guidelines - 2.43 fastners per m^2 | Manufacturers Installation Guide | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A | N/A |  | N/A
3 | Post-Work details and Survey
5.5 | As Built Drawings |  | Prior to lot closure | Recorded of as-built drawings | Fulton Hogan Procedure | Verify | This ITP signed | IP | Fulton Hogan | N/A | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent