## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-051 - NPD - Rigid Insulation Installation | itp |  |  |  |  | ITP-051 - NPD - Rigid Insulation Installation Rev1
section | Design and Submissions
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Approval of material
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: At least one week prior to works commencing, submit details of materials and material approval to client.
note | REFERENCE DOCUMENTS: Contract Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP
note | RESPONSIBILITY: Fulton Hogan/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Installation
checkpoint | 2.1 Correct Material
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: Rigid Installation Material aligns with Yarra Trams Material Approval and associated Installation Guides
note | REFERENCE DOCUMENTS: Material Approval
note | INSPECTION/TEST METHOD: Inspect
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Correct Fastners and complimentry equipment
note | FREQUENCY: Prior to works commencing
note | ACCEPTANCE CRITERIA: Fastners and Aluminum Tape are aligned with Yarra Trams Material Approval
note | REFERENCE DOCUMENTS: Material Approval
note | INSPECTION/TEST METHOD: Inspect
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Aluminum Tape
note | FREQUENCY: Prior to Works Continuing
note | ACCEPTANCE CRITERIA: All Rigid Insulation Boards have adequate aluminum tape coverage. - 25mm overlap on each exposed edge - Even tape lining on adjoining edges
note | REFERENCE DOCUMENTS: Manufacturers Installation Guide
note | INSPECTION/TEST METHOD: Inspect
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Fastner Frequency
note | FREQUENCY: Prior to Works Continuing
note | ACCEPTANCE CRITERIA: Fastners adhere to frequency outlined in manufacturers guidelines - 2.43 fastners per m^2
note | REFERENCE DOCUMENTS: Manufacturers Installation Guide
note | INSPECTION/TEST METHOD: Inspect
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Post-Work details and Survey
checkpoint | 5.5 As Built Drawings
note | FREQUENCY: Prior to lot closure
note | ACCEPTANCE CRITERIA: Recorded of as-built drawings
note | REFERENCE DOCUMENTS: Fulton Hogan Procedure
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: