## WBS
Site QA - 32 Brentford
Preline/Interior Fitout
Level 1
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 2
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 3
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 4
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 5
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 6
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 7
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Exterior
|  | North Elevation |  | QA - Exterior Finishes
|  | South Elevation |  | QA - Exterior Finishes
|  | West Elevation |  | QA - Exterior Finishes
|  | East Elevation |  | QA - Exterior Finishes
| Roof |  |  | QA - Roof Framing
Site QA - 34 Brentford
Preline/Interior Fitout
Level 1
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 2
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 3
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 4
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 5
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 6
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Level 7
|  |  | Apartment 1 | QA - Interior Fitout
|  |  | Apartment 2 | QA - Interior Fitout
|  |  | Apartment 3 | QA - Interior Fitout
|  |  | Apartment 4 | QA - Interior Fitout
Exterior
|  | North Elevation |  | QA - Exterior Finishes
|  | South Elevation |  | QA - Exterior Finishes
|  | West Elevation |  | QA - Exterior Finishes
|  | East Elevation |  | QA - Exterior Finishes
| Roof |  |  | QA - Roof Framing

## checklists
type | name | values
checklist | QA - Interior Fitout
section | Interior framing
checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
section | Steel Stud
checkpoint | Trades QA received & attached as applicable
section | Plumbing First Fix
checkpoint | Plumbing first fix complete
tickbox | Mixers are in correct position (hole allowance to work with tiles)
tickbox | All water & gas risers are complete
tickbox | All stacks are level/plumb
tickbox | All pipe insulated
checkpoint | Trades QA received & attached as applicable
checkpoint | Plumbing fitout have been tested & commissioned
section | Electrical First Fix
checkpoint | Electrical first fix complete
tickbox | Power points have been installed as per the electrical plans
tickbox | All comms are installed to allow for good detailing around
tickbox | GPO's are correct for air conditioning & functional
checkpoint | Trades QA received & attached as applicable
checkpoint | Electrical fitout have been tested & commissioned
section | Mechanical First Fix
checkpoint | Electrical first fix complete
tickbox | All aircon has been roughed in & tested
tickbox | All mech has been roughed in & completed
tickbox | All services that go through fire rated walls to be treated with collars/fire rated sealant
tickbox | Service going through exterior wall on a slope
tickbox | Duct work to be tear free & sealed prior to cleaning
checkpoint | Trades QA received & attached as applicable
checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
section | Passive Fire
checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint | Check that fire doors have been filled
checkpoint | Trades QA received & attached as applicable
section | Preline/ Wall Linings
checkpoint | Ensure installation guide has been followed for insulation
checkpoint | Ensure installation guide has been followed for fire rated walls
tickbox | All insulation fitting snug
checkpoint | All service noggs and fixing noggs complete
checkpoint | Trades QA received & attached as applicable
section | Postline/Wall Linings
checkpoint | Plywood in bathrooms correctly installed
checkpoint | Gib screwed off correctly
checkpoint | Gib in bathroom correct
checkpoint | Trades QA received & attached as applicable
section | Gib stopping
checkpoint | All stopping completed and specified level of finish achieved
tickbox | Light check complete
checkpoint | Trades QA received & attached as applicable
section | Painting
checkpoint | Trades QA received & attached as applicable
section | Bathroom & Laundry Waterproofing
checkpoint | Waterproofing completed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Joinery Fit Out
checkpoint | All bathroom joinery installed as per specifications
checkpoint | All kitchen joinery installed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Floor coverings
checkpoint | Vinyl installed as per specifications
checkpoint | Carpet installed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Fire System
checkpoint | Smoke detectors & sensors fit off completed
checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint | Sprinkler rough fit off completed
checkpoint | Sprinklers commissioned
checkpoint | Trades QA received & attached as applicable
section | Legacy Final Sign - Off
checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
tickbox | Legacy - apartment final sign off
holdpoint | Signoff
checklist | QA - Exterior Finishes
section | Exterior wall framing
checkpoint | Window opening dimension (check agreed sizes with NZ windows)
checkpoint | Bottom plate H3.2 (All other timber frame H1.2)
checkpoint | DPC
checkpoint | Stud , Nog spacing & Bracing
checkpoint | Fixing (type & spacing)
checkpoint | Connectors (type & fixing)
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Building Wrap
checkpoint | RAB board (thickness & gaps)
checkpoint | RAB board fixings
checkpoint | RAB board taping
checkpoint | All cuts primed
checkpoint | Penetration detailed
checkpoint | Sealant
checkpoint | Vaproshield (when required)
checkpoint | Check for junction flashings as required
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Cavity System
checkpoint | Head flashings
checkpoint | Cavity battens offset 10mm from the opening refer to arch detail 2/AD834
checkpoint | Cavity batten fixings in accordance with James Hardie Linea Oblique manual
checkpoint | Verman strips
checkpoint | For installation of the 3M 8067 All weather flashing tape in:
note | The sliding door opening
note | Lap over the top edge of the
note | Membrane at the jamb - to stop short from the sill
note | Provide photos of the above
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Exterior Joinery
checkpoint | Correct sizes
checkpoint | Correct jamb sizes
checkpoint | AT façade sealant 2022 12 in the sliding door openings
note | This is Soudal Gorilla MS - refer to the architectural details
checkpoint | PEF backing rod
checkpoint | Flashings
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Exterior 1st fix
checkpoint | Plumbing drains for deck
checkpoint | Fire collars (when required)
checkpoint | Lights wiring
checkpoint | Mechanical ducts
checkpoint | Hose taps pipework
checkpoint | Alarms
checkpoint | Air-con
checkpoint | Roof penetrations
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Exterior soffit framing & lining
checkpoint | Framing - DPC
checkpoint | Framing - Stud , Nog spacing & Bracing
checkpoint | Framing - Fixing (type & spacing)
checkpoint | Building paper
checkpoint | Lining - Type & Joins
checkpoint | Lining - Fixing
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Exterior cladding Linea Oblique Weatherboard
checkpoint | Correct layout
checkpoint | Correct sizes
checkpoint | Correct fixings
checkpoint | Correct fixing spacing in accordance with James Hardie Linea Oblique manual
checkpoint | Boards plumb
checkpoint | Boards level
checkpoint | All joints acceptable/sealed
checkpoint | All cuts primed with 2 coats of stain
checkpoint | Correct moldings/flashings
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Balustrades
checkpoint | Correct type
checkpoint | Correct sizes
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Fins
checkpoint | Correct type
checkpoint | Correct sizes
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Gutters/downpipes
checkpoint | Correct size gutters
checkpoint | Correct downpipe sizes
checkpoint | Correct colours
checkpoint | Gutters straight
checkpoint | Downpipes straight
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Exterior painting
checkpoint | Concrete repairs
checkpoint | Join sealant
checkpoint | Window preparation
checkpoint | Ecotone stain
checkpoint | Dulux White on white
checkpoint | Soffit colours
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Deck membrane
checkpoint | Correct membrane - please specify what membrane was used
checkpoint | Correct laps
checkpoint | Correct upstands
checkpoint | No damage
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
section | Decking
checkpoint | Correct timber (treatment)
checkpoint | Timber on correct jacks
checkpoint | Fixing (type & spacing)
checkpoint | Even gaps @ wall / balustrade
checkpoint | Request Sign Off
section | Exterior 2nd fix services
checkpoint | Plumbing drains for decks
checkpoint | Downpipes
checkpoint | Lights
checkpoint | Hose taps
checkpoint | Alarms
checkpoint | Air-con
checkpoint | Roof penetrations complete
checkpoint | Clothes line
note | Trades QA received & attached as applicable
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request Sign Off
checklist | QA - Roof Framing
checkpoint | Correct timber treatment
checkpoint | Correct fixings (incl spacing)
checkpoint | Hold down fixings
checkpoint | Connections to masonry
checkpoint | Correct flashing sizes
checkpoint | Correct flashing types
checkpoint | Roof penetrations sealed
checkpoint | Roof penetrations back flashed
checkpoint | Vaproshield (when required)
checkpoint | Trades QA received, reviewed, attached and approved
note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Request holdpoint