## QA lots subfolders and ITPs
Tier1 (Discipline) | Tier2 - (Design Package) - Calder Park Dr | Tier 3 | Tier 4 | Tier 5 | Status
Civil | MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Northen Alignment | ITP-CIV-Line Marking (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Southern Alignment | ITP-CIV-Line Marking (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Taylors Creek | ITP-CIV-Line Marking (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Victoria St | ITP-CIV-Line Marking (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | SUP | ITP-CIV-Line Marking (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Linemarking | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Northen Alignment | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Southern Alignment | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Taylors Creek | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Victoria St | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Kerb | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Northen Alignment | ITP-STR-Guard Rail (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Southern Alignment | ITP-STR-Guard Rail (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Taylors Creek | ITP-STR-Guard Rail (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Victoria St | ITP-STR-Guard Rail (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Guardrail | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Signage | Site Wide | ITP-CIV-Sign Posting Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Tactiles | Site Wide | ITP-CIV-Tactile Indicators (Supply and Install) Rev 0 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (North) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Calder Park Drive (South) | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | To be created
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Contingency lots |  | Contingency
| MRP-DPK-080-00-CRG-0010-0 - Road Alignment, Barrier and Signage | Subsoils | Contingency lots |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Kerb | Northen Alignment | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | waiting for design
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-081-00-CRG-0011-0 - Holden Road - Civil | Contingency |  |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Capping | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 1 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 2 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 1 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 2 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Upper Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Upper Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Base | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Capping | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Capping | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Capping | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Base | ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Capping | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Base |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt RC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive | Contingency lots |  | To be created
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (West) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (West) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (East) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (East) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (West) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (West) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (West) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (West) | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (East) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (East) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (East) | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (East) | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Subbase | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Base | ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | To be created, chainages TBC
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/10- Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/13 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/15 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/16 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/16C - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/17 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/1A - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/21 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/22 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/23 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/24 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/25 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/27 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/28 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/29 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/3 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/4 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-1/7 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/10 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/15 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/21 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/22 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/23 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/24 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/25 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/27 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/29 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/3 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-2/7 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/10 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/18 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/23 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/29 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/3 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-3/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/10 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/16 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/23 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/3 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/5 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-4/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-5/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-5/10 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-5/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-5/5 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-5/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-6/1 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-6/10 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-6/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-6/6 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | L-7/20 - Stormwater - Pit Installation | Stormwater - pit installation rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pit | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/1 to L-2/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/1 to L-3/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/1 to L-4/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/1 to L-5/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-5/1 to L-6/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-6/1 to L-6/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/1A to L-1/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/3 to L-2/3 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/3 to L-3/3 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/3 to L-4/3 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/3 to L-5/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/4 to L-4/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/5 to L-5/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-5/5 to L-6/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/6 to L-2/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/6 to L-3/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/6 to L-4/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/6 to L-5/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-5/6 to L-6/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-6/6 to L-7/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/7 to L-2/7 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/10 to L-2/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/10 to L-3/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/10 to L-4/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/10 to L-5/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-5/10 to L-6/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-6/10 to L-7/10 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/13 to L-2/3 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/15 to L-2/15 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/16 to L-2/16 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/16 to L-3/16 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/16 to L-4/16 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/16 to L-1/6 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/16A to L-2/16A Pipe Installtion | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/16A to L-2/16 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/16C to L-4/16 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/17 to L-2/17 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/17 to L-1/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/1A to L-2/17A Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/17A to L-2/17 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/18 to L-2/18 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/18 to L-3/18 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/18 to L-2/1 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/18 to L-1/18A Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/18B to L-2/18B Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/18C to L-3/18 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/20 to L-2/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/20 to L-3/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/20 to L-4/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/20 to L-5/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-5/20 to L-6/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-6/20 to L-7/20 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-7/20 to L-5/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/21 to L-2/21 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/21 to L-3/3 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/22 to L-2/22 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/23 to L-2/23 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/23 to L-3/23 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-3/23 to L-4/23 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-4/23 to L-3/5 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/24 to L-2/24 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/25 to L-2/25 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/27 to L-2/27 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/28 to L-2/29 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/29 to L-2/29 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/29 to L-3/29 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/30 to L-2/30 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/30 to L-3/30 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-1/31 to L-2/31 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | L-2/31 to L-3/31 Pipe Installation | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0014-0 - Flood Risk Assessment |  |  |  | No lots required
| MRP-DPK-080-00-CRG-0015-0 - Traffic Impact Assessment |  |  |  | No lots required
| MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North) | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2 | To be created
| MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South) | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2 | To be created
| MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North) | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1 | To be created
| MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South) | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1 | To be created
| MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Contingency lots |  | Contingency
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | Combined GWW Trench |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | South Connection |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | North Connection |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | South Trust restraint |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | North Trust restraint |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | GWW Sewer Manhole Riser | GWW Sewer Manhole Riser
| MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency |  |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency |  |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency |  |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency |  |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency |  |  | Subcontractor to create ITP, MRPA to review
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 1 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 2 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 3 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 4 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 5 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 6 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 7 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 8 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 9 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 10 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 11 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 12 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 13 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 14 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 15 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 16 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 17 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 18 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 19 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 20 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 21 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 22 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 23 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 24 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 25 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 26 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 27 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 28 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 29 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 30 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 31 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 32 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 33 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 34 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 35 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 36 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 37 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 38 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 39 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 40 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 41 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 42 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 43 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 44 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 45 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 46 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 47 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 48 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 49 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 50 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 51 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 52 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 53 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 54 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 55 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 56 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 57 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 58 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 59 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 60 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 61 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 62 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 63 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 64 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | North Alignment lot 65 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lot |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 1 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 2 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 3 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 4 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 5 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 6 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 7 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 8 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 9 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 10 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 11 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 12 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 13 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 14 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 15 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 16 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 17 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 18 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 19 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 20 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 21 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 22 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 23 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 24 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 25 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 26 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 27 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 28 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 29 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 30 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 31 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 32 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 33 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 34 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 35 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 36 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 37 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 38 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 39 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 40 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 41 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 42 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 43 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 44 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 45 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 46 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 47 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 48 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 49 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 50 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 51 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 52 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 53 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 54 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 55 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 56 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 57 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 58 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 59 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 60 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 61 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 62 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 63 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 64 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | South Alignment lot 65 | CHK-CIV-RSS Walls-Fill Placement Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots | Wire walls ITP needs to be created | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Supply and Installation | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Lift 2 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Lift 3 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Panel Installation Lift 4 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Supply and Installation | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 2 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 3 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 4 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 5 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 6 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 7 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Panel Installation Lift 8 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Supply and Installation | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Panel Installation Base Lift | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Panel Installation Lift 2 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Panel Installation Lift 3 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Panel Installation Lift 4 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Supply and Installation | ITP-CIV-RSS Walls (Supply and Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Base Lift Panels (x) to Panels (y) | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Base Lift Panels (x) to Panels (y) |  | To be created, panels to be renamed
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 2 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 3 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 4 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 5 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 6 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 7 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 8 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 9 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Panel Installation Lift 10 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0 | To be created
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | Contingency lots |  | Contingency
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots | Wire walls ITP needs to be created | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | Contingency lots |  | ITPs need to be created for wired wall
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts | Stormwater - Pipe and Culvert Installation Rev0.0 | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | General Concrete | ITP-CIV-General Concrete Rev 1 | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Rock Beaching |  | To be created
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Contingency lots |  | Contingency
| MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Contingency lots |  | Contingency
| MRP-DPK-080-00-CGT-0040-0 - Geotechnical Report |  |  |  | No lots required
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd | Site Wide | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd | Site Wide | ITP-CIV-Landscaping - Ground Preparation Rev 0 ITP-CIV-Landscaping - Planting Rev 0 | To be created
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Contingency
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Contingency
| MRP-DPK-080-00-AUD-0071-0 - Landscaping | Contingency
Rail | MRP-DPK-080-00-GSG-0050-0 - Rail Signalling (Enabling Works) | Stage 1 |  | Test Copies and CTC for all works (Cerified Copies)
| MRP-DPK-080-00-GSG-0053-0 - COC - Transformer Removal | Stage 2 |  | Test Copies and CTC for all works (Cerified Copies)
| MRP-DPK-080-00-GSG-0052-0 - Rail Signalling (Final) | Final Works |  | Test Copies and CTC for all works (Cerified Copies)
| MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive | Overhead Wiring Structure (A894+83) | TBC | To be created
| MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive | Overhead Wiring Structure (A894+89) | TBC | To be created
| MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive | Modification of Existing Structure (10 no. of) | TBC | To be created - Work lot map to show location of modification
| MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive | Overhead Wiring Structure Under Bridge (A893+99 and A894+02) | TBC | To be created
| MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive | Regrading of Wires (From A880+57 to A900+80) | TBC | To be created
| MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | Calder Park Dr. Pavement Removal | ITP-Rail-Track Removal & Construction Rev 1 (CPK) | To be created
| MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 25.936km - 25.959km (Calder Park) | ITP-Rail-Track Removal & Construction Rev 1 (CPK) | To be created
| MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 27.003km - 27.198km (Calder, Holden) | ITP-Rail-Track Removal & Construction Rev 1 (CPK) | To be created
| MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Holden Road | IRJ Removals - 29.448km - 29.617km (Holden Road) | ITP-Rail-Track Removal & Construction Rev 1 (CPK) | To be created
| MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Piling - SA-01 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Piling - SA-02 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Piling - SA-03 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Piling - SA-04 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Pile Extension - SA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Pile Extension - SA-02 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Pile Extension - SA-03 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Pile Extension - SA-04 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Headstock - SA-HS - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Fenderwall - SA-FW - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Bearing Pedestal - SA-01 to SA-04 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Bearing Pedestal - SA-05 to SA-09 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Lateral Restraint Block - SA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Approach Slab - SA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | SUP Approach Slab - SA-02 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | Concrete Coatings - SA-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-01 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-02 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-03 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-04 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-05 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-06 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Pile Cap - P1-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Blade Wall/Headstock - P1-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-01 to P1-05- FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-06 to P1-11 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-12 to P1-18- FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Lateral Restraint Block - P1-01- FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Concrete Coatings - P1-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-01 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-02 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-03 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-04 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-05 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Piling - P2-06 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Pile Cap - P2-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Blade Wall/Headstock - P2-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - P2-01 to P2-05 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - P2-06 to P2-11- FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - P2-12 to P2-16- FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Lateral Restraint Block - P2-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Concrete Coatings - P2-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-01 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-02 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-03 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-04 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-05 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-06 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-07 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-08 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-09 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Piling - NA-10 - Pile Installation | ITP-STR Bored Piling Rev 5 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Pile Cap - NA-01 - Pile Cap - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Abutment Wall - NA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Abutment Wall - Fender Wall - NA-02 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Abutment Wall - East Wingwall - NA-03 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Bearing Pedestal - NA-01 to NA-04 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Bearing Pedestal - NA-05 to NA-07 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Approach Slab - Roadway - NA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Approach Slab - SUP - NA-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | Concrete Coatings - NA-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G01 to S1-G07- Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G08 to S1-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | In-Situ Diaphram - S1-G07 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Deck Pour - S1-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Expansion Joint - S1-01 | ITP-STR Expansion Joints (Supply & Installation) ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BE-01 to BE-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BW-01 to BW-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Kerb - PK-01 to PK-07 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S1-E-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S2-W-01-FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G01 to S2-G07 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G08 to S2-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Pour - S2-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S1-S2-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S2-S3-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BE-09 to BE-15- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BW-09 to BW15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Kerb - PK-08 to PK-13 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-E-01- FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-W-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G01 to S3-G05 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G06 to S3-G07 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Deck Pour - S3-01- FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Expansion Joint - S3-01 | ITP-STR Expansion Joints (Supply & Installation) ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BE-16 to BE-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BW-16 to BW-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Kerb - PK-15 to PK-19 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-E-01- FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-W-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South West - FS-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02A - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02C - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02D - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SE-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SE-02 to SE-25 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SE-26 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SE-27 to SE-30 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SW-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Test Level-4v Barrier - SW-02 to SW-15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SW-17 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SW-18 to SW-21 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SE-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SW-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - East Barriers - SE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - West Barriers - SW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North West - FS-03 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North East - FS-04 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NE-01 to NE-05- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NE-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NE-07 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NE-01 to NE-05 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NW-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Test Level-4 Barrier - NW-07 to NW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NW-17 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NE-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NW-01 - FRP | ITP-STR Structural Concrete Rev 3 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - East Barriers - NE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - West Barriers - NW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1 | To be created
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-1 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-2 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-3 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-4 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-5 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0 | To be created
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Kerb - SK-01 to SK03 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Kerb - PK-01 to PK-07 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Capping - LC-01 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Stairs Case - SE-01 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type B - SE-02 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type A - SE-03 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-3 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-4 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F3-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Barrier Rail - South West | ITP-STR Structural Steel Barrier Rail (Supply & Installation) Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Spoon Drain - South West - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-6 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F2-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F1-5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F2-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-3 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F3-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Kerb - PK-10 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | L-Shaped Capping - LC-01 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type A - NE-01 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type C - NE-02 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F1-7 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F4 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Barrier Rail - North West | ITP-STR Structural Steel Barrier Rail (Supply & Installation) Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North West - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North East - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-01 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-02 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-03 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-04 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-05 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-06 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-07 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Piling - SUP-08 - Pile Installation | ITP-STR Bored Piling Rev 5
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - Abutment 1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P3 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P4 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P5 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - Abutment 2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pier - P1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pier - P2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pier - P3 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pier - P4 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pier - P5 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G01 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G01 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G02 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G02 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G03 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G03 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G04 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G05 - Precast | ITP-STR Precast Planks (Supply, Installation & Stressing) Rev 0
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Platform Pour - 1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Platform Pour - 2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Abutment 1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Abutment 2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Pier 5 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Deck Pour - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Approach Trough - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Approach Slab - 1 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Approach Slab - 2 - FRP | ITP-STR Structural Concrete Rev 3
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Steel Posts & Screens - SUP | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Contingency
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Contingency
| MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Contingency
Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion
MRP-052-C-PIT-DRG-92-MPK-CTW-092-0 -Temporary Rail Delineation Fencing
| Extra Temporary Lots | Landscaping | Clearing and Grubbing | ITP-CIV-Site Clearing and Grubbing | Lots are option
Materials Inspection